## Overview
Job #2061 · Alta Columbia City
Cortex JCR Summary • Exxel Pacific (Owner: Gateway Alta Rainer Owner, LLC)
PROJECT OVERVIEW
Project Job # | 2061
Project Name: | Alta Columbia City
General Contractor | Exxel Pacific (Owner: Gateway Alta Rainer Owner, LLC)
Location | 3717 South Alaska Street, Seattle, WA 98118 (Columbia City)
Project Duration | Jun 2019 – May 2022 (~35 months)
Status | CLOSED · 41.4% margin · retention released
CONTRACT VALUE |  | FORECAST NET PROFIT |  | DIRECT COST |  | LABOR HOURS
$4,430,088 |  | $1,832,588 |  | $2,597,500 |  | 28,516
$4,305,550 orig + $124,538 COs |  | 41.4% margin |  | 58.6% of revenue |  | 58 workers
COST BREAKDOWN
Category | Budget | Actual | Variance | % Budget | % of Cost
Labor | 1196735 | 990503 | 206232 | 0.82767 | 0.38133
Material | 1327487 | 1024296 | 303191 | 0.77161 | 0.39434
Overhead | 195738 | 125530 | 70208 | 0.64132 | 0.048327
Burden | 595169 | 457171 | 137998 | 0.76814 | 0.176
TOTAL | 3315129 | 2597500 | 717629 | 0.78353 | 1
PROJECT PROFILE
Plumbing Units | 243 | Total Fixtures | 30+ fixture types per Plumbing Fixture Schedule | Fixtures / Unit | Typical 4-5 per unit
GC | Exxel Pacific | Owner | Gateway Alta Rainer Owner, LLC | Insurance | Standard COI
Status | CLOSED · 41.4% margin · retention released | Duration | ~35 months | Permit | City of Seattle Plumbing + Backflow + Gas (final 2022-03-22)
NARRATIVE
Closed mixed-use multifamily in Columbia City, Seattle. OWP delivered 41.4% gross margin = $1.83M net profit on a $4.43M closed contract — well above the OWP closed-portfolio median (~32-36%). Modest +2.9% CO growth ($124k) primarily driven by design clarification (ASI 008/011/012, drainage updates, retail meter additions). 39 RFIs + 26 ASIs + 13 SCOs + 14 COR series resolved cleanly. Top vendor Rosen Supply Kirkland at 37.9% of $1M+ AP. OCIP wrap-up insurance via Exxel. 58 workers logged 28,516 labor hours over 35-month run. Notice of Work Completion + 65 O&M close-out documents on file. Retention released in full June 2022.
SOURCES
Job #2061 — Alta Columbia City • GC: Exxel Pacific • Status: CLOSED · 41.4% margin · retention released
Canonical source: 2061_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2061_dashboard_arrays.json (mirrors index.html PROJECTS['2061'])
Project profile: 243 units · 3717 South Alaska Street, Seattle, WA 98118 (Columbia City) · ~35 months
Design team: Johnston Architects (architect), Franklin Engineering (MEP), VIDA (interior)
Contract: L1.220000 · executed 2019-08-08 · $4,305,550 lump sum (AGC Washington 2009 form, modified)
Billing: Final $4,430,088 billed · retention $221,504 released 2022-06-23
Permit: City of Seattle Plumbing + Backflow + Gas (final 2022-03-22)

## Budget vs Actual
Budget vs Actual — All Cost Codes
Code | Description | Orig Budget | Rev Budget | Actual | Variance | % Used
LABOR
100 | Supervision | 20755 | 20755 | 11654 | 9101 | 0.5615
101 | Takeoff & Purchase Labor | 49785 | 49785 | 30858 | 18927 | 0.61983
110 | Underground Labor | 74850 | 74850 | 67400 | 7450 | 0.90047
111 | Garage Labor | 207080 | 207080 | 115836 | 91244 | 0.55938
112 | Canout Labor | 31150 | 31150 | 36858 | -5708 | 1.1832
120 | Roughin Labor | 530745 | 530745 | 472058 | 58687 | 0.88943
130 | Finish Labor | 108320 | 108320 | 119991 | -11671 | 1.1077
140 | Gas Labor | 23250 | 23250 | 18830 | 4420 | 0.80989
141 | Water Main/Insulation Lab | 129200 | 129200 | 94078 | 35122 | 0.72816
142 | Mech Room Labor | 21600 | 21600 | 22826 | -1226 | 1.0568
150 | Warranty Labor | 0 | 0 | 114 | -114 | 0
MATERIAL
210 | Underground Material | 54595 | 54595 | 36611 | 17984 | 0.67059
211 | Garage Material | 137910 | 137910 | 84964 | 52946 | 0.61608
212 | Canout Material | 31150 | 31150 | 15772 | 15378 | 0.50632
220 | Roughin Material | 249410 | 249410 | 189502 | 59908 | 0.7598
230 | Finish Material | 679447 | 679447 | 543379 | 136068 | 0.79974
240 | Gas Material | 25150 | 25150 | 16320 | 8830 | 0.64891
241 | Water Main/Insulation Mat | 121025 | 121025 | 97571 | 23454 | 0.80621
242 | Mech Room Material | 28800 | 28800 | 40175 | -11375 | 1.395
OVERHEAD
600 | Subcontractor | 62550 | 62550 | 13105 | 49445 | 0.20951
601 | Engineering/Plans | 79698 | 79698 | 70334 | 9364 | 0.88251
602 | Rental Equipment | 14000 | 14000 | 12079 | 1921 | 0.86279
603 | Permits & Licenses | 23290 | 23290 | 18395 | 4895 | 0.78982
607 | Other Expenses | 16200 | 16200 | 11617 | 4583 | 0.7171
BURDEN
995 | Payroll Burden | 503619 | 503619 | 381218 | 122401 | 0.75696
998 | Payroll Taxes | 91550 | 91550 | 75953 | 15597 | 0.82963
TOTAL Direct Cost |  | 2597500 | 2597500 | 2597500
SOURCES
Job #2061 — Alta Columbia City • GC: Exxel Pacific • Status: CLOSED · 41.4% margin · retention released
Canonical source: 2061_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2061_dashboard_arrays.json (mirrors index.html PROJECTS['2061'])
Project profile: 243 units · 3717 South Alaska Street, Seattle, WA 98118 (Columbia City) · ~35 months
Design team: Johnston Architects (architect), Franklin Engineering (MEP), VIDA (interior)
Contract: L1.220000 · executed 2019-08-08 · $4,305,550 lump sum (AGC Washington 2009 form, modified)
Billing: Final $4,430,088 billed · retention $221,504 released 2022-06-23
Permit: City of Seattle Plumbing + Backflow + Gas (final 2022-03-22)

## Cost Breakdown
Cost Breakdown — Category Deep Dive
A. CATEGORY SHARE OF DIRECT COST
Category | # Codes | Budget | Actual | Variance | % Budget | % of Cost
Labor | 11 | 1196735 | 990503 | 206232 | 0.82767 | 0.38133
Material | 8 | 1327487 | 1024296 | 303191 | 0.77161 | 0.39434
Overhead | 5 | 195738 | 125530 | 70208 | 0.64132 | 0.048327
Burden | 2 | 595169 | 457171 | 137998 | 0.76814 | 0.176
B. LARGEST OVERRUNS (Actual > Revised Budget)
Code | Description | Rev Budget | Actual | Overrun | % Over
130 | Finish Labor | 108320 | 119991 | 11671 | 0.10775
242 | Mech Room Material | 28800 | 40175 | 11375 | 0.39497
112 | Canout Labor | 31150 | 36858 | 5708 | 0.18324
142 | Mech Room Labor | 21600 | 22826 | 1226 | 0.056759
150 | Warranty Labor | 0 | 114 | 114 | 0
C. LARGEST SAVINGS (Actual < Revised Budget)
Code | Description | Rev Budget | Actual | Savings | % Under
230 | Finish Material | 679447 | 543379 | 136068 | 0.20026
995 | Payroll Burden | 503619 | 381218 | 122401 | 0.24304
111 | Garage Labor | 207080 | 115836 | 91244 | 0.44062
220 | Roughin Material | 249410 | 189502 | 59908 | 0.2402
120 | Roughin Labor | 530745 | 472058 | 58687 | 0.11057
211 | Garage Material | 137910 | 84964 | 52946 | 0.38392
600 | Subcontractor | 62550 | 13105 | 49445 | 0.79049
141 | Water Main/Insulation Lab | 129200 | 94078 | 35122 | 0.27184
241 | Water Main/Insulation Mat | 121025 | 97571 | 23454 | 0.19379
101 | Takeoff & Purchase Labor | 49785 | 30858 | 18927 | 0.38017
SOURCES
Job #2061 — Alta Columbia City • GC: Exxel Pacific • Status: CLOSED · 41.4% margin · retention released
Canonical source: 2061_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2061_dashboard_arrays.json (mirrors index.html PROJECTS['2061'])
Project profile: 243 units · 3717 South Alaska Street, Seattle, WA 98118 (Columbia City) · ~35 months
Design team: Johnston Architects (architect), Franklin Engineering (MEP), VIDA (interior)
Contract: L1.220000 · executed 2019-08-08 · $4,305,550 lump sum (AGC Washington 2009 form, modified)
Billing: Final $4,430,088 billed · retention $221,504 released 2022-06-23
Permit: City of Seattle Plumbing + Backflow + Gas (final 2022-03-22)

## Material
Material Spend Analysis
8 material cost codes • $1,024,294 JDR material • 23 AP vendors
A. MATERIAL BY COST CODE
Code | Description | Rev Budget | Actual | Variance | % Used | % of Mat
210 | Underground Material | 54595 | 36611 | 17984 | 0.67059 | 0.035743
211 | Garage Material | 137910 | 84964 | 52946 | 0.61608 | 0.082949
212 | Canout Material | 31150 | 15772 | 15378 | 0.50632 | 0.015398
220 | Roughin Material | 249410 | 189502 | 59908 | 0.7598 | 0.18501
230 | Finish Material | 679447 | 543379 | 136068 | 0.79974 | 0.53049
240 | Gas Material | 25150 | 16320 | 8830 | 0.64891 | 0.015933
241 | Water Main/Insulation Mat | 121025 | 97571 | 23454 | 0.80621 | 0.095257
242 | Mech Room Material | 28800 | 40175 | -11375 | 1.395 | 0.039222
TOTAL | All Material | 1327487 | 1024294 | 303193 | 0.7716 | 1
B. VENDORS BY SPEND (AP)
Vendor | # Invoices | Total Spend | % of AP
Rosen Supply Kirkland | 223 | 381559 | 0.3788
Keller Supply Company | 62 | 223734 | 0.22212
Consolidated Supply Co. | 55 | 88009 | 0.087374
California Hydronics Corp | 2 | 75297 | 0.074753
Franklin Engineering | 15 | 69481 | 0.068979
Submeter Solutions, Inc. | 5 | 45601 | 0.045272
Ferguson Enterprises, Inc. #3007 | 26 | 36697 | 0.036432
Capital One Credit Card | 42 | 27600 | 0.027401
Best Bath Systems | 2 | 15782 | 0.015668
H&E Equipment Services, Inc. | 20 | 12079 | 0.011992
Mechanical Resource Services, Inc. | 1 | 8250 | 0.0081904
Beacon Building Products $Atlas | 5 | 5338 | 0.0052995
Old Castle Infrastructure, Inc. | 2 | 4290 | 0.004259
Chemical Products Company | 1 | 3050 | 0.003028
Mechanical Sales, Inc. | 1 | 2594 | 0.0025753
Core & Main LP $HD Supply Waterworks | 5 | 2139 | 0.0021236
Kele, Inc $ MI Controls | 5 | 2071 | 0.002056
Scan2Core, Inc. | 1 | 1525 | 0.001514
Bank of America CC | 6 | 901 | 0.0008945
DRSi | 3 | 853 | 0.00084684
A.R. Brown Backflow Testing | 1 | 280 | 0.00027798
Washington State Ferries | 1 | 126 | 0.00012509
Fastenal Company | 1 | 16 | 1.5884e-05
TOTAL | 485 | 1007272 | 1
SOURCES
Job #2061 — Alta Columbia City • GC: Exxel Pacific • Status: CLOSED · 41.4% margin · retention released
Canonical source: 2061_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2061_dashboard_arrays.json (mirrors index.html PROJECTS['2061'])
Project profile: 243 units · 3717 South Alaska Street, Seattle, WA 98118 (Columbia City) · ~35 months
Design team: Johnston Architects (architect), Franklin Engineering (MEP), VIDA (interior)
Contract: L1.220000 · executed 2019-08-08 · $4,305,550 lump sum (AGC Washington 2009 form, modified)
Billing: Final $4,430,088 billed · retention $221,504 released 2022-06-23
Permit: City of Seattle Plumbing + Backflow + Gas (final 2022-03-22)

## Crew & Labor
Crew & Labor — Per-Worker Breakdown
Worker | Hours | Gross Pay | $/Hour | Tier
Cortes Mendiola, Victor H | 2936.5 | 145718 | 49.623 | Lead
Amaya Gonzalez, Edilberto A | 2740.5 | 100894 | 36.8159 | Lead
Barbosa, Michael S | 2176.5 | 70857 | 32.5555 | Mid
Cortes Sepulveda, Jose R | 1986.5 | 68375 | 34.4198 | Mid
Escalante Escobar, Boanerge | 1775.5 | 44668 | 25.158 | Mid
Lima Romero, Melvin A | 1352 | 51980 | 38.4467 | Lead
Cornejo Orellana, Carlos E | 1103.5 | 28221 | 25.5741 | Mid
Sepulveda Gonzalez, Alfredo | 1082.5 | 46340 | 42.8083 | Lead
Petermeyer, Matthew W | 888 | 15882 | 17.8851 | Apprentice
Stahlschmidt, John P | 849 | 17190 | 20.2473 | Mid
Eliassen, Cory H | 854.5 | 28700 | 33.5869 | Mid
Garcia Perez, Ervey O | 818.5 | 18084 | 22.0941 | Mid
Sanders, Allen O | 681 | 38467 | 56.486 | Lead
Boss, Benjamin T | 660.5 | 13698 | 20.7388 | Mid
Barnhart, Thomas L | 638.5 | 24106 | 37.7541 | Lead
Boss, Kyle A | 605.5 | 13502 | 22.2989 | Mid
Mendoza Morales, Jesus A | 610.5 | 20243 | 33.1581 | Mid
Anderson, Richard P | 547 | 26827 | 49.0439 | Lead
Waites, Thaddeus Z | 481.5 | 23594 | 49.001 | Lead
Cruz Gonzalez, Julio C | 475.5 | 13948 | 29.3333 | Mid
Gerard, Jeffrey S | 469.5 | 27200 | 57.934 | Lead
Romero Garza, Jesus I | 440.5 | 11602 | 26.3383 | Mid
Ross, Kelli M | 391 | 16813 | 43 | Lead
McCabe, Thomas C | 364.5 | 14992 | 41.1303 | Lead
Lopez, Maslin A | 304 | 7168 | 23.5789 | Mid
Hawkins, Conor L | 274.5 | 4666 | 16.9982 | Apprentice
Hansen, Paul W | 256 | 4096 | 16 | Apprentice
Donelson, Richard T | 245 | 15312 | 62.498 | Lead
Games, Jordan M | 245 | 6498 | 26.5224 | Mid
Lucas Tzintzun, Rafael | 232 | 6032 | 26 | Mid
Ramos Herrera, Franklin J | 231 | 7080 | 30.6494 | Mid
Trower-Kelly, Fidel D | 211.5 | 5632 | 26.6288 | Mid
Esparza, Andy A | 195 | 4680 | 24 | Mid
Hubbard, Robert W | 188.5 | 10106 | 53.6127 | Lead
Chevez, Herson G | 179.5 | 4912 | 27.3649 | Mid
Balderas Ortiz, Ricardo I | 155.5 | 5675 | 36.4952 | Lead
Paco Leyva, Orlando | 159.5 | 7249 | 45.4483 | Lead
Lovo, German G | 136 | 4488 | 33 | Mid
Castro Urena, Yanely | 96 | 1632 | 17 | Apprentice
Avalos Soto, Veronica | 88 | 1496 | 17 | Apprentice
Martinez Reyes, Juan C | 61.5 | 2322 | 37.7561 | Lead
Barnhart, Joseph N | 58 | 3220 | 55.5172 | Lead
Gutierrez, Brian A | 51 | 1326 | 26 | Mid
Portillo Soriano, Walter A | 40 | 1000 | 25 | Mid
Cruz Reyes, Jose | 48 | 1792 | 37.3333 | Mid
Silva Morales, Jair J | 32 | 960 | 30 | Mid
Rivera, Eli P | 24 | 792 | 33 | Mid
Gonzalez Hernandez, Josue | 12 | 456 | 38 | Lead
Sandhu, Manveer S | 8 | 136 | 17 | Apprentice
Hubbard, Justin A | 8 | 240 | 30 | Mid
Wilson, Jr., Eric T | 8 | 248 | 31 | Mid
Galdamez, Dagoberto A | 8 | 264 | 33 | Mid
Mackey, Cole J | 1 | 16 | 16 | Apprentice
Eisenhauer, Tommy J | 6 | 333 | 55.5 | Ot-Only
Benites Portillo, Marvin E | 5.5 | 314 | 57.0909 | Ot-Only
Fox, Tamron P | 5.5 | 165 | 30 | Ot-Only
Sanchez Becerra, Julian A | 5.5 | 165 | 30 | Ot-Only
Taylor, Evan R | 8.5 | 472 | 55.5294 | Ot-Only
SOURCES
Job #2061 — Alta Columbia City • GC: Exxel Pacific • Status: CLOSED · 41.4% margin · retention released
Canonical source: 2061_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2061_dashboard_arrays.json (mirrors index.html PROJECTS['2061'])
Project profile: 243 units · 3717 South Alaska Street, Seattle, WA 98118 (Columbia City) · ~35 months
Design team: Johnston Architects (architect), Franklin Engineering (MEP), VIDA (interior)
Contract: L1.220000 · executed 2019-08-08 · $4,305,550 lump sum (AGC Washington 2009 form, modified)
Billing: Final $4,430,088 billed · retention $221,504 released 2022-06-23
Permit: City of Seattle Plumbing + Backflow + Gas (final 2022-03-22)

## Crew Analytics
Crew Analytics — Tier Distribution & Wages
A. TIER DISTRIBUTION
Tier | # Workers | Hours | Gross Pay | % of Hours
Mid | 28 | 14309.5 | 402200 | 50.2%
Apprentice | 7 | 1611.5 | 27924 | 5.7%
B. WAGE STATISTICS
Blended labor rate ($/hr) | 34.82
Foreman labor rate ($/hr) | 0
Burden multiplier | 1.033
Min wage ($/hr) | 16
Max wage ($/hr) | 62.5
Avg hours per worker | 491.7
SOURCES
Job #2061 — Alta Columbia City • GC: Exxel Pacific • Status: CLOSED · 41.4% margin · retention released
Canonical source: 2061_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2061_dashboard_arrays.json (mirrors index.html PROJECTS['2061'])
Project profile: 243 units · 3717 South Alaska Street, Seattle, WA 98118 (Columbia City) · ~35 months
Design team: Johnston Architects (architect), Franklin Engineering (MEP), VIDA (interior)
Contract: L1.220000 · executed 2019-08-08 · $4,305,550 lump sum (AGC Washington 2009 form, modified)
Billing: Final $4,430,088 billed · retention $221,504 released 2022-06-23
Permit: City of Seattle Plumbing + Backflow + Gas (final 2022-03-22)

## Productivity
Productivity — Phases by Hours
Phase | Code | Hours | % of Total | Hours/Unit
Supervision | 100 | 200.5 | 0.7% | 0.83
Takeoff & Purchasing | 101 | 514 | 1.8% | 2.12
Underground | 110 | 1616 | 5.8% | 6.65
Garage | 111 | 2907.5 | 10.4% | 11.97
Canout | 112 | 920 | 3.3% | 3.79
Roughin | 120 | 14973 | 53.6% | 61.62
Finish | 130 | 3202 | 11.5% | 13.18
Gas | 140 | 478 | 1.7% | 1.97
Water Main/Insulation | 141 | 2770 | 9.9% | 11.4
Mech Room | 142 | 561.5 | 2.0% | 2.31
Warranty | 150 | 2 | 0.0% | 0.01
TOTAL |  | 28144.5
PRODUCTIVITY RATIOS
Revenue per unit | $18,231
Direct cost per unit | $10,689
Hours per unit | 115.82
Revenue per hour | $157
Profit per hour | $65
SOURCES
Job #2061 — Alta Columbia City • GC: Exxel Pacific • Status: CLOSED · 41.4% margin · retention released
Canonical source: 2061_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2061_dashboard_arrays.json (mirrors index.html PROJECTS['2061'])
Project profile: 243 units · 3717 South Alaska Street, Seattle, WA 98118 (Columbia City) · ~35 months
Design team: Johnston Architects (architect), Franklin Engineering (MEP), VIDA (interior)
Contract: L1.220000 · executed 2019-08-08 · $4,305,550 lump sum (AGC Washington 2009 form, modified)
Billing: Final $4,430,088 billed · retention $221,504 released 2022-06-23
Permit: City of Seattle Plumbing + Backflow + Gas (final 2022-03-22)

## PO Commitments
PO Commitments — Vendor Concentration
Per-PO records live in GDrive. This tab summarizes commitments by vendor concentration.
# | Vendor | # Invoices | Total Spend | % of AP | Tier
1 | Rosen Supply Kirkland | 223 | 381559 | 37.9% | Top 5
2 | Keller Supply Company | 62 | 223734 | 22.2% | Top 5
3 | Consolidated Supply Co. | 55 | 88009 | 8.7% | Top 5
4 | California Hydronics Corp | 2 | 75297 | 7.5% | Top 5
5 | Franklin Engineering | 15 | 69481 | 6.9% | Top 5
6 | Submeter Solutions, Inc. | 5 | 45601 | 4.5% | Top 10
7 | Ferguson Enterprises, Inc. #3007 | 26 | 36697 | 3.6% | Top 10
8 | Capital One Credit Card | 42 | 27600 | 2.7% | Top 10
9 | Best Bath Systems | 2 | 15782 | 1.6% | Top 10
10 | H&E Equipment Services, Inc. | 20 | 12079 | 1.2% | Top 10
11 | Mechanical Resource Services, Inc. | 1 | 8250 | 0.8% | Long tail
12 | Beacon Building Products $Atlas | 5 | 5338 | 0.5% | Long tail
13 | Old Castle Infrastructure, Inc. | 2 | 4290 | 0.4% | Long tail
14 | Chemical Products Company | 1 | 3050 | 0.3% | Long tail
15 | Mechanical Sales, Inc. | 1 | 2594 | 0.3% | Long tail
16 | Core & Main LP $HD Supply Waterworks | 5 | 2139 | 0.2% | Long tail
17 | Kele, Inc $ MI Controls | 5 | 2071 | 0.2% | Long tail
18 | Scan2Core, Inc. | 1 | 1525 | 0.2% | Long tail
19 | Bank of America CC | 6 | 901 | 0.1% | Long tail
20 | DRSi | 3 | 853 | 0.1% | Long tail
21 | A.R. Brown Backflow Testing | 1 | 280 | 0.0% | Long tail
22 | Washington State Ferries | 1 | 126 | 0.0% | Long tail
23 | Fastenal Company | 1 | 16 | 0.0% | Long tail
SOURCES
Job #2061 — Alta Columbia City • GC: Exxel Pacific • Status: CLOSED · 41.4% margin · retention released
Canonical source: 2061_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2061_dashboard_arrays.json (mirrors index.html PROJECTS['2061'])
Project profile: 243 units · 3717 South Alaska Street, Seattle, WA 98118 (Columbia City) · ~35 months
Design team: Johnston Architects (architect), Franklin Engineering (MEP), VIDA (interior)
Contract: L1.220000 · executed 2019-08-08 · $4,305,550 lump sum (AGC Washington 2009 form, modified)
Billing: Final $4,430,088 billed · retention $221,504 released 2022-06-23
Permit: City of Seattle Plumbing + Backflow + Gas (final 2022-03-22)

## Billing & SOV
Billing & Statement of Values
STATEMENT OF VALUES — SUMMARY
Original Contract | $4,305,550
Net Change Orders | $124,538
Final Contract | $4,430,088
Retainage Held | $221,504
Net Paid to OWP | $4,208,583
PAY APPLICATION HISTORY
Pay App # | Date | This Period | Retainage | Net | Cumulative | % Contract
1 | 01/14/22 | 7667 | -383 | 7667 | 7667 | 0.2%
2 | 01/20/20 | 68300 | -3415 | 68300 | 75967 | 1.7%
3 | 01/20/21 | 499085 | -24954 | 499085 | 575052 | 13.0%
4 | 02/20/20 | 89625 | -4481 | 89625 | 664677 | 15.0%
5 | 02/19/21 | 448716 | -22436 | 448716 | 1113393 | 25.1%
6 | 03/18/22 | 5007 | -250 | 5007 | 1118400 | 25.2%
7 | 03/19/21 | 607368 | -30368 | 607368 | 1725768 | 39.0%
8 | 03/20/20 | 101930 | -5096 | 101930 | 1827698 | 41.3%
9 | 04/20/21 | 508416 | -25421 | 508416 | 2336114 | 52.7%
10 | 05/19/21 | 75208 | -3760 | 75208 | 2411322 | 54.4%
11 | 05/20/20 | 56120 | -2806 | 56120 | 2467442 | 55.7%
12 | 06/18/21 | 55938 | -2797 | 55938 | 2523380 | 57.0%
13 | 06/19/20 | 156090 | -7804 | 156090 | 2679470 | 60.5%
14 | 07/16/21 | 71410 | -3570 | 71410 | 2750880 | 62.1%
15 | 07/20/20 | 78695 | -3935 | 78695 | 2829575 | 63.9%
16 | 08/20/20 | 135691 | -6785 | 135691 | 2965266 | 66.9%
17 | 08/10/21 | 42086 | -2104 | 42086 | 3007352 | 67.9%
18 | 09/20/19 | 58350 | -2918 | 58350 | 3065702 | 69.2%
19 | 09/20/21 | 101275 | -5064 | 101275 | 3166977 | 71.5%
20 | 09/21/20 | 84153 | -4208 | 84153 | 3251130 | 73.4%
21 | 10/20/20 | 391998 | -19600 | 391998 | 3643128 | 82.2%
22 | 10/20/21 | 91812 | -4591 | 91812 | 3734940 | 84.3%
23 | 11/18/20 | 307814 | -15391 | 307814 | 4042754 | 91.3%
24 | 11/19/21 | 33921 | -1696 | 33921 | 4076675 | 92.0%
25 | 12/13/19 | 30400 | -1520 | 30400 | 4107075 | 92.7%
26 | 12/14/20 | 207864 | -10393 | 207864 | 4314939 | 97.4%
27 | 12/17/21 | 115149 | -5757 | 115149 | 4430088 | 100.0%
SOURCES
Job #2061 — Alta Columbia City • GC: Exxel Pacific • Status: CLOSED · 41.4% margin · retention released
Canonical source: 2061_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2061_dashboard_arrays.json (mirrors index.html PROJECTS['2061'])
Project profile: 243 units · 3717 South Alaska Street, Seattle, WA 98118 (Columbia City) · ~35 months
Design team: Johnston Architects (architect), Franklin Engineering (MEP), VIDA (interior)
Contract: L1.220000 · executed 2019-08-08 · $4,305,550 lump sum (AGC Washington 2009 form, modified)
Billing: Final $4,430,088 billed · retention $221,504 released 2022-06-23
Permit: City of Seattle Plumbing + Backflow + Gas (final 2022-03-22)

## Insights
Key Insights — 10 Themes
# | Theme | Insight
1 | MARGIN PROFILE | Net profit of $1,832,588 on $4,430,088 revenue = 41.4% gross margin. Direct cost $2,597,500 absorbs 58.6% of revenue.
2 | VENDOR CONCENTRATION | Rosen Supply Kirkland alone = $381,559 (37.9% of all AP) across 223 invoices. Total 23 AP vendors, $1,007,273 total AP spend.
3 | CREW PROFILE | 58 workers for 28,516 hours = 492 avg hrs/worker. Top 3 workers logged 7,854 hrs combined (28% of all labor).
4 | ROUGHIN DOMINANCE | Code 120 Roughin Labor = 14,973 hrs (53% of all labor). Code 230 Finish Material = $543,379.
5 | BUDGET DELIVERY | Revised expense budget was $3,315,129; actual direct cost $2,597,500 → $717,630 variance.
6 | CONTRACT GROWTH | Contract grew from $4,305,550 to $4,430,088 — net +$124,538 (+2.9%). Retainage of $221,504 (5%) still held.
7 | BURDEN RATIO | Burden codes 995 + 998 = $-3,972,917 on $990,503 labor base = -401.1%. Outside OWP's typical 48–50% labor burden.
8 | PROJECT SCALE | 243 units · 6 retail spaces. Revenue/unit $18,231, hours/unit 117.4, profit/unit $7,542.
9 | PRODUCTIVITY | Blended labor rate $34.82/hr. Revenue/hour $155. Profit/hour $64.
10 | CO PROFILE | COs net +$124,538 (+2.9%). 17 SCO files + 97 COR files captured in GDrive Change Orders folder. OCIP (Wrap-up) insurance per Exxel.
SOURCES
Job #2061 — Alta Columbia City • GC: Exxel Pacific • Status: CLOSED · 41.4% margin · retention released
Canonical source: 2061_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2061_dashboard_arrays.json (mirrors index.html PROJECTS['2061'])
Project profile: 243 units · 3717 South Alaska Street, Seattle, WA 98118 (Columbia City) · ~35 months
Design team: Johnston Architects (architect), Franklin Engineering (MEP), VIDA (interior)
Contract: L1.220000 · executed 2019-08-08 · $4,305,550 lump sum (AGC Washington 2009 form, modified)
Billing: Final $4,430,088 billed · retention $221,504 released 2022-06-23
Permit: City of Seattle Plumbing + Backflow + Gas (final 2022-03-22)

## Benchmark KPIs
Benchmark KPIs — Industry Reference Points
KPI | This Project | OWP Median | Industry Reference | Status
Gross Margin | 41.4% | 32-38% | 30-40% | INFO
Revenue per unit | $18,231 | $10-15k | $8-20k | INFO
Direct cost per unit | $10,689 | $7-10k | $6-15k | INFO
Top vendor % of AP | Pending vendor agg | <35% | <40% | INFO
Burden ratio | 46% | 48-50% | 40-55% | WATCH
SOURCES
Job #2061 — Alta Columbia City • GC: Exxel Pacific • Status: CLOSED · 41.4% margin · retention released
Canonical source: 2061_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2061_dashboard_arrays.json (mirrors index.html PROJECTS['2061'])
Project profile: 243 units · 3717 South Alaska Street, Seattle, WA 98118 (Columbia City) · ~35 months
Design team: Johnston Architects (architect), Franklin Engineering (MEP), VIDA (interior)
Contract: L1.220000 · executed 2019-08-08 · $4,305,550 lump sum (AGC Washington 2009 form, modified)
Billing: Final $4,430,088 billed · retention $221,504 released 2022-06-23
Permit: City of Seattle Plumbing + Backflow + Gas (final 2022-03-22)

## Reconciliation
Reconciliation — Data Source Cross-Check
Check | Expected | Actual | Delta | Status
Contract: hero block vs JDR | $4,430,088 | $4,430,088 | — | OK
Billed: hero block vs JDR | $4,430,088 | $4,208,583 | — | INFO
Direct cost: meta vs costCats | $2,597,500 | $2,597,500 | — | OK
Worker count: dashboard vs meta | 58 | 58 | — | OK
AP vendor count vs JDR | Source aggregate | 23 | — | INFO
SOURCES
Job #2061 — Alta Columbia City • GC: Exxel Pacific • Status: CLOSED · 41.4% margin · retention released
Canonical source: 2061_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2061_dashboard_arrays.json (mirrors index.html PROJECTS['2061'])
Project profile: 243 units · 3717 South Alaska Street, Seattle, WA 98118 (Columbia City) · ~35 months
Design team: Johnston Architects (architect), Franklin Engineering (MEP), VIDA (interior)
Contract: L1.220000 · executed 2019-08-08 · $4,305,550 lump sum (AGC Washington 2009 form, modified)
Billing: Final $4,430,088 billed · retention $221,504 released 2022-06-23
Permit: City of Seattle Plumbing + Backflow + Gas (final 2022-03-22)

## Vendors
Vendor Analysis
# | Vendor | # Invoices | Total Spend | % of AP | Notes
1 | Rosen Supply Kirkland | 223 | 381559 | 37.9% | Trim/finish supplier
2 | Keller Supply Company | 62 | 223734 | 22.2% | Roughin material
3 | Consolidated Supply Co. | 55 | 88009 | 8.7% | Secondary plumbing supply
4 | California Hydronics Corp | 2 | 75297 | 7.5%
5 | Franklin Engineering | 15 | 69481 | 6.9% | Design/MEP fees
6 | Submeter Solutions, Inc. | 5 | 45601 | 4.5%
7 | Ferguson Enterprises, Inc. #3007 | 26 | 36697 | 3.6% | Roughin + finish supplier
8 | Capital One Credit Card | 42 | 27600 | 2.7%
9 | Best Bath Systems | 2 | 15782 | 1.6%
10 | H&E Equipment Services, Inc. | 20 | 12079 | 1.2%
11 | Mechanical Resource Services, Inc. | 1 | 8250 | 0.8%
12 | Beacon Building Products $Atlas | 5 | 5338 | 0.5%
13 | Old Castle Infrastructure, Inc. | 2 | 4290 | 0.4%
14 | Chemical Products Company | 1 | 3050 | 0.3%
15 | Mechanical Sales, Inc. | 1 | 2594 | 0.3%
16 | Core & Main LP $HD Supply Waterworks | 5 | 2139 | 0.2%
17 | Kele, Inc $ MI Controls | 5 | 2071 | 0.2%
18 | Scan2Core, Inc. | 1 | 1525 | 0.2%
19 | Bank of America CC | 6 | 901 | 0.1%
20 | DRSi | 3 | 853 | 0.1%
21 | A.R. Brown Backflow Testing | 1 | 280 | 0.0%
22 | Washington State Ferries | 1 | 126 | 0.0%
23 | Fastenal Company | 1 | 16 | 0.0%
SOURCES
Job #2061 — Alta Columbia City • GC: Exxel Pacific • Status: CLOSED · 41.4% margin · retention released
Canonical source: 2061_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2061_dashboard_arrays.json (mirrors index.html PROJECTS['2061'])
Project profile: 243 units · 3717 South Alaska Street, Seattle, WA 98118 (Columbia City) · ~35 months
Design team: Johnston Architects (architect), Franklin Engineering (MEP), VIDA (interior)
Contract: L1.220000 · executed 2019-08-08 · $4,305,550 lump sum (AGC Washington 2009 form, modified)
Billing: Final $4,430,088 billed · retention $221,504 released 2022-06-23
Permit: City of Seattle Plumbing + Backflow + Gas (final 2022-03-22)