## 01 Overview
OWP #2105 · Compass, 3000 Western
Compass General Construction 1, LLC · 219 units · CANCELLED
Forecast at Completion (Revised Basis)
Revised contract value | 0
Revised budget (expenses) | 0
Forecast net profit | 0
Forecast margin | 0%
Progress to Date
Work complete (billed) | 193091.4
Retention held | 0
Earned less retention | 193091.4
Balance to finish | -193091.4
Percent complete | 0%
Transaction Totals by Source
Source | Dollars
GL | 0
AP | 140707.25
PR | 5349.74
AR | -193091.4

## 02 Job Info
Job Information
Job ID | 2105
Project name | Compass, 3000 Western
General contractor | Compass General Construction 1, LLC
Owner | 3000 Western LLC
Units | 219
Insurance | Standard COI
Job start | N/A (cancelled)
Expected completion | CANCELLED
Architect | Encore Architects
MEP Engineer | GLUMAC / Franklin Engineering
Status | CANCELLED
JDR report date | Apr 3, 2026

## 03 Contract
Contract Summary
Item | Original | Revised | Delta
Base construction contract | 0 | 0 | 0
Executed change orders (net) | 0 | 0 | 0
Total contract value | 0 | 0 | 0
Executed Change Orders
CO # | Description | Amount

## 04 SOV-PayApps
Schedule of Values / Pay Application History
Pay App | Period End | This Period | Completed to Date | Retention Held | Previous Billed | Current Balance

## 05 Change Orders
Change Order Log
# | Type | Description | Amount | Status
date | type | ref | desc | amount

## 06 Cost Codes
Cost Code Detail (Revised Basis)
Code | Description | Original | Revised | Actual | Variance | Net Due | % Complete
101 | Takeoff & Purchase Labor | 0 | 0 | 3014 | -3014 | 0 | 0%
110 | Underground Labor | 0 | 0 | 204 | -204 | 0 | 0%
142 | Mech Room Labor | 0 | 0 | 204 | -204 | 0 | 0%
601 | Engineering/Plans | 0 | 0 | 131071.25 | -131071.25 | 0 | 0%
603 | Permits & Licenses | 0 | 0 | 9636 | -9636 | 0 | 0%
995 | Payroll Burden | 0 | 0 | 1665.94 | -1665.94 | 0 | 0%
998 | Payroll Taxes | 0 | 0 | 261.8 | -261.8 | 0 | 0%
TOTAL |  | 0 | 0 | 146056.99 | -146056.99 | 0 | 0%

## 07 Cost Categories
Cost Category Rollup
Category | # Codes | Revised Budget | Actual | Variance | % Complete
Labor | 3 | 0 | 3422 | -3422 | 0%
Material | 0 | 0 | 0 | 0 | 0%
Overhead | 2 | 0 | 140707.25 | -140707.25 | 0%
Burden | 2 | 0 | 1927.74 | -1927.74 | 0%
TOTAL | 7 | 0 | 146056.99 | -146056.99 | 0%

## 08 BVA
Budget vs Actual — Flag list
Revised budget is canonical basis. Flags: OVER >10%, CRITICAL >50%, ON ±10%, UNDER <-10%.
Code | Description | Revised | Actual | Variance | % Var | Status
101 | Takeoff & Purchase Labor | 0 | 3014 | -3014 | 0% | UNBUDGETED
110 | Underground Labor | 0 | 204 | -204 | 0% | UNBUDGETED
142 | Mech Room Labor | 0 | 204 | -204 | 0% | UNBUDGETED
601 | Engineering/Plans | 0 | 131071.25 | -131071.25 | 0% | UNBUDGETED
603 | Permits & Licenses | 0 | 9636 | -9636 | 0% | UNBUDGETED
995 | Payroll Burden | 0 | 1665.94 | -1665.94 | 0% | UNBUDGETED
998 | Payroll Taxes | 0 | 261.8 | -261.8 | 0% | UNBUDGETED

## 09 Vendor Analysis
Vendor Spend (AP source)
Vendor | Spend ($) | Invoices | % of Total AP
Franklin Engineering | 131071.25 | 10 | 93.15%
Bank of America CC | 9636 | 2 | 6.848%
TOTAL AP | 140707.25 | 12

## 10 Crew Roster
Crew Roster (PR source)
Worker | Hours | Labor $ | Avg $/hr | Tier
Barnhart, Joseph N | 27.5 | 1904 | 69.2364 | LEAD/SUPERVISOR
Gerard, Jeffrey S | 22 | 1518 | 69 | LEAD/SUPERVISOR

## 11 Wage Tiers
Wage Tier Distribution
Tier | # Workers | Hours | Labor $ | % of Hours
LEAD/SUPERVISOR | 2 | 49.5 | 3422 | 100%
JOURNEYMAN | 0 | 0 | 0 | 0%
APPRENTICE/HELPER | 0 | 0 | 0 | 0%
OT-ONLY | 0 | 0 | 0 | 0%

## 12 Productivity
Productivity Metrics
Total labor hours (to date) | 50
Active workers | 2
Hours per unit (to date) | 0.2
Revenue per labor hour (billed) | 3900.84
Percent complete | 0%

## 13 Benchmarks
Portfolio Benchmarks (vs. closed jobs)
Metric | This Job | Portfolio Median | Delta
Forecast margin % | 0% | 34% | -34%
Roughin labor share (code 120) | 0% | 45% | -45%
Top vendor concentration | 93.15% | 38% | 55.15%
Hours per unit | 0.22603 | 95 | -94.774

## 14 Predictive Signals
Predictive Signals (cancelled project)
Signal | Status | Notes
Engineering/Plans (601) unbudgeted | ⚠ WATCH | No revised budget but $131,071 actual spend — needs CO or budget transfer
Top vendor concentration (Franklin Engineering) | ⚠ WATCH | 93% of AP ($131,071) — high, monitor
Retention aging | ✓ OK | $0 held · 0.0% of billed · zero (cancelled)
Forecast margin | ⚠ WATCH | 0.0% forecast margin — monitor

## 15 Reconciliation
JDR Reconciliation
Source | Reported | Calculated | Delta
Total expenses (from code totals) | 146056.99 | 146056.99 | 0
Revenue billed (AR ·-1) | -193091.4 | 193091.4 | -386182.8
AP source total |  | 140707.25 | —
PR source total |  | 5349.74 | —
GL source total |  | 0 | —

## 16 Metric Registry
Metric Registry
Metric | Source Tab | Definition
Forecast margin % | 01 Overview | Forecast net profit / Revised contract value
Percent complete | 01 Overview | Billed to date / Revised contract value
Roughin labor share | 06 Cost Codes | Code 120 revised / Total labor revised budget
Top vendor concentration | 09 Vendor Analysis | Largest single vendor AP spend / Total AP
Hours per unit | 12 Productivity | Total PR hours to date / Unit count
BVA status codes | 08 BVA | OVER / CRITICAL / UNDER / ON / UNBUDGETED on revised basis

## 17 Change Log
Workbook Change Log
Date | Version | Note
2026-04-24 | v1.0 · cancelled | Initial build for #2105 cancelled project. 17-tab JCR schema on revised budget basis.