## 01 Overview
OWP #2109 · Marysville Ph2
Intracorp · 246 units · CANCELLED
Forecast at Completion (Revised Basis)
Revised contract value | 3718851
Revised budget (expenses) | 2119967.36
Forecast net profit | 1598883.64
Forecast margin | 42.99%
Progress to Date
Work complete (billed) | 3570012
Retention held | 153880.15
Earned less retention | 3416131.85
Balance to finish | 148839
Percent complete | 96%
Transaction Totals by Source
Source | Dollars
GL | -349534.48
AP | 1071980.16
PR | 1468646.78
AR | -3077603

## 02 Job Info
Job Information
Job ID | 2109
Project name | Marysville Ph2
General contractor | Intracorp
Owner | TBD
Units | 246
Insurance | TBD
Job start | 2026-04
Expected completion | TBD
Architect | TBD
MEP Engineer | TBD
Status | CANCELLED
JDR report date | Apr 3, 2026

## 03 Contract
Contract Summary
Item | Original | Revised | Delta
Base construction contract | 3700937 | 3718851 | 17914
Executed change orders (net) | 0 | 17914 | 17914
Total contract value | 3700937 | 3736765 | 35828
Executed Change Orders
CO # | Description | Amount

## 04 SOV-PayApps
Schedule of Values / Pay Application History
Pay App | Period End | This Period | Completed to Date | Retention Held | Previous Billed | Current Balance

## 05 Change Orders
Change Order Log
# | Type | Description | Amount | Status

## 06 Cost Codes
Cost Code Detail (Revised Basis)
Code | Description | Original | Revised | Actual | Variance | Net Due | % Complete
100 | Supervision | 18450 | 18450 | 4071 | 14379 | 0 | 22.07%
101 | Takeoff & Purchase Labor | 24600 | 24600 | 15235 | 9365 | 0 | 61.93%
141 | Water Main/Insulation Lab | 0 | 0 | 0 | 0 | 0 | 0%
150 | Warranty Labor | 0 | 0 | 14.25 | -14.25 | 0 | 0%
151 | T&M Labor | 0 | 675 | 670 | 5 | 0 | 99.26%
210 | Underground Material | 96801 | 96801 | 55460.25 | 41340.75 | 0 | 57.29%
220 | Roughin Material | 454876 | 454876 | 464398.31 | -9522.31 | 8449.81 | 102.1%
230 | Finish Material | 835857 | 838640 | 621810.17 | 216829.83 | 95810.87 | 74.15%
240 | Gas Material | 0 | 0 | 0 | 0 | 0 | 0%
241 | Water Main/Insulation Mat | 0 | 0 | 0 | 0 | 0 | 0%
242 | Mech Room Material | 0 | 0 | 2568.72 | -2568.72 | 2517.35 | 0%
600 | Subcontractor | 26000 | 26000 | 2409.88 | 23590.12 | 1334.68 | 9.269%
601 | Engineering/Plans | 5850 | 5850 | 22320 | -16470 | 0 | 381.5%
602 | Rental Equipment | 0 | 0 | 2472.45 | -2472.45 | 262.14 | 0%
603 | Permits & Licenses | 102758 | 102758 | 39307.9 | 63450.1 | 0 | 38.25%
607 | Other Expenses | 12450 | 12450 | 5515 | 6935 | 0 | 44.3%
995 | Payroll Burden | 444827.57 | 448466.07 | 428740.41 | 19725.66 | 0 | 95.6%
998 | Payroll Taxes | 89668.8 | 90401.29 | 73899.85 | 16501.44 | 0 | 81.75%
TOTAL |  | 2112138.37 | 2119967.36 | 1738893.19 | 381074.17 | 108374.85 | 82.02%

## 07 Cost Categories
Cost Category Rollup
Category | # Codes | Revised Budget | Actual | Variance | % Complete
Labor | 4 | 43050 | 19320.25 | 23729.75 | 44.88%
Material | 6 | 1390317 | 1144237.45 | 246079.55 | 82.3%
Overhead | 5 | 147058 | 72025.23 | 75032.77 | 48.98%
Burden | 2 | 538867.36 | 502640.26 | 36227.1 | 93.28%
TOTAL | 17 | 2119292.36 | 1738223.19 | 381069.17 | 82.02%

## 08 BVA
Budget vs Actual — Flag list
Revised budget is canonical basis. Flags: OVER >10%, CRITICAL >50%, ON ±10%, UNDER <-10%.
Code | Description | Revised | Actual | Variance | % Var | Status
100 | Supervision | 18450 | 4071 | 14379 | -77.93% | UNDER
101 | Takeoff & Purchase Labor | 24600 | 15235 | 9365 | -38.07% | UNDER
150 | Warranty Labor | 0 | 14.25 | -14.25 | 0% | UNBUDGETED
151 | T&M Labor | 675 | 670 | 5 | -0.7407% | ON
210 | Underground Material | 96801 | 55460.25 | 41340.75 | -42.71% | UNDER
220 | Roughin Material | 454876 | 464398.31 | -9522.31 | 2.093% | ON
230 | Finish Material | 838640 | 621810.17 | 216829.83 | -25.85% | UNDER
242 | Mech Room Material | 0 | 2568.72 | -2568.72 | 0% | UNBUDGETED
600 | Subcontractor | 26000 | 2409.88 | 23590.12 | -90.73% | UNDER
601 | Engineering/Plans | 5850 | 22320 | -16470 | 281.5% | CRITICAL
602 | Rental Equipment | 0 | 2472.45 | -2472.45 | 0% | UNBUDGETED
603 | Permits & Licenses | 102758 | 39307.9 | 63450.1 | -61.75% | UNDER
607 | Other Expenses | 12450 | 5515 | 6935 | -55.7% | UNDER
995 | Payroll Burden | 448466.07 | 428740.41 | 19725.66 | -4.398% | ON
998 | Payroll Taxes | 90401.29 | 73899.85 | 16501.44 | -18.25% | UNDER

## 09 Vendor Analysis
Vendor Spend (AP source)
Vendor | Spend ($) | Invoices | % of Total AP
Pacific Plumbing Supply Co., LLC | 500869.06 | 169 | 46.72%
Consolidated Supply Co. | 305149.79 | 107 | 28.47%
Rosen Supply Kirkland | 103987.31 | 94 | 9.7%
California Hydronics Corp | 76546 | 6 | 7.141%
Keller Supply Company | 52035.97 | 24 | 4.854%
Franklin Engineering | 22320 | 1 | 2.082%
Williams Scotsman, Inc. $Mobile Mini | 2472.45 | 10 | 0.2306%
Ferguson Enterprises, Inc. #3007 | 2408 | 1 | 0.2246%
ACME Corp | 1983.84 | 7 | 0.1851%
All Pro Repair Service LLC | 1865.27 | 3 | 0.174%
Capital One Credit Card | 1602.9 | 10 | 0.1495%
A.R. Brown Backflow Testing | 544.61 | 2 | 0.0508%
Bank of America CC | 194.96 | 2 | 0.01819%
TOTAL AP | 1071980.16 | 436

## 10 Crew Roster
Crew Roster (PR source)
Worker | Hours | Labor $ | Avg $/hr | Tier
Gerard, Jeffrey S | 168 | 11592 | 69 | LEAD/SUPERVISOR
Gerard, Jordan E | 98 | 5831 | 59.5 | LEAD/SUPERVISOR
Romero Garza, Jesus I | 60 | 0 | 0 | APPRENTICE/HELPER
Wilson, Garret A | 28.8 | 1553 | 53.9236 | LEAD/SUPERVISOR
Johnson, Jake E | 11 | 572 | 52 | LEAD/SUPERVISOR
Goodwin, Marcus A | 8.5 | 238 | 28 | JOURNEYMAN
Barnhart, Joseph N | 3 | 204 | 68 | LEAD/SUPERVISOR
Aquino, Juan | 0 | 0 | 0 | OT-ONLY
Castro, Marcus J | 0 | 0 | 0 | OT-ONLY
Araque, Mario W | 0 | 0 | 0 | OT-ONLY
Ramos Herrera, Franklin J | 0 | 0 | 0 | OT-ONLY
Young, Joshua S | 0 | 0 | 0 | OT-ONLY
Fox, Tamron P | 0 | 0 | 0 | OT-ONLY
Reed, Reuben H | 0 | 0 | 0 | OT-ONLY
Del Villar, Flabio | 0 | 0 | 0 | OT-ONLY
Balderas Ortiz, Ricardo I | 0 | 0 | 0 | OT-ONLY
Guerrero Espinoza, Mario | 0 | 0 | 0 | OT-ONLY
Rodriguez Arevalos, Christian | 0 | 0 | 0 | OT-ONLY
Perez Araque, Manuel A | 0 | 0 | 0 | OT-ONLY
Cornejo Orellana, Carlos E | 0 | 0 | 0 | OT-ONLY
Ross, Kelli M | 0 | 0 | 0 | OT-ONLY
Merino Martinez, Humberto | 0 | 0 | 0 | OT-ONLY
Portillo Soriano, Walter A | 0 | 0 | 0 | OT-ONLY
Gochez Molina, Douglas O | 0 | 0 | 0 | OT-ONLY
Castro Hernandez, Jose A | 0 | 0 | 0 | OT-ONLY
Cruz, Azael S | 0 | 0 | 0 | OT-ONLY
Gorman, Nathan W | 0 | 0 | 0 | OT-ONLY
Taylor, Evan R | 0 | 0 | 0 | OT-ONLY
Valeriano Romero, Oswaldo | 0 | 0 | 0 | OT-ONLY
Gerard, Mitchell J | 0 | 0 | 0 | OT-ONLY

## 11 Wage Tiers
Wage Tier Distribution
Tier | # Workers | Hours | Labor $ | % of Hours
LEAD/SUPERVISOR | 5 | 308.8 | 19752 | 81.84%
JOURNEYMAN | 1 | 8.5 | 238 | 2.253%
APPRENTICE/HELPER | 1 | 60 | 0 | 15.9%
OT-ONLY | 23 | 0 | 0 | 0%

## 12 Productivity
Productivity Metrics
Total labor hours (to date) | 377
Active workers | 30
Hours per unit (to date) | 1.5
Revenue per labor hour (billed) | 9463.25
Percent complete | 96%

## 13 Benchmarks
Portfolio Benchmarks (vs. closed jobs)
Metric | This Job | Portfolio Median | Delta
Forecast margin % | 42.99% | 34% | 8.994%
Roughin labor share (code 120) | 0% | 45% | -45%
Top vendor concentration | 46.72% | 38% | 8.724%
Hours per unit | 1.5335 | 95 | -93.4665

## 14 Predictive Signals
Predictive Signals (cancelled project)
Signal | Status | Notes
Engineering/Plans (601) CRITICAL overrun | ⚠ WATCH | Actual $22,320 vs revised $5,850 (+282%) — needs immediate attention
Top vendor concentration (Pacific Plumbing Sup) | ⚠ WATCH | 47% of AP ($500,869) — high, monitor
Retention aging | ✓ OK | $153,880 held · 4.3% of billed · zero (cancelled)
Forecast margin | ✓ OK | 43.0% forecast margin — healthy

## 15 Reconciliation
JDR Reconciliation
Source | Reported | Calculated | Delta
Total expenses (from code totals) | 2683501.46 | 1738893.19 | 944608.27
Revenue billed (AR ·-1) | -3570012 | 3077603 | -6647615
AP source total |  | 1071980.16 | —
PR source total |  | 1468646.78 | —
GL source total |  | -349534.48 | —

## 16 Metric Registry
Metric Registry
Metric | Source Tab | Definition
Forecast margin % | 01 Overview | Forecast net profit / Revised contract value
Percent complete | 01 Overview | Billed to date / Revised contract value
Roughin labor share | 06 Cost Codes | Code 120 revised / Total labor revised budget
Top vendor concentration | 09 Vendor Analysis | Largest single vendor AP spend / Total AP
Hours per unit | 12 Productivity | Total PR hours to date / Unit count
BVA status codes | 08 BVA | OVER / CRITICAL / UNDER / ON / UNBUDGETED on revised basis

## 17 Change Log
Workbook Change Log
Date | Version | Note
2026-04-25 | v1.0 · cancelled | Initial build for #2109 cancelled project. 17-tab JCR schema on revised budget basis.