## 01 Overview
OWP #2110 · Roosevelt Manor
Sierra · 137 units · CANCELLED
Forecast at Completion (Revised Basis)
Revised contract value | 0
Revised budget (expenses) | 0
Forecast net profit | 0
Forecast margin | 0%
Progress to Date
Work complete (billed) | 78800
Retention held | 0
Earned less retention | 78800
Balance to finish | -78800
Percent complete | 0%
Transaction Totals by Source
Source | Dollars
GL | 0
AP | 121649.5
PR | 12850.85
AR | -78800

## 02 Job Info
Job Information
Job ID | 2110
Project name | Roosevelt Manor
General contractor | Sierra
Owner | TBD
Units | 137
Insurance | TBD
Job start | 2026-05
Expected completion | TBD
Architect | TBD
MEP Engineer | TBD
Status | CANCELLED
JDR report date | Apr 3, 2026

## 03 Contract
Contract Summary
Item | Original | Revised | Delta
Base construction contract | 0 | 0 | 0
Executed change orders (net) | 0 | 0 | 0
Total contract value | 0 | 0 | 0
Executed Change Orders
CO # | Description | Amount

## 04 SOV-PayApps
Schedule of Values / Pay Application History
Pay App | Period End | This Period | Completed to Date | Retention Held | Previous Billed | Current Balance

## 05 Change Orders
Change Order Log
# | Type | Description | Amount | Status

## 06 Cost Codes
Cost Code Detail (Revised Basis)
Code | Description | Original | Revised | Actual | Variance | Net Due | % Complete
100 | Supervision | 0 | 0 | 132.75 | -132.75 | 0 | 0%
101 | Takeoff & Purchase Labor | 0 | 0 | 7486.75 | -7486.75 | 0 | 0%
120 | Roughin Labor | 0 | 0 | 612 | -612 | 0 | 0%
601 | Engineering/Plans | 0 | 0 | 93353.5 | -93353.5 | 0 | 0%
603 | Permits & Licenses | 0 | 0 | 28296 | -28296 | 0 | 0%
995 | Payroll Burden | 0 | 0 | 3989.55 | -3989.55 | 0 | 0%
998 | Payroll Taxes | 0 | 0 | 629.8 | -629.8 | 0 | 0%
TOTAL |  | 0 | 0 | 134500.35 | -134500.35 | 0 | 0%

## 07 Cost Categories
Cost Category Rollup
Category | # Codes | Revised Budget | Actual | Variance | % Complete
Labor | 3 | 0 | 8231.5 | -8231.5 | 0%
Material | 0 | 0 | 0 | 0 | 0%
Overhead | 2 | 0 | 121649.5 | -121649.5 | 0%
Burden | 2 | 0 | 4619.35 | -4619.35 | 0%
TOTAL | 7 | 0 | 134500.35 | -134500.35 | 0%

## 08 BVA
Budget vs Actual — Flag list
Revised budget is canonical basis. Flags: OVER >10%, CRITICAL >50%, ON ±10%, UNDER <-10%.
Code | Description | Revised | Actual | Variance | % Var | Status
100 | Supervision | 0 | 132.75 | -132.75 | 0% | UNBUDGETED
101 | Takeoff & Purchase Labor | 0 | 7486.75 | -7486.75 | 0% | UNBUDGETED
120 | Roughin Labor | 0 | 612 | -612 | 0% | UNBUDGETED
601 | Engineering/Plans | 0 | 93353.5 | -93353.5 | 0% | UNBUDGETED
603 | Permits & Licenses | 0 | 28296 | -28296 | 0% | UNBUDGETED
995 | Payroll Burden | 0 | 3989.55 | -3989.55 | 0% | UNBUDGETED
998 | Payroll Taxes | 0 | 629.8 | -629.8 | 0% | UNBUDGETED

## 09 Vendor Analysis
Vendor Spend (AP source)
Vendor | Spend ($) | Invoices | % of Total AP
Franklin Engineering | 93353.5 | 10 | 76.74%
Bank of America CC | 28296 | 3 | 23.26%
TOTAL AP | 121649.5 | 13

## 10 Crew Roster
Crew Roster (PR source)
Worker | Hours | Labor $ | Avg $/hr | Tier
Gerard, Jordan E | 66 | 3928 | 59.5152 | LEAD/SUPERVISOR
Gerard, Jeffrey S | 53.5 | 3692 | 69.0093 | LEAD/SUPERVISOR
Barnhart, Joseph N | 9 | 612 | 68 | LEAD/SUPERVISOR

## 11 Wage Tiers
Wage Tier Distribution
Tier | # Workers | Hours | Labor $ | % of Hours
LEAD/SUPERVISOR | 3 | 128.5 | 8232 | 100%
JOURNEYMAN | 0 | 0 | 0 | 0%
APPRENTICE/HELPER | 0 | 0 | 0 | 0%
OT-ONLY | 0 | 0 | 0 | 0%

## 12 Productivity
Productivity Metrics
Total labor hours (to date) | 128
Active workers | 3
Hours per unit (to date) | 0.9
Revenue per labor hour (billed) | 613.23
Percent complete | 0%

## 13 Benchmarks
Portfolio Benchmarks (vs. closed jobs)
Metric | This Job | Portfolio Median | Delta
Forecast margin % | 0% | 34% | -34%
Roughin labor share (code 120) | 0% | 45% | -45%
Top vendor concentration | 76.74% | 38% | 38.74%
Hours per unit | 0.93796 | 95 | -94.062

## 14 Predictive Signals
Predictive Signals (cancelled project)
Signal | Status | Notes
Engineering/Plans (601) unbudgeted | ⚠ WATCH | No revised budget but $93,354 actual spend — needs CO or budget transfer
Permits & Licenses (603) unbudgeted | ⚠ WATCH | No revised budget but $28,296 actual spend — needs CO or budget transfer
Top vendor concentration (Franklin Engineering) | ⚠ WATCH | 77% of AP ($93,354) — high, monitor
Retention aging | ✓ OK | $0 held · 0.0% of billed · zero (cancelled)
Forecast margin | ⚠ WATCH | 0.0% forecast margin — monitor

## 15 Reconciliation
JDR Reconciliation
Source | Reported | Calculated | Delta
Total expenses (from code totals) | 134500.35 | 134500.35 | 0
Revenue billed (AR ·-1) | -78800 | 78800 | -157600
AP source total |  | 121649.5 | —
PR source total |  | 12850.85 | —
GL source total |  | 0 | —

## 16 Metric Registry
Metric Registry
Metric | Source Tab | Definition
Forecast margin % | 01 Overview | Forecast net profit / Revised contract value
Percent complete | 01 Overview | Billed to date / Revised contract value
Roughin labor share | 06 Cost Codes | Code 120 revised / Total labor revised budget
Top vendor concentration | 09 Vendor Analysis | Largest single vendor AP spend / Total AP
Hours per unit | 12 Productivity | Total PR hours to date / Unit count
BVA status codes | 08 BVA | OVER / CRITICAL / UNDER / ON / UNBUDGETED on revised basis

## 17 Change Log
Workbook Change Log
Date | Version | Note
2026-04-25 | v1.0 · cancelled | Initial build for #2110 cancelled project. 17-tab JCR schema on revised budget basis.