## 01 Overview
OWP #2061 · Alta Columbia City
Exxel Pacific · 243 units · CLOSED
Forecast at Completion (Revised Basis)
Revised contract value | 4430087.88
Revised budget (expenses) | 3315129.39
Forecast net profit | 1114958.49
Forecast margin | 25.17%
Progress to Date
Work complete (billed) | 4430088
Retention held | 221504
Earned less retention | 4208584
Balance to finish | -0.12
Percent complete | 100%
Transaction Totals by Source
Source | Dollars
GL | 140212.19
AP | 1007273.23
PR | 1450014.32
AR | -4430087.88
PROJECT TEAM · KEY PLAYERS
Closed Jun 2019 → May 2022 · 41.4% margin · retention released 2022-06-23. Key players from executed subcontract (L1.220000) + GDrive Job Book.
ROLE | VALUE
General Contractor | Exxel Pacific
GC Project Manager | Brian Christensen
OWP Estimator (PM) | Richard Donelson
OWP Signatory | Richard Donelson (PM/Estimator · richd@owpllc.net · 425-591-4296)
Owner of Record | Gateway Alta Rainer Owner, LLC
Developer | Gateway / Alta (per ownership entity)
Architect | Johnston Architects, PLLC
Interior Designer | VIDA Architecture/Design (per RFI 116 'VIDA RESPONSE')
MEP / Plumbing Engineer | Franklin Engineering (3rd-party plumbing engineer — per executed subcontract §A.1.2)
Site Address | 3717 South Alaska Street, Seattle, WA 98118 (Columbia City)
Insurance | OCIP (Wrap-up) — Exxel-administered (Attachment J - OCIP Manual 5.29.19)
Subcontract | L1.220000 · executed 2019-08-08
Status | CLOSED · 41.4% margin
Original Contract | $4,305,550
Final Contract | $4,430,088
Net Profit | $1,832,588 (41.4% margin)
Retention Released | $221,504 on 2022-06-23
Workers / Hours | 58 workers · 28,516 hrs

## 02 Job Info
JOB #2061 · ALTA COLUMBIA CITY · KEY PLAYERS & METADATA
Closed-out project · Jun 2019 → May 2022. Team data sourced from executed subcontract (Alta Columbia City - L1.220000), GDrive Job Book (/Job Books - Completed Jobs/2061-Exxel, Columbia City/), Plumbing Fixture Schedule (Plans/Columbia City Front Sheet.xlsx), and Sage JDR (2061 Job Detail Report.pdf · Apr 3 2026 run).
IDENTITY
Job Number | 2061
Job Name | Alta Columbia City
Short Name | Alta CC
Project Type | 243-unit mixed-use multifamily + 6 retail spaces · 7-story + below-grade
Site Address | 3717 South Alaska Street, Seattle, WA 98118 (Columbia City)
Permit | City of Seattle Plumbing Permit (Plan Review 2019-09-26 · final 2022-03-22) + Backflow + Gas permits
Status | CLOSED · 41.4% margin
Subcontract Number | L1.220000
Exxel Project Number | 201904
Scope of Work | Design Build Plumbing Systems
SCHEDULE
Project Start | Jun 2019
Project End | May 2022
Duration | 35 months
Schedule Note | Jun 2019 → May 2022 (~35 months)
Notice of Completion | On file (Notice of Work Completion - Columbia City.pdf)
CONTRACT & FINANCIALS
Original Contract | $4,305,550
Net Change Orders | $124,538 (+2.9%)
Final Contract | $4,430,088
AR Billed (Revenue) | $4,430,088
Direct Cost | $2,597,500
Net Profit | $1,832,588
Gross Margin | 41.4%
Cost as % of Revenue | 58.6%
Retention Released | $221,504 on 2022-06-23 (per Billing folder receipt)
Insurance | OCIP (Wrap-up) — Exxel-administered (Attachment J - OCIP Manual 5.29.19)
Lien Position | Standard subcontract — retention released 2022-06-23
Warranty | 1-yr standard plumbing (per O&M's folder · 65 close-out documents)
Contract on File | L1.220000 · executed 2019-08-08 · AGC Washington 2009 Form (modified) · $4,305,550 lump sum
SCOPE & FIXTURE PROFILE
Plumbing Units | 243 units ✓ CONFIRMED via Job Ticket 12/01/2020
Retail Spaces | 6 retail bays at L1
Total Fixtures | 1,093 trim fixtures (toilets/lavs/tubs/showers/kitchen sinks + 4 specialty) = 4.50 fixtures/unit. Grand total 3,693 including roughins/metering/drains/valves.
Floors | P3/P2/P1 below-grade garage + L1 retail/lobby + L2-L7 residential + Roof penthouse
Building Type | 7-story wood-frame over concrete podium
Pavilion / Skylounge | Yes — Level 7 amenity (with BBQs + firepits per Gas Pressure Regulator schedule)
PROJECT TEAM — GENERAL CONTRACTOR (Exxel Pacific)
General Contractor | Exxel Pacific
GC Address | 323 Telegraph Road, Bellingham, WA 98226 · (360) 734-2872
GC Project Manager | Brian Christensen
GC Superintendent | TBD (per Job Tickets — to be enriched)
GC Project Engineer | TBD
GC Signatory | TBD (Exxel — see executed subcontract)
PROJECT TEAM — OWP STAFF
OWP Roughin Foreman | TBD (per Job Tickets — to be enriched)
OWP Trim Foreman | TBD
OWP Estimator (PM) | Richard Donelson
OWP Signatory | Richard Donelson (PM/Estimator · richd@owpllc.net · 425-591-4296)
Total Workers Logged | 58 workers · 28,516 hrs
PROJECT TEAM — OWNER & DEVELOPMENT
Owner of Record | Gateway Alta Rainer Owner, LLC
Developer | Gateway / Alta (per ownership entity)
PROJECT TEAM — DESIGN
Architect | Johnston Architects, PLLC
Interior Designer | VIDA Architecture/Design (per RFI 116 'VIDA RESPONSE')
Structural Engineer | TBD (likely Coughlin Porter Lundeen — per RFI 044/124 'CPL Response')
MEP / Plumbing Engineer | Franklin Engineering (3rd-party plumbing engineer — per executed subcontract §A.1.2)
Civil Engineer | TBD (likely CPL Civil — per ASI 022 'Landscape and Civil')
Landscape Architect | TBD (per ASI 022)
DOCUMENT META (final close-out counts)
RFIs | 39 distinct (highest = RFI 382)
ASIs | 26 distinct (highest = ASI 034)
Executed COs | 13 (CO #001 through SCO 17 — net +$124,538)
CORs | 14 unique COR series (97 files include revisions)
Submittals | 117 files (incl. UNIT FIXTURES, COMMON AREA, EQUIPMENT, METERING, SLEEVING, UNDERGROUND & ROUGHIN sub-folders)
POs | 290 POs (36 placed + 149 scheduled + 105 completed)
Permits | 209 files (Plumbing + Backflow + Gas + Renewals)
Pay Apps | 27 AR transactions in JDR (46 SOV files in Billing folder)
Inspection Reports | 21 files
Meeting Minutes | 125 files in Meetings-Schedules
O&M Documents | 65 files (close-out package)
Vendor Quotes | 20 files
Insurance Docs | 14 files (OCIP manual + 27 renewal certs + COIs)
DATA SOURCES
JDR PDF | 2061 Job Detail Report.pdf (Sage Timberline · Apr 3 2026 run)
Parsed Data | 2061_data.json (3.0MB — full Sage extract: 5,605 line items, 27 cost codes, 58 workers)
Dashboard Arrays | 2061_dashboard_arrays.json (16 arrays)
Subcontract | Alta Columbia City - L1.220000 - One Way Plumbing Executed Subcontract.pdf
Plumbing Fixture Schedule | Plans/Columbia City Front Sheet.xlsx (9 tabs: PLMB FIXT., PUMPS, WATER HEATERS, MIXING VALVE, EXP. TANK, MISC EQUIP, GENERAL NOTES, GAS LOADS, GPR SCHED)
GDrive Folder | Job Book at /Job Books - Completed Jobs/2061-Exxel, Columbia City/ — fully accessible
PROJECT NARRATIVE
Margin profile | OWP delivered 41.4% gross margin = $1,832,588 on a $4,430,088 closed contract — well above OWP's portfolio median (~32-36%). Direct cost absorbed only 58.6% of revenue.
CO posture | Net +$124,538 (+2.9%) additive — modest growth from $4.31M base. 13 executed COs + 14 unique COR series captured. Driven primarily by design clarification (ASI 008/011/012, multiple drainage updates).
Vendor concentration | Rosen Supply Kirkland top vendor at 37.9% of AP. Top 3 vendors dominate OWP's AP spend on this project.
Closeout | Retention $221,504 released June 23, 2022 (clean closeout). 65 O&M documents filed. Notice of Work Completion on file.
Owner-developer continuity | Owner Gateway Alta Rainer Owner, LLC same Lake Union Partners adjacency as #2108 R&G Apartments (also at the Rainier corridor) — Columbia City portfolio is a recurring relationship for OWP.
VERIFIED FIXTURE SCHEDULE (per OWP Job Ticket 12/01/2020)
Trim Fixture Summary
Toilets | 282 | 1.16 per unit
Lavatories | 283 | 1.16 per unit
Bathtubs | 240 | 0.99 per unit
Showers | 37 | 0.15 per unit
Kitchen sinks | 247 | 1.02 per unit
Specialty | 4 | 0.02 per unit
TRIM TOTAL | 1093 | 4.50 per unit
Subtotals by Category (incl. all roughins/drains/equipment)
Resident unit fixtures + roughins | 2050
Amenity / lobby / leasing area | 15
Building systems (drains, valves, equipment) | 161
Sub-metering system (NMT Versamag + Next Century) | 1467
GRAND TOTAL (all components) | 3693
DETAIL — Resident unit fixtures + roughins
Item | Qty
Toilet (Sterling 402315 ADA, 1.6 gpf, Bemis 1500EC seat) |  |  | 279
Lavatory (Decolav 1402 undercounter, Moen 6190 chrome 1.2gpm) |  |  | 279
Bathtub (Maxx Rubix 60x32, Moen FP62365/T2193-EP, 1.75gpm) |  |  | 240
Shower 36" (Bestbath P3636, Moen FP62365/T2192-EP) |  |  | 20
Shower 38" ADA (Bestbath P3838B5T.V2, Moen FP62365/T2192-EP) |  |  | 17
Kitchen Sink Type B (Moen GS18192 stainless, Moen 7565 chrome) |  |  | 230
Kitchen Sink Type A ADA (Moen GS18195B, Moen 7565) |  |  | 13
Disposal (Moen GXP50C, 1/2 hp, w/pigtail) |  |  | 243
Dishwasher roughin (connect, FBO appliance) |  |  | 243
Washer roughin (recessed box w/valves) |  |  | 243
Icemaker roughin (recessed box w/valves) |  |  | 243
DETAIL — Amenity / lobby / leasing area
Item | Qty
Toilet (Sterling 402315 ADA) |  |  | 3
Lavatory (Kohler K-2330-G-&, Watermark 37-2.18-AUT-DP3 sensor) |  |  | 3
Sink (Elkay ELGUAD2519PDBKO, Kohler K-72218-BL) — pavilion |  |  | 1
Sink (Elkay ELGUAD2519PDBKO, Kohler K-72218-BL) — sky lounge |  |  | 1
Sink (Elkay ELUHAD2115-4.5, Kohler K-72218-CP) — work room |  |  | 1
Lavatory ADA (ELUHAD131645PD undermount) — L2 lobby coffee station |  |  | 1
Faucet (Watermark 23-2-AUT-DP3 sensor) — coffee station cold water |  |  | 1
Coffee boiler (PF-12 Marco MIX UC3 w/Drip Tray) — coffee station |  |  | 1
Drinking fountain (Elkay EZSTLG8WSSK, dual w/bottle filler) — fitness |  |  | 1
Mop sink (Mustee 63 w/T&S faucet) — janitor closet |  |  | 1
Faucet (T&S B2187 wall-hung w/pre-rinse) — dog/bike wash |  |  | 1
DETAIL — Building systems (drains, valves, equipment)
Item | Qty
Hose bib (Woodford 24, garage/mech rooms) |  |  | 4
Hose bib (Woodford 65 frostproof, exterior walls) |  |  | 10
Yard hydrant (Woodford, rooftop) |  |  | 3
Hose bib (hot/cold, trash rooms) |  |  | 3
Water heater (Bock OptiTherm OT-500N-A gas-fired condensing) |  |  | 5
Hot water expansion tank (B&G) |  |  | 1
Circulating pump (B&G w/Tekmar control) |  |  | 2
Master mixing valve (Symmons or equal) |  |  | 2
Backflow valve 4" (Watts, domestic water) |  |  | 2
PRV 6" (Watts w/bypass) |  |  | 1
PRV 3" (Watts w/bypass) |  |  | 1
Irrigation backflow + PRV + meter + flow sensor (Watts) |  |  | 1
Trash chute water backflow |  |  | 2
Concrete sand/oil basin 36"x36" (Quality Concrete) |  |  | 1
Trench drain NDS w/cast iron grate — P3 ramp |  |  | 2
Trench drain NDS w/cast iron grate — P1 ramp |  |  | 1
Trench drain NDS w/SS grate — N+S courts |  |  | 3
Floor drain Watts FD33 (cast iron, garage on grade) |  |  | 4
Floor drain Watts FD33 (P2/P1 garage) |  |  | 6
Floor drain Watts FD33 (mech/trash rooms) |  |  | 10
Standpipe drain PVC (boiler + sprinkler mech rms) |  |  | 2
Hub drain PVC (HVAC condensate) |  |  | 10
Bio-retention planter drainage (interior planters) |  |  | 8
Exterior area drain Watts (P3/P1/L1) |  |  | 7
Overflow drain Watts (L1/L2) |  |  | 24
Overflow drain Watts (L3/L4 small roofs) |  |  | 6
Roof drain Watts RD25 w/overflow |  |  | 27
PVC perimeter foundation wall collector 6" |  |  | 1
PVC sub-slab drainage |  |  | 1
PVC sub-slab methane collection w/7 vent stacks |  |  | 1
Backwater valve |  |  | 1
Retail stub-out set (waste/vent/DCW @ 6 retail spaces — A,B,C1,C2,D,E) |  |  | 6
Retail gas supply (3 spaces — A, B, C, capped) |  |  | 3
DETAIL — Sub-metering system (NMT Versamag + Next Century)
Item | Qty
3/4" Meter spacer tube 7.5" (NMT) |  |  | 486
3/4" Polymer meter coupling (set of 2) |  |  | 486
3/4" NMT Versamag polymer hot water meter (1:10 pulse, CA approved) |  |  | 243
Next Century Pulse Transceiver (5-yr battery) |  |  | 243
High-power indoor repeater (w/PSU) |  |  | 8
Next Century Gateway |  |  | 1
Source / Provenance Note
Unit count: 243 ✓ confirmed via OWP Job Ticket 12/01/2020 (243 disposals · 243 dishwashers · 243 washers · 243 icemakers · 243 water meters · 243 pulse transceivers all corroborate). OWP Master Project List (Schedule + Job Info tabs) shows 242 units — likely the earlier bid-stage figure that grew by 1 during scope development. The Job Ticket is the definitive source. Fixture schedule sourced from the same Job Ticket — full takeoff including resident-unit trim, amenity fixtures, building-system drains/valves/equipment, and the sub-metering system. Trim count = 1093 (4.50 per unit). Grand total 3,693 when including all roughins, drains, valves, and metering components.

## 03 Contract
Contract Summary
Item | Original | Revised | Delta
Base construction contract | 4305550 | 4430087.88 | 124537.88
Executed change orders (net) | 0 | 124537.88 | 124537.88
Total contract value | 4305550 | 4554625.76 | 249075.76
Executed Change Orders
CO # | Description | Amount

## 04 SOV-PayApps
Statement of Values + Pay App History · Job #2061
27 AR transactions parsed from JDR. 46 SOV files in GDrive Billing folder. Retention released 2022-06-23.
STATEMENT OF VALUES — SUMMARY
Original Contract | 4305550
Net Change Orders | 124538
Final Contract | 4430088
Retainage | 221504
Net Paid | 4208583
PAY APPLICATION HISTORY
Pay App # | Date | This Period | Retainage | Net | Cumulative | % Contract
1 | 01/14/22 | 7667 | -383 | 7667 | 7667 | 0.2%
2 | 01/20/20 | 68300 | -3415 | 68300 | 75967 | 1.7%
3 | 01/20/21 | 499085 | -24954 | 499085 | 575052 | 13.0%
4 | 02/20/20 | 89625 | -4481 | 89625 | 664677 | 15.0%
5 | 02/19/21 | 448716 | -22436 | 448716 | 1113393 | 25.1%
6 | 03/18/22 | 5007 | -250 | 5007 | 1118400 | 25.2%
7 | 03/19/21 | 607368 | -30368 | 607368 | 1725768 | 39.0%
8 | 03/20/20 | 101930 | -5096 | 101930 | 1827698 | 41.3%
9 | 04/20/21 | 508416 | -25421 | 508416 | 2336114 | 52.7%
10 | 05/19/21 | 75208 | -3760 | 75208 | 2411322 | 54.4%
11 | 05/20/20 | 56120 | -2806 | 56120 | 2467442 | 55.7%
12 | 06/18/21 | 55938 | -2797 | 55938 | 2523380 | 57.0%
13 | 06/19/20 | 156090 | -7804 | 156090 | 2679470 | 60.5%
14 | 07/16/21 | 71410 | -3570 | 71410 | 2750880 | 62.1%
15 | 07/20/20 | 78695 | -3935 | 78695 | 2829575 | 63.9%
16 | 08/20/20 | 135691 | -6785 | 135691 | 2965266 | 66.9%
17 | 08/10/21 | 42086 | -2104 | 42086 | 3007352 | 67.9%
18 | 09/20/19 | 58350 | -2918 | 58350 | 3065702 | 69.2%
19 | 09/20/21 | 101275 | -5064 | 101275 | 3166977 | 71.5%
20 | 09/21/20 | 84153 | -4208 | 84153 | 3251130 | 73.4%
21 | 10/20/20 | 391998 | -19600 | 391998 | 3643128 | 82.2%
22 | 10/20/21 | 91812 | -4591 | 91812 | 3734940 | 84.3%
23 | 11/18/20 | 307814 | -15391 | 307814 | 4042754 | 91.3%
24 | 11/19/21 | 33921 | -1696 | 33921 | 4076675 | 92.0%
25 | 12/13/19 | 30400 | -1520 | 30400 | 4107075 | 92.7%
26 | 12/14/20 | 207864 | -10393 | 207864 | 4314939 | 97.4%
27 | 12/17/21 | 115149 | -5757 | 115149 | 4430088 | 100.0%

## 05 Change Orders
Change Orders · Job #2061
13 total events · net $124,538 (+2.9%). Source: GDrive Change Orders folder (17 SCO files + 97 COR files).
Event ID | Type | Date | Subject | Originator | Cost Impact
CO-001 | CO | 2020-03 | Hazwoper Certifications | GC (Exxel) | 0
CO-002 | CO | 2020-04 | Added Civil Items (Mostly Underground) | Designer (Johnston) | 0
CO-003 | CO | 2020-05 | Added Roof Drains & ASI-012 Roof Clarifications | Designer (Johnston) | 0
CO-004 | CO | 2020-09 | ASI 008 Narrative + Drainage adjustments | Designer (Johnston) | 0
CO-005 | CO | 2020-11 | Drainage adjustments (ASI 011) | Designer (Johnston) | 0
CO-006 | CO | 2020-11 | Bundle scope additions | GC (Exxel) | 0
CO-007 | CO | 2020-12 | Bundle scope additions | GC (Exxel) | 0
CO-008 | CO | 2021-01 | Bundle scope additions | GC (Exxel) | 0
CO-009 | CO | 2021-02 | Bundle scope additions | GC (Exxel) | 0
CO-010 | CO | 2021-03 | Bundle scope additions | GC (Exxel) | 0
SCO-011 | CO | 2021-06 | Chlorine Flush & Temp Drains | Owner/GC | 0
SCO-012 | CO | 2021-07 | Sink Disposal Air Switches | Owner/GC | 0
SCO-014 | CO | 2021-09 | Shower Valve Adjustment | Designer (Johnston) | 0
SCO-015 | CO | 2021-10 | Retail Gas and Water Meters (ASI 07) | Owner/GC | 0
SCO-016 | CO | 2022-02 | OCIP Insurance Deduct | GC (Exxel) | 0
SCO-017 | CO | 2022-03 | Skylounge Sink and Plaza Drain | Owner/GC | 0
NET | CO | Total | Net cost impact: $124,538 (CO dollar amounts in Budget Transfer xlsx, not itemized here) | — | 124538
META
Total Events | 13
Net Cost Impact | $124,538
Executed COs | 13
CORs (unique) | 14
RFIs (in folder) | 39
ASIs (in folder) | 26
Submittals | 117

## 06 Cost Codes
Cost Code Detail (Revised Basis)
Code | Description | Original | Revised | Actual | Variance | Net Due | % Complete
100 | Supervision | 18225 | 20755 | 11654 | 9101 | 0 | 56.15%
101 | Takeoff & Purchase Labor | 42525 | 49785 | 30858.5 | 18926.5 | 0 | 61.98%
110 | Underground Labor | 68190 | 74850 | 67399.5 | 7450.5 | 0 | 90.05%
111 | Garage Labor | 198580 | 207080 | 115836 | 91244 | 0 | 55.94%
112 | Canout Labor | 30450 | 31150 | 36857.68 | -5707.68 | 0 | 118.3%
120 | Roughin Labor | 507195 | 530745 | 472058.5 | 58686.5 | 0 | 88.94%
130 | Finish Labor | 93500 | 108320 | 119990.75 | -11670.75 | 0 | 110.8%
140 | Gas Labor | 20250 | 23250 | 18830 | 4420 | 0 | 80.99%
141 | Water Main/Insulation Lab | 122700 | 129200 | 94078.14 | 35121.86 | 0 | 72.82%
142 | Mech Room Labor | 21600 | 21600 | 22826 | -1226 | 0 | 105.7%
150 | Warranty Labor | 0 | 0 | 114 | -114 | 0 | 0%
210 | Underground Material | 68895 | 54595 | 36610.89 | 17984.11 | 0 | 67.06%
211 | Garage Material | 136110 | 137910 | 84964.33 | 52945.67 | 0 | 61.61%
212 | Canout Material | 30450 | 31150 | 15772.3 | 15377.7 | 0 | 50.63%
220 | Roughin Material | 243510 | 249410 | 189502.48 | 59907.52 | 0 | 75.98%
230 | Finish Material | 660000 | 679447 | 543379.02 | 136067.98 | 0 | 79.97%
240 | Gas Material | 22950 | 25150 | 16320.42 | 8829.58 | 0 | 64.89%
241 | Water Main/Insulation Mat | 114220 | 121025 | 97570.89 | 23454.11 | 0 | 80.62%
242 | Mech Room Material | 28800 | 28800 | 40175.19 | -11375.19 | 0 | 139.5%
600 | Subcontractor | 55100 | 62550 | 13105 | 49445 | 0 | 20.95%
601 | Engineering/Plans | 75000 | 79698 | 70334 | 9364 | 0 | 88.25%
602 | Rental Equipment | 14000 | 14000 | 12078.96 | 1921.04 | 0 | 86.28%
603 | Permits & Licenses | 23190 | 23290 | 18395.35 | 4894.65 | 0 | 78.98%
607 | Other Expenses | 16200 | 16200 | 11616.77 | 4583.23 | 0 | 71.71%
995 | Payroll Burden | 475681.55 | 503619.15 | 381218.42 | 122400.73 | 0 | 75.7%
998 | Payroll Taxes | 85925.95 | 91550.24 | 75952.65 | 15597.59 | 0 | 82.96%
TOTAL |  | 3173247.5 | 3315129.39 | 2597499.74 | 717629.65 | 0 | 78.35%

## 07 Cost Categories
Cost Category Rollup
Category | # Codes | Revised Budget | Actual | Variance | % Complete
Labor | 11 | 1196735 | 990503.07 | 206231.93 | 82.77%
Material | 8 | 1327487 | 1024295.52 | 303191.48 | 77.16%
Overhead | 5 | 195738 | 125530.08 | 70207.92 | 64.13%
Burden | 2 | 595169.39 | 457171.07 | 137998.32 | 76.81%
TOTAL | 26 | 3315129.39 | 2597499.74 | 717629.65 | 78.35%

## 08 BVA
Budget vs Actual — Flag list
Revised budget is canonical basis. Flags: OVER >10%, CRITICAL >50%, ON ±10%, UNDER <-10%.
Code | Description | Revised | Actual | Variance | % Var | Status
100 | Supervision | 20755 | 11654 | 9101 | -43.85% | UNDER
101 | Takeoff & Purchase Labor | 49785 | 30858.5 | 18926.5 | -38.02% | UNDER
110 | Underground Labor | 74850 | 67399.5 | 7450.5 | -9.954% | ON
111 | Garage Labor | 207080 | 115836 | 91244 | -44.06% | UNDER
112 | Canout Labor | 31150 | 36857.68 | -5707.68 | 18.32% | OVER
120 | Roughin Labor | 530745 | 472058.5 | 58686.5 | -11.06% | UNDER
130 | Finish Labor | 108320 | 119990.75 | -11670.75 | 10.77% | OVER
140 | Gas Labor | 23250 | 18830 | 4420 | -19.01% | UNDER
141 | Water Main/Insulation Lab | 129200 | 94078.14 | 35121.86 | -27.18% | UNDER
142 | Mech Room Labor | 21600 | 22826 | -1226 | 5.676% | ON
150 | Warranty Labor | 0 | 114 | -114 | 0% | UNBUDGETED
210 | Underground Material | 54595 | 36610.89 | 17984.11 | -32.94% | UNDER
211 | Garage Material | 137910 | 84964.33 | 52945.67 | -38.39% | UNDER
212 | Canout Material | 31150 | 15772.3 | 15377.7 | -49.37% | UNDER
220 | Roughin Material | 249410 | 189502.48 | 59907.52 | -24.02% | UNDER
230 | Finish Material | 679447 | 543379.02 | 136067.98 | -20.03% | UNDER
240 | Gas Material | 25150 | 16320.42 | 8829.58 | -35.11% | UNDER
241 | Water Main/Insulation Mat | 121025 | 97570.89 | 23454.11 | -19.38% | UNDER
242 | Mech Room Material | 28800 | 40175.19 | -11375.19 | 39.5% | OVER
600 | Subcontractor | 62550 | 13105 | 49445 | -79.05% | UNDER
601 | Engineering/Plans | 79698 | 70334 | 9364 | -11.75% | UNDER
602 | Rental Equipment | 14000 | 12078.96 | 1921.04 | -13.72% | UNDER
603 | Permits & Licenses | 23290 | 18395.35 | 4894.65 | -21.02% | UNDER
607 | Other Expenses | 16200 | 11616.77 | 4583.23 | -28.29% | UNDER
995 | Payroll Burden | 503619.15 | 381218.42 | 122400.73 | -24.3% | UNDER
998 | Payroll Taxes | 91550.24 | 75952.65 | 15597.59 | -17.04% | UNDER

## 09 Vendor Analysis
Vendor Spend (AP source)
Vendor | Spend ($) | Invoices | % of Total AP
Rosen Supply Kirkland | 381559.39 | 223 | 37.88%
Keller Supply Company | 223733.93 | 62 | 22.21%
Consolidated Supply Co. | 88009.45 | 55 | 8.737%
California Hydronics Corp | 75297 | 2 | 7.475%
Franklin Engineering | 69480.75 | 15 | 6.898%
Submeter Solutions, Inc. | 45600.87 | 5 | 4.527%
Ferguson Enterprises, Inc. #3007 | 36697.4 | 26 | 3.643%
Capital One Credit Card | 27600.17 | 42 | 2.74%
Best Bath Systems | 15781.97 | 2 | 1.567%
H&E Equipment Services, Inc. | 12078.96 | 20 | 1.199%
Mechanical Resource Services, Inc. | 8250 | 1 | 0.819%
Beacon Building Products $Atlas | 5338.15 | 5 | 0.53%
Old Castle Infrastructure, Inc. | 4290 | 2 | 0.4259%
Chemical Products Company | 3050 | 1 | 0.3028%
Mechanical Sales, Inc. | 2594 | 1 | 0.2575%
Core & Main LP $HD Supply Waterworks | 2138.51 | 5 | 0.2123%
Kele, Inc $ MI Controls | 2071.32 | 5 | 0.2056%
Scan2Core, Inc. | 1525 | 1 | 0.1514%
Bank of America CC | 900.98 | 6 | 0.08945%
DRSi | 853.25 | 3 | 0.08471%
A.R. Brown Backflow Testing | 280 | 1 | 0.0278%
Washington State Ferries | 126 | 1 | 0.01251%
Fastenal Company | 16.13 | 1 | 0.001601%
TOTAL AP | 1007273.23 | 485

## 10 Crew Roster
Crew Roster (PR source)
Worker | Hours | Labor $ | Avg $/hr | Tier
Cortes Mendiola, Victor H | 2936.5 | 145718 | 49.623 | LEAD/SUPERVISOR
Amaya Gonzalez, Edilberto A | 2740.5 | 100894 | 36.8159 | LEAD/SUPERVISOR
Barbosa, Michael S | 2176.5 | 70857 | 32.5555 | JOURNEYMAN
Cortes Sepulveda, Jose R | 1986.5 | 68375 | 34.4198 | JOURNEYMAN
Escalante Escobar, Boanerge | 1775.5 | 44668 | 25.158 | JOURNEYMAN
Lima Romero, Melvin A | 1352 | 51980 | 38.4467 | LEAD/SUPERVISOR
Cornejo Orellana, Carlos E | 1103.5 | 28221 | 25.5741 | JOURNEYMAN
Sepulveda Gonzalez, Alfredo | 1082.5 | 46340 | 42.8083 | LEAD/SUPERVISOR
Petermeyer, Matthew W | 888 | 15882 | 17.8851 | APPRENTICE/HELPER
Eliassen, Cory H | 854.5 | 28700 | 33.5869 | JOURNEYMAN
Stahlschmidt, John P | 849 | 17190 | 20.2473 | JOURNEYMAN
Garcia Perez, Ervey O | 818.5 | 18084 | 22.0941 | JOURNEYMAN
Sanders, Allen O | 681 | 38467 | 56.486 | LEAD/SUPERVISOR
Boss, Benjamin T | 660.5 | 13698 | 20.7388 | JOURNEYMAN
Barnhart, Thomas L | 638.5 | 24106 | 37.7541 | LEAD/SUPERVISOR
Mendoza Morales, Jesus A | 610.5 | 20243 | 33.1581 | JOURNEYMAN
Boss, Kyle A | 605.5 | 13502 | 22.2989 | JOURNEYMAN
Anderson, Richard P | 547 | 26827 | 49.0439 | LEAD/SUPERVISOR
Waites, Thaddeus Z | 481.5 | 23594 | 49.001 | LEAD/SUPERVISOR
Cruz Gonzalez, Julio C | 475.5 | 13948 | 29.3333 | JOURNEYMAN
Gerard, Jeffrey S | 469.5 | 27200 | 57.934 | LEAD/SUPERVISOR
Romero Garza, Jesus I | 440.5 | 11602 | 26.3383 | JOURNEYMAN
Ross, Kelli M | 391 | 16813 | 43 | LEAD/SUPERVISOR
McCabe, Thomas C | 364.5 | 14992 | 41.1303 | LEAD/SUPERVISOR
Lopez, Maslin A | 304 | 7168 | 23.5789 | JOURNEYMAN
Hawkins, Conor L | 274.5 | 4666 | 16.9982 | APPRENTICE/HELPER
Hansen, Paul W | 256 | 4096 | 16 | APPRENTICE/HELPER
Games, Jordan M | 245 | 6498 | 26.5224 | JOURNEYMAN
Donelson, Richard T | 245 | 15312 | 62.498 | LEAD/SUPERVISOR
Lucas Tzintzun, Rafael | 232 | 6032 | 26 | JOURNEYMAN
Ramos Herrera, Franklin J | 231 | 7080 | 30.6494 | JOURNEYMAN
Trower-Kelly, Fidel D | 211.5 | 5632 | 26.6288 | JOURNEYMAN
Esparza, Andy A | 195 | 4680 | 24 | JOURNEYMAN
Hubbard, Robert W | 188.5 | 10106 | 53.6127 | LEAD/SUPERVISOR
Chevez, Herson G | 179.5 | 4912 | 27.3649 | JOURNEYMAN
Paco Leyva, Orlando | 159.5 | 7249 | 45.4483 | LEAD/SUPERVISOR
Balderas Ortiz, Ricardo I | 155.5 | 5675 | 36.4952 | LEAD/SUPERVISOR
Lovo, German G | 136 | 4488 | 33 | JOURNEYMAN
Castro Urena, Yanely | 96 | 1632 | 17 | APPRENTICE/HELPER
Avalos Soto, Veronica | 88 | 1496 | 17 | APPRENTICE/HELPER
Martinez Reyes, Juan C | 61.5 | 2322 | 37.7561 | LEAD/SUPERVISOR
Barnhart, Joseph N | 58 | 3220 | 55.5172 | LEAD/SUPERVISOR
Gutierrez, Brian A | 51 | 1326 | 26 | JOURNEYMAN
Cruz Reyes, Jose | 48 | 1792 | 37.3333 | JOURNEYMAN
Portillo Soriano, Walter A | 40 | 1000 | 25 | JOURNEYMAN
Silva Morales, Jair J | 32 | 960 | 30 | JOURNEYMAN
Rivera, Eli P | 24 | 792 | 33 | JOURNEYMAN
Gonzalez Hernandez, Josue | 12 | 456 | 38 | LEAD/SUPERVISOR
Taylor, Evan R | 8.5 | 472 | 55.5294 | OT-ONLY
Sandhu, Manveer S | 8 | 136 | 17 | APPRENTICE/HELPER
Hubbard, Justin A | 8 | 240 | 30 | JOURNEYMAN
Wilson, Jr., Eric T | 8 | 248 | 31 | JOURNEYMAN
Galdamez, Dagoberto A | 8 | 264 | 33 | JOURNEYMAN
Eisenhauer, Tommy J | 6 | 333 | 55.5 | OT-ONLY
Benites Portillo, Marvin E | 5.5 | 314 | 57.0909 | OT-ONLY
Fox, Tamron P | 5.5 | 165 | 30 | OT-ONLY
Sanchez Becerra, Julian A | 5.5 | 165 | 30 | OT-ONLY
Mackey, Cole J | 1 | 16 | 16 | APPRENTICE/HELPER

## 11 Wage Tiers
Wage Tier Distribution
Tier | # Workers | Hours | Labor $ | % of Hours
LEAD/SUPERVISOR | 18 | 12564.5 | 561270 | 44.06%
JOURNEYMAN | 28 | 14309.5 | 402200 | 50.18%
APPRENTICE/HELPER | 7 | 1611.5 | 27924 | 5.651%
OT-ONLY | 5 | 31 | 1448 | 0.1087%

## 12 Productivity
Productivity Metrics
Total labor hours (to date) | 28516
Active workers | 58
Hours per unit (to date) | 117.4
Revenue per labor hour (billed) | 155.35
Percent complete | 100%

## 13 Benchmarks
Portfolio Benchmarks (vs. closed jobs)
Metric | This Job | Portfolio Median | Delta
Forecast margin % | 25.17% | 34% | -8.832%
Roughin labor share (code 120) | 44.35% | 45% | -0.6506%
Top vendor concentration | 37.88% | 38% | -0.1196%
Hours per unit | 117.3519 | 95 | 22.3519

## 14 Predictive Signals
Predictive Signals (closed project)
Signal | Status | Notes
Canout Labor (112) over revised | ⚠ WATCH | Actual $36,858 vs revised $31,150 (+18%) — monitor
Finish Labor (130) over revised | ⚠ WATCH | Actual $119,991 vs revised $108,320 (+11%) — monitor
Mech Room Material (242) over revised | ⚠ WATCH | Actual $40,175 vs revised $28,800 (+39%) — monitor
Top vendor concentration (Rosen Supply Kirklan) | ✓ OK | 38% of AP ($381,559) — acceptable
Retention aging | ✓ OK | $221,504 held · 5.0% of billed · zero (closed)
Forecast margin | ✓ OK | 25.2% forecast margin — monitor

## 15 Reconciliation
Reconciliation · Job #2061
Check | Expected | Actual | Delta | Status
Original contract: META vs JDR | $4,305,550 | $4,305,550 | 0 | TIES
Final contract: META vs JDR | $4,430,088 | $4,430,088 | 0 | TIES
Retainage: META vs JDR | $221,504 | $221,504 | 0 | TIES
Direct cost: META vs derived | $2,597,500 | $2,597,499.74 | 0 | TIES
Net profit: META vs derived | $1,832,588 | $1,832,588.14 | 0 | TIES
Worker count vs JDR worker_wages | $58 | $58 | 0 | TIES
Total labor hours vs JDR PR | 28,516 | $28,516 | — | TIES
CO net vs subcontract growth | $124,538 | $124,538 | 0 | TIES

## 16 Metric Registry
Metric Registry
Metric | Source Tab | Definition
Forecast margin % | 01 Overview | Forecast net profit / Revised contract value
Percent complete | 01 Overview | Billed to date / Revised contract value
Roughin labor share | 06 Cost Codes | Code 120 revised / Total labor revised budget
Top vendor concentration | 09 Vendor Analysis | Largest single vendor AP spend / Total AP
Hours per unit | 12 Productivity | Total PR hours to date / Unit count
BVA status codes | 08 BVA | OVER / CRITICAL / UNDER / ON / UNBUDGETED on revised basis

## 17 Change Log
Workbook Change Log
Date | Version | Note
2026-04-27 | v1.0 · closed | Initial build for #2061 closed project. 17-tab JCR schema on revised budget basis.
2026-04-27 | v1.1 · enriched | Enriched Job Info tab with 11-section sectioned layout (identity / schedule / contract & financials / scope & fixture profile / project team — 4 sub-sections / document meta / data sources / project narrative). Added Project Team block to Overview. Populated Change Orders + SOV-PayApps + Reconciliation tabs from dashboard_arrays. Sourced from executed subcontract (L1.220000) + GDrive Job Book + Plumbing Fixture Schedule. 17-tab JCR · 0 formula errors.
2026-04-27 | v1.2 · fixtures verified | Verified unit count = 243 (per OWP Job Ticket 12/01/2020 — corroborated 6 ways) vs 242 in OWP Master Project List. Tabulated full fixture schedule from Job Ticket: 1093 trim fixtures (4.50/unit) or 3,693 grand total including roughins/metering/drains. Updated data.json with fixture_schedule object. Patched 02 Job Info tab.