## Report Record
JCR TEST LABELS — JOB 2108
Report-level fields from the v4 schema (v2.2 with extensions).
Field | Value
job_number | 2108
job_name | Compass, 3000 Western
report_date | 2026-04-03
project_start_date | 2027-01
project_end_date | TBD
general_contractor | Braseth
owner | TBD
location | TBD
project_type | Multi-family apartments (on-hold · summer 26?)
units | 263
contract_original | 0
contract_final | 0
billed_to_date | 0
retention_amount | 0
line_items_count | 52
cost_code_count | 7
job_totals_revenue | -91402
job_totals_expenses | 117161.97
job_totals_net | -25759.97
job_totals_net_due | 0
job_totals_retainage | 0

## Line Items
LINE ITEMS — 52 TRANSACTIONS
Every transaction line parsed from the JDR PDF.
cost_code | description | source | ref_number | document_date | posted_date | number | name | regular_hours | overtime_hours | doubletime_hours | other_hours | regular_amount | overtime_amount | actual_amount | check_number | net_due | retainage
101 | Takeoff & Purchase Labor | PR | 530 | 02/26/25 | 02/28/25 | GE69 | Gerard, Jeffrey S | 2.5 | 0 | 0 | 0 | 172.5 | 0 | 172.5 | 43413 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 175 | 05/07/25 | 05/09/25 | GE70 | Gerard, Jordan E | 6 | 0 | 0 | 0 | 360 | 0 | 360 | 23524 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 374 | 05/14/25 | 05/16/25 | GE70 | Gerard, Jordan E | 2 | 0 | 0 | 0 | 120 | 0 | 120 | 33533 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 469 | 05/21/25 | 05/23/25 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 43541 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 470 | 05/21/25 | 05/23/25 | GE70 | Gerard, Jordan E | 3 | 0 | 0 | 0 | 180 | 0 | 180 | 43542 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 558 | 05/28/25 | 05/30/25 | GE69 | Gerard, Jeffrey S | 3 | 0 | 0 | 0 | 207 | 0 | 207 | 53550 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 207 | 06/11/25 | 06/13/25 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 23566 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 334 | 06/18/25 | 06/20/25 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 33573 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 489 | 06/25/25 | 06/27/25 | GE69 | Gerard, Jeffrey S | 5 | 0 | 0 | 0 | 345 | 0 | 345 | 43582 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 32 | 07/02/25 | 07/03/25 | GE69 | Gerard, Jeffrey S | 4 | 0 | 0 | 0 | 276 | 0 | 276 | 13589 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 33 | 07/02/25 | 07/03/25 | GE70 | Gerard, Jordan E | 1 | 0 | 0 | 0 | 60 | 0 | 60 | 13590 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 157 | 07/09/25 | 07/11/25 | GE69 | Gerard, Jeffrey S | 3 | 0 | 0 | 0 | 207 | 0 | 207 | 23596 | 0 | 0
601 | Engineering/Plans | AP | 591 | 11/20/24 | 11/21/24 | 1625FE | Franklin Engineering | [6 empty] | 1162.5 | 1308 | 0 | 0
601 | Engineering/Plans | AP | 523 | 12/18/24 | 12/20/24 | 1625FE | Franklin Engineering | [6 empty] | 3498.75 | 1345 | 0 | 0
601 | Engineering/Plans | AP | 480 | 01/17/25 | 01/22/25 | 1625FE | Franklin Engineering | [6 empty] | 4006.25 | 1367 | 0 | 0
601 | Engineering/Plans | AP | 493 | 03/20/25 | 03/21/25 | 1625FE | Franklin Engineering | [6 empty] | 13556.25 | 1443 | 0 | 0
601 | Engineering/Plans | AP | 519 | 04/19/25 | 04/21/25 | 1625FE | Franklin Engineering | [6 empty] | 18292.5 | 1479 | 0 | 0
601 | Engineering/Plans | GL | 284 | 05/09/25 | 05/09/25 | Franklin | Engineering | [6 empty] | 15858.75 |  | 0 | 0
601 | Engineering/Plans | AP | 439 | 05/21/25 | 05/21/25 | 1625FE | Franklin Engineering | [6 empty] | 24567.5 | 1516 | 0 | 0
601 | Engineering/Plans | AP | 408 | 06/19/25 | 06/24/25 | 1625FE | Franklin Engineering | [6 empty] | 9652.5 | 1560 | 0 | 0
601 | Engineering/Plans | AP | 428 | 08/21/25 | 08/22/25 | 1625FE | Franklin Engineering | [6 empty] | 9300 | 1619 | 0 | 0
601 | Engineering/Plans | AP | 365 | 09/21/25 | 09/23/25 | 1625FE | Franklin Engineering | [6 empty] | 6592.5 | 1655 | 0 | 0
602 | Rental Equipment | AP | 175 | 06/09/25 | 06/11/25 | 6502HR | Herc Rentals, Inc. | [6 empty] | 922.35 | 35512556-001 | 0 | 0
603 | Permits & Licenses | AP | 441 | 06/09/25 | 06/25/25 | 1234BA | Bank of America CC | [6 empty] | 264 | 060925J | 0 | 0
603 | Permits & Licenses | AP | 390 | 12/12/25 | 01/20/26 | 1234BA | Bank of America CC | [6 empty] | 6138 | 121225B | 0 | 0
995 | Payroll Burden | PR | 530 | 02/26/25 | 02/28/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 85.04 |  | 0 | 0
995 | Payroll Burden | PR | 175 | 05/07/25 | 05/09/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 177.48 |  | 0 | 0
995 | Payroll Burden | PR | 374 | 05/14/25 | 05/16/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 59.16 |  | 0 | 0
995 | Payroll Burden | PR | 469 | 05/21/25 | 05/23/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 34.02 |  | 0 | 0
995 | Payroll Burden | PR | 470 | 05/21/25 | 05/23/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 88.74 |  | 0 | 0
995 | Payroll Burden | PR | 558 | 05/28/25 | 05/30/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 102.05 |  | 0 | 0
995 | Payroll Burden | PR | 207 | 06/11/25 | 06/13/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 34.02 |  | 0 | 0
995 | Payroll Burden | PR | 334 | 06/18/25 | 06/20/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 34.02 |  | 0 | 0
995 | Payroll Burden | PR | 489 | 06/25/25 | 06/27/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 170.09 |  | 0 | 0
995 | Payroll Burden | PR | 32 | 07/02/25 | 07/03/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 136.07 |  | 0 | 0
995 | Payroll Burden | PR | 33 | 07/02/25 | 07/03/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 29.58 |  | 0 | 0
995 | Payroll Burden | PR | 157 | 07/09/25 | 07/11/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 102.05 |  | 0 | 0
998 | Payroll Taxes | PR | 530 | 02/26/25 | 02/28/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 13.2 |  | 0 | 0
998 | Payroll Taxes | PR | 175 | 05/07/25 | 05/09/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 27.54 |  | 0 | 0
998 | Payroll Taxes | PR | 374 | 05/14/25 | 05/16/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 9.18 |  | 0 | 0
998 | Payroll Taxes | PR | 469 | 05/21/25 | 05/23/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 470 | 05/21/25 | 05/23/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 13.77 |  | 0 | 0
998 | Payroll Taxes | PR | 558 | 05/28/25 | 05/30/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 15.84 |  | 0 | 0
998 | Payroll Taxes | PR | 207 | 06/11/25 | 06/13/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 334 | 06/18/25 | 06/20/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 489 | 06/25/25 | 06/27/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 26.39 |  | 0 | 0
998 | Payroll Taxes | PR | 32 | 07/02/25 | 07/03/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 21.11 |  | 0 | 0
998 | Payroll Taxes | PR | 33 | 07/02/25 | 07/03/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 4.59 |  | 0 | 0
998 | Payroll Taxes | PR | 157 | 07/09/25 | 07/11/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 15.84 |  | 0 | 0
999 | Sales | AR | 381 | 06/20/25 | 06/20/25 | 2108RG | Rainier & Genesee, LLC | [6 empty] | -85000 | 038448 | 0 | 0
999 | Sales | AR | 2 | 02/02/26 | 02/02/26 | 2108LU | Lake Union Partners $R&G Apts | [6 empty] | -6138 | 038534 | 0 | 0
999 | Sales | AR | 2 | 02/02/26 | 02/02/26 | 2108LU | Lake Union Partners $R&G Apts | [6 empty] | -264 | 038534 | 0 | 0

## Cost Code Summaries
COST CODE SUMMARIES — 7 CODES
code | description | category | original_budget | current_budget | plus_minus_budget | actual_amount | net_due | retainage | regular_hours | overtime_hours | doubletime_hours | other_hours
101 | Takeoff & Purchase Labor | Labor | 0 | 0 | 2134.5 | 2134.5 | 0 | 0 | 32.5 | 0 | 0 | 0
601 | Engineering/Plans | Overhead | 0 | 0 | 106487.5 | 106487.5 | 0 | 0 | 0 | 0 | 0 | 0
602 | Rental Equipment | Overhead | 0 | 0 | 922.35 | 922.35 | 0 | 0 | 0 | 0 | 0 | 0
603 | Permits & Licenses | Overhead | 0 | 0 | 6402 | 6402 | 0 | 0 | 0 | 0 | 0 | 0
995 | Payroll Burden | Burden | 0 | 0 | 1052.32 | 1052.32 | 0 | 0 | 0 | 0 | 0 | 0
998 | Payroll Taxes | Burden | 0 | 0 | 163.3 | 163.3 | 0 | 0 | 0 | 0 | 0 | 0
999 | Sales | Revenue | 0 | 0 | 91402 | -91402 | 0 | 0 | 0 | 0 | 0 | 0

## Worker Wages
WORKER NOMINAL WAGES — 2 WORKERS
Per-worker wage data derived from PR line items in the JDR.
Worker (Last, First) | Reg Hours | OT Hours | DT Hours | Other Hours | Reg Amount | OT Amount | Nominal Rate ($/hr) | Tier
LEAD/SUPERVISOR
Gerard, Jordan E | 12 | 0 | 0 | 0 | 720 | 0 | 60 | LEAD/SUPERVISOR
Gerard, Jeffrey S | 20.5 | 0 | 0 | 0 | 1414.5 | 0 | 69 | LEAD/SUPERVISOR

## Derived Fields
DERIVED FIELDS — 36 CALCULATIONS
All derived values computed from parsed data.
Field | Value | Formula / Logic
cost_by_source_pr_amount | 3350.12
cost_by_source_ap_amount | 97953.1
cost_by_source_gl_amount | 15858.75
direct_cost | 117161.97
net_profit | -25759.97
pr_pct_of_revenue | 0.036653
ap_pct_of_revenue | 1.0717
direct_cost_pct_of_revenue | 1.2818
total_labor_hours | 32.5
pr_src_cost_per_hr | 103.0806
fully_loaded_wage | 140.4843
burden_multiplier | 1.3629
straight_time_rate | 65.6769
total_workers | 2
nominal_wage_percentiles | {'p10': 60.9, 'p25': 62.25, 'p50': 64.5, 'p75': 66.75, 'p90': 68.1}
burden_total | 1215.62
material_spend_total | 0
material_budget_total | 0
material_codes_tracked | 0
material_codes_over_budget | 0
material_codes_under_budget | 0
largest_material_overrun | None
largest_material_savings | None
material_vendor_count | 3
top_vendor_spend | Franklin Engineering: $90,629 (93% of AP)
phases_over_budget | 6
phases_under_budget | 0
largest_overrun | 601 Engineering/Plans: $106,488 vs $0 budget (+$106,488)
largest_savings | 998 Payroll Taxes: $163 vs $0 budget ($163)
total_jtd_cost | 117161.97
total_budget | 0
overall_pct_budget_consumed | 0
total_over_under_budget | -117161.97
labor_unit_cost_per_hr | 65.6769
revenue_per_labor_hour | 2812.3692
material_price_variance | 0

## Reconciliation
RECONCILIATION — PER COST CODE
Parsed line item sums vs. cost code summary totals from the PDF.
Cost Code | Description | PDF Total | Parsed Sum | Difference | Status
101 | Takeoff & Purchase Labor | 2134.5 | 2134.5 |  | PASS
601 | Engineering/Plans | 106487.5 | 106487.5 |  | PASS
602 | Rental Equipment | 922.35 | 922.35 |  | PASS
603 | Permits & Licenses | 6402 | 6402 |  | PASS
995 | Payroll Burden | 1052.32 | 1052.32 |  | PASS
998 | Payroll Taxes | 163.3 | 163.3 |  | PASS
999 | Sales | -91402 | -91402 |  | PASS

## Reconciliation Log
RECONCILIATION LOG
Audit log of any reconciliation events / adjustments / re-parses.
Date | Event Type | Source | Description | Before | After | Operator
2026-04-27 | initial_parse | parse_2108.py | Initial Sage JDR parse for Job #2108. Parsed lines: 52. Cost codes: 7. Workers: 2. | (no prior parse) | 52 line items | OWP Estimating