## Overview
Job #2108 · R&G Apartments
Cortex JCR Summary • Braseth Construction (Owner: TBD)
PROJECT OVERVIEW
Project Job # | 2108
Project Name: | R&G Apartments
General Contractor | Braseth Construction (Owner: TBD)
Location | TBD
Project Duration | Q1 2027 (estimated) – TBD (Pre-construction — on hold)
Status | ON HOLD · Summer 2026?
CONTRACT VALUE |  | FORECAST NET PROFIT |  | DIRECT COST |  | LABOR HOURS
$91,402 |  | $-25,760 |  | $117,162 |  | 32
$0 orig + $0 COs |  | -28.2% margin |  | 128.2% of revenue |  | 2 workers
COST BREAKDOWN
Category | Budget | Actual | Variance | % Budget | % of Cost
Labor | 0 | 2134 | -2134 | 0 | 0.018214
Material | 0 | 0 | 0 | 0 | 0
Overhead | 0 | 113812 | -113812 | 0 | 0.97141
Burden | 0 | 1216 | -1216 | 0 | 0.010379
TOTAL | 0 | 117162 | -117162 | 0 | 1
PROJECT PROFILE
Plumbing Units | 263 | Total Fixtures | TBD | Fixtures / Unit | TBD
GC | Braseth Construction | Owner | TBD | Insurance | Standard COI
Status | ON HOLD · Summer 2026? | Duration | Pre-construction — on hold | Permit | Pre-permit
NARRATIVE
Pre-construction project — on hold pending Braseth go-ahead. OWP has sunk $117k of design + takeoff cost (Franklin Engineering $90.6k MEP design fee + $6.4k permit + $2.1k takeoff labor + $922 equipment + $1.2k burden). Only $91.4k has been billed. Carrying loss of $25.8k if project doesn't activate. Reach out to Braseth PM to confirm summer 2026 start before Q4 2026.
SOURCES
Job #2108 — R&G Apartments • GC: Braseth Construction • Status: ON HOLD · Summer 2026?
Canonical source: 2108_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2108_dashboard_arrays.json (mirrors index.html PROJECTS['2108'])
Project profile: 263 units · TBD · Pre-construction — on hold
Design team: Franklin Engineering (MEP per AP $90.6k design fee)
Contract: Not yet executed
Billing: No pay apps filed (only $91k design billing)
Permit: Pre-permit

## Budget vs Actual
Budget vs Actual — All Cost Codes
Code | Description | Orig Budget | Rev Budget | Actual | Variance | % Used
LABOR
101 | Takeoff & Purchase Labor | 0 | 0 | 2134 | -2134 | 0
OVERHEAD
601 | Engineering/Plans | 0 | 0 | 106488 | -106488 | 0
602 | Rental Equipment | 0 | 0 | 922 | -922 | 0
603 | Permits & Licenses | 0 | 0 | 6402 | -6402 | 0
BURDEN
995 | Payroll Burden | 0 | 0 | 1052 | -1052 | 0
998 | Payroll Taxes | 0 | 0 | 163 | -163 | 0
TOTAL Direct Cost |  | 117161.97 | 117161.97 | 117161.97
SOURCES
Job #2108 — R&G Apartments • GC: Braseth Construction • Status: ON HOLD · Summer 2026?
Canonical source: 2108_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2108_dashboard_arrays.json (mirrors index.html PROJECTS['2108'])
Project profile: 263 units · TBD · Pre-construction — on hold
Design team: Franklin Engineering (MEP per AP $90.6k design fee)
Contract: Not yet executed
Billing: No pay apps filed (only $91k design billing)
Permit: Pre-permit

## Cost Breakdown
Cost Breakdown — Category Deep Dive
A. CATEGORY SHARE OF DIRECT COST
Category | # Codes | Budget | Actual | Variance | % Budget | % of Cost
Labor | 1 | 0 | 2134 | -2134 | 0 | 0.018214
Overhead | 3 | 0 | 113812 | -113812 | 0 | 0.97141
Burden | 2 | 0 | 1216 | -1216 | 0 | 0.010379
B. LARGEST OVERRUNS (Actual > Revised Budget)
Code | Description | Rev Budget | Actual | Overrun | % Over
601 | Engineering/Plans | 0 | 106488 | 106488 | 0
603 | Permits & Licenses | 0 | 6402 | 6402 | 0
101 | Takeoff & Purchase Labor | 0 | 2134 | 2134 | 0
995 | Payroll Burden | 0 | 1052 | 1052 | 0
602 | Rental Equipment | 0 | 922 | 922 | 0
998 | Payroll Taxes | 0 | 163 | 163 | 0
C. LARGEST SAVINGS (Actual < Revised Budget)
Code | Description | Rev Budget | Actual | Savings | % Under
SOURCES
Job #2108 — R&G Apartments • GC: Braseth Construction • Status: ON HOLD · Summer 2026?
Canonical source: 2108_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2108_dashboard_arrays.json (mirrors index.html PROJECTS['2108'])
Project profile: 263 units · TBD · Pre-construction — on hold
Design team: Franklin Engineering (MEP per AP $90.6k design fee)
Contract: Not yet executed
Billing: No pay apps filed (only $91k design billing)
Permit: Pre-permit

## Material
Material Spend Analysis
0 material cost codes • $0 JDR material • 3 AP vendors
A. MATERIAL BY COST CODE
Code | Description | Rev Budget | Actual | Variance | % Used | % of Mat
B. VENDORS BY SPEND (AP)
Vendor | # Invoices | Total Spend | % of AP
Franklin Engineering | 9 | 90629 | 0.92523
Bank of America CC | 2 | 6402 | 0.065358
Herc Rentals, Inc. | 1 | 922 | 0.0094127
TOTAL | 12 | 97953 | 1
SOURCES
Job #2108 — R&G Apartments • GC: Braseth Construction • Status: ON HOLD · Summer 2026?
Canonical source: 2108_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2108_dashboard_arrays.json (mirrors index.html PROJECTS['2108'])
Project profile: 263 units · TBD · Pre-construction — on hold
Design team: Franklin Engineering (MEP per AP $90.6k design fee)
Contract: Not yet executed
Billing: No pay apps filed (only $91k design billing)
Permit: Pre-permit

## Crew & Labor
Crew & Labor — Per-Worker Breakdown
Worker | Hours | Gross Pay | $/Hour | Tier
Gerard, Jeffrey S | 20.5 | 1414 | 68.9756 | Senior
Gerard, Jordan E | 12 | 720 | 60 | Senior
SOURCES
Job #2108 — R&G Apartments • GC: Braseth Construction • Status: ON HOLD · Summer 2026?
Canonical source: 2108_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2108_dashboard_arrays.json (mirrors index.html PROJECTS['2108'])
Project profile: 263 units · TBD · Pre-construction — on hold
Design team: Franklin Engineering (MEP per AP $90.6k design fee)
Contract: Not yet executed
Billing: No pay apps filed (only $91k design billing)
Permit: Pre-permit

## Crew Analytics
Crew Analytics — Tier Distribution & Wages
A. TIER DISTRIBUTION
Tier | # Workers | Hours | Gross Pay | % of Hours
Senior | 2 | 32.5 | 2134 | 100.0%
B. WAGE STATISTICS
Blended labor rate ($/hr) | 65.66
Foreman labor rate ($/hr) | 69
Burden multiplier | 1.15
Min wage ($/hr) | 60
Max wage ($/hr) | 69
Avg hours per worker | 16.2
SOURCES
Job #2108 — R&G Apartments • GC: Braseth Construction • Status: ON HOLD · Summer 2026?
Canonical source: 2108_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2108_dashboard_arrays.json (mirrors index.html PROJECTS['2108'])
Project profile: 263 units · TBD · Pre-construction — on hold
Design team: Franklin Engineering (MEP per AP $90.6k design fee)
Contract: Not yet executed
Billing: No pay apps filed (only $91k design billing)
Permit: Pre-permit

## Productivity
Productivity — Phases by Hours
Phase | Code | Hours | % of Total | Hours/Unit
Takeoff & Purchasing | 101 | 32.5 | 100.0% | 0.12
TOTAL |  | 32.5
PRODUCTIVITY RATIOS
Revenue per unit | $348
Direct cost per unit | $445
Hours per unit | 0.12
Revenue per hour | $2,812
Profit per hour | $-793
SOURCES
Job #2108 — R&G Apartments • GC: Braseth Construction • Status: ON HOLD · Summer 2026?
Canonical source: 2108_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2108_dashboard_arrays.json (mirrors index.html PROJECTS['2108'])
Project profile: 263 units · TBD · Pre-construction — on hold
Design team: Franklin Engineering (MEP per AP $90.6k design fee)
Contract: Not yet executed
Billing: No pay apps filed (only $91k design billing)
Permit: Pre-permit

## PO Commitments
PO Commitments — Vendor Concentration
Per-PO records live in GDrive. This tab summarizes commitments by vendor concentration.
# | Vendor | # Invoices | Total Spend | % of AP | Tier
1 | Franklin Engineering | 9 | 90629 | 92.5% | Top 5
2 | Bank of America CC | 2 | 6402 | 6.5% | Top 5
3 | Herc Rentals, Inc. | 1 | 922 | 0.9% | Top 5
SOURCES
Job #2108 — R&G Apartments • GC: Braseth Construction • Status: ON HOLD · Summer 2026?
Canonical source: 2108_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2108_dashboard_arrays.json (mirrors index.html PROJECTS['2108'])
Project profile: 263 units · TBD · Pre-construction — on hold
Design team: Franklin Engineering (MEP per AP $90.6k design fee)
Contract: Not yet executed
Billing: No pay apps filed (only $91k design billing)
Permit: Pre-permit

## Billing & SOV
Billing & Statement of Values
STATEMENT OF VALUES — SUMMARY
Original Contract | $0
Net Change Orders | $0
Final Contract | $0
Retainage Held | $0
Net Paid to OWP | $91,402
PAY APPLICATION HISTORY
No pay-app history in dashboard. Source: Sage AR module aggregate only.
SOURCES
Job #2108 — R&G Apartments • GC: Braseth Construction • Status: ON HOLD · Summer 2026?
Canonical source: 2108_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2108_dashboard_arrays.json (mirrors index.html PROJECTS['2108'])
Project profile: 263 units · TBD · Pre-construction — on hold
Design team: Franklin Engineering (MEP per AP $90.6k design fee)
Contract: Not yet executed
Billing: No pay apps filed (only $91k design billing)
Permit: Pre-permit

## Insights
Key Insights — 10 Themes
# | Theme | Insight
1 | MARGIN PROFILE | Net profit of $-117,162 on $0 revenue = 0.0% gross margin. Direct cost $117,162 absorbs 100.0% of revenue.
2 | VENDOR CONCENTRATION | Franklin Engineering alone = $90,629 (92.5% of all AP) across 9 invoices. Total 3 AP vendors, $97,953 total AP spend.
3 | CREW PROFILE | 2 workers for 32 hours = 16 avg hrs/worker. Top 3 workers logged 32 hrs combined (100% of all labor).
4 | ROUGHIN DOMINANCE | Code 120 Roughin Labor = 0 hrs (0% of all labor) and $0 actual. Code 230 Finish Material = $0.
5 | BUDGET DELIVERY | Revised expense budget was $0; actual direct cost $117,162 → $-117,162 variance (+0.0%).
6 | CONTRACT GROWTH | Contract grew from $0 to $0 — net +$0 (+0.0%). Retainage of $0 (0%) released.
7 | BURDEN RATIO | Burden codes 995 + 998 = $1,216 on $2,134 labor base = 57.0%. Outside OWP's typical 48–50% labor burden.
8 | PROJECT SCALE | 263 units · — fixtures. Revenue/unit $0, hours/unit 0.1, profit/unit $-445.
9 | PRODUCTIVITY | Blended labor rate $65.66/hr. Revenue/hour $0. Profit/hour $-3605.
10 | CO PROFILE | 0 executed COs, 0 CORs. Net CO impact $0 (+0.0%).
SOURCES
Job #2108 — R&G Apartments • GC: Braseth Construction • Status: ON HOLD · Summer 2026?
Canonical source: 2108_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2108_dashboard_arrays.json (mirrors index.html PROJECTS['2108'])
Project profile: 263 units · TBD · Pre-construction — on hold
Design team: Franklin Engineering (MEP per AP $90.6k design fee)
Contract: Not yet executed
Billing: No pay apps filed (only $91k design billing)
Permit: Pre-permit

## Benchmark KPIs
Benchmark KPIs — Industry Reference Points
KPI | This Project | OWP Median | Industry Reference | Status
Gross Margin | -28.2% | 32-38% | 30-40% | INFO
Revenue per unit | $348 | $10-15k | $8-20k | INFO
Direct cost per unit | $445 | $7-10k | $6-15k | INFO
Top vendor % of AP | Pending vendor agg | <35% | <40% | INFO
Burden ratio | 57% | 48-50% | 40-55% | WATCH
SOURCES
Job #2108 — R&G Apartments • GC: Braseth Construction • Status: ON HOLD · Summer 2026?
Canonical source: 2108_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2108_dashboard_arrays.json (mirrors index.html PROJECTS['2108'])
Project profile: 263 units · TBD · Pre-construction — on hold
Design team: Franklin Engineering (MEP per AP $90.6k design fee)
Contract: Not yet executed
Billing: No pay apps filed (only $91k design billing)
Permit: Pre-permit

## Reconciliation
Reconciliation — Data Source Cross-Check
Check | Expected | Actual | Delta | Status
Contract: hero block vs JDR | $0 | $0 | — | OK
Billed: hero block vs JDR | $91,402 | $91,402 | — | INFO
Direct cost: meta vs costCats | $117,162 | $117,162 | — | OK
Worker count: dashboard vs meta | 2 | 2 | — | OK
AP vendor count vs JDR | Source aggregate | 3 | — | INFO
SOURCES
Job #2108 — R&G Apartments • GC: Braseth Construction • Status: ON HOLD · Summer 2026?
Canonical source: 2108_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2108_dashboard_arrays.json (mirrors index.html PROJECTS['2108'])
Project profile: 263 units · TBD · Pre-construction — on hold
Design team: Franklin Engineering (MEP per AP $90.6k design fee)
Contract: Not yet executed
Billing: No pay apps filed (only $91k design billing)
Permit: Pre-permit

## Vendors
Vendor Analysis
# | Vendor | # Invoices | Total Spend | % of AP | Notes
1 | Franklin Engineering | 9 | 90629 | 92.5% | Concentration flag
2 | Bank of America CC | 2 | 6402 | 6.5%
3 | Herc Rentals, Inc. | 1 | 922 | 0.9%
SOURCES
Job #2108 — R&G Apartments • GC: Braseth Construction • Status: ON HOLD · Summer 2026?
Canonical source: 2108_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2108_dashboard_arrays.json (mirrors index.html PROJECTS['2108'])
Project profile: 263 units · TBD · Pre-construction — on hold
Design team: Franklin Engineering (MEP per AP $90.6k design fee)
Contract: Not yet executed
Billing: No pay apps filed (only $91k design billing)
Permit: Pre-permit