## Overview
Job #2109 · Marysville Phase 2
Cortex JCR Summary • Intracorp (Owner: Intracorp (owner-GC))
PROJECT OVERVIEW
Project Job # | 2109
Project Name: | Marysville Phase 2
General Contractor | Intracorp (Owner: Intracorp (owner-GC))
Location | Marysville, WA
Project Duration | Apr 2026 (active) – Feb 2028 (estimated) (~22 months · Roughin in progress)
Status | ACTIVE · Roughin phase
CONTRACT VALUE |  | FORECAST NET PROFIT |  | DIRECT COST |  | LABOR HOURS
$3,718,851 |  | $1,035,350 |  | $2,683,501 |  | 377
$3,700,937 orig + $17,914 COs |  | 27.8% margin |  | 72.2% of revenue |  | 30 workers
COST BREAKDOWN
Category | Budget | Actual | Variance | % Budget | % of Cost
Labor | 43050 | 19320 | 23730 | 0.44878 | 0.011115
Material | 1390317 | 1144237 | 246080 | 0.823 | 0.65828
Overhead | 147058 | 72025 | 75033 | 0.48977 | 0.041436
Burden | 538867 | 502640 | 36227 | 0.93277 | 0.28917
TOTAL | 2119292 | 1738222 | 381070 | 0.82019 | 1
PROJECT PROFILE
Plumbing Units | 246 | Total Fixtures | TBD | Fixtures / Unit | TBD
GC | Intracorp | Owner | Intracorp (owner-GC) | Insurance | Standard COI
Status | ACTIVE · Roughin phase | Duration | ~22 months · Roughin in progress | Permit | TBD
NARRATIVE
Active project — Roughin in progress. OWP has billed $3.57M of $3.72M revised contract (96% complete by billing). Direct cost $2.68M = 72% of revenue → forecast 28% margin. Top vendor concentration: Pacific Plumbing $500k (47%) + Consolidated $305k (28%) + Rosen $104k (10%) = Top 3 dominate. Engineering overrun (601: actual $22.3k vs revised $5.85k = +281%) needs CO coverage check before trim.
SOURCES
Job #2109 — Marysville Phase 2 • GC: Intracorp • Status: ACTIVE · Roughin phase
Canonical source: 2109_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2109_dashboard_arrays.json (mirrors index.html PROJECTS['2109'])
Project profile: 246 units · Marysville, WA · ~22 months · Roughin in progress
Design team: Franklin Engineering (MEP per AP $22.3k)
Contract: Subcontract executed — final contract $3,718,851
Billing: AR $3.57M billed (96% of revised). Retention $153,880 held.
Permit: TBD

## Budget vs Actual
Budget vs Actual — All Cost Codes
Code | Description | Orig Budget | Rev Budget | Actual | Variance | % Used
LABOR
100 | Supervision | 18450 | 18450 | 4071 | 14379 | 0.22065
101 | Takeoff & Purchase Labor | 24600 | 24600 | 15235 | 9365 | 0.61931
141 | Water Main/Insulation Lab | 0 | 0 | 0 | 0 | 0
150 | Warranty Labor | 0 | 0 | 14 | -14 | 0
151 | T&M Labor | 675 | 675 | 670 | 5 | 0.99259
MATERIAL
210 | Underground Material | 96801 | 96801 | 55460 | 41341 | 0.57293
220 | Roughin Material | 454876 | 454876 | 464398 | -9522 | 1.0209
230 | Finish Material | 838640 | 838640 | 621810 | 216830 | 0.74145
240 | Gas Material | 0 | 0 | 0 | 0 | 0
241 | Water Main/Insulation Mat | 0 | 0 | 0 | 0 | 0
242 | Mech Room Material | 0 | 0 | 2569 | -2569 | 0
OVERHEAD
600 | Subcontractor | 26000 | 26000 | 2410 | 23590 | 0.092692
601 | Engineering/Plans | 5850 | 5850 | 22320 | -16470 | 3.8154
602 | Rental Equipment | 0 | 0 | 2472 | -2472 | 0
603 | Permits & Licenses | 102758 | 102758 | 39308 | 63450 | 0.38253
607 | Other Expenses | 12450 | 12450 | 5515 | 6935 | 0.44297
BURDEN
995 | Payroll Burden | 448466 | 448466 | 428740 | 19726 | 0.95601
998 | Payroll Taxes | 90401 | 90401 | 73900 | 16501 | 0.81747
TOTAL Direct Cost |  | 2683501.46 | 2683501.46 | 2683501.46
SOURCES
Job #2109 — Marysville Phase 2 • GC: Intracorp • Status: ACTIVE · Roughin phase
Canonical source: 2109_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2109_dashboard_arrays.json (mirrors index.html PROJECTS['2109'])
Project profile: 246 units · Marysville, WA · ~22 months · Roughin in progress
Design team: Franklin Engineering (MEP per AP $22.3k)
Contract: Subcontract executed — final contract $3,718,851
Billing: AR $3.57M billed (96% of revised). Retention $153,880 held.
Permit: TBD

## Cost Breakdown
Cost Breakdown — Category Deep Dive
A. CATEGORY SHARE OF DIRECT COST
Category | # Codes | Budget | Actual | Variance | % Budget | % of Cost
Labor | 4 | 43050 | 19320 | 23730 | 0.44878 | 0.011111
Material | 6 | 1390317 | 1144237 | 246080 | 0.823 | 0.65803
Overhead | 5 | 147058 | 72025 | 75033 | 0.48977 | 0.04142
Burden | 2 | 538867 | 502640 | 36227 | 0.93277 | 0.28906
Other | 1 | 675 | 670 | 5 | 0.99259 | 0.0003853
B. LARGEST OVERRUNS (Actual > Revised Budget)
Code | Description | Rev Budget | Actual | Overrun | % Over
601 | Engineering/Plans | 5850 | 22320 | 16470 | 2.8154
220 | Roughin Material | 454876 | 464398 | 9522 | 0.020933
242 | Mech Room Material | 0 | 2569 | 2569 | 0
602 | Rental Equipment | 0 | 2472 | 2472 | 0
150 | Warranty Labor | 0 | 14 | 14 | 0
C. LARGEST SAVINGS (Actual < Revised Budget)
Code | Description | Rev Budget | Actual | Savings | % Under
230 | Finish Material | 838640 | 621810 | 216830 | 0.25855
603 | Permits & Licenses | 102758 | 39308 | 63450 | 0.61747
210 | Underground Material | 96801 | 55460 | 41341 | 0.42707
600 | Subcontractor | 26000 | 2410 | 23590 | 0.90731
995 | Payroll Burden | 448466 | 428740 | 19726 | 0.043985
998 | Payroll Taxes | 90401 | 73900 | 16501 | 0.18253
100 | Supervision | 18450 | 4071 | 14379 | 0.77935
101 | Takeoff & Purchase Labor | 24600 | 15235 | 9365 | 0.38069
607 | Other Expenses | 12450 | 5515 | 6935 | 0.55703
151 | T&M Labor | 675 | 670 | 5 | 0.0074074
SOURCES
Job #2109 — Marysville Phase 2 • GC: Intracorp • Status: ACTIVE · Roughin phase
Canonical source: 2109_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2109_dashboard_arrays.json (mirrors index.html PROJECTS['2109'])
Project profile: 246 units · Marysville, WA · ~22 months · Roughin in progress
Design team: Franklin Engineering (MEP per AP $22.3k)
Contract: Subcontract executed — final contract $3,718,851
Billing: AR $3.57M billed (96% of revised). Retention $153,880 held.
Permit: TBD

## Material
Material Spend Analysis
6 material cost codes • $1,144,237 JDR material • 13 AP vendors
A. MATERIAL BY COST CODE
Code | Description | Rev Budget | Actual | Variance | % Used | % of Mat
210 | Underground Material | 96801 | 55460 | 41341 | 0.57293 | 0.048469
220 | Roughin Material | 454876 | 464398 | -9522 | 1.0209 | 0.40586
230 | Finish Material | 838640 | 621810 | 216830 | 0.74145 | 0.54343
240 | Gas Material | 0 | 0 | 0 | 0 | 0
241 | Water Main/Insulation Mat | 0 | 0 | 0 | 0 | 0
242 | Mech Room Material | 0 | 2569 | -2569 | 0 | 0.0022452
TOTAL | All Material | 1390317 | 1144237 | 246080 | 0.823 | 1
B. VENDORS BY SPEND (AP)
Vendor | # Invoices | Total Spend | % of AP
Pacific Plumbing Supply Co., LLC | 169 | 500869 | 0.46724
Consolidated Supply Co. | 107 | 305150 | 0.28466
Rosen Supply Kirkland | 94 | 103987 | 0.097005
California Hydronics Corp | 6 | 76546 | 0.071406
Keller Supply Company | 24 | 52036 | 0.048542
Franklin Engineering | 1 | 22320 | 0.020821
Williams Scotsman, Inc. $Mobile Mini | 10 | 2472 | 0.002306
Ferguson Enterprises, Inc. #3007 | 1 | 2408 | 0.0022463
ACME Corp | 7 | 1984 | 0.0018508
All Pro Repair Service LLC | 3 | 1865 | 0.0017398
Capital One Credit Card | 10 | 1603 | 0.0014954
A.R. Brown Backflow Testing | 2 | 545 | 0.00050841
Bank of America CC | 2 | 195 | 0.00018191
TOTAL | 436 | 1071980 | 1
SOURCES
Job #2109 — Marysville Phase 2 • GC: Intracorp • Status: ACTIVE · Roughin phase
Canonical source: 2109_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2109_dashboard_arrays.json (mirrors index.html PROJECTS['2109'])
Project profile: 246 units · Marysville, WA · ~22 months · Roughin in progress
Design team: Franklin Engineering (MEP per AP $22.3k)
Contract: Subcontract executed — final contract $3,718,851
Billing: AR $3.57M billed (96% of revised). Retention $153,880 held.
Permit: TBD

## Crew & Labor
Crew & Labor — Per-Worker Breakdown
Worker | Hours | Gross Pay | $/Hour | Tier
Gerard, Jeffrey S | 168 | 11592 | 69 | Senior
Gerard, Jordan E | 98 | 5831 | 59.5 | Senior
Romero Garza, Jesus I | 60 | 0 | 0 | Apprentice
Wilson, Garret A | 28.75 | 1553 | 54.0174 | Senior
Johnson, Jake E | 11 | 572 | 52 | Senior
Goodwin, Marcus A | 8.5 | 238 | 28 | Senior
Barnhart, Joseph N | 3 | 204 | 68 | Senior
Aquino, Juan | 0 | 0 | 0 | Apprentice
Castro, Marcus J | 0 | 0 | 0 | Apprentice
Araque, Mario W | 0 | 0 | 0 | Apprentice
Ramos Herrera, Franklin J | 0 | 0 | 0 | Apprentice
Young, Joshua S | 0 | 0 | 0 | Apprentice
Fox, Tamron P | 0 | 0 | 0 | Apprentice
Reed, Reuben H | 0 | 0 | 0 | Apprentice
Del Villar, Flabio | 0 | 0 | 0 | Apprentice
Balderas Ortiz, Ricardo I | 0 | 0 | 0 | Apprentice
Guerrero Espinoza, Mario | 0 | 0 | 0 | Apprentice
Rodriguez Arevalos, Christian | 0 | 0 | 0 | Apprentice
Perez Araque, Manuel A | 0 | 0 | 0 | Apprentice
Cornejo Orellana, Carlos E | 0 | 0 | 0 | Apprentice
Ross, Kelli M | 0 | 0 | 0 | Apprentice
Merino Martinez, Humberto | 0 | 0 | 0 | Apprentice
Portillo Soriano, Walter A | 0 | 0 | 0 | Apprentice
Gochez Molina, Douglas O | 0 | 0 | 0 | Apprentice
Castro Hernandez, Jose A | 0 | 0 | 0 | Apprentice
Cruz, Azael S | 0 | 0 | 0 | Apprentice
Gorman, Nathan W | 0 | 0 | 0 | Apprentice
Taylor, Evan R | 0 | 0 | 0 | Apprentice
Valeriano Romero, Oswaldo | 0 | 0 | 0 | Apprentice
Gerard, Mitchell J | 0 | 0 | 0 | Apprentice
SOURCES
Job #2109 — Marysville Phase 2 • GC: Intracorp • Status: ACTIVE · Roughin phase
Canonical source: 2109_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2109_dashboard_arrays.json (mirrors index.html PROJECTS['2109'])
Project profile: 246 units · Marysville, WA · ~22 months · Roughin in progress
Design team: Franklin Engineering (MEP per AP $22.3k)
Contract: Subcontract executed — final contract $3,718,851
Billing: AR $3.57M billed (96% of revised). Retention $153,880 held.
Permit: TBD

## Crew Analytics
Crew Analytics — Tier Distribution & Wages
A. TIER DISTRIBUTION
Tier | # Workers | Hours | Gross Pay | % of Hours
Senior | 6 | 317.25 | 19990 | 84.1%
Apprentice | 24 | 60 | 0 | 15.9%
B. WAGE STATISTICS
Blended labor rate ($/hr) | 52.99
Foreman labor rate ($/hr) | 69
Burden multiplier | 2.464
Min wage ($/hr) | 28
Max wage ($/hr) | 69
Avg hours per worker | 12.6
SOURCES
Job #2109 — Marysville Phase 2 • GC: Intracorp • Status: ACTIVE · Roughin phase
Canonical source: 2109_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2109_dashboard_arrays.json (mirrors index.html PROJECTS['2109'])
Project profile: 246 units · Marysville, WA · ~22 months · Roughin in progress
Design team: Franklin Engineering (MEP per AP $22.3k)
Contract: Subcontract executed — final contract $3,718,851
Billing: AR $3.57M billed (96% of revised). Retention $153,880 held.
Permit: TBD

## Productivity
Productivity — Phases by Hours
Phase | Code | Hours | % of Total | Hours/Unit
Supervision | 100 | 59 | 19.6% | 0.24
Takeoff & Purchasing | 101 | 241.5 | 80.3% | 0.98
Warranty | 150 | 0.25 | 0.1% | 0
TOTAL |  | 300.75
PRODUCTIVITY RATIOS
Revenue per unit | $15,117
Direct cost per unit | $10,909
Hours per unit | 1.22
Revenue per hour | $12,365
Profit per hour | $3,443
SOURCES
Job #2109 — Marysville Phase 2 • GC: Intracorp • Status: ACTIVE · Roughin phase
Canonical source: 2109_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2109_dashboard_arrays.json (mirrors index.html PROJECTS['2109'])
Project profile: 246 units · Marysville, WA · ~22 months · Roughin in progress
Design team: Franklin Engineering (MEP per AP $22.3k)
Contract: Subcontract executed — final contract $3,718,851
Billing: AR $3.57M billed (96% of revised). Retention $153,880 held.
Permit: TBD

## PO Commitments
PO Commitments — Vendor Concentration
Per-PO records live in GDrive. This tab summarizes commitments by vendor concentration.
# | Vendor | # Invoices | Total Spend | % of AP | Tier
1 | Pacific Plumbing Supply Co., LLC | 169 | 500869 | 46.7% | Top 5
2 | Consolidated Supply Co. | 107 | 305150 | 28.5% | Top 5
3 | Rosen Supply Kirkland | 94 | 103987 | 9.7% | Top 5
4 | California Hydronics Corp | 6 | 76546 | 7.1% | Top 5
5 | Keller Supply Company | 24 | 52036 | 4.9% | Top 5
6 | Franklin Engineering | 1 | 22320 | 2.1% | Top 10
7 | Williams Scotsman, Inc. $Mobile Mini | 10 | 2472 | 0.2% | Top 10
8 | Ferguson Enterprises, Inc. #3007 | 1 | 2408 | 0.2% | Top 10
9 | ACME Corp | 7 | 1984 | 0.2% | Top 10
10 | All Pro Repair Service LLC | 3 | 1865 | 0.2% | Top 10
11 | Capital One Credit Card | 10 | 1603 | 0.1% | Long tail
12 | A.R. Brown Backflow Testing | 2 | 545 | 0.1% | Long tail
13 | Bank of America CC | 2 | 195 | 0.0% | Long tail
SOURCES
Job #2109 — Marysville Phase 2 • GC: Intracorp • Status: ACTIVE · Roughin phase
Canonical source: 2109_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2109_dashboard_arrays.json (mirrors index.html PROJECTS['2109'])
Project profile: 246 units · Marysville, WA · ~22 months · Roughin in progress
Design team: Franklin Engineering (MEP per AP $22.3k)
Contract: Subcontract executed — final contract $3,718,851
Billing: AR $3.57M billed (96% of revised). Retention $153,880 held.
Permit: TBD

## Billing & SOV
Billing & Statement of Values
STATEMENT OF VALUES — SUMMARY
Original Contract | $3,700,937
Net Change Orders | $17,914
Final Contract | $3,718,851
Retainage Held | $153,880
Net Paid to OWP | $3,416,132
PAY APPLICATION HISTORY
No pay-app history in dashboard. Source: Sage AR module aggregate only.
SOURCES
Job #2109 — Marysville Phase 2 • GC: Intracorp • Status: ACTIVE · Roughin phase
Canonical source: 2109_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2109_dashboard_arrays.json (mirrors index.html PROJECTS['2109'])
Project profile: 246 units · Marysville, WA · ~22 months · Roughin in progress
Design team: Franklin Engineering (MEP per AP $22.3k)
Contract: Subcontract executed — final contract $3,718,851
Billing: AR $3.57M billed (96% of revised). Retention $153,880 held.
Permit: TBD

## Insights
Key Insights — 10 Themes
# | Theme | Insight
1 | MARGIN PROFILE | Forecast profit of $1,979,958 on $3,718,851 revenue = 53.2% gross margin. Direct cost $1,738,893 absorbs 46.8% of revenue.
2 | VENDOR CONCENTRATION | Pacific Plumbing Supply Co., LLC alone = $500,869 (46.7% of all AP) across 169 invoices. Total 13 AP vendors, $1,071,980 total AP spend.
3 | CREW PROFILE | 30 workers for 377 hours = 13 avg hrs/worker. Top 3 workers logged 326 hrs combined (86% of all labor).
4 | ROUGHIN DOMINANCE | Code 120 Roughin Labor = 0 hrs (0% of all labor) and $0 actual. Code 230 Finish Material = $621,810.
5 | BUDGET DELIVERY | Revised expense budget was $2,119,967; actual direct cost $1,738,893 → $381,074 variance (+18.0%).
6 | CONTRACT GROWTH | Contract grew from $3,700,937 to $3,718,851 — net +$17,914 (+0.5%). Retainage of $153,880 (4%) held.
7 | BURDEN RATIO | Burden codes 995 + 998 = $502,640 on $19,320 labor base = 2601.6%. Outside OWP's typical 48–50% labor burden.
8 | PROJECT SCALE | 246 units · — fixtures. Revenue/unit $15,117, hours/unit 1.5, profit/unit $8,049.
9 | PRODUCTIVITY | Blended labor rate $52.99/hr. Revenue/hour $9858. Profit/hour $5248.
10 | CO PROFILE | 0 executed COs, 0 CORs. Net CO impact $17,914 (+0.5%).
SOURCES
Job #2109 — Marysville Phase 2 • GC: Intracorp • Status: ACTIVE · Roughin phase
Canonical source: 2109_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2109_dashboard_arrays.json (mirrors index.html PROJECTS['2109'])
Project profile: 246 units · Marysville, WA · ~22 months · Roughin in progress
Design team: Franklin Engineering (MEP per AP $22.3k)
Contract: Subcontract executed — final contract $3,718,851
Billing: AR $3.57M billed (96% of revised). Retention $153,880 held.
Permit: TBD

## Benchmark KPIs
Benchmark KPIs — Industry Reference Points
KPI | This Project | OWP Median | Industry Reference | Status
Gross Margin | 27.8% | 32-38% | 30-40% | INFO
Revenue per unit | $15,117 | $10-15k | $8-20k | INFO
Direct cost per unit | $10,909 | $7-10k | $6-15k | INFO
Top vendor % of AP | Pending vendor agg | <35% | <40% | INFO
Burden ratio | 2602% | 48-50% | 40-55% | WATCH
SOURCES
Job #2109 — Marysville Phase 2 • GC: Intracorp • Status: ACTIVE · Roughin phase
Canonical source: 2109_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2109_dashboard_arrays.json (mirrors index.html PROJECTS['2109'])
Project profile: 246 units · Marysville, WA · ~22 months · Roughin in progress
Design team: Franklin Engineering (MEP per AP $22.3k)
Contract: Subcontract executed — final contract $3,718,851
Billing: AR $3.57M billed (96% of revised). Retention $153,880 held.
Permit: TBD

## Reconciliation
Reconciliation — Data Source Cross-Check
Check | Expected | Actual | Delta | Status
Contract: hero block vs JDR | $3,718,851 | $3,718,851 | — | OK
Billed: hero block vs JDR | $3,570,012 | $3,416,132 | — | INFO
Direct cost: meta vs costCats | $2,683,501 | $1,738,892 | — | DELTA
Worker count: dashboard vs meta | 30 | 30 | — | OK
AP vendor count vs JDR | Source aggregate | 13 | — | INFO
SOURCES
Job #2109 — Marysville Phase 2 • GC: Intracorp • Status: ACTIVE · Roughin phase
Canonical source: 2109_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2109_dashboard_arrays.json (mirrors index.html PROJECTS['2109'])
Project profile: 246 units · Marysville, WA · ~22 months · Roughin in progress
Design team: Franklin Engineering (MEP per AP $22.3k)
Contract: Subcontract executed — final contract $3,718,851
Billing: AR $3.57M billed (96% of revised). Retention $153,880 held.
Permit: TBD

## Vendors
Vendor Analysis
# | Vendor | # Invoices | Total Spend | % of AP | Notes
1 | Pacific Plumbing Supply Co., LLC | 169 | 500869 | 46.7% | Concentration flag
2 | Consolidated Supply Co. | 107 | 305150 | 28.5% | Secondary plumbing supply
3 | Rosen Supply Kirkland | 94 | 103987 | 9.7% | Trim/finish supplier
4 | California Hydronics Corp | 6 | 76546 | 7.1%
5 | Keller Supply Company | 24 | 52036 | 4.9% | Roughin material
6 | Franklin Engineering | 1 | 22320 | 2.1% | Design/MEP fees
7 | Williams Scotsman, Inc. $Mobile Mini | 10 | 2472 | 0.2%
8 | Ferguson Enterprises, Inc. #3007 | 1 | 2408 | 0.2% | Roughin + finish supplier
9 | ACME Corp | 7 | 1984 | 0.2%
10 | All Pro Repair Service LLC | 3 | 1865 | 0.2%
11 | Capital One Credit Card | 10 | 1603 | 0.1%
12 | A.R. Brown Backflow Testing | 2 | 545 | 0.1%
13 | Bank of America CC | 2 | 195 | 0.0%
SOURCES
Job #2109 — Marysville Phase 2 • GC: Intracorp • Status: ACTIVE · Roughin phase
Canonical source: 2109_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2109_dashboard_arrays.json (mirrors index.html PROJECTS['2109'])
Project profile: 246 units · Marysville, WA · ~22 months · Roughin in progress
Design team: Franklin Engineering (MEP per AP $22.3k)
Contract: Subcontract executed — final contract $3,718,851
Billing: AR $3.57M billed (96% of revised). Retention $153,880 held.
Permit: TBD