## Schedule of V. Backup
Schedule of values
PROJECT: | Legacy Mercer Island Apartments |  |  |  | PAY APPLICATION #: |  | 17
LOCATION: | 2601 76th Ave SE, Mercer Island, WA |  |  |  | APPLICATION DATE: |  | 2016-05-20
DESCRIPTION: APPLICATION FOR PAYMENT |  |  |  |  | PERIOD TO: |  | 2016-05-31
A | B |  | C | D | E | F | G |  | H | I
Area, level | DESCRIPTION | Name of Subcontractor/ | SCHEDULED | WORK COMPLETED |  |  | COMPLETED | PERCENT | BALANCE | RETAINAGE
and/or |  | Supplier | Value | FROM | THIS |  | AND STORED | COMPLETE | TO FINISH | 5%
phase |  |  |  | PREVIOUS | PERIOD |  | TO DATE
Plumbing | description of work |  | 2469500 | 2224100 | 1200 |  | 2225300 | 90.11% | 244200 | 111265
| Plumbing design, layout and engineering | EXXEL | 68200 | 68200 | 0 |  | 68200 | 100% | 0 | 3410
| plumbing permit and plan review | EXXEL | 32200 | 32200 | 0 |  | 32200 | 100% | 0 | 1610
level P underground | foundation/footing drains at level P | EXXEL | 25200 | 25200 | 0 |  | 25200 | 100% | 0 | 1260
level P underground | underground waste and drain piping at level P | EXXEL | 38600 | 38600 | 0 |  | 38600 | 100% | 0 | 1930
level 1 underground | foundation/footing drains at level 1 |  | 23400 | 23400 | 0 |  | 23400 | 100% | 0 | 1170
level 1 underground | underground waste and drain piping at level 1 | EXXEL | 35700 | 35700 | 0 |  | 35700 | 100% | 0 | 1785
level 1 PT deck | canout, sleeve, install drains PT deck at L1 | EXXEL | 14800 | 14800 | 0 |  | 14800 | 100% | 0 | 740
level 2 PT deck | canout, sleeve, install drains PT deck at level 2 |  | 19400 | 19400 | 0 |  | 19400 | 100% | 0 | 970
level 3 PT deck | canout, sleeve, install drains PT deck at level 3 |  | 49800 | 49800 | 0 |  | 49800 | 100% | 0 | 2490
level P parking | waste, vent and drain piping at parking level P | EXXEL | 86000 | 86000 | 0 |  | 86000 | 100% | 0 | 4300
level 1 parking | waste, vent and drain piping at parking level 1 and retail areas | EXXEL | 172000 | 172000 | 0 |  | 172000 | 100% | 0 | 8600
level 2 parking | waste, vent and drain piping at parking level 2 | EXXEL | 188600 | 188600 | 0 |  | 188600 | 100% | 0 | 9430
level P boiler rm | stock water heater equipment into boiler room | EXXEL | 73600 | 73600 | 0 |  | 73600 | 100% | 0 | 3680
level P boiler rm | install water heater package, expansion tank, mixing valves |  | 24200 | 24200 | 0 |  | 24200 | 100% | 0 | 1210
level P water room | stock booster pump system into mechanical room | EXXEL | 28900 | 28900 | 0 |  | 28900 | 100% | 0 | 1445
level P water room | install booster pump system and building backflow valves |  | 24900 | 24900 | 0 |  | 24900 | 100% | 0 | 1245
level P parking | roughin hot/cold and return water mains |  | 19700 | 19700 | 0 |  | 19700 | 100% | 0 | 985
level 1 parking | roughin hot/cold and return water mains | EXXEL | 33500 | 33500 | 0 |  | 33500 | 100% | 0 | 1675
level 2 parking | roughin hot/cold and return water mains |  | 65300 | 65300 | 0 |  | 65300 | 100% | 0 | 3265
gas piping | roughin gas piping |  | 22200 | 22200 | 0 |  | 22200 | 100% | 0 | 1110
level 2 | roughin plumbing in units at level 2 units |  | 49700 | 49700 | 0 |  | 49700 | 100% | 0 | 2485
level 2 | stock fiberglass tub and shower stalls at level 2 units |  | 4800 | 4800 | 0 |  | 4800 | 100% | 0 | 240
level 2 | install fiberglass stalls at level 2 units |  | 1200 | 0 | 1200 |  | 1200 | 100% | 0 | 60
level 3 | roughin plumbing in units at level 3 units |  | 286600 | 286600 | 0 |  | 286600 | 100% | 0 | 14330
level 3 | stock fiberglass tub and shower stalls at level 3 units |  | 29700 | 29700 | 0 |  | 29700 | 100% | 0 | 1485
level 3 | install fiberglass stalls at level 3 units |  | 7600 | 7600 | 0 |  | 7600 | 100% | 0 | 380
level 4 | roughin plumbing in units at level 4 units |  | 249500 | 249500 | 0 |  | 249500 | 100% | 0 | 12475
level 4 | stock fiberglass tub and shower stalls at level 4 units |  | 31300 | 31300 | 0 |  | 31300 | 100% | 0 | 1565
level 4 | install fiberglass stalls at level 4 units |  | 8000 | 8000 | 0 |  | 8000 | 100% | 0 | 400
level 5 | roughin plumbing in units at level 5 units |  | 249500 | 249500 | 0 |  | 249500 | 100% | 0 | 12475
level 5 | stock fiberglass tub and shower stalls at level 5 units |  | 31300 | 31300 | 0 |  | 31300 | 100% | 0 | 1565
level 5 | install fiberglass stalls at level 5 units |  | 8000 | 8000 | 0 |  | 8000 | 100% | 0 | 400
level 6 | roughin plumbing in units at level 6 units |  | 183400 | 183400 | 0 |  | 183400 | 100% | 0 | 9170
level 6 | stock fiberglass tub and shower stalls at level 6 units |  | 30700 | 30700 | 0 |  | 30700 | 100% | 0 | 1535
level 6 | install fiberglass stalls at level 6 units |  | 7800 | 7800 | 0 |  | 7800 | 100% | 0 | 390
level 2 | install toilets, lavs and sinks at level 2 |  | 9400 | 0 | 0 |  | 0 | 0% | 9400 | 0
level 3 | install toilets, lavs and sinks at level 3 |  | 57200 | 0 | 0 |  | 0 | 0% | 57200 | 0
level 4 | install toilets, lavs and sinks at level 4 |  | 59600 | 0 | 0 |  | 0 | 0% | 59600 | 0
level 5 | install toilets, lavs and sinks at level 5 |  | 59600 | 0 | 0 |  | 0 | 0% | 59600 | 0
level 6 | install toilets, lavs and sinks at level 6 |  | 58400 | 0 | 0 |  | 0 | 0% | 58400 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
SUBTOTAL |  |  | 2469500 | 2224100 | 1200 | 0 | 2225300 | #DIV/0! | 244200 | 111265
CHANGE ORDERS
CO# 1 | added piping, basins & pumps for sub slab ventalation system |  | 26645 | 26645 | 0 |  | 26645 | 100% | 0 | 1332.25
CO# 2-1 | add cast iron waste stacks in residential units |  | 121400 | 121400 | 0 |  | 121400 | 100% | 0 | 6070
CO# 2-2 | delete ice maker boxes |  | -32700 | -32700 | 0 |  | -32700 | 100% | 0 | -1635
CO# 3 | add piping for future grease trap |  | 2658 | 2658 | 0 |  | 2658 | 100% | 0 | 132.9
CO# 4 | Aquatic tub and shower stall changes |  | -17190 | -17190 | 0 |  | -17190 | 100% | 0 | -859.5
CO# 5 | add underground gas piping |  | 3265 | 3265 | 0 |  | 3265 | 100% | 0 | 163.25
CO# 6 | COP 079 - Upgrade plumbing fixtures |  | 27681 | 0 | 0 |  | 0 | 0% | 27681 | 0
CO# 7 | COP059 ice maker boxes |  | 32700 | 32700 | 0 |  | 32700 | 100% | 0 | 1635
CO# 8 | RFC 096 gas piping & sleeve |  | 10620 | 10620 | 0 |  | 10620 | 100% | 0 | 531
CO# 9 | correct error when adding Ice makers back into contract |  | 6290 | 6290 | 0 |  | 6290 | 100% | 0 | 314.5
CO# 10 | add floor drain for future trash room |  | 4634 | 4634 | 0 |  | 4634 | 100% | 0 | 231.7
CO# 11 | COP104-RFI 125 revise plumbing for revised washer closets |  | 12219 | 12219 | 0 |  | 12219 | 100% | 0 | 610.95
CO# 12 | add CI in Media Room |  | 1232 | 0 | 1232 |  | 1232 | 100% | 0 | 61.6
CO# 13 | ASI 24 shower remodel |  | 31612 | 0 | 31612 |  | 31612 | 100% | 0 | 1580.6
CO# 14 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
CO# 15 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
231066 | CONTRACT TOTAL |  | 2700566 | 2394641 | 34044 | 0 | 2428685 | #DIV/0! | 271881 | 121434.25
INPUT NEW
PERCENT
COMPLETES
GOTO PAYAPP FORM
GOTO DETAIL BREAKDOWN
GOTO PAYAPP
INPUT NEW
PERCENT
COMPLETES
GOTO PAYAPP FORM
GOTO DETAIL BREAKDOWN