## Schedule of V. Backup
Schedule of values
PROJECT: | Legacy Mercer Island Apartments |  |  |  | PAY APPLICATION #: |  | 3
LOCATION: | 2601 76th Ave SE, Mercer Island, WA |  |  |  | APPLICATION DATE: |  | 2015-03-19
DESCRIPTION: APPLICATION FOR PAYMENT |  |  |  |  | PERIOD TO: |  | 2015-03-31
A | B |  | C | D | E | F | G |  | H | I
Area, level | DESCRIPTION | Name of Subcontractor/ | SCHEDULED | WORK COMPLETED |  |  | COMPLETED | PERCENT | BALANCE | RETAINAGE
and/or |  | Supplier | Value | FROM | THIS |  | AND STORED | COMPLETE | TO FINISH | 5%
phase |  |  |  | PREVIOUS | PERIOD |  | TO DATE
Plumbing | description of work |  | 2469500 | 81150 | 64810 |  | 145960 | 5.911% | 2323540 | 7298
| Plumbing design, layout and engineering | EXXEL | 68200 | 51150 | 17050 |  | 68200 | 100% | 0 | 3410
| plumbing permit and plan review | EXXEL | 32200 | 0 | 32200 |  | 32200 | 100% | 0 | 1610
level P underground | foundation/footing drains at level P | EXXEL | 25200 | 15000 | 0 |  | 15000 | 59.52% | 10200 | 750
level P underground | underground waste and drain piping at level P | EXXEL | 38600 | 15000 | 8160 |  | 23160 | 60% | 15440 | 1158
level 1 underground | foundation/footing drains at level 1 |  | 23400 | 0 | 0 |  | 0 | 0% | 23400 | 0
level 1 underground | underground waste and drain piping at level 1 | EXXEL | 35700 | 0 | 0 |  | 0 | 0% | 35700 | 0
level 1 PT deck | canout, sleeve, install drains PT deck at L1 | EXXEL | 14800 | 0 | 7400 |  | 7400 | 50% | 7400 | 370
level 2 PT deck | canout, sleeve, install drains PT deck at level 2 |  | 19400 | 0 | 0 |  | 0 | 0% | 19400 | 0
level 3 PT deck | canout, sleeve, install drains PT deck at level 3 |  | 49800 | 0 | 0 |  | 0 | 0% | 49800 | 0
level P parking | waste, vent and drain piping at parking level P | EXXEL | 86000 | 0 | 0 |  | 0 | 0% | 86000 | 0
level 1 parking | waste, vent and drain piping at parking level 1 and retail areas | EXXEL | 172000 | 0 | 0 |  | 0 | 0% | 172000 | 0
level 2 parking | waste, vent and drain piping at parking level 2 | EXXEL | 188600 | 0 | 0 |  | 0 | 0% | 188600 | 0
level P boiler rm | stock water heater equipment into boiler room | EXXEL | 73600 | 0 | 0 |  | 0 | 0% | 73600 | 0
level P boiler rm | install water heater package, expansion tank, mixing valves |  | 24200 | 0 | 0 |  | 0 | 0% | 24200 | 0
level P water room | stock booster pump system into mechanical room | EXXEL | 28900 | 0 | 0 |  | 0 | 0% | 28900 | 0
level P water room | install booster pump system and building backflow valves |  | 24900 | 0 | 0 |  | 0 | 0% | 24900 | 0
level P parking | roughin hot/cold and return water mains |  | 19700 | 0 | 0 |  | 0 | 0% | 19700 | 0
level 1 parking | roughin hot/cold and return water mains | EXXEL | 33500 | 0 | 0 |  | 0 | 0% | 33500 | 0
level 2 parking | roughin hot/cold and return water mains |  | 65300 | 0 | 0 |  | 0 | 0% | 65300 | 0
gas piping | roughin gas piping |  | 22200 | 0 | 0 |  | 0 | 0% | 22200 | 0
level 2 | roughin plumbing in units at level 2 units |  | 49700 | 0 | 0 |  | 0 | 0% | 49700 | 0
level 2 | stock fiberglass tub and shower stalls at level 2 units |  | 4800 | 0 | 0 |  | 0 | 0% | 4800 | 0
level 2 | install fiberglass stalls at level 2 units |  | 1200 | 0 | 0 |  | 0 | 0% | 1200 | 0
level 3 | roughin plumbing in units at level 3 units |  | 286600 | 0 | 0 |  | 0 | 0% | 286600 | 0
level 3 | stock fiberglass tub and shower stalls at level 3 units |  | 29700 | 0 | 0 |  | 0 | 0% | 29700 | 0
level 3 | install fiberglass stalls at level 3 units |  | 7600 | 0 | 0 |  | 0 | 0% | 7600 | 0
level 4 | roughin plumbing in units at level 4 units |  | 249500 | 0 | 0 |  | 0 | 0% | 249500 | 0
level 4 | stock fiberglass tub and shower stalls at level 4 units |  | 31300 | 0 | 0 |  | 0 | 0% | 31300 | 0
level 4 | install fiberglass stalls at level 4 units |  | 8000 | 0 | 0 |  | 0 | 0% | 8000 | 0
level 5 | roughin plumbing in units at level 5 units |  | 249500 | 0 | 0 |  | 0 | 0% | 249500 | 0
level 5 | stock fiberglass tub and shower stalls at level 5 units |  | 31300 | 0 | 0 |  | 0 | 0% | 31300 | 0
level 5 | install fiberglass stalls at level 5 units |  | 8000 | 0 | 0 |  | 0 | 0% | 8000 | 0
level 6 | roughin plumbing in units at level 6 units |  | 183400 | 0 | 0 |  | 0 | 0% | 183400 | 0
level 6 | stock fiberglass tub and shower stalls at level 6 units |  | 30700 | 0 | 0 |  | 0 | 0% | 30700 | 0
level 6 | install fiberglass stalls at level 6 units |  | 7800 | 0 | 0 |  | 0 | 0% | 7800 | 0
level 2 | install toilets, lavs and sinks at level 2 |  | 9400 | 0 | 0 |  | 0 | 0% | 9400 | 0
level 3 | install toilets, lavs and sinks at level 3 |  | 57200 | 0 | 0 |  | 0 | 0% | 57200 | 0
level 4 | install toilets, lavs and sinks at level 4 |  | 59600 | 0 | 0 |  | 0 | 0% | 59600 | 0
level 5 | install toilets, lavs and sinks at level 5 |  | 59600 | 0 | 0 |  | 0 | 0% | 59600 | 0
level 6 | install toilets, lavs and sinks at level 6 |  | 58400 | 0 | 0 |  | 0 | 0% | 58400 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
SUBTOTAL |  |  | 2469500 | 81150 | 64810 | 0 | 145960 | #DIV/0! | 2323540 | 7298
CHANGE ORDERS
CO# 1 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
CO# 2 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
CO# 3 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
CO# 4 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
CO# 5 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
CO# 6 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
CO# 7 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
CO# 8 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
CO# 9 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
CO# 10 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
CO# 11 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
CO# 12 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
CO# 13 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
CO# 14 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
CO# 15 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
CO# 16 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
0 | CONTRACT TOTAL |  | 2469500 | 81150 | 64810 | 0 | 145960 | #DIV/0! | 2323540 | 7298
INPUT NEW
PERCENT
COMPLETES
GOTO PAYAPP FORM
GOTO DETAIL BREAKDOWN
GOTO PAYAPP
INPUT NEW
PERCENT
COMPLETES
GOTO PAYAPP FORM
GOTO DETAIL BREAKDOWN