## Sheet1
SUBCONTRACTORS MONTHLY BILLING SUMMARY
PROJECT NAME: | Hadley Apt (Legacy Mercer Island) (14-0905) |  |  | DATE: | 2016-02-19
SUBCONTRACTOR: | One Way Plumbing, LLC
SERVICE PROVIDED: | Plumbing
BILLING PERIOD: | 2-1-16 - 2-29-16 |  |  | INVOICE #:
| ORIGINAL CONTRACT AMOUNT: | 2469500 | a
| Previous Billing CHANGE ORDERS: | 175079 | b
| This Billing CHANGE ORDERS: | 0 | c
| NEW CONTRACT TOTAL: | 2644579 | d = a+b+c
| TOTAL AMOUNT BILLED TO DATE: | 2355798 | e = g + j
| AMOUNT REMAINING ON CONTRACT: | 288781 | f = d - e
PREVIOUSLY BILLED:
| TOTAL AMOUNT BILLED TO DATE: | 2115653 | g
| Previous retention held - total: | 105782.65 | h
| TOTAL PAID TO DATE 1: | 1706302.6 | i = g - h
CURRENT BILLING AMOUNT:
| Current billing: | 240145 | j
| Current retainage held: | 12007.25 | k
| CURRENT DUE 2: | 228137.75 | l = j - k
**Please Note:
All invoices must be submitted for payment to the CHINN Construction main office by the 20th of each month.
No invoices can or will be paid without all primary and/or secondary lien releases.
Please complete the attached PROGRESS PAYMENT LIEN RELEASE form
1 UNCONDITIONAL AMOUNT
2 CONDITIONAL AMOUNT