## Sheet1
SUBCONTRACTORS MONTHLY BILLING SUMMARY
PROJECT NAME: | Hadley Apt (Legacy Mercer Island) (14-0905) |  |  | DATE: | 2015-09-18
SUBCONTRACTOR: | One Way Plumbing, LLC
SERVICE PROVIDED: | plumbing
BILLING PERIOD: | 9-1-15 9-30-15 |  |  | INVOICE #:
| ORIGINAL CONTRACT AMOUNT: | 2469500 | a
| Previous Billing CHANGE ORDERS: | 100813 | b
| This Billing CHANGE ORDERS: | 4075 | c
| NEW CONTRACT TOTAL: | 2574388 | d = a+b+c
| TOTAL AMOUNT BILLED TO DATE: | 954511 | e = g + j
| AMOUNT REMAINING ON CONTRACT: | 1619877 | f = d - e
PREVIOUSLY BILLED:
| TOTAL AMOUNT BILLED TO DATE: | 582588 | g
| Previous retention held - total: | 29129.4 | h
| TOTAL PAID TO DATE 1: | 290845.1 | i = g - h
CURRENT BILLING AMOUNT:
| Current billing: | 371953 | j
| Current retainage held: | 18597.65 | k
| CURRENT DUE 2: | 353355.35 | l = j - k
**Please Note:
All invoices must be submitted for payment to the CHINN Construction main office by the 20th of each month.
No invoices can or will be paid without all primary and/or secondary lien releases.
Please complete the attached PROGRESS PAYMENT LIEN RELEASE form
1 UNCONDITIONAL AMOUNT
2 CONDITIONAL AMOUNT