## Sheet1
OWP LLC CHANGE ORDER BUDGET
OWP# | 2023
BUILDER: | CHINN CONSTRUCTION
JOB NAME: | HADLEY PROJECT
SALE PRICE: | 999 |  | 1891
CODE
LABOR |  | CODE | BUDGET | MATERIAL | CODE | BUDGET | DIVISION 6 | CODE | BUDGET
SUPERVISION |  | 100 | 141
TAKEOFF & PURCHASE |  | 101 | 141 | GW WASTE / STORM | 210 |  | SUBCONTRACTOR | 600
GW WASTE / STORM |  | 110 |  | GARAGE | 211 |  | ENGINEERING/PLANS | 601
GARAGE |  | 111 |  | CANOUT | 212 |  | RENTAL EQUIPMENT | 602
CANOUT |  | 112 |  | FOUNDATION DRAIN | 213 |  | PERMIT & LICENSES | 603
FOUNDATION DRAIN |  | 113 |  | ROUGHIN | 220 |  | BACKCHARGES | 604
ROUGHIN |  | 120 |  | FINISH | 230
FINISH |  | 130 | 50 | GAS | 240 | 355 | SHOP LABOR | 606
GAS |  | 140 | 275 | WATER MAIN / INSULATION | 241 |  | OTHER EXPENSES | 607
WATER MAIN / INSULATION |  | 141 |  | MECHANICAL ROOM | 242
MECHANICAL ROOM |  | 142 |  | CONDENSATION DRAINS | 243
CONDENSATION DRAINS |  | 143 |  | FIRE CAULKING | 244
FIRE CAULKING |  | 144 |  | WARRANTY | 250
WARRANTY |  | 150 |  | T & M | 251
T & M |  | 151
LABOR BURDEN | 44.35% |  | 269.2045
LABOR BURDEN | 7.65% |  | 46.4355
DESCRIPTION OF CHANGE:
Change Order 14
Skylounge gas cooktop

## COR
[7 empty] | PROJECT: | 2023 LEGACY APARTMENTS
[7 empty] | DATE: | 2016-04-04
RFI/ASI:
DESCRIPTION OF CHANGE/WORK PERFORMED
|  | Labor |  |  |  | Material/Equipment |  |  | Material | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
| LAYOUT/COORDINATION | 3 | HRS | 80 | 240
| 3/4" GAS PIPE | 8 | HRS | 60.5 | 484 | 1 | LS | 100 | 100
| FITTINGS |  |  |  |  | 1 | LS | 100 | 100
| VALVE |  |  |  |  | 1 | EA | 15 | 15
| REGULATOR |  |  |  |  | 1 | EA | 75 | 75
| FLEX CONNECTOR |  |  |  |  | 1 | EA | 65 | 65
| SUPERVISION | 3 | HRS | 80 | 240
| ADD TO PERMIT & INSPECT | 2 | HRS | 80 | 160
| TRIM LABOR | 2 | HRS | 80 | 160
| AS-BUILTING | 1 | HRS | 80 | 80
| Subtotals |  |  |  | 1364 |  |  |  | 355 |  | 0
| OH & Profit |  |  | 10% | 136.4 |  |  | 10% | 35.5 | 10% | 0
| Totals |  |  |  | 1500.4 |  |  |  | 390.5 |  | 0
1890.9
ADD GAS RANGE AT SKYLOUNGE