## Sheet1
OWP LLC CHANGE ORDER BUDGET
OWP# | 2023
BUILDER: | CHINN CONSTRUCTION
JOB NAME: | HADLEY PROJECT
SALE PRICE: | 999 |  | 1617
CODE
LABOR |  | CODE | BUDGET | MATERIAL | CODE | BUDGET | DIVISION 6 | CODE | BUDGET
SUPERVISION |  | 100 | 70
TAKEOFF & PURCHASE |  | 101 | 135 | GW WASTE / STORM | 210 |  | SUBCONTRACTOR | 600 | 680
GW WASTE / STORM |  | 110 |  | GARAGE | 211 |  | ENGINEERING/PLANS | 601
GARAGE |  | 111 |  | CANOUT | 212 |  | RENTAL EQUIPMENT | 602
CANOUT |  | 112 |  | FOUNDATION DRAIN | 213 |  | PERMIT & LICENSES | 603
FOUNDATION DRAIN |  | 113 |  | ROUGHIN | 220 | 100 | BACKCHARGES | 604
ROUGHIN |  | 120 | 150 | FINISH | 230
FINISH |  | 130 |  | GAS | 240 |  | SHOP LABOR | 606
GAS |  | 140 |  | WATER MAIN / INSULATION | 241 |  | OTHER EXPENSES | 607
WATER MAIN / INSULATION |  | 141 |  | MECHANICAL ROOM | 242
MECHANICAL ROOM |  | 142 |  | CONDENSATION DRAINS | 243
CONDENSATION DRAINS |  | 143 |  | FIRE CAULKING | 244
FIRE CAULKING |  | 144 |  | WARRANTY | 250
WARRANTY |  | 150 |  | T & M | 251
T & M |  | 151
LABOR BURDEN | 44.35% |  | 157.4425
LABOR BURDEN | 7.65% |  | 27.1575
DESCRIPTION OF CHANGE:
Change Order 17
Re-align boiler flues

## COR
[7 empty] | PROJECT: | 2023 LEGACY APARTMENTS
[7 empty] | DATE: | 2016-03-08
[7 empty] | RFI/ASI: | RFI-245
DESCRIPTION OF CHANGE/WORK PERFORMED
|  | Labor |  |  |  | Material/Equipment |  |  | Material | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
| COORDINATION/LAYOUT | 4 | HRS | 80 | 320
| CORE DRILLER | [8 empty] | LS | 600
| LINK SEALS |  |  |  |  | 4 | EA | 117 | 468
| INSTALL LINK SEALS | 2 | HRS | 60.5 | 121
| CAP UN-USED PENETRATIONS | 1 | HRS | 60.5 | 60.5 | 4 | EA | 5.23 | 20.92
| SUPERVISION | 2 | HRS | 80 | 160
| AS-BUILTING | 0.5 | HRS | 80 | 40
| Subtotals |  |  |  | 381.5 |  |  |  | 488.92 | 0 | 600
| OH & Profit |  |  | 10% | 38.15 |  |  | 10% | 48.892 | 10% | 60
| Totals |  |  |  | 419.65 |  |  |  | 537.812 |  | 660
Total this page
1617.462
RFI-245 Costs