## CGC BP
[7 empty] | PROJECT: | 2023 LEGACY APARTMENTS
[7 empty] | DATE: | 2015-02-04
RFI/ASI:
DESCRIPTION OF CHANGE/WORK PERFORMED
|  | Labor |  |  |  | Material/Equipment |  |  | Material | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
PERFORATED DRAIN SYSTEM
| 4" Perf Pipe | -53.1 | HRS | 60.5 | -3212.55 | -531 | LF | 2.9 | -1539.9
| 4" Fittings | -19.44 | HRS | 60.5 | -1176.12 | -27 | EA | 5.3 | -143.1
| 6" Perf Pipe | 118.8 | HRS | 60.5 | 7187.4 | 660 | LF | 4.5 | 2970
| 6" Fittings | 42.9 | HRS | 60.5 | 2595.45 | 33 | EA | 17.59 | 580.47
| Subtotals |  |  |  | 5394.18 |  |  |  | 1867.47 | 0 | 0
| OH & Profit |  |  | 10% | 539.418 |  |  | 10% | 186.747 | 10% | 0
| Totals |  |  |  | 5933.598 |  |  |  | 2054.217 |  | 0
Total this page
7987.815
| Cleanouts | 10 | HR | 60.5 | 605 | 10 | EA | 66.85 | 668.5
| Subtotals |  |  |  | 605 |  |  |  | 668.5 |  | 0
| OH & Profit |  |  | 10% | 60.5 |  |  | 10% | 66.85 | 10% | 0
| Totals |  |  |  | 665.5 |  |  |  | 735.35 |  | 0
Total this page
1400.85
| Type 241 Catch Basin | 12 | HR | 60.5 | 726 | 1 | EA | 357 | 357
| Type 241 Riser | 1 | HR | 60.5 | 60.5 | 1 | EA | 72 | 72
| Type 241 Lid | 1 | HR | 60.5 | 60.5 | 1 | EA | 172 | 172
| 48" Basin | 16 | HR | 60.5 | 968 | 1 | EA | 404 | 404
| 48" Riser | 1 | HR | 60.5 | 60.5 | 1 | EA | 72 | 72
| 48" Riser | 1 | HR | 60.5 | 60.5 | 1 | EA | 285 | 285
| Kor N Seal Boots | 3 | HR | 60.5 | 181.5 | 6 | EA | 60 | 360
| Subtotals |  |  |  | 2117.5 |  |  |  | 1722
| OH & Profit |  |  | 10% | 211.75 |  |  | 10% | 172.2 | 10% | 0
| Totals |  |  |  | 2329.25 |  |  |  | 1894.2 |  | 0
Total this page
4223.45
PUMP TIGHTLINE TO ROOM P-025
| 2" PVC Pumpline | 5 | HRS | 60.5 | 302.5 | 31 | LF | 1.65 | 51.15
| 2" Fittings | 3 | HRS | 60.5 | 181.5 | 6 | EA | 2.65 | 15.9
| Subtotals |  |  |  | 484 |  |  |  | 67.05
| OH & Profit |  |  | 10% | 48.4 |  |  | 10% | 6.705 | 10% | 0
| Totals |  |  |  | 532.4 |  |  |  | 73.755 |  | 0
Total this page
606.155
SEWER CONNECTION TO ROOM P-025
| 6" PVC Sewer | 7 | HRS | 60.5 | 423.5 | 31 | LF | 3.754 | 116.374
| 6" Fittings | 4 | HRS | 60.5 | 242 | 5 | EA | 17.59 | 87.95
| Subtotals |  |  |  | 665.5 |  |  |  | 204.324
| OH & Profit |  |  | 10% | 66.55 |  |  | 10% | 20.4324 | 10% | 0
| Totals |  |  |  | 732.05 |  |  |  | 224.7564 |  | 0
Total this page
956.8064
VENT TIGHTLINE TO ROOM P-025
| 6" PVC Tightline | 11.16 | HRS | 60.5 | 675.18 | 62 | LF | 3.75 | 232.5
| 6" Fittings | 7.8 | HRS | 60.5 | 471.9 | 6 | EA | 17.59 | 105.54
| Subtotals |  |  |  | 1147.08 |  |  |  | 338.04 |  | 0
| OH & Profit |  |  | 10% | 114.708 |  |  | 10% | 33.804 | 10% | 0
| Totals |  |  |  | 1261.788 |  |  |  | 371.844 |  | 0
Total this page
1633.632
VENTS FROM ROOM P-025 TO ROOF
| 8" Vents from Equip to Roof | 30 | HRS | 60.5 | 1815 | 120 | LF | 6.2475 | 749.7
| 8" Fittings | 6 | HRS | 60.5 | 363 | 8 | EA | 23.47 | 187.76
| Subtotals |  |  |  | 2178 |  |  |  | 937.46 |  | 0
| OH & Profit |  |  | 10% | 217.8 |  |  | 10% | 93.746 | 10% | 0
| Totals |  |  |  | 2395.8 |  |  |  | 1031.206 |  | 0
Total this page
3427.006
|  | Labor |  |  |  | Material/Equipment |  |  | Material | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
SIMPLEX PUMP SYSTEM
| Zoeller Pumps | 10 | HRS | 60.5 | 605 | 1 | EA | 751.571 | 751.571
| Zoeller Panel |  |  |  |  | 1 | EA | 417.3925 | 417.3925
| Zoeller Floats | 4 | HRS | 60.5 | 242 | 3 | EA | 50.968 | 152.904
| Zoeller Cord Holder | 1 | HRS | 60.5 | 60.5 | 1 | EA | 86.457 | 86.457
| Zoeller 2" cast iron check valve | 3 | HR | 60.5 | 181.5 | 1 | EA | 58.7075 | 58.7075
| Zoeller 2" PVC ball valve | 3 | HR | 60.5 | 181.5 | 1 | EA | 49.6685 | 49.6685
| Zoeller 2" Plug valve | 3 | HR | 60.5 | 181.5 | 1 | EA | 225.791 | 225.791
| Factory Startup |  |  |  |  | 1 | LS | 800 | 800
|  |  | HR | 60.5 | 0 |  | EA |  | 0
| Subtotals |  |  |  | 1452 |  |  |  | 2542.4915 |  | 0
| OH & Profit |  |  | 10% | 145.2 |  |  | 10% | 254.2492 | 10% | 0
| Totals |  |  |  | 1597.2 |  |  |  | 2796.7407 |  | 0
Total this page
4393.9407
|  | Labor |  |  |  | Material/Equipment |  |  | Material | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
DUPLEX PUMP SYSTEM
| Zoeller Pumps | 15 | HRS | 60.5 | 907.5 | 2 | EA | 751.571 | 1503.142
| Zoeller Panel |  |  |  |  | 1 | EA | 679.972 | 679.972
| Zoeller Floats | 4 | HRS | 60.5 | 242 | 3 | EA | 50.968 | 152.904
| Zoeller Cord Holder | 1 | HRS | 60.5 | 60.5 | 1 | EA | 86.457 | 86.457
| Zoeller 2" cast iron check valve | 4 | HR | 60.5 | 242 | 2 | EA | 58.7075 | 117.415
| Zoeller 2" PVC ball valve | 4 | HR | 60.5 | 242 | 2 | EA | 49.6685 | 99.337
| Zoeller 2" Plug valve | 4 | HR | 60.5 | 242 | 2 | EA | 225.791 | 451.582
| Factory Startup |  |  |  |  | 1 | LS | 800 | 800
|  |  | HR | 60.5 | 0 |  | EA |  | 0
| Subtotals |  |  |  | 1936 |  |  |  | 3890.809 |  | 0
| OH & Profit |  |  | 10% | 193.6 |  |  | 10% | 389.0809 | 10% | 0
| Totals |  |  |  | 2129.6 |  |  |  | 4279.8899 |  | 0
Total this page
6409.4899
|  | Labor |  |  |  | Material/Equipment |  |  | Material
| Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total
| 4" Perf Pipe | -53.1 | HRS | 60.5 | -3212.55 | -531 | LF | 2.9 | -1539.9
| 4" Fittings | -19.44 | HRS | 60.5 | -1176.12 | -27 | EA | 5.3 | -143.1
| 6" Perf Pipe | 118.8 | HRS | 60.5 | 7187.4 | 660 | LF | 4.5 | 2970
| 6" Fittings | 42.9 | HRS | 60.5 | 2595.45 | 33 | EA | 17.59 | 580.47
| 6" Tightline to equipment room | 11.16 | HRS | 60.5 | 675.18 | 62 | LF | 3.75 | 232.5
| 6" Fittings | 7.8 | HRS | 60.5 | 471.9 | 6 | EA | 17.59 | 105.54
| Cleanouts | 10 | HR | 60.5 | 605 | 10 | EA | 66.85 | 668.5
| Type 241 Catch Basin | 8 | HR | 60.5 | 484 | 1 | EA | 357 | 357
| Type 241 Riser | 0.5 | HR | 60.5 | 30.25 | 1 | EA | 72 | 72
| Kor N Seal Boots | 0.5 | HR | 60.5 | 30.25 | 2 | EA | 60 | 120
| Subtotals |  |  |  | 7690.76 |  |  |  | 3423.01
| OH & Profit |  |  | 15% | 1153.614 |  |  | 15% | 513.4515
| Totals |  |  |  | 8844.374 |  |  |  | 3936.4615
Total this page
12780.8355
REVISIONS TO SUB-SLAB VENTING SYSTEM.