## CGC BP
[7 empty] | PROJECT: | 2023 LEGACY APARTMENTS
[7 empty] | DATE: | 2014-12-01
RFI/ASI:
DESCRIPTION OF CHANGE/WORK PERFORMED
|  | Labor |  |  |  | Material/Equipment |  |  | Material | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
| 4" Perf Pipe | -53.1 | HRS | 60.5 | -3212.55 | -531 | LF | 2.9 | -1539.9
| 4" Fittings | -19.44 | HRS | 60.5 | -1176.12 | -27 | EA | 5.3 | -143.1
| 6" Perf Pipe | 118.8 | HRS | 60.5 | 7187.4 | 660 | LF | 4.5 | 2970
| 6" Fittings | 42.9 | HRS | 60.5 | 2595.45 | 33 | EA | 17.59 | 580.47
| 6" Tightline to equipment room | 11.16 | HRS | 60.5 | 675.18 | 62 | LF | 3.75 | 232.5
| 6" Fittings | 7.8 | HRS | 60.5 | 471.9 | 6 | EA | 17.59 | 105.54
| Cleanouts | 10 | HR | 60.5 | 605 | 10 | EA | 66.85 | 668.5
| Type 241 Catch Basin | 8 | HR | 60.5 | 484 | 1 | EA | 357 | 357
| Type 241 Riser | 0.5 | HR | 60.5 | 30.25 | 1 | EA | 72 | 72
| Kor N Seal Boots | 0.5 | HR | 60.5 | 30.25 | 2 | EA | 60 | 120
| Subtotals |  |  |  | 7690.76 |  |  |  | 3423.01 |  | 0
| OH & Profit |  |  | 15% | 1153.614 |  |  | 15% | 513.4515 | 15% | 0
| Totals |  |  |  | 8844.374 |  |  |  | 3936.4615 |  | 0
Total this page
12780.8355
|  | Labor |  |  |  | Material/Equipment |  |  | Material
| Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total
| 4" Perf Pipe | -53.1 | HRS | 60.5 | -3212.55 | -531 | LF | 2.9 | -1539.9
| 4" Fittings | -19.44 | HRS | 60.5 | -1176.12 | -27 | EA | 5.3 | -143.1
| 6" Perf Pipe | 118.8 | HRS | 60.5 | 7187.4 | 660 | LF | 4.5 | 2970
| 6" Fittings | 42.9 | HRS | 60.5 | 2595.45 | 33 | EA | 17.59 | 580.47
| 6" Tightline to equipment room | 11.16 | HRS | 60.5 | 675.18 | 62 | LF | 3.75 | 232.5
| 6" Fittings | 7.8 | HRS | 60.5 | 471.9 | 6 | EA | 17.59 | 105.54
| Cleanouts | 10 | HR | 60.5 | 605 | 10 | EA | 66.85 | 668.5
| Type 241 Catch Basin | 8 | HR | 60.5 | 484 | 1 | EA | 357 | 357
| Type 241 Riser | 0.5 | HR | 60.5 | 30.25 | 1 | EA | 72 | 72
| Kor N Seal Boots | 0.5 | HR | 60.5 | 30.25 | 2 | EA | 60 | 120
| Subtotals |  |  |  | 7690.76 |  |  |  | 3423.01
| OH & Profit |  |  | 15% | 1153.614 |  |  | 15% | 513.4515
| Totals |  |  |  | 8844.374 |  |  |  | 3936.4615
Total this page
12780.8355
REVISIONS TO SUB-SLAB VENTING SYSTEM.