## CGC BP
[7 empty] | PROJECT: | 2023 LEGACY APARTMENTS
[7 empty] | DATE: | 2016-04-04
RFI/ASI:
DESCRIPTION OF CHANGE/WORK PERFORMED
|  | Labor |  |  |  | Material/Equipment |  |  | Material | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
| LAYOUT/COORDINATION | 3 | HRS | 80 | 240
| 3/4" GAS PIPE | 8 | HRS | 60.5 | 484 | 1 | LS | 100 | 100
| FITTINGS |  |  |  |  | 1 | LS | 100 | 100
| VALVE |  |  |  |  | 1 | EA | 15 | 15
| REGULATOR |  |  |  |  | 1 | EA | 75 | 75
| FLEX CONNECTOR |  |  |  |  | 1 | EA | 65 | 65
| SUPERVISION | 3 | HRS | 80 | 240
| ADD TO PERMIT & INSPECT | 2 | HRS | 80 | 160
| TRIM LABOR | 2 | HRS | 80 | 160
| AS-BUILTING | 1 | HRS | 80 | 80
| Subtotals |  |  |  | 1364 |  |  |  | 355 |  | 0
| OH & Profit |  |  | 10% | 136.4 |  |  | 10% | 35.5 | 10% | 0
| Totals |  |  |  | 1500.4 |  |  |  | 390.5 |  | 0
1890.9
ADD GAS RANGE AT SKYLOUNGE