## COR
[11 empty] | PROJECT: | 2023 LEGACY APARTMENTS
[11 empty] | DATE: | 2016-06-10
[11 empty] | RFI/ASI: | ASI-024 SHOWER CHANGE
DESCRIPTION OF CHANGE/WORK PERFORMED
|  |  | Labor | [6 empty] | Material/Equipment |  |  | Material | SUB TIER
Item | Description | Quan 5/13 | Quan 6/10 | Quan 6/29 | UOM | Unit Cost | Total | Total | Total | Quan | UOM | Unit Cost | Total | UOM | Total
THROUGH 6/10/16 | time axis 2016-04-04 to 2016-07-15
| RICHARD DONELSON - PROJECT MANAGER | 12 | 6 | 1 | HRS | 95 | 1140 | 570 | 95 | [6 empty] | 2016-04-05: 2; 2016-04-07: 1; 2016-04-08: 1; 2016-04-12: 3; 2016-04-15: 1; 2016-04-19: 2; 2016-05-13: 2; 2016-05-17: 2; 2016-05-24: 1; 2016-06-10: 3; 2016-07-08: 1
| JEFF GERARD - PROJECT MANAGER | 2 | 4 | 0 | HRS | 95 | 190 | 380 | 0 | [6 empty] | 2016-04-19: 2; 2016-05-17: 1; 2016-05-19: 1; 2016-05-26: 1; 2016-05-31: 1
| BOB HUBBARD - SUPERINTENDENT | 4 | 1 | 0 | HRS | 85 | 340 | 85 | 0 | [6 empty] | 2016-04-20: 2; 2016-04-22: 2; 2016-05-26: 1
| JOE BARNHART - FOREMAN | 30 | 18 | 0 | HRS | 80 | 2400 | 1440 | 0 | [6 empty] | 2016-04-18: 1; 2016-04-19: 3; 2016-04-20: 3; 2016-04-21: 1; 2016-04-22: 2; 2016-04-27: 2; 2016-04-28: 4; 2016-04-29: 2; 2016-05-04: 4; 2016-05-09: 2; 2016-05-10: 2; 2016-05-12: 2; 2016-05-13: 2; 2016-05-16: 2; 2016-05-17: 1; 2016-05-18: 2; 2016-05-19: 2; 2016-05-26: 2; 2016-06-01: 2; 2016-06-02: 2; 2016-06-03: 1; 2016-06-06: 4
| THADDEUS WAITES - FOREMAN | 60 | 47.5 | 3 | HRS | 80 | 4800 | 3800 | 240 | [6 empty] | 2016-04-19: 8; 2016-04-20: 8; 2016-04-22: 8; 2016-04-25: 8; 2016-04-26: 4; 2016-04-29: 2; 2016-05-03: 2; 2016-05-04: 2; 2016-05-05: 8; 2016-05-09: 2; 2016-05-10: 2; 2016-05-12: 2; 2016-05-13: 4; 2016-05-16: 2; 2016-05-17: 1; 2016-05-18: 8; 2016-05-19: 2; 2016-05-20: 3; 2016-05-23: 2; 2016-05-24: 2; 2016-05-25: 2.5; 2016-05-26: 2; 2016-05-27: 3; 2016-05-31: 2; 2016-06-01: 2; 2016-06-02: 2; 2016-06-03: 8; 2016-06-06: 4; 2016-06-08: 1; 2016-06-09: 1; 2016-06-21: 1; 2016-06-29: 1; 2016-07-11: 1
| KELLI ROSS - JOURNEYMAN | 76 | 16 | 0 | HRS | 75 | 5700 | 1200 | 0 | [6 empty] | 2016-04-25: 8; 2016-04-29: 4; 2016-05-02: 8; 2016-05-03: 8; 2016-05-06: 8; 2016-05-09: 8; 2016-05-10: 8; 2016-05-11: 8; 2016-05-12: 8; 2016-05-13: 8; 2016-05-16: 8; 2016-05-17: 8
| HUGO PALMA - JOURNEYMAN | 0 | 8 | 0 | HRS | 75 | 0 | 600 | 0 | [6 empty] | 2016-05-20: 8
| JOSE ESPARZA - APPRENTICE | 64 | 108 | 5 | HRS | 46 | 2944 | 4968 | 230 | [6 empty] | 2016-04-26: 8; 2016-04-28: 8; 2016-05-04: 8; 2016-05-06: 8; 2016-05-10: 8; 2016-05-11: 8; 2016-05-12: 8; 2016-05-13: 8; 2016-05-16: 8; 2016-05-17: 8; 2016-05-18: 8; 2016-05-19: 8; 2016-05-20: 8; 2016-05-23: 8; 2016-05-25: 8; 2016-05-26: 8; 2016-05-27: 8; 2016-05-31: 8; 2016-06-01: 8; 2016-06-02: 8; 2016-06-03: 8; 2016-06-06: 4; 2016-06-29: 5
| GARRET WILSON - APPRENTICE | 50 | 40 | 13 | HRS | 46 | 2300 | 1840 | 598 | [6 empty] | 2016-04-21: 8; 2016-04-28: 8; 2016-04-29: 8; 2016-05-10: 2; 2016-05-11: 8; 2016-05-12: 8; 2016-05-13: 8; 2016-05-16: 8; 2016-05-17: 8; 2016-05-18: 8; 2016-05-19: 8; 2016-05-20: 8; 2016-06-21: 4; 2016-06-28: 5; 2016-07-11: 4
| JOHN WENNIG - APPRENTICE | 34 | 72 | 0 | HRS | 46 | 1564 | 3312 | 0 | [6 empty] | 2016-04-28: 8; 2016-04-29: 8; 2016-05-10: 2; 2016-05-11: 8; 2016-05-13: 8; 2016-05-16: 8; 2016-05-17: 8; 2016-05-18: 8; 2016-05-19: 8; 2016-05-23: 8; 2016-05-24: 8; 2016-05-25: 8; 2016-05-31: 8; 2016-06-01: 8
| RICARDO BALDARES - APPRENTICE | 16 | 112 | 0 | HRS | 46 | 736 | 5152 | 0 | [6 empty] | 2016-04-28: 8; 2016-05-04: 8; 2016-05-16: 8; 2016-05-17: 8; 2016-05-18: 8; 2016-05-19: 8; 2016-05-20: 8; 2016-05-23: 8; 2016-05-24: 8; 2016-05-25: 8; 2016-05-26: 8; 2016-05-27: 8; 2016-05-31: 8; 2016-06-01: 8; 2016-06-02: 8; 2016-06-03: 8
| STEVEN BROWN - APPRENTICE | 2 | 16 | 0 | HRS | 46 | 92 | 736 | 0 | [6 empty] | 2016-05-03: 2; 2016-05-18: 8; 2016-05-20: 8
| MITCH GERARD - APPRENTICE | 8 | 0 | 0 | HRS | 46 | 368 | 0 | 0 | [6 empty] | 2016-05-05: 8
| ELI RIVERA - APPRENTICE | 20 | 8 | 0 | HRS | 46 | 920 | 368 | 0 | [6 empty] | 2016-04-20: 4; 2016-04-21: 4; 2016-04-22: 4; 2016-04-28: 8; 2016-05-20: 8
| JJ KINNSIES - APPRENTICE | 16 | 12 | 0 | HRS | 46 | 736 | 552 | 0 | [6 empty] | 2016-04-21: 8; 2016-05-12: 8; 2016-05-16: 2; 2016-05-18: 2; 2016-05-20: 8
| JORDAN GARCIA - APPRENTICE | 14 | 24 | 0 | HRS | 46 | 644 | 1104 | 0 | [6 empty] | 2016-04-26: 2; 2016-04-29: 4; 2016-05-02: 8; 2016-05-16: 8; 2016-05-20: 8; 2016-05-23: 8
| ANDREW GARDNER - APPRENTICE | 1 | 70 | 0 | HRS | 46 | 46 | 3220 | 0 | [6 empty] | 2016-05-12: 1; 2016-05-16: 2; 2016-05-18: 2; 2016-05-19: 2; 2016-05-20: 8; 2016-05-24: 8; 2016-05-25: 8; 2016-05-26: 8; 2016-05-31: 8; 2016-06-01: 8; 2016-06-02: 8; 2016-06-08: 4; 2016-06-09: 4
| TOMMY MCCABE - APPRENTICE | 0 | 16 | 0 | HRS | 46 | 0 | 736 | 0 | [6 empty] | 2016-05-20: 8; 2016-05-23: 8
| JESUS MENDOZA - APPRENTICE | 0 | 64 | 5 | HRS | 46 | 0 | 2944 | 230 | [6 empty] | 2016-05-23: 8; 2016-05-25: 8; 2016-05-26: 8; 2016-05-27: 8; 2016-05-31: 8; 2016-06-01: 8; 2016-06-02: 8; 2016-06-03: 8; 2016-06-29: 5
| SCAN-2-CORE 4/19 | [12 empty] | LS | 675
| SCAN-2-CORE 4/20 | [12 empty] | LS | 825
| SCISSOR LIFT FOR THE MONTH OF MAY | [12 empty] | LS | 568.15
PVC MATERIALS:
TUB VENT STACK AND REVENTS MATERIAL X 12:
| 2X1-1/2 TEE | [8 empty] | 36 | EA | 1.38 | 49.68
| 1-1/2 90 | [8 empty] | 36 | EA | 0.66 | 23.76
| 2X1-1/2 BUSH | [8 empty] | 36 | EA | 0.56 | 20.16
| 1-1/2 45 ST | [8 empty] | 36 | EA | 0.63 | 22.68
| 1-1/2 45 REG | [8 empty] | 36 | EA | 0.71 | 25.56
| 2 COUPLING | [8 empty] | 24 | EA | 0.46 | 11.04
| 2 45 ST | [8 empty] | 36 | EA | 0.94 | 33.84
| 2 45 REG | [8 empty] | 36 | EA | 0.9 | 32.4
| 2 90 REG | [8 empty] | 24 | EA | 0.99 | 23.76
| TEST TEE | [8 empty] | 12 | EA | 6.92 | 83.04
| 2 PIPE | [8 empty] | 600 | LF | 0.61 | 366
| 1-1/2 PIPE | [8 empty] | 240 | LF | 0.5 | 120
AW VENT STACK AND REVENT AND MISC X 1:
| 2 PIPE | [8 empty] | 35 | LF | 0.61 | 21.35
| 1-1/2 PIPE | [8 empty] | 15 | LF | 0.5 | 7.5
| 2 45 ST | [8 empty] | 4 | EA | 0.94 | 3.76
| 2 45 REG | [8 empty] | 4 | EA | 0.9 | 3.6
| 2X1-1/2 TEE | [8 empty] | 3 | EA | 1.38 | 4.14
| 1-1/2 90 | [8 empty] | 3 | EA | 0.66 | 1.98
| 2 COUPLING | [8 empty] | 3 | EA | 0.46 | 1.38
| TEST TEE | [8 empty] | 2 | EA | 6.92 | 13.84
| 2X1-1/2 TEE | [8 empty] | 4 | EA | 1.38 | 5.52
| 1-1/2 90 | [8 empty] | 4 | EA | 0.66 | 2.64
| 2 45 ST | [8 empty] | 6 | EA | 0.94 | 5.64
| 2 45 REG | [8 empty] | 2 | EA | 0.9 | 1.8
| 2X1-1/2X2 TEE | [8 empty] | 4 | EA | 1.65 | 6.6
| 2 PTRAP | [8 empty] | 4 | EA | 2.75 | 11
| 2 COUPLING | [8 empty] | 6 | EA | 0.46 | 2.76
| 2 90 REG | [8 empty] | 2 | EA | 0.99 | 1.98
| 2 TEST TEE | [8 empty] | 1 | EA | 6.92 | 6.92
| 2 PIPE | [8 empty] | 50 | LF | 0.61 | 30.5
| 1-1/2 PIPE | [8 empty] | 20 | LF | 0.5 | 10
| ANCHORS, HANGERS, SUPPORTS, GLUE, ACOUSTICAL TAPE, P-TAPE, MISCELLANEOUS | [8 empty] | 1 | LS | 350 | 350
CAST IRON MATERIALS:
| 2" CAST IRON | [8 empty] | 60 | LF | 4.55 | 273
| NO-HUB BANDS | [8 empty] | 25 | EA | 1.35 | 33.75
ALL FITTINGS WERE ABLE TO BE RE-USED
PEX MATERIALS:
| 1/2" PEX RING | [8 empty] | 192 | EA | 0.15 | 28.8
| 1/2" PEX COUPLING | [8 empty] | 96 | EA | 0.75 | 72
| 1/2" PEX PIPE | [8 empty] | 100 | LF | 0.38 | 38
| Subtotals | [5 empty] | 24920 | 33007 | 1393 |  |  |  | 1750.38 | 0 | 2068.15
| OH & Profit |  |  |  |  | 10% | 2492 | 3300.7 | 139.3 |  |  | 10% | 175.038 | 10% | 206.815
| Totals | [5 empty] | 27412 | 36307.7 | 1532.3 |  |  |  | 1925.418 |  | 2274.965
MATERIALS THROUGH 6/10
| GROUT | [8 empty] | 20 | EA | 20 | 400
| Subtotals | [11 empty] | 400 | 0.1
| OH & Profit |  |  |  |  | 10% | [5 empty] | 10% | 40 | 10%
| Totals | [11 empty] | 440
MATERIALS THROUGH 6/29
| CORE DRILLING | [8 empty] | 1 | LS | 600 | 600
| FIRESTOPPING | [8 empty] | 1 | LS | 3860 | 3860
| Subtotals | [11 empty] | 4460 | 0.3
| OH & Profit |  |  |  |  | 10% | [5 empty] | 10% | 446 | 10%
| Totals | [11 empty] | 4906
TOTAL THRU 5/13
31612.383
TOTAL THRU 6/10
36747.7
TOTAL THRU 6/10
6438.3
COSTS FOR ASI-024 SHOWER CHANGE, FROM 5/16/16 THROUGH END OF BUSINESS 06/10/16
Note on BA25: Richard Donelson: per joe phone call
Note on BA26: Richard Donelson: per joe phone call

## hour breakdown
Employee & Title | Thru 5/13 | APRIL | [26 empty] | MAY
 | time axis 2016-04-04 to 2016-05-15
RICHARD DONELSON - PROJECT MANAGER | 12 | 2016-04-05: 2; 2016-04-07: 1; 2016-04-08: 1; 2016-04-12: 3; 2016-04-15: 1; 2016-04-19: 2; 2016-05-13: 2
JEFF GERARD - PROJECT MANAGER | 2 | 2016-04-19: 2
BOB HUBBARD - SUPERINTENDENT | 4 | 2016-04-20: 2; 2016-04-22: 2
JOE BARNHART - FOREMAN | 30 | 2016-04-18: 1; 2016-04-19: 3; 2016-04-20: 3; 2016-04-21: 1; 2016-04-22: 2; 2016-04-27: 2; 2016-04-28: 4; 2016-04-29: 2; 2016-05-04: 4; 2016-05-09: 2; 2016-05-10: 2; 2016-05-12: 2; 2016-05-13: 2
THADDEUS WAITES - FOREMAN | 60 | 2016-04-19: 8; 2016-04-20: 8; 2016-04-22: 8; 2016-04-25: 8; 2016-04-26: 4; 2016-04-29: 2; 2016-05-03: 2; 2016-05-04: 2; 2016-05-05: 8; 2016-05-09: 2; 2016-05-10: 2; 2016-05-12: 2; 2016-05-13: 4
KELLI ROSS - JOURNEYMAN | 76 | 2016-04-25: 8; 2016-04-29: 4; 2016-05-02: 8; 2016-05-03: 8; 2016-05-06: 8; 2016-05-09: 8; 2016-05-10: 8; 2016-05-11: 8; 2016-05-12: 8; 2016-05-13: 8
HUGO PALMA - JOURNEYMAN | 0
JOSE ESPARZA - APPRENTICE | 64 | 2016-04-26: 8; 2016-04-28: 8; 2016-05-04: 8; 2016-05-06: 8; 2016-05-10: 8; 2016-05-11: 8; 2016-05-12: 8; 2016-05-13: 8
GARRET WILSON - APPRENTICE | 50 | 2016-04-21: 8; 2016-04-28: 8; 2016-04-29: 8; 2016-05-10: 2; 2016-05-11: 8; 2016-05-12: 8; 2016-05-13: 8
JOHN WENNIG - APPRENTICE | 34 | 2016-04-28: 8; 2016-04-29: 8; 2016-05-10: 2; 2016-05-11: 8; 2016-05-13: 8
RICARDO BALDARES - APPRENTICE | 16 | 2016-04-28: 8; 2016-05-04: 8
STEVEN BROWN - APPRENTICE | 2 | 2016-05-03: 2
MITCH GERARD - APPRENTICE | 8 | 2016-05-05: 8
ELI RIVERA - APPRENTICE | 20 | 2016-04-20: 4; 2016-04-21: 4; 2016-04-22: 4; 2016-04-28: 8
JJ KINNSIES - APPRENTICE | 16 | 2016-04-21: 8; 2016-05-12: 8
JORDAN GARCIA - APPRENTICE | 14 | 2016-04-26: 2; 2016-04-29: 4; 2016-05-02: 8
ANDREW GARDNER - APPRENTICE | 1 | bar: 2016-05-12
TOMMY MCCABE - APPRENTICE | 0
JESUS MENDOZA - APPRENTICE | 0
| 409 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 | 0 | 1 | 15 | 17 | 21 | 16 | 0 | 0 | 16 | 14 | 2 | 44 | 28 | 0 | 0 | 16 | 12 | 22 | 16 | 16 | 0 | 0 | 12 | 24 | 32 | 37 | 40 | 0 | 0
Employee & Title | Thru 6/15 | 2016-04-04: MAY; 2016-04-20: JUNE
|  | 2016-05-16 | 2016-05-17 | 2016-05-18 | 2016-05-19 | 2016-05-20 | 2016-05-21 | 2016-05-22 | 2016-05-23 | 2016-05-24 | 2016-05-25 | 2016-05-26 | 2016-05-27 | 2016-05-28 | 2016-05-29 | 2016-05-30 | 2016-05-31 | 2016-06-01 | 2016-06-02 | 2016-06-03 | 2016-06-04 | 2016-06-05 | 2016-06-06 | 2016-06-07 | 2016-06-08 | 2016-06-09 | 2016-06-10 | 2016-06-11 | 2016-06-12 | 2016-06-13 | 2016-06-14 | 2016-06-15 | 2016-06-16 | 2016-06-17
RICHARD DONELSON - PROJECT MANAGER | 6 | 2016-05-17: 2; 2016-05-24: 1; 2016-06-10: 3
JEFF GERARD - PROJECT MANAGER | 4 | bar: 2016-05-17; 2016-05-19; 2016-05-26; 2016-05-31
BOB HUBBARD - SUPERINTENDENT | 1 | bar: 2016-05-26
JOE BARNHART - FOREMAN | 18 | 2016-05-16: 2; 2016-05-17: 1; 2016-05-18: 2; 2016-05-19: 2; 2016-05-26: 2; 2016-06-01: 2; 2016-06-02: 2; 2016-06-03: 1; 2016-06-06: 4
THADDEUS WAITES - FOREMAN | 47.5 | 2016-05-16: 2; 2016-05-17: 1; 2016-05-18: 8; 2016-05-19: 2; 2016-05-20: 3; 2016-05-23: 2; 2016-05-24: 2; 2016-05-25: 2.5; 2016-05-26: 2; 2016-05-27: 3; 2016-05-31: 2; 2016-06-01: 2; 2016-06-02: 2; 2016-06-03: 8; 2016-06-06: 4; 2016-06-08: 1; 2016-06-09: 1
KELLI ROSS - JOURNEYMAN | 16 | 2016-05-16: 8; 2016-05-17: 8
HUGO PALMA - JOURNEYMAN | 8 | 2016-05-20: 8
JOSE ESPARZA - APPRENTICE | 108 | 2016-05-16: 8; 2016-05-17: 8; 2016-05-18: 8; 2016-05-19: 8; 2016-05-20: 8; 2016-05-23: 8; 2016-05-25: 8; 2016-05-26: 8; 2016-05-27: 8; 2016-05-31: 8; 2016-06-01: 8; 2016-06-02: 8; 2016-06-03: 8; 2016-06-06: 4
GARRET WILSON - APPRENTICE | 40 | 2016-05-16: 8; 2016-05-17: 8; 2016-05-18: 8; 2016-05-19: 8; 2016-05-20: 8
JOHN WENNIG - APPRENTICE | 72 | 2016-05-16: 8; 2016-05-17: 8; 2016-05-18: 8; 2016-05-19: 8; 2016-05-23: 8; 2016-05-24: 8; 2016-05-25: 8; 2016-05-31: 8; 2016-06-01: 8
RICARDO BALDARES - APPRENTICE | 112 | 2016-05-16: 8; 2016-05-17: 8; 2016-05-18: 8; 2016-05-19: 8; 2016-05-20: 8; 2016-05-23: 8; 2016-05-24: 8; 2016-05-25: 8; 2016-05-26: 8; 2016-05-27: 8; 2016-05-31: 8; 2016-06-01: 8; 2016-06-02: 8; 2016-06-03: 8
STEVEN BROWN - APPRENTICE | 16 | 2016-05-18: 8; 2016-05-20: 8
MITCH GERARD - APPRENTICE | 0
ELI RIVERA - APPRENTICE | 8 | 2016-05-20: 8
JJ KINNSIES - APPRENTICE | 12 | 2016-05-16: 2; 2016-05-18: 2; 2016-05-20: 8
JORDAN GARCIA - APPRENTICE | 24 | 2016-05-16: 8; 2016-05-20: 8; 2016-05-23: 8
ANDREW GARDNER - APPRENTICE | 70 | 2016-05-16: 2; 2016-05-18: 2; 2016-05-19: 2; 2016-05-20: 8; 2016-05-24: 8; 2016-05-25: 8; 2016-05-26: 8; 2016-05-31: 8; 2016-06-01: 8; 2016-06-02: 8; 2016-06-08: 4; 2016-06-09: 4
TOMMY MCCABE - APPRENTICE | 16 | 2016-05-20: 8; 2016-05-23: 8
JESUS MENDOZA - APPRENTICE | 64 | 2016-05-23: 8; 2016-05-25: 8; 2016-05-26: 8; 2016-05-27: 8; 2016-05-31: 8; 2016-06-01: 8; 2016-06-02: 8; 2016-06-03: 8
| 642.5 | 56 | 45 | 54 | 39 | 83 | 0 | 0 | 50 | 27 | 42.5 | 38 | 27 | 0 | 0 | 0 | 43 | 44 | 36 | 33 | 0 | 0 | 12 | 0 | 5 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 4-20
2014-PIKE MOTORWORKS | 2024-MERRILL GARDENS |  |  | 2028-RESERVE LYNNWOOD |  |  | 050-CLOSED JOBS |  |  | LABOR CODES | [5 empty] | 141- MAIN / INSULATION
2019-8REP | 2025-CORA |  |  | 2029-PARSONAGE | [5 empty] | 110- UNDERGROUND |  |  | 120-ROUGH IN |  |  | 142- MECH ROOM
2021-ADMIRAL | 2026-525 BOREN |  |  | 2030-EAST UNION |  |  | CONFIRM HOURS |  |  | 111-GARAGE |  |  | 130- FINISH |  |  | 143- CONDENSATION
2023-LEGACY | 2027-550 BROADWAY |  |  | 2031-GATEWAY |  |  | EVERYDAY |  |  | 112-CANOUT |  |  | 140-GAS |  |  | 151-T&M
LEGACY
| 2016-04-14 |  |  | 2016-04-15 |  |  | 2016-04-18 |  |  | 2016-04-19 |  |  | 2016-04-20 |  |  | 2016-04-16
| THURSDAY |  |  | FRIDAY |  |  | MONDAY |  |  | TUESDAY |  |  | WEDNESDAY |  |  | WEEKEND |  | TOTAL
NAME
BARNHART JOE | 2023 | 140 | 3 | 2023 | 120 | 8 | 2027 | 110 | 2 | 2023 | 120 | 5 | 2023 | 120 | 5 |  |  | 23
| 2027 | 110 | 5 |  |  |  | 2023 | 111 | 5 | 2023 | 151 | 3 | 2023 | 151 | 3 |  |  | 16
[7 empty] | 2023 | 151 | 1 | [8 empty] | 1
BALDERAS RICARDO | 2023 | 111 | 8 | 2023 | 111 | 8 | 2023 | 111 | 8 | off |  |  | 2023 | 120 | 8 |  |  | 32
0
BROWN STEVEN | off |  |  | off |  |  | 2023 | 141 | 8 | 2023 | 141 | 8 | 2023 | 141 | 8 |  |  | 24
0
ESPARZA JOSE | 2023 | 120 | 8 | off |  |  | 2023 | 120 | 8 | 2023 | 120 | 8 | 2023 | 120 | 8 |  |  | 32
0
GARCIA JORDAN | 2023 | 140 | 8 | off |  |  | 2023 | 120 | 8 | 2023 | 120 | 8 | 2023 | 140 | 8 |  |  | 32
0
GARDNER ANDREW | 2023 | 120 | 8 | off |  |  | off |  |  | 2023 | 120 | 8 | 2023 | 140 | 8 |  |  | 24
0
KINSSIES JJ | off |  |  | 2023 | 120 | 8 | off |  |  | off |  |  | 2023 | 120 | 8 |  |  | 16
| court | [16 empty] | 0
McCABE TOM | 2023 | 141 | 8 | 2023 | 141 | 8 | 2023 | 141 | 4 | 2023 | 141 | 2.5 | 2023 | 141 | 8 |  |  | 30.5
[7 empty] | 2019 | 120 | 4 |  | left early | [6 empty] | 4
RIVERA ELI | 2023 | 120 | 8 | 2023 | 120 | 8 | 2023 | 120 | 8 | 2023 | 120 | 8 | 2023 | 120 | 4 |  |  | 36
[13 empty] | 2023 | 151 | 4 |  |  | 4
ROSS KELLI | 2023 | 120 | 8 | 2023 | 120 | 8 | 2023 | 120 | 8 | 2023 | 111 | 8 | 2023 | 120 | 8 |  |  | 40
0
WAITES THADDEUS | 2023 | 120 | 8 | 2023 | 120 | 8 | 2023 | 120 | 4 | 2023 | 151 | 8 | 2023 | 151 | 8 |  |  | 36
[7 empty] | 2019 | 120 | 4 | [8 empty] | 4
WENNING JOHN | off |  |  | off |  |  | 2023 | 120 | 8 | 2023 | 120 | 8 | 2023 | 120 | 8 | cash out | pto | 24
0
WILSON GARRETT | 2023 | 120 | 3 | 2023 | 120 | 8 | off |  |  | 2023 | 120 | 8 | 2023 | 120 | 8 |  |  | 27
| 2027 | 110 | 7 | [14 empty] | 7
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## 4-27
| 2014-PIKE MOTORWORKS | 2024-MERRILL GARDENS |  |  | 2028-RESERVE LYNNWOOD |  |  | 050-CLOSED JOBS |  |  | LABOR CODES | [5 empty] | 141- MAIN / INSULATION
| 2019-8REP | 2025-CORA |  |  | 2029-PARSONAGE | [5 empty] | 110- UNDERGROUND |  |  | 120-ROUGH IN |  |  | 142- MECH ROOM
| 2021-ADMIRAL | 2026-525 BOREN |  |  | 2030-EAST UNION |  |  | CONFIRM HOURS |  |  | 111-GARAGE |  |  | 130- FINISH |  |  | 143- CONDENSATION
| 2023-LEGACY | 2027-550 BROADWAY |  |  | 2031-GATEWAY |  |  | EVERYDAY |  |  | 112-CANOUT |  |  | 140-GAS |  |  | 151-T&M
LEGACY
|  | 2016-04-21 |  |  | 2016-04-22 |  |  | 2016-04-25 |  |  | 2016-04-26 |  |  | 2016-04-27 |  |  | 2016-04-23
|  | THURSDAY |  |  | FRIDAY |  |  | MONDAY |  |  | TUESDAY |  |  | WEDNESDAY |  |  | WEEKEND | TOTAL
NAME
2 | BARNHART JOE | 2023 | 120 | 7 | 2027 | 110 | 3 | 2027 | 110 | 8 | 2027 | 110 | 8 | 2027 | 110 | 3 |  | 29
|  | 2023 | 151 | 1 | 2023 | 120 | 3 | [6 empty] | 2023 | 120 | 3 |  | 7
|  | 2027 | 110 | 2.5 | 2023 | 151 | 2 | [6 empty] | 2023 | 151 | 2 |  | 6.5
1 | BALDERAS RICARDO | 2023 | 120 | 8 | 2023 | 120 | 8 | off |  |  | 2023 | 120 | 8 | 2023 | 120 | 8 |  | 32
0
3 | BROWN STEVEN | off |  |  | off |  |  | 2023 | 141 | 8 | 2023 | 141 | 8 | 2023 | 141 | 8 |  | 24
0
4 | ESPARZA JOSE | 2023 | 120 | 8 | 2023 | 120 | 8 | off |  |  | 2023 | 151 | 8 | 2023 | 120 | 8 |  | 32
0
5 | GARCIA JORDAN | 2023 | 142 | 8 | off |  |  | 2023 | 120 | 8 | 2023 | 120 | 6 | 2023 | 120 | 8 |  | 30
[11 empty] | 2023 | 151 | 2 |  |  |  |  | 2
6 | GARDNER ANDREW | 2023 | 111 | 8 | off |  |  | off |  |  | 2023 | 120 | 8 | 2023 | 120 | 8 |  | 24
0
7 | McCABE TOM | 2023 | 141 | 8 | 2023 | 141 | 8 | off |  |  | 2023 | 141 | 8 | 2023 | 141 | 8 |  | 32
0
8 | RIVERA ELI | 2023 | 120 | 4 | 2023 | 120 | 4 | 2023 | 120 | 8 | 2023 | 120 | 8 | 2023 | 120 | 8 |  | 32
|  | 2023 | 151 | 4 | 2023 | 151 | 4 | [10 empty] | 8
9 | ROSS KELLI | pto |  | 8 | off |  |  | 2023 | 151 | 8 | 2023 | 120 | 8 | 2023 | 120 | 8 |  | 32
0
10 | WAITES THADDEUS | pto |  | 8 | 2023 | 151 | 8 | 2023 | 151 | 8 | 2023 | 120 | 4 | 2023 | 120 | 8 |  | 36
|  | dr.appt | [8 empty] | 2023 | 151 | 4 |  |  |  |  | 4
11 | WENNING JOHN | off |  |  | off |  |  | off |  |  | 2023 | 120 | 8 | 2023 | 120 | 8 |  | 16
0
| WILSON GARRETT | 2023 | 151 | 8 | 2023 | 120 | 5 | 2027 | 110 | 8 | 2027 | 110 | 8 | 2023 | 120 | 8 |  | 37
[5 empty] | left early | [12 empty] | 0
| KINSSIES JJ | 2023 | 151 | 8 | 2023 | 120 | 5 | OFF |  | 0 | OFF |  | 0 | 2023 | 130 | 8 |  | 21
[5 empty] | left early | [12 empty] | 0
0
0

## 5-4
2014-PIKE MOTORWORKS | 2024-MERRILL GARDENS |  |  | 2028-RESERVE LYNNWOOD |  |  | 050-CLOSED JOBS |  |  | LABOR CODES | [5 empty] | 141- MAIN / INSULATION
2019-8REP | 2025-CORA |  |  | 2029-PARSONAGE | [5 empty] | 110- UNDERGROUND |  |  | 120-ROUGH IN |  |  | 142- MECH ROOM
2021-ADMIRAL | 2026-525 BOREN |  |  | 2030-EAST UNION |  |  | CONFIRM HOURS |  |  | 111-GARAGE |  |  | 130- FINISH |  |  | 143- CONDENSATION
2023-LEGACY | 2027-550 BROADWAY |  |  | 2031-GATEWAY |  |  | EVERYDAY |  |  | 112-CANOUT |  |  | 140-GAS |  |  | 151-T&M
LEGACY
| 2016-04-28 |  |  | 2016-04-29 |  |  | 2016-05-02 |  |  | 2016-05-03 |  |  | 2016-05-04 |  |  | 2016-04-30
NAME | THURSDAY |  |  | FRIDAY |  |  | MONDAY |  |  | TUESDAY |  |  | WEDNESDAY |  |  | WEEKEND | TOTAL
BARNHART JOE | 2023 | 120 | 4 | 2023 | 120 | 2 | 2027 | 110 | 8 | 2027 | 110 | 9 | 2023 | 142 | 4 |  | 27
| 2023 | 151 | 4 | 2023 | 151 | 2 | [6 empty] | 2023 | 151 | 4 |  | 10
|  |  |  | 2027 | 110 | 4 | [10 empty] | 4
BALDERAS RICARDO | 2023 | 151 | 8 | 2023 | 120 | 8 | off |  |  | 2023 | 120 | 8 | 2023 | 151 | 8 |  | 32
0
BROWN STEVEN | off |  |  | off |  |  | 2023 | 120 | 8 | 2023 | 111 | 6 | 2023 | 111 | 8 |  | 22
[10 empty] | 2023 | 151 | 2 |  |  |  |  | 2
ESPARZA JOSE | 2023 | 151 | 8 | off |  |  | off |  |  |  | CLASS |  | 2023 | 151 | 8 |  | 16
[10 empty] | SHOP | 606 | 8 |  |  |  |  | 8
GARCIA JORDAN | 2023 | 120 | 8 | 2023 | 120 | 4 | 2023 | 151 | 8 | 2023 | 120 | 8 | 2023 | 120 | 8 |  | 36
|  |  |  | 2023 | 151 | 4 | [10 empty] | 4
GARDNER ANDREW | 2023 | 111 | 8 | off |  |  | off |  |  | off |  |  | 2023 | 111 | 8 |  | 16
0
McCABE TOM | 2023 | 141 | 8 | 2023 | 141 | 8 | off |  |  | off |  |  | 2023 | 120 | 8 |  | 24
0
RIVERA ELI | 2023 | 151 | 8 | off |  |  | off |  |  | off |  |  | off |  |  |  | 8
|  |  |  | surgery | [12 empty] | 0
ROSS KELLI | 2023 | 120 | 8 | 2023 | 120 | 4 | 2023 | 151 | 8 | 2023 | 151 | 8 | 2023 | 120 | 8 |  | 36
|  |  |  | 2023 | 151 | 4 | [10 empty] | 4
PALMA VIDES JORGE | 2021 | 141 | 8 | 2021 | 14 | 8 | 2023 | 141 | 8 | 2023 | 141 | 8 | 2023 | 141 | 8 |  | 40
0
PALMA VIDES HUGO | 2021 | 141 | 4 | 2021 | 140 | 8 | 2023 | 141 | 8 | 2023 | 141 | 8 | 2023 | 141 | 8 |  | 36
| 2021 | 141 | 4 | [13 empty] | 4
WAITES THADDEUS | OFF |  | 0 | 2023 | 120 | 6 | 2023 | 120 | 8 | 2023 | 120 | 6 | 2023 | 120 | 6 |  | 26
|  | SICK |  | 2023 | 151 | 2 |  |  |  | 2023 | 151 | 2 | 2023 | 151 | 2 |  | 6
WENNING JOHN | 2023 | 151 | 8 | 2023 | 151 | 8 | 2023 | 120 | 8 | 2023 | 120 | 8 | 2023 | 120 | 8 |  | 40
0
WILSON GARRETT | 2023 | 151 | 8 | 2023 | 151 | 8 | 2027 | 110 | 8 | 2027 | 110 | 8 | 2023 | 142 | 8 |  | 40

## 5-11
2014-PIKE MOTORWORKS | 2024-MERRILL GARDENS |  |  | 2028-RESERVE LYNNWOOD |  |  | 050-CLOSED JOBS |  |  | LABOR CODES | [5 empty] | 141- MAIN / INSULATION
2019-8REP | 2025-CORA |  |  | 2029-PARSONAGE | [5 empty] | 110- UNDERGROUND |  |  | 120-ROUGH IN |  |  | 142- MECH ROOM
2021-ADMIRAL | 2026-525 BOREN |  |  | 2030-EAST UNION |  |  | CONFIRM HOURS |  |  | 111-GARAGE |  |  | 130- FINISH |  |  | 143- CONDENSATION
2023-LEGACY | 2027-550 BROADWAY |  |  | 2031-GATEWAY |  |  | EVERYDAY |  |  | 112-CANOUT |  |  | 140-GAS |  |  | 151-T&M
LEGACY
| 2016-05-05 |  |  | 2016-05-06 |  |  | 2016-05-09 |  |  | 2016-05-10 |  |  | 2016-05-11 |  |  | 2016-05-07
NAME | THURSDAY |  |  | FRIDAY |  |  | MONDAY |  |  | TUESDAY |  |  | WEDNESDAY |  |  | WEEKEND | TOTAL
BARNHART JOE | 2023 | 120 | 8 | 2027 | 110 | 6 | 2023 | 120 | 6 | 2027 | 110 | 1 | 2023 | 120 | 8 |  | 29
|  |  |  | 2023 | 130 | 2 | 2023 | 151 | 2 | 2023 | 120 | 5 |  |  |  |  | 9
[10 empty] | 2023 | 151 | 2 |  |  |  |  | 2
BALDERAS RICARDO | 2023 | 141 | 8 | 2023 | 141 | 8 | off |  |  | off |  |  | off |  |  |  | 16
0
BROWN STEVEN | off |  |  | off |  |  | 2023 | 120 | 8 | 2023 | 130 | 8 | 2023 | 130 | 8 |  | 24
0
ESPARZA JOSE | off testing |  |  | 2023 | 151 | 8 | 2023 | 141 | 8 | 2023 | 151 | 8 | 2023 | 151 | 8 |  | 32
0
GARCIA JORDAN | 2023 | 120 | 8 | 2023 | 120 | 8 | 2023 | 140 | 8 | 2023 | 140 | 8 | 2023 | 140 | 8 |  | 40
0
GARDNER ANDREW | 2023 | 120 | 8 | 2023 | 111 | 8 | off |  |  | 2023 | 130 | 8 | 2023 | 130 | 8 |  | 32
0
McCABE TOM | 2023 | 120 | 8 | 2023 | 120 | 8 | 2023 | 140 | 8 | 2023 | 140 | 8 | 2023 | 140 | 8 |  | 40
0
RIVERA ELI | off |  |  | off |  |  | off |  |  | 2023 | 120 | 8 | 2023 | 111 | 8 |  | 16
0
ROSS KELLI | 2023 | 120 | 8 | 2023 | 151 | 8 | 2023 | 151 | 8 | 2023 | 151 | 8 | 2023 | 151 | 8 |  | 40
0
PALMA VIDES JORGE | 2023 | 141 | 8 | 2023 | 141 | 8 | 2023 | 141 | 8 | 2023 | 141 | 8 | 1002 | 180 | 8 |  | 40
0
PALMA VIDES HUGO | 2023 | 141 | 8 | 2023 | 141 | 8 | 2023 | 141 | 5 | 2023 | 141 | 8 | 2023 | 141 | 8 |  | 37
[7 empty] | doc app | [9 empty] | 0
WAITES THADDEUS | 2023 | 151 | 8 | 2023 | 120 | 8 | 2023 | 120 | 6 | 2023 | 120 | 6 | 2023 | 120 | 8 |  | 36
[7 empty] | 2023 | 151 | 2 | 2023 | 151 | 2 |  |  |  |  | 4
WENNING JOHN | off |  |  | off |  |  | 2023 | 120 | 8 | 2023 | 120 | 6 | 2023 | 151 | 8 |  | 22
[10 empty] | 2023 | 151 | 2 |  |  |  |  | 2
WILSON GARRETT | 2023 | 142 | 8 | 2023 | 142 | 8 | 2023 | 142 | 8 | 2023 | 120 | 6 | 2023 | 151 | 8 |  | 38
[10 empty] | 2023 | 151 | 2 |  |  |  |  | 2
GERARD MITCHELL | 2023 | 151 | 8 | 2027 | 110 | 6 | 2023 | 142 | 8 | 2027 | 110 | 8 | 2023 | 120 | 8 |  | 38
|  |  |  | 2023 | 142 | 2 | [10 empty] | 2

## 5-18
2014-PIKE MOTORWORKS | 2024-MERRILL GARDENS |  |  | 2028-RESERVE LYNNWOOD |  |  | 050-CLOSED JOBS |  |  | LABOR CODES | [5 empty] | 141- MAIN / INSULATION
2019-8REP | 2025-CORA |  |  | 2029-PARSONAGE | [5 empty] | 110- UNDERGROUND |  |  | 120-ROUGH IN |  |  | 142- MECH ROOM
2021-ADMIRAL | 2026-525 BOREN |  |  | 2030-EAST UNION |  |  | CONFIRM HOURS |  |  | 111-GARAGE |  |  | 130- FINISH |  |  | 143- CONDENSATION
2023-LEGACY | 2027-550 BROADWAY |  |  | 2031-GATEWAY |  |  | EVERYDAY |  |  | 112-CANOUT |  |  | 140-GAS |  |  | 151-T&M
LEGACY
| 2016-05-12 |  |  | 2016-05-13 |  |  | 2016-05-16 |  |  | 2016-05-17 |  |  | 2016-05-18 |  |  | 2016-05-14
NAME | THURSDAY |  |  | FRIDAY |  |  | MONDAY |  |  | TUESDAY |  |  | WEDNESDAY |  |  | WEEKEND |  |  | TOTAL
BARNHART JOE | 2023 | 120 | 6 | 2027 | 110 | 4 | 2023 | 120 | 6 | 2023 | 120 | 7 | 2023 | 111 | 6 |  |  |  | 29
| 2023 | 151 | 2 | 2023 | 120 | 6 | 2023 | 151 | 2 | 2023 | 151 | 1 | 2023 | 151 | 2 |  |  |  | 13
|  |  |  | 2023 | 151 | 2 | [12 empty] | 2
BALDERAS RICARDO | off |  |  | off |  |  | 2023 | 151 | 8 | 2023 | 151 | 8 | 2023 | 151 | 8 |  |  |  | 24
0
BROWN STEVEN | off |  |  | off |  |  | 2023 | 120 | 8 | 2023 | 120 | 8 | 2023 | 151 | 8 |  |  |  | 24
0
ESPARZA JOSE | 2023 | 151 | 8 | 2023 | 151 | 8 | 2023 | 151 | 8 | 2023 | 151 | 8 | 2023 | 151 | 8 |  |  |  | 40
0
GARCIA JORDAN | 2023 | 120 | 8 | 2023 | 120 | 8 | 2023 | 151 | 8 | 2023 | 120 | 8 | 2023 | 142 | 8 | pto |  | 3 | 43
0
GARDNER ANDREW | 2023 | 120 | 7 | off |  |  | 2023 | 151 | 2 | 2023 | 120 | 8 | 2023 | 151 | 2 | cash out pto |  |  | 19
| 2023 | 151 | 1 |  |  |  | 2023 | 120 | 6 |  |  |  | 2023 | 120 | 6 |  |  |  | 13
McCABE TOM | 2023 | 120 | 8 | 2023 | 111 | 8 | off court |  |  | 2023 | 142 | 8 | 2023 | 142 | 8 |  |  |  | 32
0
RIVERA ELI | 2023 | 141 | 8 | 2023 | 141 | 8 | 2023 | 141 | 8 | 2023 | 141 | 8 | 2023 | 141 | 8 | loan?? |  |  | 40
[16 empty] | 1000 |  |  | 0
ROSS KELLI | 2023 | 151 | 8 | 2023 | 151 | 8 | 2023 | 151 | 8 | 2023 | 151 | 8 | off |  |  |  | 100 A WEEK |  | 32
[13 empty] | Lori sick | [5 empty] | 0
PALMA VIDES HUGO | 2023 | 141 | 8 | 2023 | 141 | 8 | 2023 | 141 | 8 | 2023 | 141 | 8 | 2023 | 141 | 8 |  |  |  | 40
0
WAITES THADDEUS | 2023 | 120 | 6 | 2023 | 120 | 4 | 2023 | 120 | 6 | 2023 | 120 | 7 | 2023 | 151 | 8 |  |  |  | 31
| 2023 | 151 | 2 | 2023 | 151 | 4 | 2023 | 151 | 2 | 2023 | 151 | 1 | [6 empty] | 9
WENNING JOHN | off |  |  | 2023 | 151 | 8 | 2023 | 151 | 8 | 2023 | 151 | 8 | 2023 | 151 | 8 |  |  |  | 32
0
WILSON GARRETT | 2023 | 151 | 8 | 2023 | 151 | 8 | 2023 | 151 | 8 | 2023 | 151 | 8 | 2023 | 151 | 8 |  |  |  | 40
0
KINSSIES JJ | 2023 | 151 | 8 | 2023 | 130 | 8 | 2023 | 151 | 2 | 2023 | 120 | 8 | 2023 | 151 | 2 |  |  |  | 28
[7 empty] | 2023 | 130 | 6 |  |  |  | 2023 | 120 | 6 |  |  |  | 12

## 5-25
2014-PIKE MOTORWORKS | 2024-MERRILL GARDENS |  |  | 2028-RESERVE LYNNWOOD |  |  | 050-CLOSED JOBS |  |  | LABOR CODES | [5 empty] | 141- MAIN / INSULATION
2019-8REP | 2025-CORA |  |  | 2029-PARSONAGE | [5 empty] | 110- UNDERGROUND |  |  | 120-ROUGH IN |  |  | 142- MECH ROOM
2021-ADMIRAL | 2026-525 BOREN |  |  | 2030-EAST UNION |  |  | CONFIRM HOURS |  |  | 111-GARAGE |  |  | 130- FINISH |  |  | 143- CONDENSATION
2023-LEGACY | 2027-550 BROADWAY | [5 empty] | EVERYDAY |  |  | 112-CANOUT |  |  | 140-GAS |  |  | 151-T&M
LEGACY
| 2016-05-19 |  |  | 2016-05-20 |  |  | 2016-05-23 |  |  | 2016-05-24 |  |  | 2016-05-25 |  |  | 2016-05-21
NAME | THURSDAY |  |  | FRIDAY |  |  | MONDAY |  |  | TUESDAY |  |  | WEDNESDAY |  |  | WEEKEND |  | TOTAL
0
BARNHART JOE | 2023 | 120 | 6 | pto |  | 8 | 2027 | 110 | 8 | 2027 | 112 | 2 | 2027 | 110 | 7 |  |  | 31
| 2023 | 151 | 2 | [6 empty] | 2027 | 110 | 6 | 2027 | 112 | 1 |  |  | 9
0
BALDERAS RICARDO | 2023 | 151 | 8 | 2023 | 151 | 8 | 2023 | 151 | 8 | 2023 | 151 | 8 | 2023 | 151 | 8 |  |  | 40
0
BROWN STEVEN | pto |  | 8 | 2023 | 151 | 8 | 1002 | 180 | 8 | 1002 | 180 | 8 | 1002 | 180 | 8 |  |  | 40
|  | OFF | [15 empty] | 0
ESPARZA JOSE | 2023 | 151 | 8 | 2023 | 151 | 8 | 2023 | 151 | 8 | off |  | 0 | 2023 | 151 | 8 |  |  | 32
[10 empty] | sick | [7 empty] | 0
GARCIA JORDAN | 2023 | 140 | 8 | 2023 | 151 | 8 | 2023 | 151 | 8 | 2023 | 140 | 8 | off |  | 0 | pto | 8 | 40
[14 empty] | day in jail |  |  |  | 0
GARDNER ANDREW | 2023 | 120 | 6 | 2023 | 151 | 8 | off |  |  | 2023 | 151 | 8 | 2023 | 151 | 8 |  |  | 30
| 2023 | 151 | 2 | [14 empty] | 2
McCABE TOM | 2023 | 140 | 8 | 2023 | 151 | 8 | 2023 | 151 | 8 | 2023 | 140 | 8 | 2023 | 142 | 7 |  |  | 39
[14 empty] | LEFT EARLY |  |  |  | 0
MENDOZA JESUS | 1001 | 180 | 8 | 1001 | 180 | 8 | 2023 | 151 | 8 | OFF |  | 0 | 2023 | 151 | 8 |  |  | 32
0
RIVERA ELI | 2023 | 141 | 8 | 2023 | 151 | 8 | 2023 | 141 | 8 | 2023 | 141 | 8 | 2023 | 141 | 8 |  |  | 40
0
ROSS KELLI | off |  | 0 | off |  |  | off |  |  | off |  |  | off |  |  |  |  | 0
[8 empty] | PERSONAL | [9 empty] | 0
PALMA VIDES HUGO | 2023 | 141 | 8 | 2023 | 151 | 8 | 2023 | 141 | 8 | 2023 | 141 | 8 | 2023 | 141 | 5 |  |  | 37
[14 empty] | LEFT EARLY |  |  |  | 0
WAITES THADDEUS | 2023 | 120 | 6 | 2023 | 120 | 5 | 2023 | 120 | 6 | 2023 | 120 | 6 | 2023 | 120 | 6 |  |  | 29
| 2023 | 151 | 2 | 2023 | 151 | 3 | 2023 | 151 | 2 | 2023 | 151 | 2 | 2023 | 151 | 2.5 |  |  | 11.5
WENNING JOHN | 2023 | 151 | 8 | off |  |  | 2023 | 151 | 8 | 2023 | 151 | 8 | 2023 | 151 | 8 |  |  | 32
0
WILSON GARRETT | 2023 | 151 | 8 | 2023 | 151 | 8 | 2027 | 110 | 8 | 2027 | 110 | 8 | 2027 | 110 | 8 |  |  | 40
0
KINSSIES JJ | 2023 | 120 | 3 | 2023 | 151 | 8 | off |  |  | off |  |  | 2023 | 120 | 8 |  |  | 19
| court | [16 empty] | 0

## 6-1
2014-PIKE MOTORWORKS | 2024-MERRILL GARDENS |  |  | 2028-RESERVE LYNNWOOD |  |  | 050-CLOSED JOBS |  | LABOR CODES | [5 empty] | 141- MAIN / INSULATION
2019-8REP | 2025-CORA |  |  | 2029-PARSONAGE |  |  |  |  | 110- UNDERGROUND |  |  | 120-ROUGH IN |  |  | 142- MECH ROOM
2021-ADMIRAL | 2026-525 BOREN |  |  | 2030-EAST UNION |  |  | CONFIRM HOURS |  | 111-GARAGE |  |  | 130- FINISH |  |  | 143- CONDENSATION
2023-LEGACY | 2027-550 BROADWAY | [5 empty] | EVERYDAY |  | 112-CANOUT |  |  | 140-GAS |  |  | 151-T&M
LEGACY
| 2016-05-26 |  |  | 2016-05-27 |  |  | 2016-05-30 |  | 2016-05-31 |  |  | 2016-06-01 |  |  | 2016-05-28
NAME | THURSDAY |  |  | FRIDAY |  |  | MONDAY |  | TUESDAY |  |  | WEDNESDAY |  |  | WEEKEND | TOTAL
0
BARNHART JOE | 2023 | 142 | 6 | 2027 | 110 | 2 | holiday | 8 | 2027 | 110 | 8 | 2023 | 111 | 5 |  | 29
| 2023 | 151 | 2 | 2014 | 141 | 2 | [5 empty] | 2023 | 151 | 2 |  | 6
|  |  |  | 2023 | 120 | 4 | [5 empty] | 2027 | 110 | 1 |  | 5
BALDERAS RICARDO | 2023 | 151 | 8 | 2023 | 151 | 8 | holiday | 8 | 2023 | 151 | 8 | 2023 | 151 | 8 |  | 40
0
ESPARZA JOSE | 2023 | 151 | 8 | 2023 | 151 | 8 | holiday | 8 | 2023 | 151 | 8 | 2023 | 151 | 8 |  | 40
0
GARCIA JORDAN | 2023 | 140 | 8 | 2023 | 140 | 8 | holiday | 8 | 2023 | 140 | 8 | 2023 | 140 | 8 |  | 40
0
GARDNER ANDREW | 2023 | 151 | 8 | off |  | 0 | holiday | 8 | 2023 | 151 | 8 | 2023 | 151 | 8 |  | 32
0
McCABE TOM | 2023 | 140 | 8 | 2023 | 140 | 8 | holiday | 8 | 2023 | 140 | 8 | 2023 | 140 | 8 |  | 40
0
MENDOZA JESUS | 2023 | 151 | 8 | 2023 | 151 | 8 | holiday | 8 | 2023 | 151 | 8 | 2023 | 151 | 8 |  | 40
0
RIVERA ELI | 2023 | 120 | 8 | 2023 | 120 | 8 | holiday | 8 | 2023 | 141 | 8 | 2023 | 141 | 8 |  | 40
0
ROSS KELLI | off |  | 0 | 2023 | 120 | 8 | holiday | 8 | 2023 | 140 | 8 | 2023 | 140 | 8 |  | 32
0
PALMA VIDES HUGO | 2023 | 141 | 8 | 2023 | 141 | 8 | holiday | 8 | 2023 | 141 | 8 | 2023 | 141 | 8 |  | 40
0
WAITES THADDEUS | 2023 | 120 | 6 | 2023 | 120 | 5 | holiday | 8 | 2023 | 120 | 6 | 2023 | 120 | 6 |  | 31
| 2023 | 151 | 2 | 2023 | 151 | 3 |  |  | 2023 | 151 | 2 | 2023 | 151 | 2 |  | 9
WENNING JOHN | off |  |  | off |  |  | holiday | 8 | 2023 | 151 | 8 | 2023 | 151 | 8 |  | 24
0
WILSON GARRETT | 2023 | 111 | 8 | pto |  | 8 | holiday | 8 | 2027 | 110 | 8 | 2023 | 120 | 8 |  | 40
0

## 6-8
2014-PIKE MOTORWORKS | 2024-MERRILL GARDENS |  |  | 2028-RESERVE LYNNWOOD |  |  | 050-CLOSED JOBS |  |  | LABOR CODES | [5 empty] | 141- MAIN / INSULATION
2019-8REP | 2025-CORA |  |  | 2029-PARSONAGE | [5 empty] | 110- UNDERGROUND |  |  | 120-ROUGH IN |  |  | 142- MECH ROOM
2021-ADMIRAL | 2026-525 BOREN |  |  | 2030-EAST UNION |  |  | CONFIRM HOURS |  |  | 111-GARAGE |  |  | 130- FINISH |  |  | 143- CONDENSATION
2023-LEGACY | 2027-550 BROADWAY | [5 empty] | EVERYDAY |  |  | 112-CANOUT |  |  | 140-GAS |  |  | 151-T&M
LEGACY
| 2016-06-02 |  |  | 2016-06-03 |  |  | 2016-06-06 |  |  | 2016-06-07 |  |  | 2016-06-08 |  |  | 2016-06-04
NAME | THURSDAY |  |  | FRIDAY |  |  | MONDAY |  |  | TUESDAY |  |  | WEDNESDAY |  |  | WEEKEND |  | TOTAL
0
BARNHART JOE | 2023 | 120 | 6 | 2027 | 110 | 2 | 2027 | 110 | 1 | 2023 | 120 | 2 | 2023 | 130 | 4 |  |  | 15
| 2023 | 151 | 2 | 2023 | 142 | 5 | 2023 | 142 | 3 |  | 111 | 2 |  | 120 | 2 |  |  | 14
|  |  |  | 2023 | 151 | 1 | 2023 | 151 | 4 |  | 140 | 2 |  | 140 | 2 |  |  | 9
[11 empty] | 130 | 2 | [5 empty] | 2
BALDERAS RICARDO | 2023 | 151 | 8 | 2023 | 151 | 8 | 2023 | 120 | 8 | 2023 | 120 | 8 | 2023 | 120 | 8 |  |  | 40
0
ESPARZA JOSE | 2023 | 151 | 8 | 2023 | 151 | 8 | 2023 | 151 | 4 | 2023 | 120 | 8 | 2023 | 120 | 8 |  |  | 36
[7 empty] | 2023 | 120 | 4 | [8 empty] | 4
GARCIA JORDAN | 2023 | 140 | 8 | 2023 | 140 | 8 | off |  |  | 2023 | 140 | 8 | 2023 | 140 | 8 |  |  | 32
0
GARDNER ANDREW | 2023 | 151 | 8 | off |  |  | off |  |  | 2023 | 130 | 8 | 2023 | 120 | 4 |  |  | 20
[13 empty] | 2023 | 151 | 4 |  |  | 4
McCABE TOM | 2023 | 140 | 8 | 2023 | 140 | 8 | call in 😵 |  |  | 2023 | 140 | 8 | 2023 | 140 | 8 |  |  | 32
0
MENDOZA JESUS | 2023 | 151 | 8 | 2023 | 151 | 8 | 2023 | 120 | 8 | 2023 | 141 | 8 | 2023 | 120 | 8 |  |  | 40
0
RIVERA ELI | 2023 | 141 | 8 | 2023 | 141 | 8 | 2023 | 120 | 8 | 2023 | 141 | 7.5 | 2023 | 141 | 8 |  |  | 39.5
[11 empty] | left early | [6 empty] | 0
PALMA VIDES JORGE | 1002 | 180 | 8 | 1002 | 180 | 8 | 2023 | 141 | 8 | 2023 | 141 | 7.5 | 2023 | 141 | 8 |  |  | 39.5
[11 empty] | left early | [6 empty] | 0
PALMA VIDES HUGO | 2023 | 141 | 8 | 2023 | 141 | 8 | 2023 | 141 | 8 | 2023 | 141 | 7.5 | 2023 | 141 | 8 |  |  | 39.5
[11 empty] | left early | [6 empty] | 0
WAITES THADDEUS | 2023 | 120 | 6 | 2023 | 151 | 8 | 2023 | 140 | 4 | 2023 | 120 | 8 | 2023 | 120 | 7 |  |  | 33
| 2023 | 151 | 2 |  |  |  | 2023 | 151 | 4 |  |  |  | 2023 | 151 | 1 |  |  | 7
WENNING JOHN | 2023 | 120 | 8 | off |  |  | 2023 | 140 | 8 | 2023 | 120 | 8 | 2023 | 120 | 8 |  |  | 32
0
WILSON GARRETT | 2027 | 112 | 5.5 | off |  |  | 2023 | 140 | 8 | 2023 | 120 | 8 | 2023 | 120 | 8 |  | CASH OUT PTO | 29.5
|  | LEFT EARLY |  | personal | [13 empty] | 0
0

## 6-15
2014-PIKE MOTORWORKS | 2024-MERRILL GARDENS |  |  | 2028-RESERVE LYNNWOOD | 050-CLOSED JOBS | LABOR CODES |  | 141- MAIN / INSULATION
2019-8REP | 2025-CORA |  |  | 2029-PARSONAGE |  | 110- UNDERGROUND | 120-ROUGH IN | 142- MECH ROOM
2021-ADMIRAL | 2026-525 BOREN |  |  | 2030-EAST UNION | CONFIRM HOURS | 111-GARAGE | 130- FINISH | 143- CONDENSATION
2023-LEGACY | 2027-550 BROADWAY |  |  |  | EVERYDAY | 112-CANOUT | 140-GAS | 151-T&M
LEGACY
| 2016-06-09 |  |  | 2016-06-10 | 2016-06-13 | 2016-06-14 | 2016-06-15 | 2016-06-11
NAME | THURSDAY |  |  | FRIDAY | MONDAY | TUESDAY | WEDNESDAY | WEEKEND | TOTAL
0
BARNHART JOE | [8 empty] | 0
[5 empty] | TIMECARD NOT FILLED OUT AT THIS TIME, BUT THE FOLLOWING IS WHAT WAS SPENT ON T&M ISSUE: |  |  |  | 0
0
0
BALDERAS RICARDO | [8 empty] | 0
0
ESPARZA JOSE | [8 empty] | 0
0
GARCIA JORDAN | [8 empty] | 0
0
GARDNER ANDREW | 2023 | 151 | 4 | [5 empty] | 4
0
McCABE TOM | [8 empty] | 0
0
MENDOZA JESUS | [8 empty] | 0
0
RIVERA ELI | [8 empty] | 0
0
PALMA VIDES JORGE | [8 empty] | 0
0
PALMA VIDES HUGO | [8 empty] | 0
0
WAITES THADDEUS | 2023 | 151 | 1 | [5 empty] | 1
0
WENNING JOHN | [8 empty] | 0
0
WILSON GARRETT | [8 empty] | 0
0
0

## RD 4-6
| 2014-PIKE MOTORWORKS | 2023-LEGACY |  |  | 2027-550 BROADWAY | [8 empty] | LABOR CODES
| 2019-8REP | 2024-MERRILL GARDENS |  |  | 2028-RESERVE LYNNWOOD |  |  | 100 - SUPERVISION |  |  | 110- UNDERGROUND |  |  | 120-ROUGH IN |  |  | 141- MAIN / INSULATION
| 2020-BMV | 2025-HARRISON |  |  | 2029-PARSONAGE |  |  | 101 - TAKEOFF & PURCHASE |  |  | 111-GARAGE |  |  | 130- FINISH |  |  | 142- MECH ROOM
| 2021-ADMIRAL | 2026-BOREN |  |  | 050-CLOSED JOBS |  |  | 151 - T&M |  |  | 112-CANOUT |  |  | 140-GAS |  |  | 143- CONDENSATION
RICHARD
|  | 2016-03-31 |  |  | 2016-04-01 |  |  | 2016-04-04 |  |  | 2016-04-05 |  |  | 2016-04-06 |  |  | 2016-04-02
|  | THURSDAY |  |  | FRIDAY |  |  | MONDAY |  |  | TUESDAY |  |  | WEDNESDAY |  |  | WEEKEND |  |  | TOTAL
31
| NAME | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS
0
0
0
0
1 | DONELSON RICHARD | 050 | 800 |  | 050 | 800 |  | 050 | 800 | 1 | 050 | 800 | 2 | 050 | 800 | 1 |  |  |  | 4
|  | 2023 | 101 | 1 | whistler |  |  | 2021 | 101 | 2 | 2027 | 101 | 1 | 2027 | 101 | 2 |  |  |  | 6
|  | 2025 | 101 | 1 |  |  |  | 2023 | 101 | 1 | 2023 | 151 | 2 | 2028 | 100 | 3 |  |  |  | 7
|  | 2021 | 101 | 1 |  |  |  | 2027 | 101 | 2 | 2028 | 101 | 1 | 2027 | 100 | 2 |  |  |  | 6
| OWP: 2027; C#: 101; HRS: 2; OWP: 2025; C#: 101; HRS: 1; OWP: 2014; C#: 101; HRS: 2 | 5
| OWP: 2014; C#: 101; HRS: 1; OWP: 2024; C#: 101; HRS: 1 | 2
| OWP: 2024; C#: 100; HRS: 1 | 1
| OWP: left early | 0
0
0
0
0
0
0
0
0
0
0

## RD 4-13
| 2014-PIKE MOTORWORKS | 2023-LEGACY |  |  | 2027-550 BROADWAY | [8 empty] | LABOR CODES
| 2019-8REP | 2024-MERRILL GARDENS |  |  | 2028-RESERVE LYNNWOOD |  |  | 100 - SUPERVISION |  |  | 110- UNDERGROUND |  |  | 120-ROUGH IN |  |  | 141- MAIN / INSULATION
| 2020-BMV | 2025-HARRISON |  |  | 2029-PARSONAGE |  |  | 101 - TAKEOFF & PURCHASE |  |  | 111-GARAGE |  |  | 130- FINISH |  |  | 142- MECH ROOM
| 2021-ADMIRAL | 2026-BOREN |  |  | 050-CLOSED JOBS |  |  | 151 - T&M |  |  | 112-CANOUT |  |  | 140-GAS |  |  | 143- CONDENSATION
RICHARD
|  | 2016-04-07 |  |  | 2016-04-08 |  |  | 2016-04-11 |  |  | 2016-04-12 |  |  | 2016-04-13 |  |  | 2016-04-09
|  | THURSDAY |  |  | FRIDAY |  |  | MONDAY |  |  | TUESDAY |  |  | WEDNESDAY |  |  | WEEKEND |  |  | TOTAL
36
| NAME | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS
0
0
0
0
1 | DONELSON RICHARD | 050 | 800 |  | 050 | 800 | 3 | 050 | 800 | 4 | 050 | 800 |  | 050 | 800 | 4 |  |  |  | 11
|  | 2028 | 101 | 2 | 2026 | 101 | 3 | 2027 | 101 | 1 | 2023 | 101 | 1 | 2027 | 101 | 2 |  |  |  | 9
|  | 2023 | 151 | 1 | 2023 | 151 | 1 | 2026 | 101 | 1 | 2023 | 151 | 3 | 2014 | 101 | 1 |  |  |  | 7
|  | 2027 | 101 | 1 | 2027 | 101 | 1 | 2025 | 101 | 2 | 2021 | 100 | 2 | 2028 | 101 | 1 |  |  |  | 7
| OWP: golf w/ exxel; OWP: 2021; C#: 101; HRS: 1 | 1
| OWP: 2027; C#: 101; HRS: 1 | 1
0
0
0
0
0
0
0
0
0
0
0
0

## RD 4-20
| 2014-PIKE MOTORWORKS | 2023-LEGACY |  |  | 2027-550 BROADWAY | [8 empty] | LABOR CODES
| 2019-8REP | 2024-MERRILL GARDENS |  |  | 2028-RESERVE LYNNWOOD |  |  | 100 - SUPERVISION |  |  | 110- UNDERGROUND |  |  | 120-ROUGH IN |  |  | 141- MAIN / INSULATION
| 2020-BMV | 2025-HARRISON |  |  | 2029-PARSONAGE |  |  | 101 - TAKEOFF & PURCHASE |  |  | 111-GARAGE |  |  | 130- FINISH |  |  | 142- MECH ROOM
| 2021-ADMIRAL | 2026-BOREN |  |  | 050-CLOSED JOBS |  |  | 151 - T&M |  |  | 112-CANOUT |  |  | 140-GAS |  |  | 143- CONDENSATION
RICHARD
|  | 2016-04-14 |  |  | 2016-04-15 |  |  | 2016-04-18 |  |  | 2016-04-19 |  |  | 2016-04-20 |  |  | 2016-04-16
|  | THURSDAY |  |  | FRIDAY |  |  | MONDAY |  |  | TUESDAY |  |  | WEDNESDAY |  |  | WEEKEND |  |  | TOTAL
39
| NAME | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS
0
0
0
0
1 | DONELSON RICHARD | 050 | 800 | 2 | 050 | 800 | 1 | 050 | 800 | 2 | 050 | 800 | 1 | 050 | 800 | 2 |  |  |  | 8
|  | 2028 | 101 | 2 | 2028 | 101 | 2 | 2027 | 101 | 3 | 2028 | 101 | 1 | 2024 | 101 | 3 |  |  |  | 11
|  | 2026 | 101 | 1 | 2027 | 101 | 1 | 2028 | 101 | 1 | 2023 | 151 | 2 | 2023 | 101 | 1 |  |  |  | 6
|  | 2027 | 101 | 2 | 2023 | 151 | 1 | 2023 | 101 | 1 | 2026 | 100 | 1 | 2021 | 101 | 1 |  |  |  | 5
|  | 2024 | 101 | 1 | 2028 | 100 | 3 | 2025 | 101 | 1 | 2025 | 100 | 1 | 2028 | 101 | 1 |  |  |  | 7
| OWP: 2024; C#: 100; HRS: 2 | 2
0
0
0
0
0
0
0
0
0
0
0
0

## RD 5-18
| 2014-PIKE MOTORWORKS | 2023-LEGACY |  |  | 2027-550 BROADWAY | [8 empty] | LABOR CODES
| 2019-8REP | 2024-MERRILL GARDENS |  |  | 2028-RESERVE LYNNWOOD |  |  | 100 - SUPERVISION |  |  | 110- UNDERGROUND |  |  | 120-ROUGH IN |  |  | 141- MAIN / INSULATION
| 2020-BMV | 2025-HARRISON |  |  | 2029-PARSONAGE |  |  | 101 - TAKEOFF & PURCHASE |  |  | 111-GARAGE |  |  | 130- FINISH |  |  | 142- MECH ROOM
| 2021-ADMIRAL | 2026-BOREN |  |  | 050-CLOSED JOBS |  |  | 151 - T&M |  |  | 112-CANOUT |  |  | 140-GAS |  |  | 143- CONDENSATION
RICHARD
|  | 2016-05-12 |  |  | 2016-05-13 |  |  | 2016-05-16 |  |  | 2016-05-17 |  |  | 2016-05-18 |  |  | 2016-05-14
|  | THURSDAY |  |  | FRIDAY |  |  | MONDAY |  |  | TUESDAY |  |  | WEDNESDAY |  |  | WEEKEND |  |  | TOTAL
40
| NAME | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS
0
0
0
0
1 | DONELSON RICHARD | 050 | 800 | 3 | 050 | 800 | 6 | 050 | 800 | 3 | 050 | 800 | 4 | 050 | 800 | 3 |  |  |  | 19
|  | 2021 | 101 | 1 | 2023 | 151 | 2 | 2027 | 101 | 3 | 2026 | 101 | 2 | 2027 | 101 | 1 |  |  |  | 9
|  | 2028 | 101 | 2 |  |  |  | 2023 | 101 | 1 | 2023 | 151 | 2 | 2026 | 101 | 1 |  |  |  | 6
| OWP: 2027; C#: 101; HRS: 2; OWP: 2026; C#: 101; HRS: 1; OWP: 2023; C#: 100; HRS: 1 | 4
| OWP: 2027; C#: 100; HRS: 1 | 1
| OWP: 2019; C#: 100; HRS: 1 | 1
0
0
0
0
0
0
0
0
0
0
0
0

## RD 5-25
| 2014-PIKE MOTORWORKS | 2023-LEGACY |  |  | 2027-550 BROADWAY | [8 empty] | LABOR CODES
| 2019-8REP | 2024-MERRILL GARDENS |  |  | 2028-RESERVE LYNNWOOD |  |  | 100 - SUPERVISION |  |  | 110- UNDERGROUND |  |  | 120-ROUGH IN |  |  | 141- MAIN / INSULATION
| 2020-BMV | 2025-HARRISON |  |  | 2029-PARSONAGE |  |  | 101 - TAKEOFF & PURCHASE |  |  | 111-GARAGE |  |  | 130- FINISH |  |  | 142- MECH ROOM
| 2021-ADMIRAL | 2026-BOREN |  |  | 050-CLOSED JOBS |  |  | 151 - T&M |  |  | 112-CANOUT |  |  | 140-GAS |  |  | 143- CONDENSATION
RICHARD
|  | 2016-05-19 |  |  | 2016-05-20 |  |  | 2016-05-23 |  |  | 2016-05-24 |  |  | 2016-05-25 |  |  | 2016-05-21
|  | THURSDAY |  |  | FRIDAY |  |  | MONDAY |  |  | TUESDAY |  |  | WEDNESDAY |  |  | WEEKEND |  |  | TOTAL
31
| NAME | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS
0
0
0
0
1 | DONELSON RICHARD | 050 | 800 | 5 | 050 | 800 | 3 | 050 | 800 |  | 050 | 800 | 3 | 050 | 800 | 2 |  |  |  | 13
|  | 2025 | 101 | 2 | 2023 | 101 | 2 | LA wedding |  |  | 2019 | 101 | 1 | 2024 | 101 | 1 |  |  |  | 6
|  | 2025 | 100 | 1 | 2027 | 101 | 1 |  |  |  | 2025 | 101 | 1 | 2021 | 101 | 1 |  |  |  | 4
| OWP: left early; OWP: 2026; C#: 101; HRS: 2; OWP: 2023; C#: 101; HRS: 1 | 4
| OWP: 2023; C#: 151; HRS: 1; OWP: 2025; C#: 101; HRS: 1 | 2
| OWP: 2026; C#: 101; HRS: 2 | 2
0
0
0
0
0
0
0
0
0
0
0
0

## RD 6-15
| 2014-PIKE MOTORWORKS | 2023-LEGACY |  |  | 2027-550 BROADWAY | [8 empty] | LABOR CODES
| 2019-8REP | 2024-MERRILL GARDENS |  |  | 2028-RESERVE LYNNWOOD |  |  | 100 - SUPERVISION |  |  | 110- UNDERGROUND |  |  | 120-ROUGH IN |  |  | 141- MAIN / INSULATION
| 2020-BMV | 2025-HARRISON |  |  | 2029-PARSONAGE |  |  | 101 - TAKEOFF & PURCHASE |  |  | 111-GARAGE |  |  | 130- FINISH |  |  | 142- MECH ROOM
| 2021-ADMIRAL | 2026-BOREN |  |  | 050-CLOSED JOBS |  |  | 151 - T&M |  |  | 112-CANOUT |  |  | 140-GAS |  |  | 143- CONDENSATION
RICHARD
|  | 2016-06-09 |  |  | 2016-06-10 |  |  | 2016-06-13 |  |  | 2016-06-14 |  |  | 2016-06-15 |  |  | 2016-06-11
|  | THURSDAY |  |  | FRIDAY |  |  | MONDAY |  |  | TUESDAY |  |  | WEDNESDAY |  |  | WEEKEND |  |  | TOTAL
41
| NAME | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS
0
0
0
0
1 | DONELSON RICHARD | 050 | 800 | 6 | 050 | 800 | 5 | 050 | 800 | 6 | 050 | 800 | 2 | 050 | 800 | 4 |  |  |  | 23
|  | 2019 | 101 | 1 | 2023 | 151 | 3 | 2028 | 101 | 1 | 2024 | 101 | 1 | 2023 | 151 | 2 |  |  |  | 8
|  | 2024 | 101 | 1 |  |  |  | 2021 | 101 | 1 | 2023 | 101 | 1 | 2023 | 100 | 2 |  |  |  | 5
| OWP: 2023; C#: 100; HRS: 3 | 4
| OWP: 2019; C#: 101; HRS: 1 | 1
0
0
0
0
0
0
0
0
0
0
0
0
0

## JG 4-20
| 2014-PIKE MOTORWORKS | 2021-ADMIRAL |  |  | 050-CLOSED JOBS | [5 empty] | LABOR CODES
| 2015-ROOSTER | 2022-INTERLAKE | [5 empty] | 110- UNDERGROUND |  |  | 120-ROUGH IN |  |  | 141- MAIN / INSULATION
| 2019-8REP | 2023-LEGACY | [5 empty] | 111-GARAGE |  |  | 130- FINISH |  |  | 142- MECH ROOM
| 2020-BMV | 2024-MERRILL GARDENS | [5 empty] | 112-CANOUT |  |  | 140-GAS |  |  | 143- CONDENSATION |  |  | 151 - T&M
GERARD
|  | 2016-04-14 |  |  | 2016-04-15 |  |  | 2016-04-18 |  |  | 2016-04-19 |  |  | 2016-04-20 |  |  | 2016-04-16
|  | THURSDAY |  |  | FRIDAY |  |  | MONDAY |  |  | TUESDAY |  |  | WEDNESDAY |  |  | WEEKEND |  |  | TOTAL
| NAME | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS
0
0
0
0
1 | GERARD JEFF | 2028 | 101 | 2 | 2025 | 101 | 1 | 2027 | 101 | 2 | 2026 | 101 | 1 | 2028 | 101 | 2 |  |  |  | 8
|  | 2027 | 101 | 1 | 2026 | 101 | 1 | 2028 | 101 | 2 | 2028 | 101 | 2 | 2025 | 101 | 1 |  |  |  | 7
|  | 2026 | 101 | 1 | 2027 | 101 | 2 | 2025 | 101 | 2 | 2027 | 101 | 1 | 2026 | 101 | 1 |  |  |  | 7
|  | 2024 | 100 | 1 | 2028 | 101 | 2 | 2028 | 100 | 2 | 2023 | 151 | 2 | 2027 | 101 | 2 |  |  |  | 9
|  | 2028 | 112 | 3 | 2028 | 112 | 2 |  |  |  | 2028 | 100 | 2 | 2024 | 100 | 2 |  |  |  | 9
0
0
0
2 | HUBBARD DUSTIN | SHOP | 606 | 5 |  | OFF |  | SHOP | 606 | 8 | SHOP | 606 | 8 | SHOP | 606 | 8 |  |  |  | 29
| THURSDAY OWP: 2021; THURSDAY C#: 120; THURSDAY HRS: 1 | 1
| THURSDAY OWP: 2024; THURSDAY C#: 140; THURSDAY HRS: 1 | 1
| THURSDAY OWP: 2027; THURSDAY C#: 110; THURSDAY HRS: 1 | 1
0
0
0
0
0
0

## JG 5-18
| 2014-PIKE MOTORWORKS | 2021-ADMIRAL |  |  | 050-CLOSED JOBS | [5 empty] | LABOR CODES
| 2015-ROOSTER | 2022-INTERLAKE | [5 empty] | 110- UNDERGROUND |  |  | 120-ROUGH IN |  |  | 141- MAIN / INSULATION
| 2019-8REP | 2023-LEGACY | [5 empty] | 111-GARAGE |  |  | 130- FINISH |  |  | 142- MECH ROOM
| 2020-BMV | 2024-MERRILL GARDENS | [5 empty] | 112-CANOUT |  |  | 140-GAS |  |  | 143- CONDENSATION |  |  | 151 - T&M
GERARD
|  | 2016-05-12 |  |  | 2016-05-13 |  |  | 2016-05-16 |  |  | 2016-05-17 |  |  | 2016-05-18 |  |  | 2016-05-14
|  | THURSDAY |  |  | FRIDAY |  |  | MONDAY |  |  | TUESDAY |  |  | WEDNESDAY |  |  | WEEKEND |  |  | TOTAL
| NAME | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS
0
0
0
0
1 | GERARD JEFF | 2028 | 101 | 2 | O50 | 800 | 4 | 2026 | 101 | 2 | O50 | 800 | 1 | O50 | 800 | 2 |  |  |  | 11
|  | 2027 | 101 | 2 | 2021 | 100 | 1 | 2027 | 101 | 1 | 2026 | 101 | 1 | 2027 | 101 | 1 |  |  |  | 6
|  | 2026 | 101 | 1 | 2024 | 100 | 1 | 2028 | 101 | 1 | 2023 | 151 | 1 | 2025 | 101 | 1 |  |  |  | 5
|  | 2024 | 100 | 2 | 2028 | 100 | 1 | 2025 | 101 | 1 | 2027 | 101 | 1 | 2026 | 101 | 1 |  |  |  | 6
|  | 2021 | 100 | 1 | 2023 | 100 | 1 | 2024 | 100 | 1.5 | 2026 | 100 | 2 | 2023 | 100 | 1.5 |  |  |  | 7
| MONDAY OWP: 2028; MONDAY C#: 100; MONDAY HRS: 1.5; TUESDAY OWP: 2027; TUESDAY C#: 100; TUESDAY HRS: 1; WEDNESDAY OWP: 2024; WEDNESDAY C#: 100; WEDNESDAY HRS: 1.5 | 4
| TUESDAY OWP: 2025; TUESDAY C#: 100; TUESDAY HRS: 1 | 1
0
2 | HUBBARD DUSTIN |  | OFF |  |  | OFF |  | 2023 | 120 | 1 | SHOP | 606 | 8 | SHOP | 606 | 4 |  |  |  | 13
| MONDAY OWP: 2028; MONDAY C#: 110; MONDAY HRS: 1; WEDNESDAY OWP: 2021; WEDNESDAY C#: 130; WEDNESDAY HRS: 1.5 | 2.5
| MONDAY OWP: SHOP; MONDAY C#: 606; MONDAY HRS: 6; WEDNESDAY OWP: 2024; WEDNESDAY C#: 130; WEDNESDAY HRS: 1.5 | 7.5
| WEDNESDAY OWP: 2027; WEDNESDAY C#: 142; WEDNESDAY HRS: 1 | 1
0
0
0
0
0
0

## JG 5-25
| 2014-PIKE MOTORWORKS | 2021-ADMIRAL |  |  | 050-CLOSED JOBS | [5 empty] | LABOR CODES
| 2015-ROOSTER | 2022-INTERLAKE | [5 empty] | 110- UNDERGROUND |  |  | 120-ROUGH IN |  |  | 141- MAIN / INSULATION
| 2019-8REP | 2023-LEGACY | [5 empty] | 111-GARAGE |  |  | 130- FINISH |  |  | 142- MECH ROOM
| 2020-BMV | 2024-MERRILL GARDENS | [5 empty] | 112-CANOUT |  |  | 140-GAS |  |  | 143- CONDENSATION |  |  | 151 - T&M
GERARD
|  | 2016-05-19 |  |  | 2016-05-20 |  |  | 2016-05-23 |  |  | 2016-05-24 |  |  | 2016-05-25 |  |  | 2016-05-21
|  | THURSDAY |  |  | FRIDAY |  |  | MONDAY |  |  | TUESDAY |  |  | WEDNESDAY |  |  | WEEKEND |  |  | TOTAL
| NAME | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS
0
0
0
0
1 | GERARD JEFF | O50 | 800 | 2 | O50 | 800 | 2 | O50 | 800 | 2 | 2027 | 101 | 1 | 2026 | 101 | 1 |  |  |  | 8
|  | 2021 | 101 | 1 | 2027 | 101 | 2 | 2026 | 101 | 1 | 2025 | 101 | 1 | 2027 | 101 | 1 |  |  |  | 6
|  | 2023 | 151 | 1 | 2025 | 101 | 1 | 2025 | 101 | 1 | 2026 | 101 | 1 | 2025 | 101 | 1 |  |  |  | 5
|  | 2024 | 101 | 1 | 2026 | 101 | 1 | 2027 | 101 | 1 | 2026 | 100 | 1 | 2028 | 101 | 1 |  |  |  | 5
|  | 2028 | 101 | 1 | 2021 | 100 | 1 | 2025 | 100 | 1 | 2027 | 100 | 2 | 2025 | 100 | 2 |  |  |  | 7
|  | 2024 | 100 | 1 | 2028 | 100 | 1 | 2026 | 100 | 1 | 2028 | 100 | 2 | 2028 | 100 | 2 |  |  |  | 7
| THURSDAY OWP: 2028; THURSDAY C#: 100; THURSDAY HRS: 1; MONDAY OWP: 2028; MONDAY C#: 100; MONDAY HRS: 1 | 2
0
2 | HUBBARD DUSTIN |  | OFF |  |  | OFF |  | SHOP | 606 | 5 | SHOP | 606 | 8 | SHOP | 606 | 8 |  |  |  | 21
| MONDAY OWP: 2024; MONDAY C#: 143; MONDAY HRS: 1 | 1
| MONDAY OWP: 2027; MONDAY C#: 110; MONDAY HRS: 1 | 1
| MONDAY OWP: 2021; MONDAY C#: 141; MONDAY HRS: 1 | 1
0
0
0
0
0
0

## JG 6-1
| 2014-PIKE MOTORWORKS | 2021-ADMIRAL |  |  | 050-CLOSED JOBS | [5 empty] | LABOR CODES
| 2015-ROOSTER | 2022-INTERLAKE | [5 empty] | 110- UNDERGROUND |  |  | 120-ROUGH IN |  |  | 141- MAIN / INSULATION
| 2019-8REP | 2023-LEGACY | [5 empty] | 111-GARAGE |  |  | 130- FINISH |  |  | 142- MECH ROOM
| 2020-BMV | 2024-MERRILL GARDENS | [5 empty] | 112-CANOUT |  |  | 140-GAS |  |  | 143- CONDENSATION |  |  | 151 - T&M
GERARD
|  | 2016-05-26 |  |  | 2016-05-27 |  |  | 2016-05-30 |  |  | 2016-05-31 |  |  | 2016-06-01 |  |  | 2016-05-28
|  | THURSDAY |  |  | FRIDAY |  |  | MONDAY |  |  | TUESDAY |  |  | WEDNESDAY |  |  | WEEKEND |  |  | TOTAL
| NAME | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS
0
0
0
0
1 | GERARD JEFF | O50 | 800 | 1 | 2025 | 101 | 2 |  |  | 8 | 2026 | 101 | 1 | O50 | 800 | 3 |  |  |  | 15
|  | 2023 | 151 | 1 | 2026 | 101 | 1 |  |  |  | 2025 | 101 | 3 | 2027 | 101 | 1 |  |  |  | 6
|  | 2026 | 101 | 1 | 2027 | 101 | 1 |  |  |  | 2028 | 101 | 1 | 2025 | 101 | 1 |  |  |  | 4
|  | 2027 | 101 | 1 | 2028 | 101 | 1 |  |  |  | 2023 | 151 | 1 | 2026 | 101 | 1 |  |  |  | 4
|  | 2025 | 100 | 1 | 2026 | 100 | 1 |  |  |  | 2021 | 100 | 1 | 2026 | 100 | 1 |  |  |  | 4
|  | 2026 | 100 | 2 | 2028 | 100 | 2 |  |  |  | 2028 | 100 | 1 | 2028 | 100 | 1 |  |  |  | 6
| THURSDAY OWP: 2028; THURSDAY C#: 100; THURSDAY HRS: 1 | 1
0
2 | NAME: HUBBARD DUSTIN; THURSDAY C#: OFF; FRIDAY C#: OFF; MONDAY HRS: 8; TUESDAY OWP: 2021; TUESDAY C#: 120; TUESDAY HRS: 1; WEDNESDAY OWP: SHOP; WEDNESDAY C#: 606; WEDNESDAY HRS: 8 | 17
| TUESDAY OWP: 2023; TUESDAY C#: 120; TUESDAY HRS: 1 | 1
| TUESDAY OWP: 2024; TUESDAY C#: 120; TUESDAY HRS: 1 | 1
| TUESDAY OWP: SHOP; TUESDAY C#: 606; TUESDAY HRS: 5 | 5
0
0
0
0
0
0

## BH 4-20
2014-PIKE MOTORWORKS | 2024-MERRILL GARDENS |  |  | 2028-RESERVE LYNNWOOD |  |  | 050-CLOSED JOBS |  |  | LABOR CODES | [5 empty] | 141- MAIN / INSULATION
2019-8REP | 2025-CORA |  |  | 2029-PARSONAGE | [5 empty] | 110- UNDERGROUND |  |  | 120-ROUGH IN |  |  | 142- MECH ROOM
2021-ADMIRAL | 2026-525 BOREN |  |  | 2030-EAST UNION |  |  | CONFIRM HOURS |  |  | 111-GARAGE |  |  | 130- FINISH |  |  | 143- CONDENSATION
2023-LEGACY | 2027-550 BROADWAY |  |  | 2031-GATEWAY |  |  | EVERYDAY |  |  | 112-CANOUT |  |  | 140-GAS |  |  | 151 - T&M
HUBBARD
| 2016-04-14 |  |  | 2016-04-15 |  |  | 2016-04-18 |  |  | 2016-04-19 |  |  | 2016-04-20 |  |  | 2016-04-16
| THURSDAY |  |  | FRIDAY |  |  | MONDAY |  |  | TUESDAY |  |  | WEDNESDAY |  |  | WEEKEND |  |  | TOTAL
NAME | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS
0
HUBBARD BOB | 2021 | 142 | 2 | 2021 | 141 | 5 | 2021 | 142 | 2 | 2021 | 141 | 1 | 2028 | 112 | 4 |  |  |  | 14
| 2021 | 141 | 2 | 2025 | 112 | 3 | 2021 | 141 | 2 | 2021 | 142 | 2 | 2021 | 111 | 2 |  |  |  | 11
| 2024 | 111 | 4 |  |  |  | 2028 | 112 | 4 | 2021 | 111 | 1 | 2023 | 151 | 2 |  |  |  | 11
TUESDAY OWP: 2024; TUESDAY C#: 111; TUESDAY HRS: 2 | 2
TUESDAY OWP: 2028; TUESDAY C#: 112; TUESDAY HRS: 2 | 2
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## BH 4-27
2014-PIKE MOTORWORKS | 2024-MERRILL GARDENS |  |  | 2028-RESERVE LYNNWOOD |  |  | 050-CLOSED JOBS |  |  | LABOR CODES | [5 empty] | 141- MAIN / INSULATION
2019-8REP | 2025-CORA |  |  | 2029-PARSONAGE | [5 empty] | 110- UNDERGROUND |  |  | 120-ROUGH IN |  |  | 142- MECH ROOM
2021-ADMIRAL | 2026-525 BOREN |  |  | 2030-EAST UNION |  |  | CONFIRM HOURS |  |  | 111-GARAGE |  |  | 130- FINISH |  |  | 143- CONDENSATION
2023-LEGACY | 2027-550 BROADWAY |  |  | 2031-GATEWAY |  |  | EVERYDAY |  |  | 112-CANOUT |  |  | 140-GAS |  |  | 151 - T&M
HUBBARD
| 2016-04-21 |  |  | 2016-04-22 |  |  | 2016-04-25 |  |  | 2016-04-26 |  |  | 2016-04-27 |  |  | 2016-04-23
| THURSDAY |  |  | FRIDAY |  |  | MONDAY |  |  | TUESDAY |  |  | WEDNESDAY |  |  | WEEKEND |  |  | TOTAL
NAME | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS
0
HUBBARD BOB | 2021 | 111 | 2 | 2021 | 111 | 4 | 2028 | 112 | 2 | 2021 | 142 | 4 | 2021 | 142 | 2 |  |  |  | 14
| 2021 | 142 | 2 | 2024 | 111 | 2 | 2021 | 142 | 2 | 2021 | 111 | 4 | 2021 | 111 | 2 |  |  |  | 12
| 2028 | 112 | 3 | 2023 | 151 | 2 | 2021 | 111 | 1 |  |  |  | 2024 | 111 | 2 |  |  |  | 8
THURSDAY OWP: 2024; THURSDAY C#: 111; THURSDAY HRS: 1; MONDAY OWP: 2024; MONDAY C#: 111; MONDAY HRS: 3; WEDNESDAY OWP: 2028; WEDNESDAY C#: 112; WEDNESDAY HRS: 2 | 6
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## BH 6-1
2014-PIKE MOTORWORKS | 2024-MERRILL GARDENS |  |  | 2028-RESERVE LYNNWOOD |  |  | 050-CLOSED JOBS |  |  | LABOR CODES | [5 empty] | 141- MAIN / INSULATION
2019-8REP | 2025-CORA |  |  | 2029-PARSONAGE | [5 empty] | 110- UNDERGROUND |  |  | 120-ROUGH IN |  |  | 142- MECH ROOM
2021-ADMIRAL | 2026-525 BOREN |  |  | 2030-EAST UNION |  |  | CONFIRM HOURS |  |  | 111-GARAGE |  |  | 130- FINISH |  |  | 143- CONDENSATION
2023-LEGACY | 2027-550 BROADWAY | [5 empty] | EVERYDAY |  |  | 112-CANOUT |  |  | 140-GAS |  |  | 151 - T&M
HUBBARD
| 2016-05-26 |  |  | 2016-05-27 |  |  | 2016-05-30 |  |  | 2016-05-31 |  |  | 2016-06-01 |  |  | 2016-05-28
| THURSDAY |  |  | FRIDAY |  |  | MONDAY |  |  | TUESDAY |  |  | WEDNESDAY |  |  | WEEKEND |  |  | TOTAL
NAME | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS | OWP | C# | HRS
0
HUBBARD BOB | 2021 | 111 | 3 | 2021 | 111 | 6 | holiday |  | 8 | 2021 | 111 | 6 | 2024 | 111 | 8 |  |  |  | 31
THURSDAY OWP: 2021; THURSDAY C#: 140; THURSDAY HRS: 1; FRIDAY OWP: 2021; FRIDAY C#: 143; FRIDAY HRS: 1; TUESDAY OWP: 2024; TUESDAY C#: 111; TUESDAY HRS: 2 | 4
THURSDAY OWP: 2021; THURSDAY C#: 142; THURSDAY HRS: 3; FRIDAY OWP: 2028; FRIDAY C#: 111; FRIDAY HRS: 1 | 4
THURSDAY OWP: 2023; THURSDAY C#: 151; THURSDAY HRS: 1 | 1
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0