## COR
[7 empty] | PROJECT: | 2023 LEGACY APARTMENTS
[7 empty] | DATE: | 2016-05-13
[7 empty] | RFI/ASI: | ASI-024 SHOWER CHANGE
DESCRIPTION OF CHANGE/WORK PERFORMED
|  | Labor |  |  |  | Material/Equipment |  |  | Material | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
THROUGH 5/13/16
| RICHARD DONELSON - PROJECT MANAGER | 12 | HRS | 95 | 1140
| JEFF GERARD - PROJECT MANAGER | 2 | HRS | 95 | 190
| BOB HUBBARD - SUPERINTENDENT | 4 | HRS | 85 | 340
| JOE BARNHART - FOREMAN | 30 | HRS | 80 | 2400
| THADDEUS WAITES - FOREMAN | 60 | HRS | 80 | 4800
| KELLI ROSS - JOURNEYMAN | 76 | HRS | 75 | 5700
| JOSE ESPARZA - APPRENTICE | 64 | HRS | 46 | 2944
| GARRET WILSON - APPRENTICE | 50 | HRS | 46 | 2300
| JOHN WENNIG - APPRENTICE | 34 | HRS | 46 | 1564
| RICARDO BALDARES - APPRENTICE | 16 | HRS | 46 | 736
| STEVEN BROWN - APPRENTICE | 2 | HRS | 46 | 92
| MITCH GERARD - APPRENTICE | 8 | HRS | 46 | 368
| ELI RIVERA - APPRENTICE | 20 | HRS | 46 | 920
| JJ KINNSIES - APPRENTICE | 16 | HRS | 46 | 736
| JORDAN GARCIA - APPRENTICE | 14 | HRS | 46 | 644
| ANDREW GARDNER - APPRENTICE | 1 | HRS | 46 | 46
| SCAN-2-CORE 4/19 | [8 empty] | LS | 675
| SCAN-2-CORE 4/20 | [8 empty] | LS | 825
| SCISSOR LIFT FOR THE MONTH OF MAY | [8 empty] | LS | 568.15
PVC MATERIALS:
TUB VENT STACK AND REVENTS MATERIAL X 12:
| 2X1-1/2 TEE |  |  |  |  | 36 | EA | 1.38 | 49.68
| 1-1/2 90 |  |  |  |  | 36 | EA | 0.66 | 23.76
| 2X1-1/2 BUSH |  |  |  |  | 36 | EA | 0.56 | 20.16
| 1-1/2 45 ST |  |  |  |  | 36 | EA | 0.63 | 22.68
| 1-1/2 45 REG |  |  |  |  | 36 | EA | 0.71 | 25.56
| 2 COUPLING |  |  |  |  | 24 | EA | 0.46 | 11.04
| 2 45 ST |  |  |  |  | 36 | EA | 0.94 | 33.84
| 2 45 REG |  |  |  |  | 36 | EA | 0.9 | 32.4
| 2 90 REG |  |  |  |  | 24 | EA | 0.99 | 23.76
| TEST TEE |  |  |  |  | 12 | EA | 6.92 | 83.04
| 2 PIPE |  |  |  |  | 600 | LF | 0.61 | 366
| 1-1/2 PIPE |  |  |  |  | 240 | LF | 0.5 | 120
AW VENT STACK AND REVENT AND MISC X 1:
| 2 PIPE |  |  |  |  | 35 | LF | 0.61 | 21.35
| 1-1/2 PIPE |  |  |  |  | 15 | LF | 0.5 | 7.5
| 2 45 ST |  |  |  |  | 4 | EA | 0.94 | 3.76
| 2 45 REG |  |  |  |  | 4 | EA | 0.9 | 3.6
| 2X1-1/2 TEE |  |  |  |  | 3 | EA | 1.38 | 4.14
| 1-1/2 90 |  |  |  |  | 3 | EA | 0.66 | 1.98
| 2 COUPLING |  |  |  |  | 3 | EA | 0.46 | 1.38
| TEST TEE |  |  |  |  | 2 | EA | 6.92 | 13.84
| 2X1-1/2 TEE |  |  |  |  | 4 | EA | 1.38 | 5.52
| 1-1/2 90 |  |  |  |  | 4 | EA | 0.66 | 2.64
| 2 45 ST |  |  |  |  | 6 | EA | 0.94 | 5.64
| 2 45 REG |  |  |  |  | 2 | EA | 0.9 | 1.8
| 2X1-1/2X2 TEE |  |  |  |  | 4 | EA | 1.65 | 6.6
| 2 PTRAP |  |  |  |  | 4 | EA | 2.75 | 11
| 2 COUPLING |  |  |  |  | 6 | EA | 0.46 | 2.76
| 2 90 REG |  |  |  |  | 2 | EA | 0.99 | 1.98
| 2 TEST TEE |  |  |  |  | 1 | EA | 6.92 | 6.92
| 2 PIPE |  |  |  |  | 50 | LF | 0.61 | 30.5
| 1-1/2 PIPE |  |  |  |  | 20 | LF | 0.5 | 10
| ANCHORS, HANGERS, SUPPORTS, GLUE, ACOUSTICAL TAPE, P-TAPE, MISCELLANEOUS |  |  |  |  | 1 | LS | 350 | 350
CAST IRON MATERIALS:
| 2" CAST IRON |  |  |  |  | 60 | LF | 4.55 | 273
| NO-HUB BANDS |  |  |  |  | 25 | EA | 1.35 | 33.75
ALL FITTINGS WERE ABLE TO BE RE-USED
PEX MATERIALS:
| 1/2" PEX RING |  |  |  |  | 192 | EA | 0.15 | 28.8
| 1/2" PEX COUPLING |  |  |  |  | 96 | EA | 0.75 | 72
| 1/2" PEX PIPE |  |  |  |  | 100 | LF | 0.38 | 38
| Subtotals |  |  |  | 24920 |  |  |  | 1750.38 | 0 | 2068.15
| OH & Profit |  |  | 10% | 2492 |  |  | 10% | 175.038 | 10% | 206.815
| Totals |  |  |  | 27412 |  |  |  | 1925.418 |  | 2274.965
Total this page
31612.383
COSTS FOR ASI-024 SHOWER CHANGE, FROM INCEPTION THROUGH END OF BUSINESS 05/13/16