## CGC BP
[7 empty] | PROJECT: | 2023 LEGACY APARTMENTS
[7 empty] | DATE: | 2015-06-23
[7 empty] | RFI/ASI: | asi-03
DESCRIPTION OF CHANGE/WORK PERFORMED
|  | Labor |  |  |  | Material/Equipment |  |  | Material | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
MOVE HUB DRAIN AT ELEVATOR MACHINE ROOM
| LAYOUT/COORDINATE WITH CORE DRILLER | 2 | HRS | 80 | 160
| FILL UNUSED CORE HOLE | 2 | HRS | 75 | 150
| IMAGING | [8 empty] | LS | 500
| CORE DRILLING | [8 empty] | LS | 150
| FRANKLIN ENGINEERING - MAKE REVISIONS TO PRINTS (2HRS @ $95/HR) | [8 empty] | LS | 190
| Subtotals |  |  |  | 310 |  |  |  | 0 | 0 | 840
| OH & Profit |  |  | 10% | 31 |  |  | 10% | 0 | 10% | 84
| Totals |  |  |  | 341 |  |  |  | 0 |  | 924
Total this page
1265
MOVE HUB DRAIN AT ELEVATOR MACHINE ROOM PER ASI-03. ALSO INCLUDES MODIFICATIONS TO PLANS