## CGC BP
[7 empty] | PROJECT: | 2023 LEGACY APARTMENTS
[7 empty] | DATE: | 2015-03-24
RFI/ASI:
DESCRIPTION OF CHANGE/WORK PERFORMED
|  | Labor |  |  |  | Material/Equipment |  |  | Material | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
ADD DRAIN IN PSE TRANSFORMER AREA, ADD OIL/WATER SEPARATOR
| LAYOUT/COORDINATE WITH EXCAVATOR | 4 | HRS | 80 | 320
| INSTALL 577 OWS | 24 | HRS | 60.5 | 1452 | 1 | EA | 2463 | 2463
| EJ 00371082 - 4/24 RING AND COVER DRAIN | 2 | HRS | 60.5 | 121 | 1 | EA | 285 | 285
| EJ 00366103 - 4/12 RING AND COVER DRAIN | 2 | HRS | 60.5 | 121 | 2 | EA | 102 | 204
| KOR-N-SEAL BOOTS | 1 | HRS | 60.5 | 60.5 | 2 | LS | 60 | 120
| 4" PIPING | 2 | HRS | 60.5 | 121 | 20 | LF | 2.05 | 41
| DRAIN - CB-40 | 2 | HRS | 60.5 | 121 | 1 | EA | 305 | 305
| FITTINGS | 1 | HRS | 60.5 | 60.5 | 1 | LOT | 151 | 53
| AS BUILTING | 1 | HRS | 80 | 80
| Subtotals |  |  |  | 2457 |  |  |  | 3471 | 0 | 0
| OH & Profit |  |  | 10% | 245.7 |  |  | 10% | 347.1 | 10% | 0
| Totals |  |  |  | 2702.7 |  |  |  | 3818.1 |  | 0
Total this page
6520.8
ADD A DRAIN AT THE PSE VAULT AND ADD AN OIL/WATER SEPARATOR FOR IT.