## CGC BP
[7 empty] | PROJECT: | 2023 LEGACY APARTMENTS
[7 empty] | DATE: | 2015-02-23
RFI/ASI:
DESCRIPTION OF CHANGE/WORK PERFORMED
|  | Labor |  |  |  | Material/Equipment |  |  | Material | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
ADD DRAIN IN PSE VAULT
| LAYOUT/COORDINATE WITH EXCAVATOR | 1 | HRS | 80 | 80
| 4" PIPING | 3 | HRS | 60.5 | 181.5 | 30 | LF | 2.05 | 61.5
| DRAIN | 1 | HRS | 60.5 | 60.5 | 1 | EA | 125 | 125
| FITTINGS/SUPPORTS | 1 | HRS | 60.5 | 60.5 | 1 | LOT | 51 | 53
| AS BUILTING | 1 | HRS | 80 | 80
| Subtotals |  |  |  | 462.5 |  |  |  | 239.5 | 0 | 0
| OH & Profit |  |  | 10% | 46.25 |  |  | 10% | 23.95 | 10% | 0
| Totals |  |  |  | 508.75 |  |  |  | 263.45 |  | 0
Total this page
772.2
ADD A DRAIN AT THE PSE VAULT.