## CGC BP
[7 empty] | PROJECT: | 2023 LEGACY APARTMENTS
[7 empty] | DATE: | 2016-03-10
RFI/ASI:
DESCRIPTION OF CHANGE/WORK PERFORMED
|  | Labor |  |  |  | Material/Equipment |  |  | Material | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
HORIZONTAL
| REMOVAL | 2 | HRS | 75 | 150
| RE-LAYOUT | 2 | HRS | 75 | 150
| REINSTALL | 7 | HRS | 75 | 525
| 3" PIPE |  |  |  |  | 40 | LF | 6 | 240
| 3" FITTINGS |  |  |  |  | 12 | EA | 12 | 144
| 2" PIPE |  |  |  |  | 50 | LF | 4.25 | 212.5
| 2" FITTINGS |  |  |  |  | 12 | EA | 7 | 84
| HANGERS/ALL THREAD |  |  |  |  | 1 | LOT | 35 | 35
| SUPERVISION | 3 | HRS | 80 | 240
| Subtotals |  |  |  | 1065 |  |  |  | 715.5 | 0 | 0
| OH & Profit |  |  | 10% | 106.5 |  |  | 10% | 71.55 | 10% | 0
| Totals |  |  |  | 1171.5 |  |  |  | 787.05 |  | 0
Total this page
1958.55
|  | Labor |  |  |  | Material/Equipment |  |  | Material | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
VERTICAL
| REMOVAL | 1 | HRS | 75 | 75
| REINSTALL | 4 | HRS | 75 | 300
| 3" PIPE |  |  |  |  | 40 | LF | 6 | 240
| 3" FITTINGS |  |  |  |  | 7 | EA | 12 | 84
| 4" PIPE |  |  |  |  | 20 | LF | 7.75 | 155
| 4" FITTINGS |  |  |  |  | 6 | EA | 16 | 96
| HANGERS/ALL THREAD |  |  |  |  | 1 | LOT | 10 | 10
| SUPERVISION | 2 | HRS | 80 | 160
| Subtotals |  |  |  | 535 |  |  |  | 585 | 0 | 0
| OH & Profit |  |  | 10% | 53.5 |  |  | 10% | 58.5 | 10% | 0
| Totals |  |  |  | 588.5 |  |  |  | 643.5 |  | 0
Total this page
1232
COST TO CHANGE FROM PVC TO CAST IRON IN MEDIA ROOM