## CGC BP
[7 empty] | PROJECT: | 2023 LEGACY APARTMENTS
[7 empty] | DATE: | 2015-03-24
RFI/ASI:
DESCRIPTION OF CHANGE/WORK PERFORMED
|  | Labor |  |  |  | Material/Equipment |  |  | Material | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
INSTALL 2" PIPING UNDERGROUND DUE TO GAS METER LOCATION CHANGE
| LAYOUT/COORDINATE WITH EXCAVATOR | 2 | HRS | 80 | 160
| CORE DRILL | 2 | HRS | 80 | 160 |  |  |  |  | LS | 350
| 2" GAS PIPING & FITTINGS | 8 | HRS | 60.5 | 484 | 1 | LS | 429 | 429
| 4" PVC SLEEVING & FITTINGS | 8 | HRS | 60.5 | 484 | 1 | LS | 501 | 501
| SUPERVISION | 4 | HRS | 80 | 320
| CAD / AS BUILTING | 1 | HRS | 80 | 80
| Subtotals |  |  |  | 1688 |  |  |  | 930 |  | 350
| OH & Profit |  |  | 10% | 168.8 |  |  | 10% | 93 | 10% | 35
| Totals |  |  |  | 1856.8 |  |  |  | 1023 |  | 385
Total this page
3264.8
|  | Labor |  |  |  | Material/Equipment |  |  | Material | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
INSTALL ADDED SLEEVE FROM NE CORNER OF LOADING DOCK TO GAS METER ALCOVE
| LAYOUT/COORDINATE WITH EXCAVATOR | 1 | HRS | 80 | 80
| 4" SLEEVING & FITTINGS | 4 | HRS | 60.5 | 242 | 1 | LS | 100 | 100
| SUPERVISION | 1 | HRS | 80 | 80
| CAD / AS BUILTING | 1 | HRS | 80 | 80
| Subtotals |  |  |  | 482 |  |  |  | 100 |  | 0
| OH & Profit |  |  | 10% | 48.2 |  |  | 10% | 10 | 10% | 0
| Totals |  |  |  | 530.2 |  |  |  | 110 |  | 0
Total this page
640.2
|  | Labor |  |  |  | Material/Equipment |  |  | Material | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
INSTALL OVERHEAD GAS PIPING TO RETAIL AREAS - ONE MAINLINE
| ENGINEERING - BRETT MORTIMORE | 4 | HRS | 100 | 400
| CAD DETAILING - FRANKLIN ENGINEERING | [8 empty] | LS | 380
| LAYOUT | 8 | HRS | 80 | 640
| 2" GAS PIPING | 23 | HRS | 60.5 | 1391.5 | 117 | LF | 2.79 | 326.43
| 1-1/2" GAS PIPING | 23 | HRS | 60.5 | 1391.5 | 156 | LF | 2.06 | 321.36
| 1-1/4" GAS PIPING | 3 | HRS | 60.5 | 181.5 | 23 | LF | 1.29 | 29.67
| 1" GAS PIPING | 6 | HRS | 60.5 | 363 | 46 | LF | 0.85 | 39.1
| FITTINGS |  |  |  |  | 1 | LS | 395 | 395
| SUPERVISION | 4 | HRS | 80 | 320
| SHUTOFF VALVES | 6 | HRS | 60.5 | 363 | 6 | EA | 22.5 | 135
| PROSET PENETRATIONS | 0.5 | HRS | 60.5 | 30.25 | 1 | EA | 15 | 15
| SCISSOR LIFT | [8 empty] | LS | 350
| CAD / AS BUILTING | 3 | HRS | 80 | 240
| Subtotals |  |  |  | 5320.75 |  |  |  | 1261.56 |  | 730
| OH & Profit |  |  | 10% | 532.075 |  |  | 10% | 126.156 | 10% | 73
| Totals |  |  |  | 5852.825 |  |  |  | 1387.716 |  | 803
Total this page
8043.541
EXCLUDES: SUPPLY AN DINSTALL OF METERS, PRESSURE REGULATORS, FLEX CONNECTIONS, WATERPROOFING
|  | Labor |  |  |  | Material/Equipment |  |  | Material | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
INSTALL SEPARATE GAS CONNECTIONS FOR EACH RETAIL AREA
| LAYOUT/COORDINATE WITH EXCAVATOR | 3 | HRS | 80 | 240
| CORE DRILL | 4 | HRS | 80 | 320 |  |  |  |  | LS | 250
| 3/4" GAS PIPING & FITTINGS | 30 | HRS | 60.5 | 1815 | 1 | LS | 229 | 229
| 3" SLEEVING & FITTINGS | 24 | HRS | 60.5 | 1452 | 1 | LS | 201 | 201
| SUPERVISION | 8 | HRS | 80 | 640
| CAD / AS BUILTING | 3 | HRS | 80 | 240
| Subtotals |  |  |  | 4707 |  |  |  | 430 |  | 250
| OH & Profit |  |  | 10% | 470.7 |  |  | 10% | 43 | 10% | 25
| Totals |  |  |  | 5177.7 |  |  |  | 473 |  | 275
Total this page
5925.7
|  | Labor |  |  |  | Material/Equipment |  |  | Material | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
INSTALL OVERHEAD GAS PIPING TO RETAIL AREAS - SEPARATE MAINLINES
| ENGINEERING - BRETT MORTIMORE | 8 | HRS | 100 | 800
| CAD DETAILING - FRANKLIN ENGINEERING | [8 empty] | LS | 680
| LAYOUT | 24 | HRS | 80 | 1920
| 3/4" GAS PIPING | 225 | HRS | 60.5 | 13612.5 | 1500 | LF | 0.85 | 1275
| FITTINGS |  |  |  |  | 1 | LS | 395 | 395
| SUPERVISION | 24 | HRS | 80 | 1920
| SHUTOFF VALVES | 6 | HRS | 60.5 | 363 | 6 | EA | 22.5 | 135
| PROSET PENETRATIONS | 2 | HRS | 60.5 | 121 | 6 | EA | 15 | 90
| SCISSOR LIFT | [8 empty] | LS | 700
| CAD / AS BUILTING | 5 | HRS | 80 | 400
| Subtotals |  |  |  | 19136.5 |  |  |  | 1895 |  | 1380
| OH & Profit |  |  | 10% | 1913.65 |  |  | 10% | 189.5 | 10% | 138
| Totals |  |  |  | 21050.15 |  |  |  | 2084.5 |  | 1518
Total this page
24652.65
EXCLUDES: SUPPLY AN DINSTALL OF METERS, PRESSURE REGULATORS, FLEX CONNECTIONS, WATERPROOFING
GAS PIPING CHANGES