## CGC BP
[7 empty] | PROJECT: | 2023 LEGACY APARTMENTS
[7 empty] | DATE: | 2015-06-23
[7 empty] | RFI/ASI: | RFI-071 & 071.1
DESCRIPTION OF CHANGE/WORK PERFORMED
|  | Labor |  |  |  | Material/Equipment |  |  | Material | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
DRAIN
| LAYOUT/COORDINATE WITH CORE DRILLER | 3 | HRS | 80 | 240
| IMAGING | [8 empty] | LS | 500
| CORE DRILLING | [8 empty] | LS | 300
| WASTE PIPING | 5 | HRS | 75 | 375
| PIPE & FITTINGS |  |  |  |  | 1 | LS | 105 | 105
| INSTALL NEW DRAIN, GROUT IN PLACE | 4 | HRS | 75 | 300
| DRAIN |  |  |  |  | 1 | EA | 75 | 75
| Subtotals |  |  |  | 915 |  |  |  | 180 | 0 | 800
| OH & Profit |  |  | 0% | 0 |  |  | 0% | 0 | 0% | 0
| Totals |  |  |  | 915 |  |  |  | 180 |  | 800
Total this page
1895
|  | Labor |  |  |  | Material/Equipment |  |  | Material | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
HOSEBIB
| LAYOUT | 2 | HRS | 75 | 150
| WATER PIPING | 5 | HRS | 75 | 375
| PIPE & FITTINGS |  |  |  |  | 1 | LS | 165 | 165
| SYMMONS MIXING VALVE | 1 | HR | 75 | 75 | 1 | LS | 117.579 | 117.579
| WATER SHUTOFF VALVES | 1 | HR | 75 | 75 | 2 | EA | 12.5 | 25
| HOSEBIB | 1 | HR | 75 | 75 | 1 | EA | 65 | 65
| Subtotals |  |  |  | 750 |  |  |  | 372.579 | 0 | 0
| OH & Profit |  |  | 0% | 0 |  | 0 | 0% | 0 | 0% | 0
| Totals |  |  |  | 750 |  |  |  | 372.579 |  | 0
Total this page
1122.579
|  | Labor |  |  |  | Material/Equipment |  |  | Material | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
FILL UNUSED CORE HOLES
| FILL UNUSED CORE HOLES | 9 | HRS | 75 | 675
| BAGS OF GROUT |  |  |  |  | 3 | EA | 15 | 45
| Subtotals |  |  |  | 675 |  |  |  | 45 | 0 | 0
| OH & Profit |  |  | 0% | 0 |  |  | 0% | 0 | 0% | 0
| Totals |  |  |  | 675 |  |  |  | 45 |  | 0
Total this page
720
|  | Labor |  |  |  | Material/Equipment |  |  | Material | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
REDESIGN PLANS
| FRANKLIN ENGINEERING - MAKE REVISIONS TO PRINTS (5HRS @ $95/HR) | [8 empty] | LS | 475
| Subtotals |  |  |  | 0 |  |  |  | 0 | 0 | 475
| OH & Profit |  |  | 0% | 0 |  |  | 0% | 0 | 0% | 0
| Totals |  |  |  | 0 |  |  |  | 0 |  | 475
Total this page
475
4212.579
| 10% | 421.2579
4633.8369
RELOCATE PLUMBING LINES, INSTALL ADDED DRAIN AND HOSEBIB IN TRASH ROOM. ALSO INCLUDES MODIFICATIONS TO PLANS