## CGC BP
[7 empty] | PROJECT: | 2023 LEGACY APARTMENTS
[7 empty] | DATE: | 2015-12-30
[7 empty] | RFI/ASI: | RFI-125 ROM
DESCRIPTION OF CHANGE/WORK PERFORMED
|  | Labor |  |  |  | Material/Equipment |  |  | Material | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
| LAYOUT/COORDINATE WITH CORE DRILLER | 8 | HRS | 80 | 640
| PLUMBING REVISIONS, FRAMING CORRECTIONS DONE BY OWP, IMPACT TO PRODUCTIVITY | 80 | HRS | 75 | 6000
| PIPE/FITTINGS |  |  |  |  | 1 | LS | 750 | 750
| ADDED COST OF FIRE RATED BOXES |  |  |  |  | 20 | EA | 18 | 360
| IMAGING/CORE DRILLING | [8 empty] | LS | 2478
| SUPERVISION | 8 | HRS | 80 | 640
| AS-BUILTING | 3 | HRS | 80 | 240
| Subtotals |  |  |  | 7520 |  |  |  | 1110 | 0 | 2478
| OH & Profit |  |  | 10% | 752 |  |  | 10% | 111 | 10% | 247.8
| Totals |  |  |  | 8272 |  |  |  | 1221 |  | 2725.8
Total this page
12218.8
ROM COST FOR RFI-125