## CGC BP
[7 empty] | PROJECT: | 2023 LEGACY APARTMENTS
[7 empty] | DATE: | 2016-05-20
[7 empty] | RFI/ASI: | TRENCH DRAINS
DESCRIPTION OF CHANGE/WORK PERFORMED
|  | Labor |  |  |  | Material/Equipment |  |  | Material | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
| LAYOUT/COORDINATE WITH OTHER SUBS | 8 | HRS | 80 | 640
| SUBMITTALS/PRICING/ORDERING MATERIAL | 4 | HRS | 95 | 380
| CLIP EARS OFF SIDE OF TRENCH DRAIN (40LF/HR) | 4 | HRS | 60.5 | 242
| INSTALL TRENCH DRAIN BODY (4LF/HR) FINE GRADE W/ SHOVEL DRIVE STAKES AT ONE SIDE PIN OPPOSITE SIDE TO CONCRETE WALL ATTACH EACH TRENCH SECTION TO EACH OTHER SECURE WITH HARDWARE | 40 | HRS | 60.5 | 2420
| ZURN Z886-HPD TRENCH DRAIN |  |  |  |  | 160 | LF | 51.42 | 8227.2
| ZURN E1 CLOSED END CAP |  |  |  |  | 6 | EA | 14.72 | 88.32
| ZURN E2, 3, 4 NO-HUB END OUTLET |  |  |  |  | 6 | EA | 14.72 | 88.32
| ZURN U2, 3, 4 NO-HUB BOTTOM OUTLET |  |  |  |  | 6 | EA | 14.72 | 88.32
| ZURN DB BOTTOM DOME STRAINER |  |  |  |  | 3 | EA | 28.18 | 84.54
| ZURN JOINT CONNECTOR |  |  |  |  | 28 | EA | 28.18 | 789.04
| ZURN CUTTING CHARGE |  |  |  |  | 6 | EA | 32.15 | 192.9
| HARDWARE, MISCELLANEOUS |  |  |  |  | 1 | LS | 300 | 300
| WRAP/PROTECT TRENCH DRAIN FOR POUR | 8 | HRS | 60.5 | 484
| POUR WATCH | 4 | HRS | 60.5 | 242
| REMOVE PROTECTION, CLEAN CONCRETE | 8 | HRS | 60.5 | 484
| INSTALL TRENCH DRAIN COVERS (15LF/HR) | 10.6667 | HRS | 60.5 | 645.3333
| SUPERVISION | 12 | HRS | 80 | 960
| AS-BUILTING | 2 | HRS | 80 | 160
| Subtotals |  |  |  | 6657.3333 |  |  |  | 9858.64 | 0 | 0
| OH & Profit |  |  | 10% | 665.7333 |  |  | 10% | 985.864 | 10% | 0
| Totals |  |  |  | 7323.0667 |  |  |  | 10844.504 |  | 0
Total this page
18167.5707
|  | Labor |  |  |  | Material/Equipment |  |  | Material | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
| SLEEVE RETAINING WALLS | 8 | HRS | 60.5 | 484
| SLEEVING MATERIAL |  |  |  |  | 8 | EA | 20 | 160
| SUPERVISION | 3 | HRS | 80 | 240
| Subtotals |  |  |  | 724 |  |  |  | 160 | 0 | 0
| OH & Profit |  |  | 10% | 72.4 |  |  | 10% | 16 | 10% | 0
| Totals |  |  |  | 796.4 |  |  |  | 176 |  | 0
Total this page
972.4
|  | Labor |  |  |  | Material/Equipment |  |  | Material | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
| INSTALL PIPE DOWN AND THRU WALL | 24 | HRS | 60.5 | 1452
| 4" PIPE |  |  |  |  | 132 | LF | 1.93 | 254.76
| PIPE/FITTINGS/COUPLINGS/GLUE/ETC |  |  |  |  | 1 | LS | 450 | 450
| SUPERVISION | 4 | HRS | 80 | 320
| Subtotals |  |  |  | 1772 |  |  |  | 704.76 | 0 | 0
| OH & Profit |  |  | 10% | 177.2 |  |  | 10% | 70.476 | 10% | 0
| Totals |  |  |  | 1949.2 |  |  |  | 775.236 |  | 0
Total this page
2724.436
COST TO INSTALL TRENCH DRAINS AT EAST PLAZA