## CGC BP
[7 empty] | PROJECT: | 2023 LEGACY APARTMENTS
[7 empty] | DATE: | 2016-04-06
RFI/ASI:
DESCRIPTION OF CHANGE/WORK PERFORMED
|  | Labor |  |  |  | Material/Equipment |  |  | Material | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
UNIT WITHOUT SHOWER INSTALLED
| JOE BARNHART COORDINATION | 3 | HRS | 80 | 240
| DEMO PIPING | 2 | HRS | 60.5 | 121
| REINSTALL WATER & WASTE PIPING | 6 | HRS | 60.5 | 363
| TEST & INSPECT | 2 | HRS | 60.5 | 121
| PIPE & FITTINGS |  |  |  |  | 1 | LS | 200 | 200
| Subtotals |  |  |  | 845 |  |  |  | 200 | 0 | 0
| OH & Profit |  |  | 10% | 84.5 |  |  | 10% | 20 | 10% | 0
| Totals |  |  |  | 929.5 |  |  |  | 220 |  | 0
Total this page
1149.5
|  | Labor |  |  |  | Material/Equipment |  |  | Material | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
UNIT WITH SHOWER INSTALLED
| JOE BARNHART COORDINATION | 3 | HRS | 80 | 240
| REMOVE SHOWER | 2 | HRS | 60.5 | 121
| DEMO PIPING | 2 | HRS | 60.5 | 121
| REINSTALL WATER & WASTE PIPING | 6 | HRS | 60.5 | 363
| TEST & INSPECT | 2 | HRS | 60.5 | 121
| PIPE & FITTINGS |  |  |  |  | 1 | LS | 200 | 200
| REINSTALL SHOWER | 2 | HRS | 60.5 | 121
| MORTAR |  |  |  |  | 2 | BAG | 10 | 20
| Subtotals |  |  |  | 1087 |  |  |  | 220 | 0 | 0
| OH & Profit |  |  | 10% | 108.7 |  |  | 10% | 22 | 10% | 0
| Totals |  |  |  | 1195.7 |  |  |  | 242 |  | 0
Total this page
1437.7
|  | Labor |  |  |  | Material/Equipment |  |  | Material | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
UNIT WITH SHOWER INSTALLED
| JOE BARNHART COORDINATION | 2 | HRS | 80 | 160
| REMOVE SHOWER | 1 | HRS | 60.5 | 60.5
| DEMO PIPING | 1.5 | HRS | 60.5 | 90.75
| REINSTALL WATER & WASTE PIPING | 3 | HRS | 60.5 | 181.5
| TEST & INSPECT | 1 | HRS | 60.5 | 60.5
| PIPE & FITTINGS |  |  |  |  | 1 | LS | 200 | 200
| REINSTALL SHOWER | 1 | HRS | 60.5 | 60.5
| WATTS FD-15 DRAIN |  |  |  |  | 1 | EA | 85 | 85
| Subtotals |  |  |  | 613.75 |  |  |  | 285 | 0 | 0
| OH & Profit |  |  | 10% | 61.375 |  |  | 10% | 28.5 | 10% | 0
| Totals |  |  |  | 675.125 |  |  |  | 313.5 |  | 0
Total this page
988.625
SHOWER REMODEL