## Sheet1
Subject | Amount | Date Sent | Notes | CO Received | CO #
INSTALL CAST IRON WASTE STACKS IN LIEU OF PVC AT RESIDENTIAL LEVELS. VENT STACKS TO REMAIN PVC. | 121400 | CONTRACT |  | 2015-05-13 | 2
DELETE ICE MAKER BOXES | -32700 | CONTRACT |  | 2015-05-13 | 2
ADD PIPING FOR FUTURE GREASE TRAP | 2658 | 2015-03-12 |  | 2015-05-13 | 3
AQUATIC TUBS/SHOWERS | -17190 | 2015-07-27 |  | 2015-07-28 | 4
UNDERGROUND GAS PIPING | 4075 |  | WRONG AMOUNT ON CO. | 2015-09-11 | 5
GAS TO RETAIL AREAS | 9980 | 2015-06-15 |  | 2015-12-15 | 8
SUB SLAB DRAIN FILTRATION AND VENTILATION SYSTEMS | 26645 | 2015-02-05 |  | 2015-03-20 | 1
ADD DRAIN TO PSE VAULT | 702 | 2015-02-23 | CANCELLED BY GC
STUD SHOES | 46000 | 2015-03-10 | CANCELLED BY GC
ADD OIL WATER SEPARATOR FOR PSE VAULT | 6521 | 2015-03-24 | CANCELLED BY GC
ASI-03 ELEVATOR MACHINE ROOM RELOCATION | 1265 | 2015-06-23
RFI-071 & 071.1 RETAIL TRASH ROOM | 4634 | 2015-06-30
ADD ICEMAKERS BACK TO PROJECT | 32700 | 2015-12-16 |  | 2015-12-15 | 7
FUTURE GAS SLEEVE | 640 | 2015-12-15 |  | 2015-12-15 | 8

## Sheet2
Subject | Amount | Date Sent | Notes
Upgrade Fire Caulking | 1955 | 2015-01-07
RFI-314 Dog Turf Drains | 2873 | 2015-01-09
ASI-019 South Building | 11299 | 2015-01-16
Hose bibs for pet patches | 5106 | 2015-01-20
ASI-024.5 Gas Main Relocation | 1981 | 2015-02-23
ASI-024 Overtime - Joe Barnhart | 4232 | 2015-03-02
Credit for Sterling Tubs @ 206, 301, 305, 311, 317, 319, 320, 321 | -3795 | 2015-03-02
RFI-464 Wall Changes | 494 | 2015-03-06
Temp Gas Hookups | 1495 | 2015-03-16
Common Area Gas Range Credit | -363 | 2015-03-16
ASI-024 Overtime - Complete | 8920 | 2015-03-17
South Building Water Management | 1680 | 2015-03-17
Remove Pipe for Mason | 492 | 2015-03-18
North Building Shower Drains | 2022 | 2015-03-25
RFI-484 - Added Roof Drain S. Building | 1323 | 2015-03-30
J&S Masonry Backcharges | -624 | 2015-04-07
Change to Cast Iron Piping in LW4-6 | 3674 | 2015-05-04
RFI-482 - Raise Drains | 2130 | 2015-04-28
Gas Meter Vent Pipe - Proceed T&M per JC 4/18/15 | 276 | 2015-05-11
RFI-491 - Possibly need to lower water mains due to dropped soffits | 1060 | 2015-05-11
ASI-033 Demo & Remove Gas Piping | 474 | 2015-06-09
Move Icemakers at all South Building Refers | TBD |  | T&M - Waiting on notice to proceed from Exxel
Costs/Credits to delete RL01 & RL02 bathrooms | TBD |  | ROM pricing given. Waiting on decision from Exxel.