Change Order Request

June 30, 2015

Chinn Construction, LLC

14715 NE 95th Street, Suite 101

Redmond, WA 98052

Attn: 	Charlie Poggemann

Re:	Hadley Apartment Project – Change Order Request

Charlie,

RFI-071 & 071.1 deleted the storage room wall and added a drain and hot/cold hosebib in the new retail area trash room.  This change was issued after the L2 deck slab had already been placed.  Costs for each change are broken down below.

| - There are five existing sleeves next to the storage room walls that can no longer be used and will need to be filled with grout. |  | $720 |
| --- | --- | --- |
| - Provide imaging and core drilling of structural deck, installation of new floor drain and associated piping to nearest available garage drain waste line. |  | $1,895 |
| - Install hot/cold hosebib with shutoffs and mixing valve, as well as associated piping. Piping to be ran in stick-pin insulation to avoid heat trace. |  | $1,123 |
| - Engineering costs to redesign plumbing, including moving all plumbing lines to gridline 2, new drain and new hot/cold hosebib. |  | $475 |
| - OH&P @ 10% |  | $421 |
| - Total Change Order |  | $4,634 |

Please let me know if you have any questions or comments.  Thank you.

Sincerely,

Richard Donelson

Project Manager / Estimator

LEED® Green Associate

richd@owpllc.net

425-591-4296 cell