Change Order Request

December 30, 2015

Chinn Construction, LLC

14715 NE 95th Street, Suite 101

Redmond, WA 98052

Attn: 	Charlie Poggemann

Re:	Hadley Apartment Project – Change Order Request

Charlie,

RFI-125 revised the washer closet sizes/configurations/layout for several units, which created added work for OWP (see below).  Total cost for RFI-125 is $11,108 + 10% OH&P = $12,219.

Impacts and added work for OWP:

- Remove plumbing already installed on Level 2.  Re-layout, re-drill/anchor, and reinstall plumbing using new pipe and fittings.

- Field coordinate change with SRM and framer.

- After the re-framing was complete, cut out sill plates and move studs to layout for core driller.

- Imaging & core-drilling.

- There were five unit stacks (20 total units) where the washer boxes were relocated from an interior unit wall to the corridor wall, which required that the boxes were changed from non-rated washer boxes to more expensive fire-rated washer boxes.

- Field engineering costs to redesign plumbing.

- Field supervision to ensure plumbing revisions were installed correctly.

- As-builting.

- Impacts to productivity and efficiency.  Workers could not plumb the washer stacks as they were plumbing the kitchens/bathrooms, requiring them to go back after the unit was done to install the revised plumbing.

Please let me know if you have any questions or comments.  Thank you.

Sincerely,

Richard Donelson

Project Manager / Estimator

LEED® Green Associate

richd@owpllc.net

425-591-4296 cell