## README
OWP Productivity Metrics
Reverse-engineered from 65 historical jobs · for OWP bidding tool calibration
Purpose | This workbook turns 65 jobs of OWP project history into the productivity benchmarks needed by the bidding tool. Three primary signals drive the bid model: (1) labor hours per plumbing unit by phase, (2) crew size and composition vs. project duration, and (3) material variance — original takeoff budget vs. actual spend.
Source data | 66 project folders from cortex-mockup repo. 53 cortex-output JSONs (V1, V2.2, V_TX schemas) plus 17 supabase rolled-up JSONs (older jobs not in cortex output). Cross-referenced against OWP Project List with Schedule (UPDATED 04-01-26) for unit counts, GC, address, dates.
Schema mix | V1 schema: 18 jobs (cortex output, codes/workers dicts) · V2.2: 32 jobs (cost_code_summaries lists) · V_TX: 2 jobs (transactions/code_totals) · SUPABASE: 13 jobs (rolled-up benchmark format). Cortex preferred when both available; supabase fills gaps for jobs 2001, 2008–2019, 2021, 2022.
Live vs. completed | 14 jobs flagged is_live (jobs 2098, 2103–2107, 2111–2119) — partial data only. Excluded from benchmark medians where labor hours < 1,500 or duration < 2 months. They appear in Per-Job Rollup but are visually distinct (cream highlight) and capped from the Bid Calibration sheet.
Methodology — productivity rates | hours_per_unit = total_labor_hours / plumbing_units. Plumbing units come from the Schedule tab and are typically apartment/condo unit counts; for non-residential jobs the field is blank, so productivity-per-unit metrics are skipped on those rows. Phase hours/unit pulls labor-code phase mappings (100s codes → underground, rough-in, trim/finish, gas, etc.).
Methodology — material variance | material_orig_to_actual_pct = (actual − original_budget) / original_budget. NEGATIVE values mean OWP came in UNDER budget (conservative takeoff). Across the 52 completed jobs with both numbers, the median is roughly −25%, which is the strongest single signal for the bid model — OWP can sharpen takeoff or hold cushion as a deliberate margin contribution.
Methodology — crew composition | avg_crew_fte = total_hours / (duration_months × 173.33). top5_pct_of_hours flags supervisor or lead-tech concentration. blended_wage = labor_cost / total_hours; fully_loaded_wage adds burden_cost (cost code 995). burden_multiplier = loaded_wage / blended_wage.
Caveats | V_TX jobs (2111, 2112) have transactions but no cost_code_summaries → labor/material totals from transaction sums; phase splits inferred from code numbers. Some live jobs have only deposits/POs and very few hours — interpret cautiously. Material vendor data is missing on supabase rollups.
How to use | Per-Job Rollup is the master record. Productivity Rates, Crew Composition, Material Variance are pivot views of the rollup. Phase Splits show breakdown by construction phase. Bid Calibration gives you medians and quartiles to feed the bidding tool — read those numbers as the OWP house standard against which a new bid should be sense-checked.
Companion file | OWP_Productivity_Insights.json — narrative insights and headline numbers for the Cortex layer. That file is the structured version of "what should the bidding tool know" and is intended to flow into Cortex (cross-job intelligence) per the architecture decision.
Built | 2026-04-27 · 65 jobs

## Instructions
How to Use This Calibration File
Instructions for Claude (or any agent) when bidding a new OWP project
Purpose
This file is the productivity-calibration layer for the OWP bidding tool. It supplements Cortex's comparable-matching by providing cost-code-level historical data so the bid output reflects how OWP actually executes, not just how it estimates.
Division of responsibility
This file | Carries the productivity calibration data (per-code rates, variances, structural rules) and these instructions.
Cortex | Selects comparable past jobs by size, GC, project type, vintage. This file does NOT segment by cohort — Cortex does.
Estimator | Produces the takeoff (units, fixtures, code-level quantities). This file calibrates the takeoff.
Required inputs (the agent should request these before bidding)
plumbing_units | Drives per-unit rate calculations.
general_contractor | Optional but improves Cortex match quality.
project_type | Optional — e.g. 'apartment', 'mixed-use', 'senior'.
estimator_takeoff | Dict by cost code: the bid's draft line items.
comparable_job_ids | Provided by Cortex; the IDs whose history this file should pull from.
Workflow
STEP 1 | Comparable selection (Cortex)
Cortex returns N comparable past jobs by size, GC, project type, etc. Hand the list of job IDs forward.
STEP 2 | Retrieve per-code productivity from comparables
For each comparable job ID, pull its (job, code) rows from the Cost Code Detail table. Aggregate by code: median(hours_per_unit), median(actual_per_unit), median(variance_orig_to_actual). FALLBACK: if comparables have <5 jobs for a code, supplement with cost_code_benchmarks.by_code[code] (full-dataset).
STEP 3 | Compute calibrated rates
For each code in the takeoff: • expected_hours = units × median(hours_per_unit) • expected_dollars = units × median(actual_per_unit) • tuning_factor = 1 + median(variance_orig_to_actual) • calibrated_value = estimator_takeoff × tuning_factor
STEP 4 | Apply structural adjustments
These overrides apply on top of the rates from step 3. They encode known systematic errors: • Code 120 (Roughin Labor): +12% to hours takeoff (rule OWP-BID-007). Only major labor code that overruns. • Codes 210/211/212/220/230/240/241/242 (200-series material): choose cushion policy explicitly per OWP-BID-003. Tighten takeoff ~24%, OR hold as declared margin. Do not let cushion compound implicitly. • Code 600 (Subcontractor): flag but do not auto-correct (small dollars, takeoff convention issue).
STEP 5 | Price labor at fully-loaded wage
Apply rule OWP-BID-002. Default $40.23/hr (median); use current loaded wage if known. Burden multiplier 1.34× — never use blended wage alone.
STEP 6 | Macro sanity-check
Validate bid totals at the project level. Flag (do not auto-decide) when: • hours_per_unit outside 94–155 (P25–P75 band) • labor_pct_revenue far from benchmark median • gross_margin_pct below 33.9% (P25) — require sign-off • burden_multiplier outside 1.0–1.6× — review wage assumption
STEP 7 | Document the tuning
Bid output must include audit trail: • Comparable job IDs used (from Cortex) and selection rationale • Per line item: estimator_takeoff, calibrated_value, rate source (comparables vs full-dataset), n_jobs behind that rate • Any structural adjustments (cite rule_id) • Macro sanity-check results — pass/flag per metric • Any flags raised for human decision
Fallback rules (precedence: top to bottom)
1 | Comparables <5 for a code → use cost_code_benchmarks.by_code[code] full-dataset benchmark.
2 | Comparables = 0 or Cortex unavailable → use full-dataset benchmarks throughout; flag bid as 'uncalibrated to comparables'.
3 | Code n_jobs_with_data < 20 in full dataset → DO NOT apply variance correction; use estimator's takeoff verbatim; note 'low historical N'.
4 | Code missing from cost_code_benchmarks → use estimator's takeoff verbatim; flag as 'unknown code'.
5 | Live jobs (is_live=true) → DO NOT use as comparables. Partial data.
Quality thresholds (when to flag rather than auto-decide)
Single comparable | Do not auto-tune. Flag for analyst; present comparable data alongside full-dataset benchmark.
Wide variance band | If P75 − P25 > 30% for a code, present both endpoints; have user pick deliberately.
Out-of-range units | If plumbing_units outside historical 18–398, flag — extrapolation risk.
No GC match | Calibration is GC-agnostic; note this in output.
What this file does NOT provide
Not here | Comparable selection logic — that's Cortex's job.
Not here | Cohort-segmented benchmarks — Cortex computes these from per-job data on the fly.
Not here | Real-time wage/burden updates — defaults are historical medians; pass current values to override.
Not here | Subcontractor (code 600) pricing — flagged for human review.
Data freshness
As of | 2026-04-27
Jobs in calibration | 50 completed jobs (≥1,500 hrs) out of 65 total.
Live jobs excluded | 14 (partial data — present in long table but not in benchmark medians).
Refresh trigger | Re-extract when new completed jobs are added OR when variance medians shift >5 pp across the most recent 10 jobs.

## Per-Job Rollup
Job | Status | Schema | Project Name | GC | Units | Duration (mo) | First Inv | Last Inv | Contract Final | Revenue | Direct Cost | Net Profit | Gross Margin % | Labor Cost | Total Hours | Workers | Substantive Workers (≥80h) | Avg Crew FTE | Top-5 % of Hours | Avg Days/Worker | Blended Wage | Loaded Wage | Burden Mult | OT % | Material Cost | Vendors | Top Vendor | Top Vendor % | Hours/Unit | Labor/Unit | Material/Unit | Revenue/Unit | Labor % Rev | Material % Rev | Hours/Month | Units/Month | Labor Orig Bud | Labor Rev Bud | Labor Actual | Labor Var (orig→act) | Mat Orig Bud | Mat Rev Bud | Mat Actual | Mat Var (orig→act)
2001 | Done | SUPABASE | 230 Broadway | SRM | 234 | 18 |  |  | 2121873.5 | 2121873.5 | 1278216.41 | 843657.09 |  | 425500.68 | 44632 | 28 | 25 | 14.3054 | 66.41% |  | 21.0798 | 14.42 | 0.68 | 0% | 637990.88 | 0 |  |  | 190.735 | 1818.379 | 2726.4568 | 9067.8355 | 20.05% | 30.07% | 2479.5556 | 13 | 396328 | 396328 | 425500.68 | 7.361% | 717142 | 717142 | 637990.88 | -11.04%
2008 | Done | SUPABASE | 101 Taylor | SRM | 258 | 15 |  |  |  | 2328917 | 1782682.55 | 546234.45 |  | 593780.08 | 59248.5 | 50 | 44 | 22.7883 | 62.35% |  | 20.0276 | 15.4 | 0.77 | 0% | 816046.33 | 0 |  |  | 229.6453 | 2301.4732 | 3162.9703 | 9026.8101 | 25.5% | 35.04% | 3949.9 | 17.2 | 535720 | 551450 | 593780.08 | 10.84% | 1016555 | 1043740 | 816046.33 | -19.72%
2009 | Done | SUPABASE | Greenwood | Chinn | 56 | 16 |  |  | 392855 | 394208 | 279998.81 | 114209.19 |  | 80901.5 | 8318 | 24 | 17 | 2.9993 | 71.24% |  | 20.6703 | 14.64 | 0.71 | 0% | 151064.39 | 0 |  |  | 148.5357 | 1444.6696 | 2697.5784 | 7039.4286 | 20.52% | 38.32% | 519.875 | 3.5 | 69240 | 72340 | 80901.5 | 16.84% | 196250 | 195311 | 151064.39 | -23.02%
2010 | Done | SUPABASE | Old Town | Chinn | 149 | 24 |  |  | 1386419 | 1386419 | 584809.72 | 801609.28 |  | 196271.13 | 19847 | 23 | 14 | 4.771 | 79.86% |  | 19.3239 | 15.1 | 0.78 | 0% | 282662.77 | 0 |  |  | 133.2013 | 1317.2559 | 1897.0656 | 9304.8255 | 14.16% | 20.39% | 826.9583 | 6.2083 | 329465 | 303565 | 196271.13 | -40.43% | 570975 | 504680 | 282662.77 | -50.49%
2011 | Done | SUPABASE | Barrett Park | Chinn | 117 | 17 |  |  | 869823.5 | 869823.5 | 535728.69 | 334094.81 |  | 142882.75 | 13606 | 32 | 22 | 4.6175 | 70.85% |  | 20.3871 | 15.85 | 0.78 | 0% | 295005.88 | 0 |  |  | 116.2906 | 1221.2201 | 2521.4178 | 7434.3889 | 16.43% | 33.92% | 800.3529 | 6.8824 | 168705 | 174655 | 142882.75 | -15.31% | 358945 | 393359 | 295005.88 | -17.81%
2012 | Done | SUPABASE | 8th Ave | Exxel Pacific | 162 | 16 |  |  | 1393316 | 1323743.25 | 851276.4 | 472466.85 |  | 291321.88 | 14607.25 | 42 | 31 | 5.2671 | 35.32% | 43.6095 | 30.0264 | 30.02 | 1 | 0% | 390750.86 | 17 | Keller Supply Company | 38.39% | 90.1682 | 1798.2832 | 2412.0423 | 8171.2546 | 22.01% | 29.52% | 912.9531 | 10.125 | 305975 | 305975 | 291321.88 | -4.789% | 553400 | 561666 | 390750.86 | -29.39%
2015 | Done | SUPABASE | Rooster | Exxel Pacific | 197 | 25 |  |  | 2045883 | 2146708 | 1583004.56 | 563703.44 |  | 583482.62 | 51911 | 54 | 48 | 11.9797 | 60.97% |  | 19.7337 | 16.92 | 0.86 | 0% | 661468.33 | 0 |  |  | 263.5076 | 2961.8407 | 3357.7073 | 10896.9949 | 27.18% | 30.81% | 2076.44 | 7.88 | 428030 | 479050 | 583482.62 | 36.32% | 841015 | 866894 | 661468.33 | -21.35%
2017 | Done | SUPABASE | 36 Stone | Exxel Pacific | 119 | 16 |  |  | 1365227 | 1369989 | 856803.39 | 513185.61 |  | 292755.75 | 29950 | 46 | 30 | 10.7995 | 65.53% |  | 19.6695 | 14.93 | 0.76 | 0% | 378313.74 | 0 |  |  | 251.6807 | 2460.1324 | 3179.1071 | 11512.5126 | 21.37% | 27.61% | 1871.875 | 7.4375 | 267020 | 272340 | 292755.75 | 9.638% | 534360 | 502391 | 378313.74 | -29.2%
2018 | Done | SUPABASE | Astro | SRM | 211 | 15 |  |  | 2524038.49 | 2305058 | 1232269.8 | 1072788.2 |  | 440392.94 | 47132 | 49 | 43 | 18.128 | 58.45% |  | 19.0439 | 14.22 | 0.75 | 0% | 556906.77 | 0 |  |  | 223.3744 | 2087.1703 | 2639.3686 | 10924.4455 | 19.11% | 24.16% | 3142.1333 | 14.0667 | 463275 | 468235 | 440392.94 | -4.939% | 776247 | 722677 | 556906.77 | -28.26%
2019 | Done | SUPABASE | 8th Republic | Exxel Pacific | 211 | 22 |  |  |  | 2877218.6 | 1524058.73 | 1353159.87 |  | 550832.62 | 52897 | 57 | 43 | 13.8719 | 62.63% |  | 20.5868 | 15.19 | 0.74 | 0% | 660548.93 | 0 |  |  | 250.6967 | 2610.5811 | 3130.5636 | 13636.1071 | 19.14% | 22.96% | 2404.4091 | 9.5909 | 592300 | 630261 | 550832.62 | -7.001% | 941700 | 974017 | 660548.93 | -29.86%
2020 | Done | SUPABASE | Bellevue Main | SRM | 256 | 22 |  |  |  | 3119000 | 1934503.21 | 1184496.79 |  | 766929.01 | 76015 | 58 | 52 | 19.9344 | 64.08% |  | 19.6158 | 15.33 | 0.78 | 0% | 735694.62 | 0 |  |  | 296.9336 | 2995.8164 | 2873.8071 | 12183.5938 | 24.59% | 23.59% | 3455.2273 | 11.6364 | 680013 | 593974 | 766929.01 | 12.78% | 1099380 | 997196 | 735694.62 | -33.08%
2021 | Done | SUPABASE | Admiral | Exxel Pacific | 136 | 19 |  |  |  | 1581818 | 1133076.79 | 448741.21 |  | 429422.78 | 41555 | 41 | 35 | 12.6182 | 64.28% |  | 22.0597 | 15.46 | 0.7 | 0% | 423924.46 | 0 |  |  | 305.5515 | 3157.5204 | 3117.0916 | 11631.0147 | 27.15% | 26.8% | 2187.1053 | 7.1579 | 370930 | 387079 | 429422.78 | 15.77% | 512085 | 494749 | 423924.46 | -17.22%
2022 | Done | SUPABASE | Interlake | Exxel Pacific | 18 | 11 |  |  | 242637 | 242637 | 155475.37 | 87161.63 |  | 57917.75 | 3952 | 21 | 10 | 2.0728 | 78.64% |  | 21.9795 | 22.11 | 1.01 | 0% | 60804.36 | 0 |  |  | 219.5556 | 3217.6528 | 3378.02 | 13479.8333 | 23.87% | 25.06% | 359.2727 | 1.6364 | 51190 | 52240 | 57917.75 | 13.14% | 82480 | 89109 | 60804.36 | -26.28%
2023 | Done | V1 | Hadley | Chinn | 209 | 22.9 | 2015-01-19T00:00:00 | 2016-12-15T00:00:00 | 2771369 | 2771369 | 1873341.44 | 898027.56 | 32.4% | 702744.35 | 33107 | 52 | 47 | 8.3409 | 24.39% | 24.6538 | 21.492 | 32.3012 | 1.5029 | 0.1208% | 725504.82 | 31 | Rosen Supply Company, Inc. $Legacy | 26.28% | 158.4067 | 3362.4132 | 3471.3149 | 13260.1388 | 25.36% | 26.18% | 1445.7205 | 9.1266 | 505870 | 609147 | 702744.35 | 38.92% | 900375 | 982300 | 725504.82 | -19.42%
2024 | Done | V1 | Merrill Gardens | SRM | 117 | 15.1 | 2015-05-19T00:00:00 | 2016-08-22T00:00:00 | 1811843 | 1811843 | 925434.96 | 886408.04 | 48.92% | 379757.5 | 17098 | 40 | 28 | 6.5327 | 37.44% | 17.85 | 22.2442 | 33.717 | 1.5158 | 0.2164% | 336538.34 | 23 | Rosen Supply Company, Inc. $MG-Ballard | 30.33% | 146.1368 | 3245.7906 | 2876.3961 | 15485.8376 | 20.96% | 18.57% | 1132.3179 | 7.7483 | 399300 | 414758 | 379757.5 | -4.894% | 574700 | 587857 | 336538.34 | -41.44%
2025 | Done | V1 | The Cora | Exxel Pacific | 75 | 17.8 | 2016-02-24T00:00:00 | 2017-08-18T00:00:00 | 1208338 | 1208338 | 746934.31 | 461403.69 | 38.18% | 287298.5 | 11488.5 | 36 | 27 | 3.7237 | 40.77% | 14.4722 | 24.3974 | 38.0013 | 1.5576 | 0.008704% | 263607.67 | 23 | Keller Supply Company $Cora | 29.78% | 153.18 | 3830.6467 | 3514.7689 | 16111.1733 | 23.78% | 21.82% | 645.4213 | 4.2135 | 268960 | 275655.5 | 287298.5 | 6.818% | 369935 | 376656.5 | 263607.67 | -28.74%
2026 | Done | V1 | Boren | Synnergy | 49 | 16.1 | 2016-03-21T00:00:00 | 2017-07-24T00:00:00 | 830667 | 830667 | 547967.06 | 282699.94 | 34.03% | 210715.5 | 8541.5 | 25 | 16 | 3.0608 | 71.94% | 16.24 | 24.4407 | 37.4898 | 1.5339 | 0% | 194870.36 | 13 | Rosen Supply Company, Inc. $Boren | 25.48% | 174.3163 | 4300.3163 | 3976.9461 | 16952.3878 | 25.37% | 23.46% | 530.528 | 3.0435 | 191780 | 191921 | 210715.5 | 9.874% | 261100 | 265270 | 194870.36 | -25.37%
2027 | Done | V1 | 550 Broadway | Exxel Pacific | 170 | 18.9 | 2016-02-24T00:00:00 | 2017-09-20T00:00:00 | 2275444 | 2275444 | 1353483.06 | 921960.94 | 40.52% | 491249.77 | 21014 | 43 | 36 | 6.4147 | 37.43% | 18.9302 | 23.1384 | 34.1239 | 1.4748 | 1.223% | 548337.59 | 26 | Rosen Supply Company, Inc. $550 Broadway | 23.74% | 123.6118 | 2889.7045 | 3225.5152 | 13384.9647 | 21.59% | 24.1% | 1111.8519 | 8.9947 | 557925 | 559702 | 491249.77 | -11.95% | 686465 | 696496 | 548337.59 | -20.12%
2028 | Done | V1 | Reserve @ Lynnwood | Exxel Pacific | 296 | 12.4 | 2016-01-20T00:00:00 | 2017-01-31T00:00:00 | 2684887 | 2684887 | 1371278.1 | 1313608.9 | 48.93% | 567651.09 | 24097 | 45 | 41 | 11.2116 | 25.31% | 19.0889 | 23.1485 | 35.8391 | 1.5482 | 0% | 458753.13 | 21 | Ferguson Enterprises, Inc. $Reserve@Lynn | 29.15% | 81.4088 | 1917.7402 | 1549.8417 | 9070.5642 | 21.14% | 17.09% | 1943.3065 | 23.871 | 812960 | 707526.5 | 567651.09 | -30.17% | 826455 | 694434 | 458753.13 | -44.49%
2029 | Done | V1 | Parsonage | Exxel Pacific | 83 | 14 | 2016-07-20T00:00:00 | 2017-09-20T00:00:00 | 1123747 | 1123747 | 563588.99 | 560158.01 | 49.85% | 188045.5 | 7596 | 21 | 12 | 3.1303 | 69.98% | 17.7619 | 24.7136 | 37.6287 | 1.5226 | 0% | 242874.9 | 13 | Keller Supply Company $Parsonage | 39.69% | 91.5181 | 2265.6084 | 2926.2036 | 13539.1205 | 16.73% | 21.61% | 542.5714 | 5.9286 | 257600 | 260628.5 | 188045.5 | -27% | 306800 | 310049.5 | 242874.9 | -20.84%
2030 | Done | V1 | East Union | Exxel Pacific | 144 | 20.5 | 2016-12-16T00:00:00 | 2018-09-01T00:00:00 | 2322781 | 2322781 | 1437428.97 | 885352.03 | 38.12% | 504091.25 | 18665 | 45 | 30 | 5.2529 | 43.85% | 16.4889 | 26.2351 | 41.0511 | 1.5647 | 2.836% | 569904.99 | 26 | Rosen Supply Company, Inc. $East Union | 24.05% | 129.6181 | 3500.6337 | 3957.6735 | 16130.4236 | 21.7% | 24.54% | 910.4878 | 7.0244 | 541485 | 575631 | 504091.25 | -6.906% | 713730 | 771610 | 569904.99 | -20.15%
2031 | Done | V1 | Issaquah Gateway | Exxel Pacific | 398 | 31.1 | 2016-11-15T00:00:00 | 2019-06-19T00:00:00 | 5187754 | 5187754 | 1129564.53 | 4058189.47 | 78.23% | 564920.38 | 22023 | 72 | 54 | 4.0855 | 28.67% | 26.5694 | 23.1074 | 25.6514 | 1.1101 | 1.069% | 485439.43 | 28 | Rosen Supply Company, Inc. $Gateway | 92.13% | 55.3342 | 1419.3979 | 1219.6971 | 13034.5578 | 10.89% | 9.357% | 708.135 | 12.7974 | 607025 | 648765 | 564920.38 | -6.936% | 657109 | 642830 | 485439.43 | -26.12%
2032 | Done | V1 | Luna | Blueprint | 71 | 15.6 | 2017-01-27T00:00:00 | 2018-05-18T00:00:00 | 726403 | 726403 | 398294.52 | 328108.48 | 45.17% | 134465.25 | 5157 | 26 | 16 | 1.9072 | 61.38% | 12.6538 | 25.3991 | 39.6516 | 1.5611 | 0.3781% | 167700.53 | 16 | Keller Supply Co. $Roosevelt | 28.48% | 72.6338 | 1893.8768 | 2361.9793 | 10231.0282 | 18.51% | 23.09% | 330.5769 | 4.5513 | 176220 | 181623 | 134465.25 | -23.69% | 204375 | 230569 | 167700.53 | -17.94%
2033 | Done | V1 | Vuecrest | Compass | 139 | 24.8 | 2016-10-21T00:00:00 | 2018-11-16T00:00:00 | 2343188 | 2343188 | 1332680.44 | 1010507.56 | 43.13% | 526277.63 | 19509 | 44 | 25 | 4.5385 | 46.77% | 19.3864 | 26.6936 | 39.7834 | 1.4904 | 0.5536% | 460263.33 | 25 | Rosen Supply Company, Inc. $Vuecrest | 36.84% | 140.3525 | 3786.17 | 3311.247 | 16857.4676 | 22.46% | 19.64% | 786.6532 | 5.6048 | 611660 | 569257 | 526277.63 | -13.96% | 850125 | 691518 | 460263.33 | -45.86%
2034 | Done | V1 | Park Lane | Compass | 128 | 17.1 | 2016-12-15T00:00:00 | 2018-05-18T00:00:00 | 1897650.9 | 1897650.9 | 1281948.22 | 615702.68 | 32.45% | 539464.25 | 21637.75 | 45 | 36 | 7.3003 | 36.99% | 18.6222 | 24.7274 | 36.8436 | 1.49 | 0.1017% | 419880.12 | 23 | Rosen Supply Company, Inc. $Park Lane | 42.73% | 169.0449 | 4214.5645 | 3280.3134 | 14825.3977 | 28.43% | 22.13% | 1265.3655 | 7.4854 | 448700 | 477178 | 539464.25 | 20.23% | 614030 | 602753 | 419880.12 | -31.62%
2035 | Done | V1 | 162 Ten | Natural & Built | 92 | 16.6 | 2016-12-02T00:00:00 | 2018-04-20T00:00:00 | 722290 | 722290 | 363766.71 | 358523.29 | 49.64% | 133452.5 | 5204.75 | 24 | 13 | 1.8089 | 69.61% | 13.25 | 25.1948 | 38.9736 | 1.5469 | 0.1585% | 159409.61 | 15 | Consolidated Supply Co. $162Ten | 40.06% | 56.5734 | 1450.5707 | 1732.7132 | 7850.9783 | 18.48% | 22.07% | 313.5392 | 5.5422 | 183890 | 185274 | 133452.5 | -27.43% | 211875 | 210340 | 159409.61 | -24.76%
2036 | Done | V1 | Westridge | Exxel Pacific | 31 | 17.9 | 2017-05-19T00:00:00 | 2018-11-16T00:00:00 | 418677 | 418677 | 276208.96 | 142468.04 | 34.03% | 112585.75 | 4098 | 30 | 10 | 1.3208 | 69.58% | 9.8333 | 27.3423 | 41.7595 | 1.5273 | 0.4392% | 104252.85 | 12 | Ferguson Enterprises, Inc. $Westridge | 32.96% | 132.1935 | 3631.7984 | 3362.9952 | 13505.7097 | 26.89% | 24.9% | 228.9385 | 1.7318 | 107430 | 112414 | 112585.75 | 4.799% | 102770 | 115827 | 104252.85 | 1.443%
2037 | Done | V1 | University Apartments | Marpac | 122 | 26 | 2017-05-19T00:00:00 | 2019-07-19T00:00:00 | 2076783 | 2076783 | 1217234.63 | 859548.37 | 41.39% | 440145.25 | 14799 | 50 | 29 | 3.2839 | 42.52% | 15.04 | 29.1154 | 45.3241 | 1.5567 | 4.122% | 487276.21 | 26 | Rosen Supply Company, Inc. $University | 19.25% | 121.3033 | 3607.748 | 3994.0673 | 17022.8115 | 21.19% | 23.46% | 569.1923 | 4.6923 | 494845 | 521000 | 440145.25 | -11.05% | 576480 | 643201 | 487276.21 | -15.47%
2038 | Done | V1 | 2nd & John | Compass | 80 | 22.7 | 2017-04-27T00:00:00 | 2019-03-20T00:00:00 | 1229419 | 1229419 | 807313.13 | 422105.87 | 34.33% | 324824.75 | 11814.25 | 36 | 24 | 3.0027 | 41.37% | 16.1944 | 26.3938 | 40.6786 | 1.5412 | 1.094% | 268693.54 | 20 | Rosen Supply Company, Inc. $2nd & John | 44.43% | 147.6781 | 4060.3094 | 3358.6692 | 15367.7375 | 26.42% | 21.86% | 520.4515 | 3.5242 | 285250 | 300550 | 324824.75 | 13.87% | 391395 | 372182 | 268693.54 | -31.35%
2039 | Done | V1 | Ravello Gas Piping | Shelter Holdings |  | 9.8 | 2017-07-24T00:00:00 | 2018-05-18T00:00:00 | 54900 | 54900 | 19392.46 | 35507.54 | 64.68% | 8172.25 | 238 | 12 | 1 | 0.14011 | 84.76% | 3.4167 | 27.5371 | 52.5822 | 1.9095 | 7.353% | 2697.34 | 4 | Franklin Engineering | 123.7% |  |  |  |  | 14.89% | 4.913% | 24.2857 |  | 9976 | 9976 | 8172.25 | -18.08% | 10650 | 10650 | 2697.34 | -74.67%
2040 | Done | V1 | Roosevelt 65th | Blueprint | 55 | 17 | 2017-08-18T00:00:00 | 2019-01-18T00:00:00 | 624171 | 624171 | 404517.76 | 219653.24 | 35.19% | 146699.25 | 5454 | 32 | 15 | 1.8509 | 62.5% | 10.9375 | 25.8477 | 40.8844 | 1.5817 | 3.516% | 154104.17 | 20 | Keller Supply Company | 24.35% | 99.1636 | 2667.2591 | 2801.894 | 11348.5636 | 23.5% | 24.69% | 320.8235 | 3.2353 | 154435 | 156965 | 146699.25 | -5.009% | 173720 | 185986 | 154104.17 | -11.29%
2041 | Done | V2.2 | Chinn California Ave Luna | Chinn Construction | 108 |  |  |  | 1883761 | 1883761 | 1329860.36 | 553900.64 | 29.4% | 467297.5 | 14566.5 | 44 | 21 |  | 50.21% |  | 32.5752 | 66.4535 | 1.3421 | 5.938% | 502616.05 | 0 |  |  | 134.875 | 4326.8287 | 4653.8523 | 17442.2315 | 24.81% | 26.68% |  |  | 432100 | 448910 | 467297.5 | 8.146% | 598130 | 639725 | 502616.05 | -15.97%
2042 | Done | V2.2 | ShelterHoldings MetroLine | Shelter Holdings | 75 |  |  |  | 922104 | 922104 | 593584.52 | 328519.48 | 35.63% | 194340.5 | 7093 | 35 | 17 |  | 59.44% |  | 26.9356 | 54.9488 | 1.3421 | 1.896% | 250243.51 | 0 |  |  | 94.5733 | 2591.2067 | 3336.5801 | 12294.72 | 21.08% | 27.14% |  |  | 213138 | 215243 | 194340.5 | -8.819% | 310497 | 316790 | 250243.51 | -19.41%
2043 | Done | V2.2 | Compass Aegis-Mercer Isl | Compass Harbor | 89 |  |  |  | 1583445 | 1583445 | 855439.25 | 728005.75 | 45.98% | 325026 | 10969 | 32 | 18 |  | 58.43% |  | 29.4969 | 60.1737 | 1.3421 | 3.779% | 320019.62 | 0 |  |  | 123.2472 | 3651.9775 | 3595.7261 | 17791.5169 | 20.53% | 20.21% |  |  | 358840 | 368155 | 325026 | -9.423% | 548895 | 551921 | 320019.62 | -41.7%
2044 | Done | V2.2 | Blueprint Track 66 Apts | Blueprint | 78 |  |  |  | 855264 | 855264 | 588885.61 | 266378.39 | 31.15% | 219024.35 | 7722.75 | 24 | 15 |  | 62.73% |  | 28.4915 | 58.1227 | 1.3421 | 1.256% | 216377.88 | 0 |  |  | 99.0096 | 2808.0045 | 2774.0754 | 10964.9231 | 25.61% | 25.3% |  |  | 206175 | 208605 | 219024.35 | 6.232% | 262392 | 279401 | 216377.88 | -17.54%
2045 | Done | V2.2 | GRE Notch Apartments | GRE | 158 |  |  |  | 2110205 | 2110205 | 1138172 | 972033 | 46.06% | 404811.73 | 14541 | 39 | 29 |  | 45.73% |  | 27.4148 | 55.9263 | 1.3421 | 2.61% | 497590.37 | 0 |  |  | 92.0316 | 2562.0996 | 3149.3061 | 13355.7278 | 19.18% | 23.58% |  |  | 533695 | 595919 | 404811.73 | -24.15% | 520410 | 608708 | 497590.37 | -4.385%
2046 | Done | V2.2 | Marpac 4218 Roosevelt | Marpac | 110 |  |  |  | 1721867 | 1721867 | 971410.53 | 750456.47 | 43.58% | 349617.68 | 12479.5 | 32 | 21 |  | 44.76% |  | 27.5871 | 56.2777 | 1.3421 | 4.167% | 378784.06 | 0 |  |  | 113.45 | 3178.3425 | 3443.4915 | 15653.3364 | 20.3% | 22% |  |  | 426875 | 439190 | 349617.68 | -18.1% | 459229 | 493642 | 378784.06 | -17.52%
2047 | Done | V2.2 | GRE Greenlake | GRE | 70 |  |  |  | 553189 | 553189 | 366275.78 | 186913.22 | 33.79% | 150690.75 | 5837 | 33 | 17 |  | 53.45% |  | 25.1445 | 51.2948 | 1.3421 | 3.752% | 133195.02 | 0 |  |  | 83.3857 | 2152.725 | 1902.786 | 7902.7 | 27.24% | 24.08% |  |  | 127757 | 145329 | 150690.75 | 17.95% | 149685 | 172896 | 133195.02 | -11.02%
2048 | Done | V2.2 | GRE Greenlake | GRE | 72 |  |  |  | 517068 | 517068 | 294712.63 | 222355.37 | 43% | 117360.75 | 4658.5 | 30 | 15 |  | 52.58% |  | 25.1227 | 51.2504 | 1.3421 | 7.17% | 115436.54 | 0 |  |  | 64.7014 | 1630.0104 | 1603.2853 | 7181.5 | 22.7% | 22.33% |  |  | 137961 | 145518 | 117360.75 | -14.93% | 143792 | 151898 | 115436.54 | -19.72%
2049 | Done | V2.2 | GRE Greenlake | GRE | 296 |  |  |  | 2999780 | 2999780 | 1532182.53 | 1467597.47 | 48.92% | 568449.55 | 21791.25 | 58 | 36 |  | 38.51% |  | 26.1853 | 53.4181 | 1.3421 | 6.311% | 618442.18 | 0 |  |  | 73.6191 | 1920.4377 | 2089.3317 | 10134.3919 | 18.95% | 20.62% |  |  | 810120 | 848910 | 568449.55 | -29.83% | 669800 | 691822 | 618442.18 | -7.668%
2050 | Done | V2.2 | GRE Greenlake | GRE | 50 |  |  |  | 918566 | 918566 | 491756.9 | 426809.1 | 46.46% | 163505.5 | 5681.5 | 22 | 14 |  | 67.25% |  | 28.4052 | 57.9979 | 1.3421 | 2.543% | 204958.79 | 0 |  |  | 113.63 | 3270.11 | 4099.1758 | 18371.32 | 17.8% | 22.31% |  |  | 201030 | 207425 | 163505.5 | -18.67% | 305655 | 311905 | 204958.79 | -32.94%
2051 | Done | V2.2 | Vail Apartments | Compass | 163 |  |  |  | 2588279.5 | 2588279.5 | 1288549.21 | 1299730.29 | 50.22% | 536090.57 | 18720.5 | 45 | 31 |  | 35.72% |  | 27.5204 | 55.2992 | 1.3354 | 1.322% | 431531 | 0 |  |  | 114.8497 | 3288.8992 | 2647.4294 | 15879.0153 | 20.71% | 16.67% |  |  | 737325 | 657984 | 536090.57 | -27.29% | 755185 | 673732 | 431531 | -42.86%
2052 | Done | V2.2 | Fifth & Roy | Farrell-McKenna Construction LLC | 107 |  |  |  | 2231035 | 2231035 | 1217236.76 | 1013798.24 | 45.44% | 443242.25 | 15292.5 | 39 | 25 |  | 43.26% |  | 28.7792 | 58.7096 | 1.3421 | 2.54% | 479362.75 | 0 |  |  | 142.9206 | 4142.4509 | 4480.0257 | 20850.7944 | 19.87% | 21.49% |  |  | 492160 | 520965 | 443242.25 | -9.939% | 725720 | 754934 | 479362.75 | -33.95%
2053 | Done | V2.2 | Bellevue Parkside | Compass Harbor Construction | 136 |  |  |  | 2332680 | 2332680 | 1398972.74 | 933707.26 | 40.03% | 557411.5 | 19334 | 39 | 23 |  | 47.98% |  | 28.7533 | 56.3566 | 1.3243 | 2.113% | 478591.1 | 0 |  |  | 142.1618 | 4098.614 | 3519.0522 | 17152.0588 | 23.9% | 20.52% |  |  | 517023 | 525505 | 557411.5 | 7.812% | 785523 | 787591 | 478591.1 | -39.07%
2054 | Done | V2.2 | 800 5th Apartments | Blueprint Capital Services, LLC | 68 |  |  |  | 843087 | 843087 | 645060.46 | 122055.54 | 14.48% | 282896.5 | 8861.5 | 36 | 18 |  | 62.11% |  | 29.1346 | 58.4777 | 1.3349 | 2.945% | 264321 | 0 |  |  | 130.3162 | 4160.2426 | 3887.0735 | 12398.3382 | 33.55% | 31.35% |  |  | 199006 | 202906 | 282896.5 | 42.15% | 247326 | 290842 | 264321 | 6.871%
2055 | Done | V2.2 | Dockside Apartments | Blueprint Capital Services, LLC | 98 |  |  |  | 1315429 | 1315429 | 976727.45 | 338701.55 | 25.75% | 334415.5 | 9850.5 | 38 | 25 |  | 51.36% |  | 33.9147 | 67.3574 | 1.3302 | 1.386% | 406456.61 | 0 |  |  | 100.5153 | 3412.4031 | 4147.5164 | 13422.7449 | 25.42% | 30.9% |  |  | 291480 | 339230 | 334415.5 | 14.73% | 377441 | 405741 | 406456.61 | 7.687%
2056 | Done | V2.2 | Acme Farms | Exxel Pacific | 321 |  |  |  | 6034876 | 6034876 | 3389454.98 | 2645421.02 | 43.84% | 1358055.41 | 16334 | 66 | 53 |  | 27.37% |  | 32.7586 | 62.2984 | 1.3108 | 0.8112% | 1238306.14 | 0 |  |  | 50.8847 | 4230.7022 | 3857.6515 | 18800.2368 | 22.5% | 20.52% |  |  | 1484649 | 1508608 | 1358055.41 | -8.527% | 1922880 | 1931720 | 1238306.14 | -35.6%
2057 | Done | V2.2 | Plaza Apartments | Natural & Built | 111 |  |  |  | 1133967 | 1133967 | 575025.92 | 558941.08 | 49.29% | 221400.5 | 7091 | 23 | 14 |  | 70.87% |  | 31.2139 | 63.6766 | 1.3421 | 1.777% | 232848.36 | 0 |  |  | 63.8829 | 1994.5991 | 2097.733 | 10215.9189 | 19.52% | 20.53% |  |  | 252554 | 262737 | 221400.5 | -12.34% | 419205 | 431063 | 232848.36 | -44.45%
2058 | Done | V2.2 | Howell Apartments | Blueprint Capital Services, LLC | 77 |  |  |  | 961556 | 961556 | 772807.92 | 264719.08 | 27.53% | 277607.5 | 8884.5 | 24 | 15 |  | 60.49% |  | 31.2463 | 62.5253 | 1.3336 | 0.1126% | 244128.93 | 0 |  |  | 115.3831 | 3605.2922 | 3170.5056 | 12487.7403 | 28.87% | 25.39% |  |  | 219004 | 230204 | 277607.5 | 26.76% | 287240 | 299744 | 244128.93 | -15.01%
2059 | Done | V2.2 | Meeker | GRE Construction LLC | 365 |  |  |  | 4492453 | 4492453 | 3015419.73 | 1477033.27 | 32.88% | 1244296.75 | 37109.75 | 48 | 40 |  | 27.93% |  | 32.8191 | 65.6781 | 1.3336 | 0.446% | 1034930.53 | 0 |  |  | 101.6705 | 3409.0322 | 2835.4261 | 12308.0904 | 27.7% | 23.04% |  |  | 1077345 | 1125989 | 1244296.75 | 15.5% | 1478085 | 1516510 | 1034930.53 | -29.98%
2060 | Done | V2.2 | Marina Square | Compass Construction | 270 |  |  |  | 6156577 | 6156577 | 2572356.64 | 3584220.36 | 58.22% | 922171.59 | 27144 | 46 | 28 |  | 48.48% |  | 33.9049 | 67.4035 | 1.3307 | 3.352% | 1009043.67 | 0 |  |  | 100.5333 | 3415.4503 | 3737.1988 | 22802.137 | 14.98% | 16.39% |  |  | 1336625 | 1540041 | 922171.59 | -31.01% | 1739148 | 2038248 | 1009043.67 | -41.98%
2098 | LIVE | V2.2 | Trailside Apartment Community Phase II | Chinn Construction, LLC | 170 |  |  |  | 6917965.74 | 6917965.74 | 4082381.54 | -4076118.54 | -58.92% | 1532523.96 | 38113.75 | 79 | 56 |  | 27.54% |  | 37.9052 | 76.0236 | 1.3346 | 0.4369% | 1518915.7 | 0 |  |  | 224.1985 | 9014.8468 | 8934.7982 | 40693.9161 | 22.15% | 21.96% |  |  | 1761110 | 1799290 | 1532523.96 | -12.98% | 2199597 | 2209412 | 1518915.7 | -30.95%
2103 | LIVE | V2.2 | Northgate Station M2 | Compass General Construction I, LLC | 234 |  |  |  | 6625153.34 | 6608301.34 | 4680785.34 | -4680785.34 | -70.83% | 1811122.75 | 41202.25 | 59 | 45 |  | 27.78% |  | 43.608 | 89.1287 | 1.3429 | 0.3234% | 1854483.43 | 0 |  |  | 176.078 | 7739.8408 | 7925.1429 | 28240.604 | 27.41% | 28.06% |  |  | 1587456 | 1779241 | 1811122.75 | 14.09% | 2172207 | 2387628 | 1854483.43 | -14.63%
2104 | LIVE | V2.2 | Big 1410 Apartments | BMDC Services, LLC | 24 |  |  |  | 1196549 | 1193734 | 770053.1 | -770053.1 | -64.51% | 202081 | 4603.25 | 22 | 7 |  | 87.65% |  | 43.8235 | 91.0608 | 1.3502 | 0.01086% | 432579.38 | 0 |  |  | 191.8021 | 8420.0417 | 18024.1408 | 49738.9167 | 16.93% | 36.24% |  |  | 188055 | 197405 | 202081 | 7.458% | 530143 | 558927 | 432579.38 | -18.4%
2105 | LIVE | V2.2 | Compass, 3000 Western | Compass General Construction | 219 |  |  |  |  | 193091.4 | 146056.99 | 47034.41 | 24.36% | 3422 | 49.5 | 2 | 0 |  | 100% |  | 69.1313 | 147.0198 | 1.3603 | 2.02% | 0 | 0 |  |  | 0.22603 | 15.6256 |  | 881.6959 | 1.772% |  |  |  | 0 | 0 | 3422 |  | 0 | 0 | 0
2106 | LIVE | V2.2 | Chinn, 6220 Roosevelt | Chinn Construction, LLC | 146 |  |  |  |  | 49275 | 45726.76 | 3548.24 | 7.201% | 9982.25 | 152 | 3 | 1 |  | 100% |  | 65.6727 | 138.6268 | 1.3571 | 0% | 0 | 0 |  |  | 1.0411 | 68.3716 |  | 337.5 | 20.26% |  |  |  | 0 | 0 | 9982.25 |  | 0 | 0 | 0
2107 | LIVE | V2.2 | 68th & Roosevelt | Chinn Construction, LLC | 244 |  |  |  | 4889866 | 4422211 | 3408879.35 | -3408879.35 | -77.09% | 1100218.51 | 24977.25 | 33 | 31 |  | 32.54% |  | 43.7914 | 92.883 | 1.3592 | 0.01001% | 1100377.27 | 0 |  |  | 102.3658 | 4509.0923 | 4509.7429 | 18123.8156 | 24.88% | 24.88% |  |  | 1194213 | 1258563 | 1100218.51 | -7.871% | 1911015 | 1930422 | 1100377.27 | -42.42%
2111 | LIVE | V_TX | Northgate M3 | Compass | 186 | 10.8 | 2025-05-09T00:00:00 | 2026-04-03T00:00:00 | 4589762 | 2280568 | 1084959.39 | 1195608.61 | 52.43% | 378611.38 | 8736.5 | 33 | 27 | 4.667 | 47.8% | 11.3636 | 65.8642 | 65.7687 | 0.99855 | 0.08299% | 344768.24 | 0 |  |  | 46.9704 | 2035.5451 | 1853.5927 | 12261.1183 | 16.6% | 15.12% | 808.9352 | 17.2222 | 976975 | 999175 | 378611.38 | -61.25% | 1590100 | 1618150 | 344768.24 | -78.32%
2112 | LIVE | V_TX | BIG3 | BMDC | 20 | 11 | 2025-05-02T00:00:00 | 2026-04-03T00:00:00 | 696427 | 518063 | 256480.87 | 261582.13 | 50.49% | 103520.5 | 2352 | 18 | 8 | 1.2336 | 81.44% | 9.6111 | 68.6242 | 68.6242 | 1 | 0.09566% | 91340.7 | 0 |  |  | 117.6 | 5176.025 | 4567.035 | 25903.15 | 19.98% | 17.63% | 213.8182 | 1.8182 | 141830 | 149780 | 103520.5 | -27.01% | 256952 | 272837 | 91340.7 | -64.45%
2114 | LIVE | V2.2 | Ballard Blossom Apartments | Holland Construction | 239 |  |  |  |  | 80000 | 66355.58 | 13644.42 | 17.06% | 7372.25 | 114.25 | 2 | 0 |  | 100% |  | 64.5274 | 134.2574 | 1.3508 | 0% | 0 | 0 |  |  | 0.47803 | 30.8462 |  | 334.728 | 9.215% |  |  |  | 0 | 0 | 7372.25 |  | 0 | 0 | 0
2115 | LIVE | V2.2 | Elowen Apartments | Chinn Construction, LLC | 201 | [5 empty] | 12976.92 | -12976.92 |  | 1653.75 | 26.25 | 2 | 0 |  | 100% |  | 63 | 132.7653 | 1.3564 | 0% | 0 | 0 |  |  | 0.1306 | 8.2276 | [6 empty] | 0 | 0 | 1653.75 |  | 0 | 0 | 0
2116 | LIVE | V2.2 | The V Apartments | SRM Construction, Inc. | 166 | [5 empty] | 10092.02 | -10092.02 |  | 6489 | 101 | 2 | 0 |  | 100% |  | 64.2475 | 135.5945 | 1.357 | 0% | 0 | 0 |  |  | 0.60843 | 39.0904 | [6 empty] | 35026 | 35026 | 6489 | -81.47% | 0 | 0 | 0
2117 | LIVE | V2.2 | Lachlan Apartments | Ravenna Partners | 104 | [5 empty] | 11007.25 | -11007.25 |  | 197 | 3 | 2 | 0 |  | 100% |  | 65.6667 | 138.3333 | 1.3562 | 0% | 0 | 0 |  |  | 0.028846 | 1.8942 | [6 empty] | 0 | 0 | 197 |  | 0 | 0 | 0
2118 | LIVE | V2.2 | Exxel, Edmonds Behar | Exxel Pacific, Inc. | 406 | [8 empty] | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | [10 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
2119 | LIVE | V2.2 | The Frank (508 Fremont) | Exxel Pacific, Inc. | [9 empty] | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | [10 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
COUNT |  |  | 65
MEDIAN |  |  |  |  | 136 | 17 |  |  |  | 1582631.5 | 856803.39 | 472466.85 | 40.03% | 324824.75 | 12479.5 | 35 | 23 | 4.667 | 59.44% | 16.24 | 27.3423 | 51.2948 | 1.3421 | 0.3234% | 344768.24 | 0 |  | 30.33% | 116.9453 | 2978.8286 | 3202.3111 | 13260.1388 | 21.28% | 23.46% | 808.9352 | 7.0911 | 305975 | 305975 | 324824.75 | -6.921% | 520410 | 502391 | 344768.24 | -25.37%

## Productivity Rates
Productivity Rates · per plumbing unit
Hours and dollars per unit, by phase. Live jobs and jobs without unit counts excluded from medians.
Job | Status | Name | Units | Duration (mo) | Total Hrs | Hrs/Unit | Labor $/Unit | Material $/Unit | Revenue/Unit | Hrs/Month | Supervision Hrs/Unit | Takeoff Hrs/Unit | Underground Hrs/Unit | Rough In Hrs/Unit | Trim Finish Hrs/Unit | Gas Hrs/Unit | Water Main Hrs/Unit | Mech Room Hrs/Unit | Condensation Hrs/Unit | Fire Caulking Hrs/Unit | Service Other Hrs/Unit
2001 | Done | 230 Broadway | 234 | 18 | 44632 | 190.735 | 1818.379 | 2726.4568 | 9067.8355 | 2479.5556
2008 | Done | 101 Taylor | 258 | 15 | 59248.5 | 229.6453 | 2301.4732 | 3162.9703 | 9026.8101 | 3949.9
2009 | Done | Greenwood | 56 | 16 | 8318 | 148.5357 | 1444.6696 | 2697.5784 | 7039.4286 | 519.875
2010 | Done | Old Town | 149 | 24 | 19847 | 133.2013 | 1317.2559 | 1897.0656 | 9304.8255 | 826.9583
2011 | Done | Barrett Park | 117 | 17 | 13606 | 116.2906 | 1221.2201 | 2521.4178 | 7434.3889 | 800.3529
2012 | Done | 8th Ave | 162 | 16 | 14607.25 | 90.1682 | 1798.2832 | 2412.0423 | 8171.2546 | 912.9531 | 1.02 |  | 9.19 | 57.53 | 13.45 | 0.64 | 4.94 | 2.34
2015 | Done | Rooster | 197 | 25 | 51911 | 263.5076 | 2961.8407 | 3357.7073 | 10896.9949 | 2076.44
2017 | Done | 36 Stone | 119 | 16 | 29950 | 251.6807 | 2460.1324 | 3179.1071 | 11512.5126 | 1871.875
2018 | Done | Astro | 211 | 15 | 47132 | 223.3744 | 2087.1703 | 2639.3686 | 10924.4455 | 3142.1333
2019 | Done | 8th Republic | 211 | 22 | 52897 | 250.6967 | 2610.5811 | 3130.5636 | 13636.1071 | 2404.4091
2020 | Done | Bellevue Main | 256 | 22 | 76015 | 296.9336 | 2995.8164 | 2873.8071 | 12183.5938 | 3455.2273
2021 | Done | Admiral | 136 | 19 | 41555 | 305.5515 | 3157.5204 | 3117.0916 | 11631.0147 | 2187.1053
2022 | Done | Interlake | 18 | 11 | 3952 | 219.5556 | 3217.6528 | 3378.02 | 13479.8333 | 359.2727
2023 | Done | Hadley | 209 | 22.9 | 33107 | 158.4067 | 3362.4132 | 3471.3149 | 13260.1388 | 1445.7205 | 1.48 |  | 30.49 | 85 | 13.91 | 4.65 | 15.38 | 4.19 | 0.03
2024 | Done | Merrill Gardens | 117 | 15.1 | 17098 | 146.1368 | 3245.7906 | 2876.3961 | 15485.8376 | 1132.3179 | 2.52 |  | 28.05 | 74.62 | 9.83 | 3.47 | 13.29 | 2.94 | 7.3
2025 | Done | The Cora | 75 | 17.8 | 11488.5 | 153.18 | 3830.6467 | 3514.7689 | 16111.1733 | 645.4213 | 1.27 |  | 28.09 | 84.67 | 14.25 | 2.61 | 12.28 | 6.59
2026 | Done | Boren | 49 | 16.1 | 8541.5 | 174.3163 | 4300.3163 | 3976.9461 | 16952.3878 | 530.528 | 0.93 |  | 26.55 | 100.02 | 12.77 | 2.72 | 19.73 | 8.88
2027 | Done | 550 Broadway | 170 | 18.9 | 21014 | 123.6118 | 2889.7045 | 3225.5152 | 13384.9647 | 1111.8519 | 0.73 |  | 16.55 | 74.54 | 12.69 | 1.98 | 12.99 | 2.43
2028 | Done | Reserve @ Lynnwood | 296 | 12.4 | 24097 | 81.4088 | 1917.7402 | 1549.8417 | 9070.5642 | 1943.3065 | 0.71 |  | 11.12 | 54.81 | 0.06 | 1.44 | 9.58 | 2.24 | 0.12
2029 | Done | Parsonage | 83 | 14 | 7596 | 91.5181 | 2265.6084 | 2926.2036 | 13539.1205 | 542.5714 | 0.86 |  | 8.1 | 54.86 | 11.8 | 1.09 | 6.66 | 5.6
2030 | Done | East Union | 144 | 20.5 | 18665 | 129.6181 | 3500.6337 | 3957.6735 | 16130.4236 | 910.4878 | 0.71 |  | 25.39 | 67.31 | 12.07 | 4.01 | 13.12 | 4.28
2031 | Done | Issaquah Gateway | 398 | 31.1 | 22023 | 55.3342 | 1419.3979 | 1219.6971 | 13034.5578 | 708.135 | 1.15 |  | 7.79 | 31.32 | 6.71 | 0.65 | 3.64 | 2.31 | 0.09
2032 | Done | Luna | 71 | 15.6 | 5157 | 72.6338 | 1893.8768 | 2361.9793 | 10231.0282 | 330.5769 | 0.88 |  | 3.25 | 44.11 | 9.61 | 0.71 | 7.87 | 3.86
2033 | Done | Vuecrest | 139 | 24.8 | 19509 | 140.3525 | 3786.17 | 3311.247 | 16857.4676 | 786.6532 | 0.34 |  | 21.6 | 82.38 | 13.27 | 2.33 | 7.88 | 2.55 | 8.04
2034 | Done | Park Lane | 128 | 17.1 | 21637.75 | 169.0449 | 4214.5645 | 3280.3134 | 14825.3977 | 1265.3655 | 0.56 |  | 36.13 | 82.9 | 11.47 | 2.53 | 23.49 | 1.61 | 8.11
2035 | Done | 162 Ten | 92 | 16.6 | 5204.75 | 56.5734 | 1450.5707 | 1732.7132 | 7850.9783 | 313.5392 | 1.03 |  | 8.93 | 31.42 | 6.41 |  | 6.48 | 0.15
2036 | Done | Westridge | 31 | 17.9 | 4098 | 132.1935 | 3631.7984 | 3362.9952 | 13505.7097 | 228.9385 | 2.29 |  | 12.92 | 83.31 | 23.6 |  | 5.81 | 0.31
2037 | Done | University Apartments | 122 | 26 | 14799 | 121.3033 | 3607.748 | 3994.0673 | 17022.8115 | 569.1923 | 1.17 |  | 23.96 | 66.86 | 13.48 | 1.59 | 8.06 | 3.66 | 0.2
2038 | Done | 2nd & John | 80 | 22.7 | 11814.25 | 147.6781 | 4060.3094 | 3358.6692 | 15367.7375 | 520.4515 | 0.4 |  | 26.77 | 88.75 | 10.91 | 1.14 | 16.74
2039 | Done | Ravello Gas Piping |  | 9.8 | 238 |  |  |  |  | 24.2857
2040 | Done | Roosevelt 65th | 55 | 17 | 5454 | 99.1636 | 2667.2591 | 2801.894 | 11348.5636 | 320.8235 | 0.8 |  | 8.02 | 62.36 | 9.67 | 1.51 | 11.55 | 3.49
2041 | Done | Chinn California Ave Luna | 108 |  | 14566.5 | 134.875 | 4326.8287 | 4653.8523 | 17442.2315 |  | 0.93 |  | 40.18 | 56.77 | 11.94 | 2.01 | 15.72 | 3.93 | 0.64
2042 | Done | ShelterHoldings MetroLine | 75 |  | 7093 | 94.5733 | 2591.2067 | 3336.5801 | 12294.72 |  | 0.44 |  | 4.81 | 66.53 | 8.68 | 0.55 | 7.81 | 3.79
2043 | Done | Compass Aegis-Mercer Isl | 89 |  | 10969 | 123.2472 | 3651.9775 | 3595.7261 | 17791.5169 |  | 0.78 |  | 19.66 | 59.02 | 10.37 | 3.09 | 18.48 | 3.24 | 5.49
2044 | Done | Blueprint Track 66 Apts | 78 |  | 7722.75 | 99.0096 | 2808.0045 | 2774.0754 | 10964.9231 |  | 0.39 |  | 2.51 | 67.88 | 9.51 | 1.74 | 12.71 | 3.19
2045 | Done | GRE Notch Apartments | 158 |  | 14541 | 92.0316 | 2562.0996 | 3149.3061 | 13355.7278 |  | 1.16 |  | 13.86 | 54.18 | 16 |  | 4.42 | 0.79
2046 | Done | Marpac 4218 Roosevelt | 110 |  | 12479.5 | 113.45 | 3178.3425 | 3443.4915 | 15653.3364 |  | 0.63 |  | 9.17 | 67.4 | 9.57 | 1.24 | 21.21 | 2.48 | 0.19
2047 | Done | GRE Greenlake | 70 |  | 5837 | 83.3857 | 2152.725 | 1902.786 | 7902.7 |  | 0.71 |  |  | 68.03 | 13.19
2048 | Done | GRE Greenlake | 72 |  | 4658.5 | 64.7014 | 1630.0104 | 1603.2853 | 7181.5 |  | 0.88 |  |  | 45.55 | 17.01
2049 | Done | GRE Greenlake | 296 |  | 21791.25 | 73.6191 | 1920.4377 | 2089.3317 | 10134.3919 |  | 0.26 |  | 3.66 | 48.67 | 10.23 | 1.32 | 7.61 | 1.25 | 0.05
2050 | Done | GRE Greenlake | 50 |  | 5681.5 | 113.63 | 3270.11 | 4099.1758 | 18371.32 |  | 0.52 |  | 24.65 | 57.25 | 10.06 | 3.56 | 9.46 | 5.09
2051 | Done | Vail Apartments | 163 |  | 18720.5 | 114.8497 | 3288.8992 | 2647.4294 | 15879.0153 |  | 0.71 |  | 19.94 | 61.89 | 16.8 |  | 10.56 | 2.79 | 0.1
2052 | Done | Fifth & Roy | 107 |  | 15292.5 | 142.9206 | 4142.4509 | 4480.0257 | 20850.7944 |  |  |  | 17.2 | 66.71 | 10.56 | 0.96 | 42.4 | 2.99
2053 | Done | Bellevue Parkside | 136 |  | 19334 | 142.1618 | 4098.614 | 3519.0522 | 17152.0588 |  | 0.2 |  | 22.45 | 82.89 | 16.03 | 3.13 | 11.5 | 3.88 | 0.02
2054 | Done | 800 5th Apartments | 68 |  | 8861.5 | 130.3162 | 4160.2426 | 3887.0735 | 12398.3382 |  | 0.79 |  | 5.32 | 71.98 |  | 3.09 | 43.38 | 4.71
2055 | Done | Dockside Apartments | 98 |  | 9850.5 | 100.5153 | 3412.4031 | 4147.5164 | 13422.7449 |  | 0.28 |  | 10.77 | 57.46 | 10.41 | 2.15 | 11.53 | 6.87
2056 | Done | Acme Farms | 321 |  | 16334 | 50.8847 | 4230.7022 | 3857.6515 | 18800.2368 |  | 0.47 |  | 19.53 |  | 11.57 | 1.14 | 13.97 | 2.54
2057 | Done | Plaza Apartments | 111 |  | 7091 | 63.8829 | 1994.5991 | 2097.733 | 10215.9189 |  | 0.59 |  | 12.62 | 29 | 6.18 | 2.3 | 10.43 | 1.25
2058 | Done | Howell Apartments | 77 |  | 8884.5 | 115.3831 | 3605.2922 | 3170.5056 | 12487.7403 |  | 0.4 |  | 2.69 | 84.2 | 9.19 | 2.61 | 10.61 | 4.32
2059 | Done | Meeker | 365 |  | 37109.75 | 101.6705 | 3409.0322 | 2835.4261 | 12308.0904 |  | 0.53 |  | 13.93 | 59.31 | 13.98 | 0.5 | 12.43 |  | 0.03
2060 | Done | Marina Square | 270 |  | 27144 | 100.5333 | 3415.4503 | 3737.1988 | 22802.137 |  | 0.07 |  | 17.74 | 48.89 | 12.47 | 1.61 | 14.24 | 3.58
2098 | LIVE | Trailside Apartment Community Phase II | 170 |  | 38113.75 | 224.1985 | 9014.8468 | 8934.7982 | 40693.9161 |  | 0.88 |  | 29.2 | 133.8 | 35.17 | 2.89 | 19.39
2103 | LIVE | Northgate Station M2 | 234 |  | 41202.25 | 176.078 | 7739.8408 | 7925.1429 | 28240.604 |  | 0.73 |  | 28.13 | 106.71 | 12.79 | 1.84 | 17.52 | 4.62
2104 | LIVE | Big 1410 Apartments | 24 |  | 4603.25 | 191.8021 | 8420.0417 | 18024.1408 | 49738.9167 |  | 2.65 |  | 12.1 | 133.99 | 9.26 | 3.43 | 18.28 | 5.7
2105 | LIVE | Compass, 3000 Western | 219 |  | 49.5 | 0.22603 | 15.6256 |  | 881.6959 |  |  |  | 0.01 |  |  |  |  | 0.01
2106 | LIVE | Chinn, 6220 Roosevelt | 146 |  | 152 | 1.0411 | 68.3716 |  | 337.5 |  | 0.01
2107 | LIVE | 68th & Roosevelt | 244 |  | 24977.25 | 102.3658 | 4509.0923 | 4509.7429 | 18123.8156 |  | 0.56 |  | 23.25 | 61.47 | 0 | 0.87 | 10.46 | 2.63
2111 | LIVE | Northgate M3 | 186 | 10.8 | 8736.5 | 46.9704 | 2035.5451 | 1853.5927 | 12261.1183 | 808.9352 | 0.19 |  | 12.05 | 30.21 |  |  | 2.22
2112 | LIVE | BIG3 | 20 | 11 | 2352 | 117.6 | 5176.025 | 4567.035 | 25903.15 | 213.8182 | 2.65 |  | 9.32 | 84.45 | 2.49 |  | 9.5 | 0.64
2114 | LIVE | Ballard Blossom Apartments | 239 |  | 114.25 | 0.47803 | 30.8462 |  | 334.728
2115 | LIVE | Elowen Apartments | 201 |  | 26.25 | 0.1306 | 8.2276
2116 | LIVE | The V Apartments | 166 |  | 101 | 0.60843 | 39.0904 |  |  |  | 0.01
2117 | LIVE | Lachlan Apartments | 104 |  | 3 | 0.028846 | 1.8942
2118 | LIVE | Exxel, Edmonds Behar | 406 |  | 0
2119 | LIVE | The Frank (508 Fremont) |  |  | 0
MEDIAN (completed, units > 0) |  |  | 136 | 17 | 12479.5 | 116.9453 | 2978.8286 | 3202.3111 | 13260.1388 | 808.9352 | 0.71 |  | 13.93 | 66.71 | 11.52 | 1.91 | 11.54 | 3.19 | 0.155

## Phase Splits — Labor
Phase Splits · Labor
Labor hours and dollars by construction phase, by job.
Job | Status | Name | Units | Total Hrs | Supervision Hrs | Takeoff Hrs | Underground Hrs | Rough In Hrs | Trim Finish Hrs | Gas Hrs | Water Main Hrs | Mech Room Hrs | Condensation Hrs | Fire Caulking Hrs | Service Other Hrs | Total Labor $ | Supervision $ | Takeoff $ | Underground $ | Rough In $ | Trim Finish $ | Gas $ | Water Main $ | Mech Room $ | Condensation $ | Fire Caulking $ | Service Other $
2001 | Done | 230 Broadway | 234 | 44632 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 425500.68 | 4198.3 |  | 91969.63 | 218574.15 | 46041.22 | 14211.67 | 36651.38 | 12626.53
2008 | Done | 101 Taylor | 258 | 59248.5 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 593780.08 | 8811.5 |  | 90038.25 | 303122.05 | 76470 | 21795.5 | 64816.03 | 13633.25
2009 | Done | Greenwood | 56 | 8318 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 80901.5 | 2992 |  | 17211.5 | 46114 | 11530 |  | 0 | 1730
2010 | Done | Old Town | 149 | 19847 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 196271.13 | 4944 |  | 34899.75 | 114688.38 | 30198 | 1712 | 3672 | 1871
2011 | Done | Barrett Park | 117 | 13606 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 142882.75 | 4164 |  | 22087 | 81010.75 | 30893 |  | 208 | 1007
2012 | Done | 8th Ave | 162 | 14607.25 | 165 |  | 1488.5 | 9319.5 | 2178.75 | 104 | 800 | 379 |  |  |  | 291321.88 | 6023 |  | 32698.25 | 177291.75 | 41439.38 | 2168 | 15756 | 9784
2015 | Done | Rooster | 197 | 51911 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 583482.62 | 7355 |  | 68467.5 | 387658.09 | 45395.28 | 11582.5 | 37466.75 | 8975
2017 | Done | 36 Stone | 119 | 29950 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 292755.75 | 4744 |  | 43495 | 173312.75 | 36292.5 | 7448 | 19505.5 | 85
2018 | Done | Astro | 211 | 47132 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 440392.94 | 7795 |  | 52561.75 | 256945.47 | 59097.75 | 8626.5 | 31534.47 | 14152
2019 | Done | 8th Republic | 211 | 52897 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 550832.62 | 13841.5 |  | 124232.5 | 301244.35 | 36001.25 | 7665 | 39821.52 | 814
2020 | Done | Bellevue Main | 256 | 76015 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 766929.01 | 13026.5 |  | 178603.25 | 348602.98 | 64250.9 | 32025.5 | 85831.88 | 26035.5
2021 | Done | Admiral | 136 | 41555 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 429422.78 | 8726 |  | 71216.09 | 232285.5 | 30179 | 10305.46 | 56135.73 | 1144.5
2022 | Done | Interlake | 18 | 3952 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 57917.75 | 1042 |  | 8667 | 39476.75 | 5302 |  | 472.5
2023 | Done | Hadley | 209 | 33107 | 308.5 |  | 6372.5 | 17765 | 2906.5 | 971 | 3214.5 | 875.5 | 7 |  |  | 702744.35 | 13424.5 |  | 126840.16 | 373123.5 | 62630.5 | 21481 | 54198.43 | 21196.26 | 175
2024 | Done | Merrill Gardens | 117 | 17098 | 295 |  | 3282 | 8731 | 1150.5 | 406.5 | 1554.5 | 343.5 | 854.5 |  |  | 379757.5 | 12228.5 |  | 80127.5 | 164177 | 28250.5 | 9547 | 33366.5 | 10740.5 | 20595.5
2025 | Done | The Cora | 75 | 11488.5 | 95 |  | 2106.5 | 6350 | 1069 | 195.5 | 921 | 494.5 |  |  |  | 287298.5 | 4337 |  | 56825.5 | 150592 | 23808 | 5854 | 20707 | 13230
2026 | Done | Boren | 49 | 8541.5 | 45.5 |  | 1301 | 4901 | 625.5 | 133.5 | 967 | 435 |  |  |  | 210715.5 | 2078.5 |  | 34913 | 116564.5 | 12520 | 3916 | 20543 | 14056.5
2027 | Done | 550 Broadway | 170 | 21014 | 124.5 |  | 2813.5 | 12672 | 2157.5 | 336.5 | 2208 | 412.5 |  |  |  | 491249.77 | 5755.5 |  | 77474.5 | 278595.5 | 48849.27 | 7836.5 | 46631.5 | 12684.5
2028 | Done | Reserve @ Lynnwood | 296 | 24097 | 209.5 |  | 3293 | 16225 | 19 | 425.5 | 2837 | 664.5 | 37 |  |  | 567651.09 | 9454.5 |  | 83561 | 366998.59 | 719 | 10210.5 | 60276 | 18210 | 905
2029 | Done | Parsonage | 83 | 7596 | 71.5 |  | 672 | 4553.5 | 979 | 90.5 | 553 | 465 |  |  |  | 188045.5 | 3269.5 |  | 18887 | 103433 | 25915.5 | 2133 | 12249 | 12326
2030 | Done | East Union | 144 | 18665 | 102.5 |  | 3656.75 | 9692.25 | 1737.5 | 578 | 1889 | 617 |  |  |  | 504091.25 | 4994.5 |  | 98609 | 255360.5 | 47557.25 | 16593 | 42757 | 18473
2031 | Done | Issaquah Gateway | 398 | 22023 | 459 |  | 3100.5 | 12464.75 | 2669.5 | 260.5 | 1450.25 | 920 | 37 |  |  | 564920.38 | 21845.5 |  | 79250 | 289348.75 | 69830.75 | 6952.5 | 31378.38 | 32815 | 1419
2032 | Done | Luna | 71 | 5157 | 62.5 |  | 231 | 3132 | 682.5 | 50.5 | 558.5 | 274 |  |  |  | 134465.25 | 2980.5 |  | 6693 | 77199.5 | 15430.25 | 1836 | 12390 | 9868.5
2033 | Done | Vuecrest | 139 | 19509 | 47.5 |  | 3002 | 11450.5 | 1845 | 324.5 | 1096 | 355 | 1117 |  |  | 526277.63 | 2336.5 |  | 85861.5 | 299136 | 42783.5 | 9941.5 | 29860.13 | 13827 | 29278.5
2034 | Done | Park Lane | 128 | 21637.75 | 72 |  | 4625 | 10611.5 | 1468.75 | 324 | 3006.5 | 206 | 1037.5 |  |  | 539464.25 | 3636.5 |  | 118785.5 | 248837 | 37411.5 | 10151 | 74191.25 | 8618.5 | 23734
2035 | Done | 162 Ten | 92 | 5204.75 | 95 |  | 821.25 | 2891 | 590 |  | 596 | 14 |  |  |  | 133452.5 | 4434 |  | 25027.5 | 65658 | 15449 |  | 12963 | 588
2036 | Done | Westridge | 31 | 4098 | 71 |  | 400.5 | 2582.5 | 731.5 |  | 180 | 9.5 |  |  |  | 112585.75 | 3394 |  | 11913.5 | 66604.5 | 18527.25 |  | 5620 | 405
2037 | Done | University Apartments | 122 | 14799 | 142.5 |  | 2923.5 | 8156.5 | 1644 | 194 | 983.5 | 446.5 | 24 |  |  | 440145.25 | 7079 |  | 85554.75 | 240637.46 | 41886.75 | 6410 | 25492.04 | 17394.75 | 432
2038 | Done | 2nd & John | 80 | 11814.25 | 32 |  | 2141.25 | 7100 | 872.5 | 91 | 1339 | 0 |  |  |  | 324824.75 | 1667 |  | 59108.5 | 181998 | 20959 | 2740 | 38061 | 7634.5
2039 | Done | Ravello Gas Piping |  | 238 | 3 |  | 2 |  |  | 226 | 0 |  |  |  |  | 8172.25 | 159.5 |  | 72 |  |  | 7599.75 | 0
2040 | Done | Roosevelt 65th | 55 | 5454 | 44 |  | 441 | 3429.75 | 531.75 | 83 | 635.5 | 192 |  |  |  | 146699.25 | 2160 |  | 14102 | 86788 | 13510.25 | 2784 | 15056.5 | 7174
2041 | Done | Chinn California Ave Luna | 108 | 14566.5 | 100 |  | 4339 | 6131 | 1290 | 217 | 1697.5 | 424.5 | 69 |  |  | 467297.5 | 5242 |  | 145642.91 | 187351.59 | 33336 | 7098 | 53432 | 15740.5 | 2447
2042 | Done | ShelterHoldings MetroLine | 75 | 7093 | 33 |  | 361 | 4990 | 651 | 41 | 585.5 | 284.5 |  |  |  | 194340.5 | 1676 |  | 12475 | 128045 | 16956.5 | 1625.5 | 13633.5 | 12026.5
2043 | Done | Compass Aegis-Mercer Isl | 89 | 10969 | 69.5 |  | 1749.5 | 5253 | 922.5 | 275 | 1645 | 288 | 489 |  |  | 325026 | 3510.5 |  | 55409 | 146478 | 25473 | 9705 | 45112 | 10649.5 | 13291
2044 | Done | Blueprint Track 66 Apts | 78 | 7722.75 | 30.5 |  | 195.5 | 5294.75 | 741.5 | 135.5 | 991 | 249 |  |  |  | 219024.35 | 1590.75 |  | 6720 | 150429.23 | 17219.5 | 4551.5 | 23970.37 | 9685
2045 | Done | GRE Notch Apartments | 158 | 14541 | 183.5 |  | 2190.5 | 8560.5 | 2528.5 |  | 698.5 | 125 |  |  |  | 404811.73 | 9511.5 |  | 61256.25 | 227602.48 | 67247 |  | 21040.5 | 4376
2046 | Done | Marpac 4218 Roosevelt | 110 | 12479.5 | 69 |  | 1009 | 7414.5 | 1052.5 | 136.5 | 2333 | 272.5 | 20.5 |  |  | 349617.68 | 3541 |  | 30105.5 | 199226.75 | 36570 | 5168.5 | 54625.61 | 9940.82 | 722.5
2047 | Done | GRE Greenlake | 70 | 5837 | 49.5 |  | 0 | 4762 | 923.5 |  | 0 | 0 | 0 |  |  | 150690.75 | 2402 |  | 0 | 119374 | 23539.75 |  | 0 | 0 | 0
2048 | Done | GRE Greenlake | 72 | 4658.5 | 63.5 |  | 0 | 3279.5 | 1224.5 | [6 empty] | 117360.75 | 3089.5 |  | 0 | 82885.25 | 26670.5
2049 | Done | GRE Greenlake | 296 | 21791.25 | 77.5 |  | 1082 | 14406 | 3028.5 | 391 | 2253 | 371.25 | 16 |  |  | 568449.55 | 3977.5 |  | 30705 | 361459.35 | 83036.25 | 11964.5 | 55727.75 | 11736.7 | 530
2050 | Done | GRE Greenlake | 50 | 5681.5 | 26 |  | 1232.5 | 2862.5 | 503 | 178 | 473 | 254.5 |  |  |  | 163505.5 | 1419.75 |  | 36704.5 | 78450 | 12091.25 | 5268.5 | 11432.5 | 9014
2051 | Done | Vail Apartments | 163 | 18720.5 | 115.5 |  | 3250.5 | 10088 | 2738.5 | 0 | 1721.5 | 455.5 | 16 |  |  | 536090.57 | 6172.5 |  | 100944.32 | 261842.25 | 74007.5 | 10694 | 46255 | 16058 | 416
2052 | Done | Fifth & Roy | 107 | 15292.5 | 0 |  | 1840 | 7137.5 | 1130 | 103 | 4536.5 | 320 |  |  |  | 443242.25 | 5783 |  | 56187 | 201052.75 | 34751 | 4126.5 | 117138.5 | 11567
2053 | Done | Bellevue Parkside | 136 | 19334 | 27 |  | 3053 | 11273.5 | 2180.5 | 425.5 | 1563.5 | 527 | 3 |  |  | 557411.5 | 1448.5 |  | 100555.5 | 301988 | 58885.5 | 13994 | 46415.5 | 17521.5 | 106
2054 | Done | 800 5th Apartments | 68 | 8861.5 | 54 |  | 361.5 | 4894.5 | 0 | 210 | 2949.5 | 320 |  |  |  | 282896.5 | 2903.5 |  | 13215.5 | 147001.5 | 21750 | 6735 | 74881.5 | 12228
2055 | Done | Dockside Apartments | 98 | 9850.5 | 27 |  | 1055.5 | 5631 | 1020.5 | 210.5 | 1130 | 673.5 |  |  |  | 334415.5 | 1582 |  | 38666.5 | 182281.5 | 32494.5 | 7800 | 37064.5 | 28376
2056 | Done | Acme Farms | 321 | 16334 | 150 |  | 6270.5 | 0 | 3715 | 365 | 4485.5 | 814.5 |  |  |  | 1358055.41 | 8525.5 |  | 205202.75 | 802553.37 | 119715 | 12589 | 142511.29 | 35212
2057 | Done | Plaza Apartments | 111 | 7091 | 65 |  | 1401 | 3219.5 | 685.5 | 255 | 1157.5 | 138.5 |  |  |  | 221400.5 | 3488.5 |  | 45342 | 96775 | 17090.5 | 8361 | 35756 | 5049.5
2058 | Done | Howell Apartments | 77 | 8884.5 | 30.5 |  | 207 | 6483.5 | 708 | 201 | 817 | 332.5 |  |  |  | 277607.5 | 1731.5 |  | 8088 | 195332 | 25477 | 5276 | 22890 | 12628.5
2059 | Done | Meeker | 365 | 37109.75 | 194.5 |  | 5086 | 21647.5 | 5104 | 183 | 4536.75 |  | 11 |  |  | 1244296.75 | 10931.5 |  | 202776.5 | 700399 | 171108.5 | 7514 | 131285.25 |  | 284
2060 | Done | Marina Square | 270 | 27144 | 20 |  | 4791 | 13201 | 3366.5 | 435 | 3846 | 966.5 |  |  |  | 922171.59 | 1166 |  | 180227.75 | 422639.89 | 107754 | 17179.5 | 114150.95 | 47501.5
2098 | LIVE | Trailside Apartment Community Phase II | 170 | 38113.75 | 149.5 |  | 4963.5 | 22746.25 | 5979 | 490.5 | 3297 | 0 | 0 |  |  | 1532523.96 | 10219 |  | 221184.76 | 797900.1 | 222921 | 23969.5 | 120399.72 | 80791 | 0
2103 | LIVE | Northgate Station M2 | 234 | 41202.25 | 171 |  | 6583 | 24970.5 | 2992 | 430.75 | 4098.75 | 1081.25 |  |  |  | 1811122.75 | 11762 |  | 304379.75 | 1041296.25 | 132682.75 | 21237.25 | 185051 | 61170.75
2104 | LIVE | Big 1410 Apartments | 24 | 4603.25 | 63.5 |  | 290.5 | 3215.75 | 222.25 | 82.25 | 438.75 | 136.75 |  |  |  | 202081 | 4363.5 |  | 15169.5 | 132816 | 10320.5 | 3848 | 17012.5 | 9336
2105 | LIVE | Compass, 3000 Western | 219 | 49.5 |  |  | 3 |  |  |  |  | 3 |  |  |  | 3422 |  |  | 204 |  |  |  |  | 204
2106 | LIVE | Chinn, 6220 Roosevelt | 146 | 152 | 1 | [10 empty] | 9982.25 | 69
2107 | LIVE | 68th & Roosevelt | 244 | 24977.25 | 136 |  | 5672.25 | 14998 | 1 | 211.75 | 2553 | 642.25 |  |  |  | 1100218.51 | 9357 |  | 251655.25 | 646310.26 | 65 | 7647.75 | 108097.75 | 28970
2111 | LIVE | Northgate M3 | 186 | 8736.5 | 35 |  | 2241 | 5618.75 |  |  | 413.75 |  |  |  |  | 378611.38 | 2415 |  | 96312.38 | 236097 |  |  | 16804.5
2112 | LIVE | BIG3 | 20 | 2352 | 53 |  | 186.5 | 1689 | 49.75 |  | 190 | 12.75 |  |  |  | 103520.5 | 3612 |  | 8197.5 | 67991 | 2682.5 |  | 9882.75 | 535.5
2114 | LIVE | Ballard Blossom Apartments | 239 | 114.25 | [11 empty] | 7372.25
2115 | LIVE | Elowen Apartments | 201 | 26.25 | [11 empty] | 1653.75
2116 | LIVE | The V Apartments | 166 | 101 | 1 | [10 empty] | 6489 | 69
2117 | LIVE | Lachlan Apartments | 104 | 3 | [11 empty] | 197
2118 | LIVE | Exxel, Edmonds Behar | 406 | 0 | [11 empty] | 0
2119 | LIVE | The Frank (508 Fremont) |  | 0 | [11 empty] | 0
MEDIAN |  |  | 136 | 12479.5 | 53 |  | 1068.75 | 5273.875 | 872.5 | 194 | 944 | 274 | 22.25 |  |  | 324824.75 | 4164 |  | 55798 | 197279.375 | 32494.5 | 7665 | 34561.25 | 11736.7 | 626.25

## Phase Splits — Material
Phase Splits · Material
Material spend by construction phase, with original→revised→actual variance.
Job | Status | Name | Units | Mat Orig | Mat Rev | Mat Actual | Var (Orig→Act) | Condensation Actual | Fire Caulking Actual | Gas Actual | Mech Room Actual | Other Material Actual | Rough In Actual | Trim Finish Actual | Underground Actual | Water Main Actual
2001 | Done | 230 Broadway | 234 | 717142 | 717142 | 637990.88 | -11.04% |  |  | 10163.67 | 2968.89 |  | 148282.22 | 327741.23 | 73281.51 | 75553.36
2008 | Done | 101 Taylor | 258 | 1016555 | 1043740 | 816046.33 | -19.72% |  |  | 11391.29 | 2236.93 |  | 178543.02 | 429417.91 | 114008.94 | 80448.24
2009 | Done | Greenwood | 56 | 196250 | 195311 | 151064.39 | -23.02% |  |  |  | 641.45 |  | 30742.47 | 109975.66 | 9704.81 | 0
2010 | Done | Old Town | 149 | 570975 | 504680 | 282662.77 | -50.49% |  |  | 1080.05 | 1098.46 |  | 66457.52 | 174300.17 | 19726.08 | 20000.49
2011 | Done | Barrett Park | 117 | 358945 | 393359 | 295005.88 | -17.81% |  | 0 |  | 1233.58 |  | 48840.52 | 207985.82 | 21798.94 | 15147.02
2012 | Done | 8th Ave | 162 | 553400 | 561666 | 390750.86 | -29.39% |  |  | 996.32 | 22695.31 |  | 94000.7 | 212424.21 | 23669.65 | 36964.67
2015 | Done | Rooster | 197 | 841015 | 866894 | 661468.33 | -21.35% |  |  | 6984.66 | 29343.46 |  | 176561.56 | 337546.71 | 64282.61 | 46749.33
2017 | Done | 36 Stone | 119 | 534360 | 502391 | 378313.74 | -29.2% |  |  | 2769 | 8987.73 |  | 98571.05 | 192296.61 | 29784.74 | 45904.61
2018 | Done | Astro | 211 | 776247 | 722677 | 556906.77 | -28.26% |  |  | 3578.52 | 1947.18 |  | 141396.65 | 273202.23 | 88443.92 | 48338.27
2019 | Done | 8th Republic | 211 | 941700 | 974017 | 660548.93 | -29.86% |  | 0 | 4568.01 | 24175.21 |  | 176444.92 | 313722.19 | 72332.91 | 69305.69
2020 | Done | Bellevue Main | 256 | 1099380 | 997196 | 735694.62 | -33.08% |  |  | 8263.12 | 2198.97 |  | 87900.72 | 411991.97 | 103174.59 | 122165.25
2021 | Done | Admiral | 136 | 512085 | 494749 | 423924.46 | -17.22% |  | 133.04 | 3604.09 | 5.44 |  | 99695.01 | 202739.69 | 67808.6 | 49938.59
2022 | Done | Interlake | 18 | 82480 | 89109 | 60804.36 | -26.28% |  |  |  | 2510.08 |  | 20929.54 | 32656.07 | 4708.67
2023 | Done | Hadley | 209 | 900375 | 982300 | 725504.82 | -19.42% | 182.88 | 654.39 | 4873.37 | 105558.69 |  | 158305.23 | 287126.83 | 91458.15 | 77345.28
2024 | Done | Merrill Gardens | 117 | 574700 | 587857 | 336538.34 | -41.44% | 1704 |  | 4159.94 | 76386.17 |  | 75249.36 | 70943.89 | 57437.65 | 50657.33
2025 | Done | The Cora | 75 | 369935 | 376656.5 | 263607.67 | -28.74% |  |  | 1507.91 | 36585.89 |  | 58515.95 | 110946.04 | 36467.14 | 19584.74
2026 | Done | Boren | 49 | 261100 | 265270 | 194870.36 | -25.37% | 27.08 | 178.63 | 625.77 | 33752.74 |  | 42655.4 | 68397.28 | 28130.43 | 21103.03
2027 | Done | 550 Broadway | 170 | 686465 | 696496 | 548337.59 | -20.12% | 15.84 |  | 1363.51 | 99306.42 |  | 91274.89 | 220048.68 | 64724.24 | 71604.01
2028 | Done | Reserve @ Lynnwood | 296 | 826455 | 694434 | 458753.13 | -44.49% | 38.65 |  | 4382.08 | 68176.58 |  | 77241.99 | 140999.27 | 70807.97 | 97106.59
2029 | Done | Parsonage | 83 | 306800 | 310049.5 | 242874.9 | -20.84% | 13.2 |  | 1057.3 | 53061.22 |  | 63196.04 | 82322 | 17047.92 | 26177.22
2030 | Done | East Union | 144 | 713730 | 771610 | 569904.99 | -20.15% | 21.41 |  | 3056.66 | 27223.2 |  | 104992.07 | 290680.64 | 97389.7 | 46541.31
2031 | Done | Issaquah Gateway | 398 | 657109 | 642830 | 485439.43 | -26.12% | 6.64 |  | 5822.71 | 38991.48 |  | 90966.27 | 268692.84 | 32457.27 | 48502.22
2032 | Done | Luna | 71 | 204375 | 230569 | 167700.53 | -17.94% | 0 |  | 1008.16 | 11291.75 |  | 27891.8 | 98389.06 | 7694.5 | 21425.26
2033 | Done | Vuecrest | 139 | 850125 | 691518 | 460263.33 | -45.86% | 3093.95 |  | 2339.62 | 43786.76 |  | 67263.77 | 219513.43 | 56801.36 | 67464.44
2034 | Done | Park Lane | 128 | 614030 | 602753 | 419880.12 | -31.62% | 2280.11 |  | 3977.41 | 22432.91 |  | 100919.24 | 181853.14 | 52186.52 | 56230.79
2035 | Done | 162 Ten | 92 | 211875 | 210340 | 159409.61 | -24.76% | 121.8 |  |  | 7233.3 |  | 17359.05 | 96906.5 | 20442.43 | 17346.53
2036 | Done | Westridge | 31 | 102770 | 115827 | 104252.85 | 1.443% | [5 empty] | 21242.97 | 65661.22 | 7734.29 | 9614.37
2037 | Done | University Apartments | 122 | 576480 | 643201 | 487276.21 | -15.47% | 106.54 |  | 4633.76 | 24688.69 |  | 106312.24 | 273944.52 | 44531.36 | 33059.1
2038 | Done | 2nd & John | 80 | 391395 | 372182 | 268693.54 | -31.35% | 258.5 |  | 1301.17 | 13768.11 |  | 61984.15 | 116427.88 | 42713.64 | 32240.09
2039 | Done | Ravello Gas Piping |  | 10650 | 10650 | 2697.34 | -74.67% |  |  | 2667.14 |  |  | 30.2
2040 | Done | Roosevelt 65th | 55 | 173720 | 185986 | 154104.17 | -11.29% | 7.2 |  | 1504.45 | 15297.78 |  | 24915.98 | 88855.74 | 6470.34 | 17052.68
2041 | Done | Chinn California Ave Luna | 108 | 598130 | 639725 | 502616.05 | -15.97% | 0 |  | 4155.07 | 19825.43 |  | 79004.39 | 251663.7 | 85820.97 | 62146.49
2042 | Done | ShelterHoldings MetroLine | 75 | 310497 | 316790 | 250243.51 | -19.41% | 91.07 |  | 665.67 | 16059.71 |  | 62128.4 | 148333.68 | 9801.58 | 13163.4
2043 | Done | Compass Aegis-Mercer Isl | 89 | 548895 | 551921 | 320019.62 | -41.7% | 1275 |  | 3780.25 | 12806.38 |  | 30692.52 | 200687.65 | 40958.58 | 29819.24
2044 | Done | Blueprint Track 66 Apts | 78 | 262392 | 279401 | 216377.88 | -17.54% | 0 |  | 2098.38 | 15511.19 |  | 42382.13 | 133693.08 | 8593.44 | 14099.66
2045 | Done | GRE Notch Apartments | 158 | 520410 | 608708 | 497590.37 | -4.385% | 0 |  | 63.72 | 7101 |  | 97191 | 293213.41 | 34777.62 | 65243.62
2046 | Done | Marpac 4218 Roosevelt | 110 | 459229 | 493642 | 378784.06 | -17.52% |  |  | 2670.82 | 24087.86 |  | 91683.71 | 199016.45 | 21407.72 | 39917.5
2047 | Done | GRE Greenlake | 70 | 149685 | 172896 | 133195.02 | -11.02% |  |  |  | 0 |  | 56003.99 | 77180.43 | 10.6
2048 | Done | GRE Greenlake | 72 | 143792 | 151898 | 115436.54 | -19.72% | [5 empty] | 51415.82 | 64020.72 | 0 | 0
2049 | Done | GRE Greenlake | 296 | 669800 | 691822 | 618442.18 | -7.668% | 0 |  | 11428.68 | 27383.35 |  | 140166.18 | 335404.06 | 7507.03 | 96552.88
2050 | Done | GRE Greenlake | 50 | 305655 | 311905 | 204958.79 | -32.94% | 2.16 |  | 1913.88 | 10877.78 |  | 40315.08 | 111207.3 | 19986.98 | 20655.61
2051 | Done | Vail Apartments | 163 | 755185 | 673732 | 431531 | -42.86% | 0 |  | 5341.44 | 20399.37 |  | 47851.97 | 281538.12 | 33044.47 | 43355.63
2052 | Done | Fifth & Roy | 107 | 725720 | 754934 | 479362.75 | -33.95% |  |  | 6559.15 | 15179.21 | 81.68 | 87583.59 | 273004.96 | 55677.36 | 41276.8
2053 | Done | Bellevue Parkside | 136 | 785523 | 787591 | 478591.1 | -39.07% | 0 |  | 6882.96 | 20788.7 |  | 74601.11 | 287966.65 | 42888.95 | 45462.73
2054 | Done | 800 5th Apartments | 68 | 247326 | 290842 | 264321 | 6.871% |  |  | 3477.36 | 22105.44 |  | 34199.43 | 147852.36 | 38476.06 | 18210.35
2055 | Done | Dockside Apartments | 98 | 377441 | 405741 | 406456.61 | 7.687% |  |  | 4654.15 | 29539.9 |  | 84940.23 | 216460.37 | 38588.71 | 32273.25
2056 | Done | Acme Farms | 321 | 1922880 | 1931720 | 1238306.14 | -35.6% |  |  | 8134.74 | 79516.1 |  | 239543.21 | 650099 | 157337.55 | 103675.54
2057 | Done | Plaza Apartments | 111 | 419205 | 431063 | 232848.36 | -44.45% | 0 |  | 1138.79 | 7324.66 |  | 25828.61 | 141842.79 | 25991.76 | 30721.75
2058 | Done | Howell Apartments | 77 | 287240 | 299744 | 244128.93 | -15.01% |  |  | 3600.92 | 17680.02 |  | 32023.13 | 150779.38 | 23952.05 | 16093.43
2059 | Done | Meeker | 365 | 1478085 | 1516510 | 1034930.53 | -29.98% |  |  | 6691.94 | 7790.2 |  | 205612.27 | 682969.44 | 73948.12 | 57918.56
2060 | Done | Marina Square | 270 | 1739148 | 2038248 | 1009043.67 | -41.98% |  |  | 13263.56 | 69474.91 |  | 162471.68 | 539813.97 | 89415.95 | 134603.6
2098 | LIVE | Trailside Apartment Community Phase II | 170 | 2199597 | 2209412 | 1518915.7 | -30.95% |  |  | 14686.12 | 58031.73 | 1481.84 | 266624.03 | 912915.01 | 143549.66 | 121627.31
2103 | LIVE | Northgate Station M2 | 234 | 2172207 | 2387628 | 1854483.43 | -14.63% |  |  | 14023.31 | 71241.58 | 0 | 429974.35 | 971188.26 | 241274.55 | 126781.38
2104 | LIVE | Big 1410 Apartments | 24 | 530143 | 558927 | 432579.38 | -18.4% |  |  | 2063.38 | 28522.36 |  | 18939.04 | 343464.97 | 8197.14 | 31392.49
2105 | LIVE | Compass, 3000 Western | 219 | 0 | 0 | 0
2106 | LIVE | Chinn, 6220 Roosevelt | 146 | 0 | 0 | 0
2107 | LIVE | 68th & Roosevelt | 244 | 1911015 | 1930422 | 1100377.27 | -42.42% |  |  | 7204.51 | 82317.36 |  | 209687.42 | 546778.65 | 116420.07 | 137969.26
2111 | LIVE | Northgate M3 | 186 | 1590100 | 1618150 | 344768.24 | -78.32% | [5 empty] | 224000.12 | 43213.45 | 61772.15 | 15782.52
2112 | LIVE | BIG3 | 20 | 256952 | 272837 | 91340.7 | -64.45% | [5 empty] | 32236.67 | 42798.91 | 4486.52 | 11818.6
2114 | LIVE | Ballard Blossom Apartments | 239 | 0 | 0 | 0
2115 | LIVE | Elowen Apartments | 201 | 0 | 0 | 0
2116 | LIVE | The V Apartments | 166 | 0 | 0 | 0
2117 | LIVE | Lachlan Apartments | 104 | 0 | 0 | 0
2118 | LIVE | Exxel, Edmonds Behar | 406 | 0 | 0 | 0
2119 | LIVE | The Frank (508 Fremont) |  | 0 | 0 | 0
MEDIAN |  |  | 136 | 520410 | 502391 | 344768.24 | -25.37% | 15.84 | 133.04 | 3692.17 | 20594.035 | 81.68 | 77241.99 | 205362.755 | 38532.385 | 42316.215

## Crew Composition
Crew Composition · workers, FTE, wages
avg_crew_fte = total_hours / (duration × 173.33). Loaded wage adds burden (995 codes).
Job | Status | Name | Duration (mo) | Total Hrs | All Workers | Substantive (≥80h) | Avg Crew FTE | Top-5 % Hrs | Avg Days/Worker | Blended Wage | Loaded Wage | Burden Mult | OT % of Hrs | OT Hrs | Wage P25 | Wage P50 | Wage P75 | Wage P90
2001 | Done | 230 Broadway | 18 | 44632 | 28 | 25 | 14.3054 | 66.41% |  | 21.0798 | 14.42 | 0.68 | 0% | 0
2008 | Done | 101 Taylor | 15 | 59248.5 | 50 | 44 | 22.7883 | 62.35% |  | 20.0276 | 15.4 | 0.77 | 0% | 0
2009 | Done | Greenwood | 16 | 8318 | 24 | 17 | 2.9993 | 71.24% |  | 20.6703 | 14.64 | 0.71 | 0% | 0
2010 | Done | Old Town | 24 | 19847 | 23 | 14 | 4.771 | 79.86% |  | 19.3239 | 15.1 | 0.78 | 0% | 0
2011 | Done | Barrett Park | 17 | 13606 | 32 | 22 | 4.6175 | 70.85% |  | 20.3871 | 15.85 | 0.78 | 0% | 0
2012 | Done | 8th Ave | 16 | 14607.25 | 42 | 31 | 5.2671 | 35.32% | 43.6095 | 30.0264 | 30.02 | 1 | 0% | 0
2015 | Done | Rooster | 25 | 51911 | 54 | 48 | 11.9797 | 60.97% |  | 19.7337 | 16.92 | 0.86 | 0% | 0
2017 | Done | 36 Stone | 16 | 29950 | 46 | 30 | 10.7995 | 65.53% |  | 19.6695 | 14.93 | 0.76 | 0% | 0
2018 | Done | Astro | 15 | 47132 | 49 | 43 | 18.128 | 58.45% |  | 19.0439 | 14.22 | 0.75 | 0% | 0
2019 | Done | 8th Republic | 22 | 52897 | 57 | 43 | 13.8719 | 62.63% |  | 20.5868 | 15.19 | 0.74 | 0% | 0
2020 | Done | Bellevue Main | 22 | 76015 | 58 | 52 | 19.9344 | 64.08% |  | 19.6158 | 15.33 | 0.78 | 0% | 0
2021 | Done | Admiral | 19 | 41555 | 41 | 35 | 12.6182 | 64.28% |  | 22.0597 | 15.46 | 0.7 | 0% | 0
2022 | Done | Interlake | 11 | 3952 | 21 | 10 | 2.0728 | 78.64% |  | 21.9795 | 22.11 | 1.01 | 0% | 0
2023 | Done | Hadley | 22.9 | 33107 | 52 | 47 | 8.3409 | 24.39% | 24.6538 | 21.492 | 32.3012 | 1.5029 | 0.1208% | 40
2024 | Done | Merrill Gardens | 15.1 | 17098 | 40 | 28 | 6.5327 | 37.44% | 17.85 | 22.2442 | 33.717 | 1.5158 | 0.2164% | 37
2025 | Done | The Cora | 17.8 | 11488.5 | 36 | 27 | 3.7237 | 40.77% | 14.4722 | 24.3974 | 38.0013 | 1.5576 | 0.008704% | 1
2026 | Done | Boren | 16.1 | 8541.5 | 25 | 16 | 3.0608 | 71.94% | 16.24 | 24.4407 | 37.4898 | 1.5339 | 0% | 0
2027 | Done | 550 Broadway | 18.9 | 21014 | 43 | 36 | 6.4147 | 37.43% | 18.9302 | 23.1384 | 34.1239 | 1.4748 | 1.223% | 257
2028 | Done | Reserve @ Lynnwood | 12.4 | 24097 | 45 | 41 | 11.2116 | 25.31% | 19.0889 | 23.1485 | 35.8391 | 1.5482 | 0% | 0
2029 | Done | Parsonage | 14 | 7596 | 21 | 12 | 3.1303 | 69.98% | 17.7619 | 24.7136 | 37.6287 | 1.5226 | 0% | 0
2030 | Done | East Union | 20.5 | 18665 | 45 | 30 | 5.2529 | 43.85% | 16.4889 | 26.2351 | 41.0511 | 1.5647 | 2.836% | 529.25
2031 | Done | Issaquah Gateway | 31.1 | 22023 | 72 | 54 | 4.0855 | 28.67% | 26.5694 | 23.1074 | 25.6514 | 1.1101 | 1.069% | 235.5
2032 | Done | Luna | 15.6 | 5157 | 26 | 16 | 1.9072 | 61.38% | 12.6538 | 25.3991 | 39.6516 | 1.5611 | 0.3781% | 19.5
2033 | Done | Vuecrest | 24.8 | 19509 | 44 | 25 | 4.5385 | 46.77% | 19.3864 | 26.6936 | 39.7834 | 1.4904 | 0.5536% | 108
2034 | Done | Park Lane | 17.1 | 21637.75 | 45 | 36 | 7.3003 | 36.99% | 18.6222 | 24.7274 | 36.8436 | 1.49 | 0.1017% | 22
2035 | Done | 162 Ten | 16.6 | 5204.75 | 24 | 13 | 1.8089 | 69.61% | 13.25 | 25.1948 | 38.9736 | 1.5469 | 0.1585% | 8.25
2036 | Done | Westridge | 17.9 | 4098 | 30 | 10 | 1.3208 | 69.58% | 9.8333 | 27.3423 | 41.7595 | 1.5273 | 0.4392% | 18
2037 | Done | University Apartments | 26 | 14799 | 50 | 29 | 3.2839 | 42.52% | 15.04 | 29.1154 | 45.3241 | 1.5567 | 4.122% | 610
2038 | Done | 2nd & John | 22.7 | 11814.25 | 36 | 24 | 3.0027 | 41.37% | 16.1944 | 26.3938 | 40.6786 | 1.5412 | 1.094% | 129.25
2039 | Done | Ravello Gas Piping | 9.8 | 238 | 12 | 1 | 0.14011 | 84.76% | 3.4167 | 27.5371 | 52.5822 | 1.9095 | 7.353% | 17.5
2040 | Done | Roosevelt 65th | 17 | 5454 | 32 | 15 | 1.8509 | 62.5% | 10.9375 | 25.8477 | 40.8844 | 1.5817 | 3.516% | 191.75
2041 | Done | Chinn California Ave Luna |  | 14566.5 | 44 | 21 |  | 50.21% |  | 32.5752 | 66.4535 | 1.3421 | 5.938% | 865 | 23.31 | 29 | 36.98 | 47.82
2042 | Done | ShelterHoldings MetroLine |  | 7093 | 35 | 17 |  | 59.44% |  | 26.9356 | 54.9488 | 1.3421 | 1.896% | 134.5 | 17.82 | 23.8 | 32.5 | 43.34
2043 | Done | Compass Aegis-Mercer Isl |  | 10969 | 32 | 18 |  | 58.43% |  | 29.4969 | 60.1737 | 1.3421 | 3.779% | 414.5 | 18 | 23.61 | 29.95 | 44.69
2044 | Done | Blueprint Track 66 Apts |  | 7722.75 | 24 | 15 |  | 62.73% |  | 28.4915 | 58.1227 | 1.3421 | 1.256% | 97 | 19.75 | 28.63 | 42.01 | 49.64
2045 | Done | GRE Notch Apartments |  | 14541 | 39 | 29 |  | 45.73% |  | 27.4148 | 55.9263 | 1.3421 | 2.61% | 379.5 | 18 | 22 | 31.68 | 43.76
2046 | Done | Marpac 4218 Roosevelt |  | 12479.5 | 32 | 21 |  | 44.76% |  | 27.5871 | 56.2777 | 1.3421 | 4.167% | 520 | 20.5 | 27.24 | 34.5 | 46.36
2047 | Done | GRE Greenlake |  | 5837 | 33 | 17 |  | 53.45% |  | 25.1445 | 51.2948 | 1.3421 | 3.752% | 219 | 16 | 19 | 28.15 | 42.28
2048 | Done | GRE Greenlake |  | 4658.5 | 30 | 15 |  | 52.58% |  | 25.1227 | 51.2504 | 1.3421 | 7.17% | 334 | 18 | 21 | 31 | 42.39
2049 | Done | GRE Greenlake |  | 21791.25 | 58 | 36 |  | 38.51% |  | 26.1853 | 53.4181 | 1.3421 | 6.311% | 1375.25 | 18 | 23.78 | 32.1 | 44.59
2050 | Done | GRE Greenlake |  | 5681.5 | 22 | 14 |  | 67.25% |  | 28.4052 | 57.9979 | 1.3421 | 2.543% | 144.5 | 21.52 | 26 | 33.34 | 48.9
2051 | Done | Vail Apartments |  | 18720.5 | 45 | 31 |  | 35.72% |  | 27.5204 | 55.2992 | 1.3354 | 1.322% | 247.5 | 19.9 | 27 | 35.15 | 49.1
2052 | Done | Fifth & Roy |  | 15292.5 | 39 | 25 |  | 43.26% |  | 28.7792 | 58.7096 | 1.3421 | 2.54% | 388.5 | 18.25 | 26 | 32.8 | 47.94
2053 | Done | Bellevue Parkside |  | 19334 | 39 | 23 |  | 47.98% |  | 28.7533 | 56.3566 | 1.3243 | 2.113% | 408.5 | 19.3 | 25 | 31.8 | 47.83
2054 | Done | 800 5th Apartments |  | 8861.5 | 36 | 18 |  | 62.11% |  | 29.1346 | 58.4777 | 1.3349 | 2.945% | 261 | 20.25 | 27.76 | 34.78 | 51.25
2055 | Done | Dockside Apartments |  | 9850.5 | 38 | 25 |  | 51.36% |  | 33.9147 | 67.3574 | 1.3302 | 1.386% | 136.5 | 25.99 | 35.41 | 43.85 | 55.8
2056 | Done | Acme Farms |  | 16334 | 66 | 53 |  | 27.37% |  | 32.7586 | 62.2984 | 1.3108 | 0.8112% | 132.5 | 23.65 | 33 | 38 | 46.64
2057 | Done | Plaza Apartments |  | 7091 | 23 | 14 |  | 70.87% |  | 31.2139 | 63.6766 | 1.3421 | 1.777% | 126 | 21.42 | 27.39 | 35.09 | 50
2058 | Done | Howell Apartments |  | 8884.5 | 24 | 15 |  | 60.49% |  | 31.2463 | 62.5253 | 1.3336 | 0.1126% | 10 | 18 | 29.49 | 40.75 | 53.74
2059 | Done | Meeker |  | 37109.75 | 48 | 40 |  | 27.93% |  | 32.8191 | 65.6781 | 1.3336 | 0.446% | 165.5 | 22.61 | 30.5 | 36.13 | 49.65
2060 | Done | Marina Square |  | 27144 | 46 | 28 |  | 48.48% |  | 33.9049 | 67.4035 | 1.3307 | 3.352% | 910 | 27.27 | 34.54 | 43.5 | 53.92
2098 | LIVE | Trailside Apartment Community Phase II |  | 38113.75 | 79 | 56 |  | 27.54% |  | 37.9052 | 76.0236 | 1.3346 | 0.4369% | 166.5 | 22.81 | 33 | 46 | 58.2
2103 | LIVE | Northgate Station M2 |  | 41202.25 | 59 | 45 |  | 27.78% |  | 43.608 | 89.1287 | 1.3429 | 0.3234% | 133.25 | 29 | 41 | 52.5 | 61.27
2104 | LIVE | Big 1410 Apartments |  | 4603.25 | 22 | 7 |  | 87.65% |  | 43.8235 | 91.0608 | 1.3502 | 0.01086% | 0.5 | 24.74 | 36.5 | 52.75 | 64.52
2105 | LIVE | Compass, 3000 Western |  | 49.5 | 2 | 0 |  | 100% |  | 69.1313 | 147.0198 | 1.3603 | 2.02% | 1 | 68.25 | 68.5 | 68.75 | 68.9
2106 | LIVE | Chinn, 6220 Roosevelt |  | 152 | 3 | 1 |  | 100% |  | 65.6727 | 138.6268 | 1.3571 | 0% | 0 | 63.81 | 68 | 68.5 | 68.8
2107 | LIVE | 68th & Roosevelt |  | 24977.25 | 33 | 31 |  | 32.54% |  | 43.7914 | 92.883 | 1.3592 | 0.01001% | 2.5 | 33 | 44 | 54 | 61.63
2111 | LIVE | Northgate M3 | 10.8 | 8736.5 | 33 | 27 | 4.667 | 47.8% | 11.3636 | 65.8642 | 65.7687 | 0.99855 | 0.08299% | 7.25
2112 | LIVE | BIG3 | 11 | 2352 | 18 | 8 | 1.2336 | 81.44% | 9.6111 | 68.6242 | 68.6242 | 1 | 0.09566% | 2.25
2114 | LIVE | Ballard Blossom Apartments |  | 114.25 | 2 | 0 |  | 100% |  | 64.5274 | 134.2574 | 1.3508 | 0% | 0 | 61.67 | 64.11 | 66.56 | 68.02
2115 | LIVE | Elowen Apartments |  | 26.25 | 2 | 0 |  | 100% |  | 63 | 132.7653 | 1.3564 | 0% | 0 | 61.5 | 64 | 66.5 | 68
2116 | LIVE | The V Apartments |  | 101 | 2 | 0 |  | 100% |  | 64.2475 | 135.5945 | 1.357 | 0% | 0 | 61.5 | 64 | 66.5 | 68
2117 | LIVE | Lachlan Apartments |  | 3 | 2 | 0 |  | 100% |  | 65.6667 | 138.3333 | 1.3562 | 0% | 0 | 61.5 | 64 | 66.5 | 68
2118 | LIVE | Exxel, Edmonds Behar |  | 0 | 0 | 0 | [7 empty] | 0
2119 | LIVE | The Frank (508 Fremont) |  | 0 | 0 | 0 | [7 empty] | 0
MEDIAN |  |  | 17 | 12479.5 | 35 | 23 | 4.667 | 59.44% | 16.24 | 27.3423 | 51.2948 | 1.3421 | 0.3234% | 18 | 22.065 | 29.245 | 37.49 | 49.825

## Material Variance
Material Variance · takeoff calibration
The single strongest signal for the bid model. Negative = under budget.
Job | Status | Name | Units | Mat Cost | Mat Orig Bud | Mat Rev Bud | Mat Actual | Variance (Orig→Act) | Variance (Rev→Act) | Top Vendor | Top Vendor $ | Top Vendor % | Total Vendors
2001 | Done | 230 Broadway | 234 | 637990.88 | 717142 | 717142 | 637990.88 | -11.04% | -11.04% |  |  |  | 0
2008 | Done | 101 Taylor | 258 | 816046.33 | 1016555 | 1043740 | 816046.33 | -19.72% | -21.82% |  |  |  | 0
2009 | Done | Greenwood | 56 | 151064.39 | 196250 | 195311 | 151064.39 | -23.02% | -22.65% |  |  |  | 0
2010 | Done | Old Town | 149 | 282662.77 | 570975 | 504680 | 282662.77 | -50.49% | -43.99% |  |  |  | 0
2011 | Done | Barrett Park | 117 | 295005.88 | 358945 | 393359 | 295005.88 | -17.81% | -25% |  |  |  | 0
2012 | Done | 8th Ave | 162 | 390750.86 | 553400 | 561666 | 390750.86 | -29.39% | -30.43% | Keller Supply Company | 150007.88 | 38.39% | 17
2015 | Done | Rooster | 197 | 661468.33 | 841015 | 866894 | 661468.33 | -21.35% | -23.7% |  |  |  | 0
2017 | Done | 36 Stone | 119 | 378313.74 | 534360 | 502391 | 378313.74 | -29.2% | -24.7% |  |  |  | 0
2018 | Done | Astro | 211 | 556906.77 | 776247 | 722677 | 556906.77 | -28.26% | -22.94% |  |  |  | 0
2019 | Done | 8th Republic | 211 | 660548.93 | 941700 | 974017 | 660548.93 | -29.86% | -32.18% |  |  |  | 0
2020 | Done | Bellevue Main | 256 | 735694.62 | 1099380 | 997196 | 735694.62 | -33.08% | -26.22% |  |  |  | 0
2021 | Done | Admiral | 136 | 423924.46 | 512085 | 494749 | 423924.46 | -17.22% | -14.32% |  |  |  | 0
2022 | Done | Interlake | 18 | 60804.36 | 82480 | 89109 | 60804.36 | -26.28% | -31.76% |  |  |  | 0
2023 | Done | Hadley | 209 | 725504.82 | 900375 | 982300 | 725504.82 | -19.42% | -26.14% | Rosen Supply Company, Inc. $Legacy | 190637.35 | 26.28% | 31
2024 | Done | Merrill Gardens | 117 | 336538.34 | 574700 | 587857 | 336538.34 | -41.44% | -42.75% | Rosen Supply Company, Inc. $MG-Ballard | 102072.49 | 30.33% | 23
2025 | Done | The Cora | 75 | 263607.67 | 369935 | 376656.5 | 263607.67 | -28.74% | -30.01% | Keller Supply Company $Cora | 78491.13 | 29.78% | 23
2026 | Done | Boren | 49 | 194870.36 | 261100 | 265270 | 194870.36 | -25.37% | -26.54% | Rosen Supply Company, Inc. $Boren | 49659.22 | 25.48% | 13
2027 | Done | 550 Broadway | 170 | 548337.59 | 686465 | 696496 | 548337.59 | -20.12% | -21.27% | Rosen Supply Company, Inc. $550 Broadway | 130186.55 | 23.74% | 26
2028 | Done | Reserve @ Lynnwood | 296 | 458753.13 | 826455 | 694434 | 458753.13 | -44.49% | -33.94% | Ferguson Enterprises, Inc. $Reserve@Lynn | 133734.62 | 29.15% | 21
2029 | Done | Parsonage | 83 | 242874.9 | 306800 | 310049.5 | 242874.9 | -20.84% | -21.67% | Keller Supply Company $Parsonage | 96387.89 | 39.69% | 13
2030 | Done | East Union | 144 | 569904.99 | 713730 | 771610 | 569904.99 | -20.15% | -26.14% | Rosen Supply Company, Inc. $East Union | 137047.71 | 24.05% | 26
2031 | Done | Issaquah Gateway | 398 | 485439.43 | 657109 | 642830 | 485439.43 | -26.12% | -24.48% | Rosen Supply Company, Inc. $Gateway | 447211.94 | 92.13% | 28
2032 | Done | Luna | 71 | 167700.53 | 204375 | 230569 | 167700.53 | -17.94% | -27.27% | Keller Supply Co. $Roosevelt | 47765.16 | 28.48% | 16
2033 | Done | Vuecrest | 139 | 460263.33 | 850125 | 691518 | 460263.33 | -45.86% | -33.44% | Rosen Supply Company, Inc. $Vuecrest | 169567.03 | 36.84% | 25
2034 | Done | Park Lane | 128 | 419880.12 | 614030 | 602753 | 419880.12 | -31.62% | -30.34% | Rosen Supply Company, Inc. $Park Lane | 179409.27 | 42.73% | 23
2035 | Done | 162 Ten | 92 | 159409.61 | 211875 | 210340 | 159409.61 | -24.76% | -24.21% | Consolidated Supply Co. $162Ten | 63855.41 | 40.06% | 15
2036 | Done | Westridge | 31 | 104252.85 | 102770 | 115827 | 104252.85 | 1.443% | -9.993% | Ferguson Enterprises, Inc. $Westridge | 34359.22 | 32.96% | 12
2037 | Done | University Apartments | 122 | 487276.21 | 576480 | 643201 | 487276.21 | -15.47% | -24.24% | Rosen Supply Company, Inc. $University | 93793.49 | 19.25% | 26
2038 | Done | 2nd & John | 80 | 268693.54 | 391395 | 372182 | 268693.54 | -31.35% | -27.81% | Rosen Supply Company, Inc. $2nd & John | 119372.62 | 44.43% | 20
2039 | Done | Ravello Gas Piping |  | 2697.34 | 10650 | 10650 | 2697.34 | -74.67% | -74.67% | Franklin Engineering | 3337.5 | 123.7% | 4
2040 | Done | Roosevelt 65th | 55 | 154104.17 | 173720 | 185986 | 154104.17 | -11.29% | -17.14% | Keller Supply Company | 37520.04 | 24.35% | 20
2041 | Done | Chinn California Ave Luna | 108 | 502616.05 | 598130 | 639725 | 502616.05 | -15.97% | -21.43% |  |  |  | 0
2042 | Done | ShelterHoldings MetroLine | 75 | 250243.51 | 310497 | 316790 | 250243.51 | -19.41% | -21.01% |  |  |  | 0
2043 | Done | Compass Aegis-Mercer Isl | 89 | 320019.62 | 548895 | 551921 | 320019.62 | -41.7% | -42.02% |  |  |  | 0
2044 | Done | Blueprint Track 66 Apts | 78 | 216377.88 | 262392 | 279401 | 216377.88 | -17.54% | -22.56% |  |  |  | 0
2045 | Done | GRE Notch Apartments | 158 | 497590.37 | 520410 | 608708 | 497590.37 | -4.385% | -18.25% |  |  |  | 0
2046 | Done | Marpac 4218 Roosevelt | 110 | 378784.06 | 459229 | 493642 | 378784.06 | -17.52% | -23.27% |  |  |  | 0
2047 | Done | GRE Greenlake | 70 | 133195.02 | 149685 | 172896 | 133195.02 | -11.02% | -22.96% |  |  |  | 0
2048 | Done | GRE Greenlake | 72 | 115436.54 | 143792 | 151898 | 115436.54 | -19.72% | -24% |  |  |  | 0
2049 | Done | GRE Greenlake | 296 | 618442.18 | 669800 | 691822 | 618442.18 | -7.668% | -10.61% |  |  |  | 0
2050 | Done | GRE Greenlake | 50 | 204958.79 | 305655 | 311905 | 204958.79 | -32.94% | -34.29% |  |  |  | 0
2051 | Done | Vail Apartments | 163 | 431531 | 755185 | 673732 | 431531 | -42.86% | -35.95% |  |  |  | 0
2052 | Done | Fifth & Roy | 107 | 479362.75 | 725720 | 754934 | 479362.75 | -33.95% | -36.5% |  |  |  | 0
2053 | Done | Bellevue Parkside | 136 | 478591.1 | 785523 | 787591 | 478591.1 | -39.07% | -39.23% |  |  |  | 0
2054 | Done | 800 5th Apartments | 68 | 264321 | 247326 | 290842 | 264321 | 6.871% | -9.119% |  |  |  | 0
2055 | Done | Dockside Apartments | 98 | 406456.61 | 377441 | 405741 | 406456.61 | 7.687% | 0.1764% |  |  |  | 0
2056 | Done | Acme Farms | 321 | 1238306.14 | 1922880 | 1931720 | 1238306.14 | -35.6% | -35.9% |  |  |  | 0
2057 | Done | Plaza Apartments | 111 | 232848.36 | 419205 | 431063 | 232848.36 | -44.45% | -45.98% |  |  |  | 0
2058 | Done | Howell Apartments | 77 | 244128.93 | 287240 | 299744 | 244128.93 | -15.01% | -18.55% |  |  |  | 0
2059 | Done | Meeker | 365 | 1034930.53 | 1478085 | 1516510 | 1034930.53 | -29.98% | -31.76% |  |  |  | 0
2060 | Done | Marina Square | 270 | 1009043.67 | 1739148 | 2038248 | 1009043.67 | -41.98% | -50.49% |  |  |  | 0
2098 | LIVE | Trailside Apartment Community Phase II | 170 | 1518915.7 | 2199597 | 2209412 | 1518915.7 | -30.95% | -31.25% |  |  |  | 0
2103 | LIVE | Northgate Station M2 | 234 | 1854483.43 | 2172207 | 2387628 | 1854483.43 | -14.63% | -22.33% |  |  |  | 0
2104 | LIVE | Big 1410 Apartments | 24 | 432579.38 | 530143 | 558927 | 432579.38 | -18.4% | -22.61% |  |  |  | 0
2105 | LIVE | Compass, 3000 Western | 219 | 0 | 0 | 0 | 0 | [5 empty] | 0
2106 | LIVE | Chinn, 6220 Roosevelt | 146 | 0 | 0 | 0 | 0 | [5 empty] | 0
2107 | LIVE | 68th & Roosevelt | 244 | 1100377.27 | 1911015 | 1930422 | 1100377.27 | -42.42% | -43% |  |  |  | 0
2111 | LIVE | Northgate M3 | 186 | 344768.24 | 1590100 | 1618150 | 344768.24 | -78.32% | -78.69% |  |  |  | 0
2112 | LIVE | BIG3 | 20 | 91340.7 | 256952 | 272837 | 91340.7 | -64.45% | -66.52% |  |  |  | 0
2114 | LIVE | Ballard Blossom Apartments | 239 | 0 | 0 | 0 | 0 | [5 empty] | 0
2115 | LIVE | Elowen Apartments | 201 | 0 | 0 | 0 | 0 | [5 empty] | 0
2116 | LIVE | The V Apartments | 166 | 0 | 0 | 0 | 0 | [5 empty] | 0
2117 | LIVE | Lachlan Apartments | 104 | 0 | 0 | 0 | 0 | [5 empty] | 0
2118 | LIVE | Exxel, Edmonds Behar | 406 | 0 | 0 | 0 | 0 | [5 empty] | 0
2119 | LIVE | The Frank (508 Fremont) |  | 0 | 0 | 0 | 0 | [5 empty] | 0
MEDIAN |  |  | 136 | 344768.24 | 520410 | 502391 | 344768.24 | -25.37% | -26.14% |  | 102072.49 | 30.33% | 0
P25 (best 25%) | [7 empty] | -33.95% | -33.94%
P75 (worst 25%) | [7 empty] | -17.54% | -22.33%

## Bid Calibration
Bid Calibration · benchmark inputs for the bidding tool
Computed from completed (non-live) jobs with sufficient signal. Use these to seed the bid model.
Productivity (per plumbing unit)
Metric | N | P25 | Median | P75 | Mean | Min | Max | Notes
Hours per unit | 50 | 93.9379 | 123.4295 | 154.4867 | 136.5598 | 50.8847 | 305.5515
Labor $ per unit | 50 | 2064.0275 | 3076.6684 | 3613.7606 | 2905.7194 | 1221.2201 | 4326.8287
Material $ per unit | 50 | 2645.4142 | 3166.7379 | 3515.8398 | 3060.8531 | 1219.6971 | 4653.8523
Revenue per unit | 50 | 10227.2509 | 13147.3483 | 15937.0548 | 13113.947 | 7039.4286 | 22802.137
Cost share of revenue
Metric | N | P25 | Median | P75 | Mean | Min | Max | Notes
Labor % of revenue | 50 | 19.44% | 21.65% | 25.38% | 22.19% | 10.89% | 33.55%
Material % of revenue | 50 | 21.27% | 23.46% | 26.3% | 23.96% | 9.357% | 38.32%
Gross margin % | 37 | 33.91% | 41.39% | 47.69% | 40.98% | 14.48% | 78.23%
Throughput
Metric | N | P25 | Median | P75 | Mean | Min | Max | Notes
Hours per month | 30 | 528.0088 | 868.7231 | 1976.5898 | 1276.398 | 228.9385 | 3949.9
Units per month | 30 | 4.4668 | 7.0911 | 9.7244 | 7.8479 | 1.6364 | 23.871
Avg crew FTE | 30 | 3.0463 | 5.012 | 11.4036 | 7.364 | 1.3208 | 22.7883
Duration (months) | 30 | 15.9 | 17.45 | 22.175 | 18.75 | 11 | 31.1
Wages & burden
Metric | N | P25 | Median | P75 | Mean | Min | Max | Notes
Blended wage ($/hr) | 50 | 22.0396 | 25.6234 | 28.7598 | 25.7048 | 19.0439 | 33.9147
Fully-loaded wage ($/hr) | 50 | 24.766 | 40.231 | 56.7669 | 40.8588 | 14.22 | 67.4035
Burden multiplier | 50 | 1.0075 | 1.3421 | 1.5061 | 1.2537 | 0.68 | 1.5817
OT % of hours | 50 | 0% | 0.4998% | 2.56% | 1.441% | 0% | 7.17%
Top-5 % concentration | 50 | 41.22% | 55.94% | 64.59% | 53.19% | 24.39% | 79.86%
Variance (orig budget → actual)
Metric | N | P25 | Median | P75 | Mean | Min | Max | Notes
Labor variance | 50 | -15.03% | -4.974% | 12.87% | -1.96% | -40.43% | 42.15%
Material variance | 50 | -32.98% | -23.89% | -17.44% | -24.33% | -50.49% | 7.687%
Variance (revised budget → actual)
Metric | N | P25 | Median | P75 | Mean | Min | Max | Notes
Labor variance | 50 | -18.27% | -7.045% | 7.776% | -5.101% | -40.12% | 39.42%
Material variance | 50 | -32.5% | -24.85% | -21.61% | -26.44% | -50.49% | 0.1764%
How to use these numbers
• Default the bid model to the MEDIAN row for each metric. P25/P75 give the credible range — bids outside that band should require explicit justification.
• Material variance is the sharpest calibration: a typical OWP job comes in ~25% under original takeoff. The bid model can either tighten the takeoff by ~25% on a like-for-like job, or hold the cushion as a declared margin contribution.
• Hours per unit varies by project type more than productivity — segment by GC and unit type before applying medians to a new bid (residential apartment vs. mixed-use vs. senior living differ meaningfully). The Per-Job Rollup sheet has GC and project name for that segmentation.
• Live jobs (yellow rows in other sheets) are excluded here because their hours/dollars are partial — including them would understate productivity and inflate variance.
• Cortex (the cross-job intelligence layer) carries the narrative version of these numbers; this sheet is the structured input.

## Cost Code Calibration
Cost Code Calibration · per-code benchmarks
One row per OWP cost code, aggregated across completed jobs (≥1,500 hrs). Use for line-item bid calibration.
Code | Category | Phase | Description | N Jobs | Hrs P25 | Hrs Median | Hrs P75 | Actual $ P25 | Actual $ Median | Actual $ P75 | Orig Bud P25 | Orig Bud Median | Orig Bud P75 | Var(O→A) P25 | Var(O→A) Med | Var(O→A) P75 | Var(R→A) Med | Hrs/Unit Med | $/Unit Med | Total $ (sum) | Total Hrs (sum)
011 | labor | underground | DS & RD Labor | 7 | 183 | 183 | 183 | 1645 | 3752.5 | 11671.12 | 3250 | 12500 | 33300 | -75.02% | -69.98% | -34.46% | -69.98% | 1.1296 | 23.1636 | 46076.3 | 183
100 | labor | supervision | Supervision | 50 | 44.75 | 71 | 133.5 | 2385.625 | 4181.15 | 7465 | 6982.5 | 10270 | 13517.5 | -73.08% | -53.04% | -31.84% | -53.84% | 0.7118 | 37.257 | 314457.3 | 4441
101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 50 | 142.75 | 226.75 | 306.5 | 6143.25 | 10791 | 16969.5 | 9695 | 13450 | 20216.25 | -47.18% | -30.55% | -0.16% | -31.58% | 1.9566 | 93.8227 | 835251.3 | 12995.25
110 | labor | underground | Underground Labor | 48 | 149.5 | 263.25 | 507.625 | 5174.8275 | 7744.25 | 15372.625 | 6740 | 12657.5 | 18545 | -51.61% | -21.22% | 6.72% | -33.48% | 2.7033 | 70.796 | 876271.93 | 21480
111 | labor | underground | Garage Labor | 44 | 714 | 1617 | 2618 | 21274.25 | 39498.945 | 64719 | 30900 | 51800 | 93610 | -33.44% | -14.12% | 13.56% | -15.37% | 10.9206 | 274.6223 | 2512229.34 | 65852.25
112 | labor | underground | Canout Labor | 44 | 132.5 | 283.75 | 434.5 | 4637 | 9508.75 | 13848.75 | 5500 | 9355 | 15768.75 | -42.33% | -20.39% | 5.84% | -21.13% | 2.4468 | 65.611 | 677432.27 | 14523.25
113 | labor | underground | Foundation Drain Labor | 8 | 50 | 50 | 50 | 960 | 2063.5 | 2745.75 | 2012 | 2843 | 6625 | -64.55% | -27.82% | 0% | -45.19% | 0.3086 | 10.3085 | 15070.66 | 50
120 | labor | rough_in | Roughin Labor | 50 | 4828.25 | 7100 | 10942.5 | 116095.47 | 191341.795 | 291795.5625 | 97668.25 | 184702.5 | 261938.75 | -10.57% | 10.16% | 24.33% | 7.72% | 66.5333 | 1642.3086 | 13960956.29 | 371795.75
130 | labor | trim_finish | Finish Labor | 50 | 719.75 | 1130 | 2169 | 20351.0625 | 32915.25 | 51210.14 | 23186.25 | 31760 | 48870 | -17.39% | -2.28% | 11.81% | -3.45% | 11.4746 | 289.813 | 2395734.05 | 66278.75
140 | labor | gas | Gas Labor | 42 | 134 | 210.25 | 357.875 | 5014.25 | 7732.5 | 10916.125 | 5875 | 7625 | 9750 | -34.41% | -12.02% | 23.93% | -18.45% | 1.8583 | 61.6609 | 439878.88 | 9771.75
141 | labor | water_main | Water Main/Insulation Lab | 47 | 804.25 | 1394.625 | 2313 | 19505.5 | 36651.38 | 54625.61 | 26867.5 | 36300 | 52285 | -43.71% | -16.36% | 24.64% | -21.27% | 11.5426 | 273.7545 | 2432183.43 | 73200.75
142 | labor | mech_room | Mech Room Labor | 46 | 268 | 363.125 | 502.625 | 7519.375 | 11881.6 | 15819.875 | 7000 | 12030 | 17125 | -28.72% | -1.5% | 53.2% | -4.97% | 3.2141 | 96.9733 | 761418.06 | 15796.75
143 | labor | condensation | Condensation Drains Labor | 14 | 14.75 | 30.5 | 580.375 | 383 | 813.75 | 15117.125 | [6 empty] | 942.7% | 0.1557 | 3.5532 | 94335.5 | 3738.5
145 | labor | trim_finish | Tub/Shower Labor | 7 | 338 | 338 | 338 | 101.5 | 373 | 6781 | 19800 | 19800 | 19800 | -65.75% | -65.75% | -65.75% | -65.75% | 2.0864 | 2.5034 | 17239.5 | 338
150 | labor | warranty | Warranty Labor | 13 | 1.75 | 3 | 8.5 | 76.75 | 137.5 | 331.5 | [6 empty] | 15.62% | 0.0267 | 1.0667 | 30043.63 | 66.5
151 | labor | unmapped_labor | T&M Labor | 1 | 3 | 3 | 3 | 187.5 | 187.5 | 187.5 | [7 empty] | 0.06 | 3.75 | 1458.75 | 30.75
039 | material | underground | DS & RD Material | 7 |  |  |  | 1134.76 | 2380.94 | 10684.8 | 3856.25 | 14700 | 40867.5 | -79.4% | -71.08% | -65.82% | -71.08% |  | 20.0079 | 47045.49
210 | material | underground | Underground Material | 48 |  |  |  | 3690.345 | 8302.975 | 14401.4575 | 7080 | 12850 | 22331.25 | -58.94% | -33.04% | -8.41% | -41.73% |  | 68.0859 | 727477.06 | 462
211 | material | underground | Garage Material | 48 |  |  |  | 6708.295 | 18509.48 | 33694.2475 | 27110 | 42025 | 77592.5 | -66.35% | -47.12% | -21.48% | -48.78% |  | 145.2387 | 1400242.86
212 | material | underground | Canout Material | 46 |  |  |  | 5038.445 | 8039.075 | 11751.2425 | 6350 | 9310 | 18754 | -41.04% | -28.32% | -7.7% | -29.67% |  | 66.9966 | 603632.54
213 | material | underground | Foundation Material | 9 |  |  |  | 1052.3 | 2839.07 | 4518.55 | 2343.75 | 10275 | 11716.25 | -66.54% | -41.53% | -8.45% | -38.92% |  | 15.2314 | 32708.52
220 | material | rough_in | Roughin Material | 50 |  |  |  | 42587.0825 | 76245.675 | 101937.4475 | 58165 | 117385 | 197602.5 | -41.76% | -28.3% | -17.54% | -29.51% |  | 656.6416 | 5425782.58
230 | material | trim_finish | Finish Material | 50 |  |  |  | 111141.985 | 201713.67 | 287336.785 | 141795 | 246220.5 | 343859.25 | -29.74% | -14.03% | -1.7% | -19.58% |  | 1615.7484 | 13949815.52
240 | material | gas | Gas Material | 43 |  |  |  | 1504.45 | 3604.09 | 5822.71 | 5500 | 7350 | 10500 | -71.54% | -58.5% | -30.69% | -62.52% |  | 25.3419 | 222178.49
241 | material | water_main | Water Main/Insulation Mat | 46 |  |  |  | 20991.175 | 44409.18 | 65798.825 | 32873.75 | 51300 | 71237.5 | -36.51% | -19.97% | 4.31% | -22.55% |  | 323.0902 | 2634132.11
242 | material | mech_room | Mech Room Material | 47 |  |  |  | 7324.66 | 19825.43 | 29539.9 | 12000 | 22500 | 57907.5 | -61.05% | -24.6% | 14.56% | -25.36% |  | 159.0387 | 1441148.62
243 | material | condensation | Condensation Drains Mat | 17 |  |  |  | 14.52 | 91.07 | 766.75 | [6 empty] | 34.87% |  | 0.8733 | 9246.03
244 | material | fire_caulking | Fire Caulking Material | 3 |  |  |  | 178.63 | 178.63 | 178.63 | [8 empty] | 3.1311 | 966.06
245 | material | trim_finish | Tub/Shower Material | 5 |  |  |  | 592.03 | 653.01 | 1581.805 | 2600 | 2600 | 2600 | -79.36% | -79.36% | -79.36% | -79.36% |  | 4.3453 | 5000.68
251 | material | unmapped_material | T&M Material | 1 |  |  |  | 81.68 | 81.68 | 81.68 | [8 empty] | 0.7634 | 169.51
600 | overhead | overhead | Subcontractor | 49 |  |  |  | 1638.5 | 4653.75 | 16267.82 | 1000 | 1000 | 3850 | -49.74% | 106% | 488% | 12.34% |  | 50 | 561066.13
601 | overhead | overhead | Engineering/Plans | 46 |  |  |  | 9429.095 | 20176.78 | 37617.9375 | 17875 | 28500 | 46250 | -40.61% | -18.68% | 11.18% | -19.59% |  | 244.7214 | 1711208.26
602 | overhead | overhead | Rental Equipment | 28 |  |  |  | 629.525 | 2235 | 5311.1775 | 3000 | 5000 | 8060 | -73.95% | -32.81% | 37.42% | -18.36% |  | 15.4861 | 158508.9
603 | overhead | overhead | Permits & Licenses | 45 |  |  |  | 1979.13 | 6197.36 | 11027.865 | 5382.5 | 9110 | 17695 | -37.37% | -19.03% | -9.41% | -19.1% |  | 63.9636 | 537380.77
604 | overhead | overhead | Backcharges | 2 |  |  |  | 17940.355 | 17940.355 | 17940.355 | [8 empty] | 123.8769 | 35880.71
607 | overhead | overhead | Other Expenses | 34 |  |  |  | 546.175 | 5381.1 | 8980.4075 | 7000 | 10000 | 11750 | -75.21% | -38.26% | -14.76% | -36.42% |  | 59.6652 | 356490.86
995 | burden | burden | Payroll Burden | 49 |  |  |  | 87036.795 | 155266.79 | 220021.58 | 90942.055 | 167567.61 | 228764.445 | -17.4% | -4.71% | 12.5% | -5.7% |  | 1322.8975 | 10731471.06
998 | tax | tax | Payroll Taxes | 49 |  |  |  | 15198.92 | 26782.71 | 41213.335 | 15575.595 | 28904 | 41125.635 | -15.12% | -4.64% | 11.45% | -6.54% |  | 243.4792 | 1917699.96
999 | sales | sales | Sales | 37 |  |  |  | -2337934 | -1721867 | -886915 | -2384904.5 | -1648500 | -865350 | 1.64% | 3.19% | 6.99% | 0% |  | -13505.7097 | -89131447.88
310 | other | other | Flats Underground Labor | 2 | 2118.75 | 2118.75 | 2118.75 | 101967.5 | 101967.5 | 101967.5 | 143266 | 143266 | 143266 | -28.83% | -28.83% | -28.83% | -26.29% | 5.3698 | 256.1997 | 101967.5 | 4237.5
320 | other | other | Flats Roughin Labor | 1 | 21198.75 | 21198.75 | 21198.75 | 452849.38 | 452849.38 | 452849.38 | 423275 | 423275 | 423275 | 6.99% | 6.99% | 6.99% | 0.81% | 53.2632 | 1137.8125 | 452849.38 | 21198.75
330 | other | other | Flats Finish Labor | 1 | 4717 | 4717 | 4717 | 118040 | 118040 | 118040 | 117750 | 117750 | 117750 | 0.25% | 0.25% | 0.25% | -0.25% | 11.8518 | 296.5829 | 118040 | 4717
410 | other | other | Flats Underground Mat | 1 |  |  |  | 50431.67 | 50431.67 | 50431.67 | 58800 | 58800 | 58800 | -14.23% | -14.23% | -14.23% | 33.39% |  | 126.7127 | 50431.67
420 | other | other | Flats Roughin Material | 1 |  |  |  | 200867.48 | 200867.48 | 200867.48 | 259245 | 259245 | 259245 | -22.52% | -22.52% | -22.52% | -26.74% |  | 504.6922 | 200867.48
430 | other | other | Flats Finish Material | 1 |  |  |  | 373687.67 | 373687.67 | 373687.67 | 460418 | 460418 | 460418 | -18.84% | -18.84% | -18.84% | -20.55% |  | 938.9137 | 373687.67
800 | other | other | Office Time | 1 | 4 | 4 | 4 | 208 | 208 | 208 | [7 empty] | 0.08 | 4.16 | 208 | 4
997 | other | other | Employee Benefits | 2 | 8 | 8 | 8 | 164 | 164 | 164 | [7 empty] | 0.091 | 1.6921 | 328 | 16
How to read
Coverage |  |  | N Jobs ≥ 20 → reliable benchmark. Codes with low N (≤10 jobs) shown for completeness but should not anchor bid defaults.
Variance |  |  | Negative Var(O→A) = actual came in UNDER original budget (cushion). Positive = over budget. Medians color-coded green↔red.
Hours columns blank |  |  | Material codes (200s) and overhead/burden/tax/sales codes do not carry direct labor hours — those columns blank by design.
Bid mapping |  |  | For a new bid: use Median row as the default; flag anything outside the P25–P75 band as a sanity check failure.
Headline finding |  |  | Rough-in labor (120) is the only major labor code that runs OVER budget at the median (+10%). Every other labor code is underrun. Material codes are systematically underrun (~−14% to −47%).

## Cost Code Detail
Cost Code Detail · long table
One row per (job, code). Filter or pivot to drill into any code or job.
Job | Status | Schema | Units | Code | Category | Phase | Description | Total Hrs | OT Hrs | Actual $ | Original Bud $ | Revised Bud $ | Var (O→A) | Var (R→A) | Hrs/Unit | Actual $/Unit
2001 | Done | SUPABASE | 234 | 011 | labor | underground | DS & RD Labor |  |  | 21823.68 | 33300 | 33300 | -34.46% | -34.46% |  | 93.2636
2008 | Done | SUPABASE | 258 | 011 | labor | underground | DS & RD Labor |  |  | 11671.12 | 46715 | 46715 | -75.02% | -75.02% |  | 45.2369
2009 | Done | SUPABASE | 56 | 011 | labor | underground | DS & RD Labor |  |  | 1645 | 1250 | 1250 | 31.6% | 31.6% |  | 29.375
2010 | Done | SUPABASE | 149 | 011 | labor | underground | DS & RD Labor |  |  | 2137 | 7590 | 7590 | -71.84% | -71.84% |  | 14.3423
2011 | Done | SUPABASE | 117 | 011 | labor | underground | DS & RD Labor |  |  | 1008 | 3250 | 3250 | -68.98% | -68.98% |  | 8.6154
2012 | Done | SUPABASE | 162 | 011 | labor | underground | DS & RD Labor | 183 |  | 3752.5 | 12500 | 12500 | -69.98% | -69.98% | 1.1296 | 23.1636
2018 | Done | SUPABASE | 211 | 011 | labor | underground | DS & RD Labor |  |  | 4039 | 17545 | 19105 | -76.98% | -78.86% |  | 19.1422
2107 | LIVE | V2.2 | 244 | 011 | labor | underground | DS & RD Labor
2001 | Done | SUPABASE | 234 | 100 | labor | supervision | Supervision |  |  | 4198.3 | 11000 | 11000 | -61.83% | -61.83% |  | 17.9415
2008 | Done | SUPABASE | 258 | 100 | labor | supervision | Supervision |  |  | 8811.5 | 11600 | 11915 | -24.04% | -26.05% |  | 34.1531
2009 | Done | SUPABASE | 56 | 100 | labor | supervision | Supervision |  |  | 2992 | 3000 | 3000 | -0.2667% | -0.2667% |  | 53.4286
2010 | Done | SUPABASE | 149 | 100 | labor | supervision | Supervision |  |  | 4944 | 10430 | 10430 | -52.6% | -52.6% |  | 33.1812
2011 | Done | SUPABASE | 117 | 100 | labor | supervision | Supervision |  |  | 4164 | 8190 | 8190 | -49.16% | -49.16% |  | 35.5897
2012 | Done | SUPABASE | 162 | 100 | labor | supervision | Supervision | 165 |  | 6023 | 8100 | 8100 | -25.64% | -25.64% | 1.0185 | 37.179
2015 | Done | SUPABASE | 197 | 100 | labor | supervision | Supervision |  |  | 7355 | 11820 | 12360 | -37.77% | -40.49% |  | 37.335
2017 | Done | SUPABASE | 119 | 100 | labor | supervision | Supervision |  |  | 4744 | 6500 | 6500 | -27.02% | -27.02% |  | 39.8655
2018 | Done | SUPABASE | 211 | 100 | labor | supervision | Supervision |  |  | 7795 | 10000 | 10000 | -22.05% | -22.05% |  | 36.9431
2019 | Done | SUPABASE | 211 | 100 | labor | supervision | Supervision |  |  | 13841.5 | 14700 | 18480 | -5.84% | -25.1% |  | 65.5995
2020 | Done | SUPABASE | 256 | 100 | labor | supervision | Supervision |  |  | 13026.5 | 12800 | 13700 | 1.77% | -4.916% |  | 50.8848
2021 | Done | SUPABASE | 136 | 100 | labor | supervision | Supervision |  |  | 8726 | 12920 | 13414 | -32.46% | -34.95% |  | 64.1618
2022 | Done | SUPABASE | 18 | 100 | labor | supervision | Supervision |  |  | 1042 | 3000 | 3000 | -65.27% | -65.27% |  | 57.8889
2023 | Done | V1 | 209 | 100 | labor | supervision | Supervision | 308.5 |  | 13424.5 | 14630 | 15828 | -8.24% | -15.19% | 1.4761 | 64.2321
2024 | Done | V1 | 117 | 100 | labor | supervision | Supervision | 295 |  | 12228.5 | 14000 | 14800 | -12.65% | -17.38% | 2.5214 | 104.5171
2025 | Done | V1 | 75 | 100 | labor | supervision | Supervision | 95 |  | 4337 | 7875 | 8157 | -44.93% | -46.83% | 1.2667 | 57.8267
2026 | Done | V1 | 49 | 100 | labor | supervision | Supervision | 45.5 |  | 2078.5 | 7840 | 7840 | -73.49% | -73.49% | 0.92857 | 42.4184
2027 | Done | V1 | 170 | 100 | labor | supervision | Supervision | 124.5 |  | 5755.5 | 11000 | 11188 | -47.68% | -48.56% | 0.73235 | 33.8559
2028 | Done | V1 | 296 | 100 | labor | supervision | Supervision | 209.5 |  | 9454.5 | 20000 | 10499 | -52.73% | -9.949% | 0.70777 | 31.9409
2029 | Done | V1 | 83 | 100 | labor | supervision | Supervision | 71.5 |  | 3269.5 | 8700 | 8747 | -62.42% | -62.62% | 0.86145 | 39.3916
2030 | Done | V1 | 144 | 100 | labor | supervision | Supervision | 102.5 |  | 4994.5 | 14400 | 16050 | -65.32% | -68.88% | 0.71181 | 34.684
2031 | Done | V1 | 398 | 100 | labor | supervision | Supervision | 459 |  | 21845.5 | 57900 | 59438 | -62.27% | -63.25% | 1.1533 | 54.8882
2032 | Done | V1 | 71 | 100 | labor | supervision | Supervision | 62.5 |  | 2980.5 | 6390 | 6531 | -53.36% | -54.36% | 0.88028 | 41.9789
2033 | Done | V1 | 139 | 100 | labor | supervision | Supervision | 47.5 |  | 2336.5 | 11120 | 12269 | -78.99% | -80.96% | 0.34173 | 16.8094
2034 | Done | V1 | 128 | 100 | labor | supervision | Supervision | 72 |  | 3636.5 | 13440 | 14536 | -72.94% | -74.98% | 0.5625 | 28.4102
2035 | Done | V1 | 92 | 100 | labor | supervision | Supervision | 95 |  | 4434 | 9200 | 9200 | -51.8% | -51.8% | 1.0326 | 48.1957
2036 | Done | V1 | 31 | 100 | labor | supervision | Supervision | 71 |  | 3394 | 5120 | 5220 | -33.71% | -34.98% | 2.2903 | 109.4839
2037 | Done | V1 | 122 | 100 | labor | supervision | Supervision | 142.5 |  | 7079 | 10110 | 11810 | -29.98% | -40.06% | 1.168 | 58.0246
2038 | Done | V1 | 80 | 100 | labor | supervision | Supervision | 32 |  | 1667 | 7460 | 7660 | -77.65% | -78.24% | 0.4 | 20.8375
2039 | Done | V1 |  | 100 | labor | supervision | Supervision | 3 |  | 159.5 | 1128 | 1128 | -85.86% | -85.86%
2040 | Done | V1 | 55 | 100 | labor | supervision | Supervision | 44 |  | 2160 | 5225 | 5225 | -58.66% | -58.66% | 0.8 | 39.2727
2041 | Done | V2.2 | 108 | 100 | labor | supervision | Supervision | 100 |  | 5242 | 8640 | 9440 | -39.33% | -44.47% | 0.92593 | 48.537
2042 | Done | V2.2 | 75 | 100 | labor | supervision | Supervision | 33 |  | 1676 | 5760 | 5760 | -70.9% | -70.9% | 0.44 | 22.3467
2043 | Done | V2.2 | 89 | 100 | labor | supervision | Supervision | 69.5 |  | 3510.5 | 12900 | 13200 | -72.79% | -73.41% | 0.7809 | 39.4438
2044 | Done | V2.2 | 78 | 100 | labor | supervision | Supervision | 30.5 |  | 1590.75 | 6750 | 6750 | -76.43% | -76.43% | 0.39103 | 20.3942
2045 | Done | V2.2 | 158 | 100 | labor | supervision | Supervision | 183.5 |  | 9511.5 | 12640 | 13040 | -24.75% | -27.06% | 1.1614 | 60.1994
2046 | Done | V2.2 | 110 | 100 | labor | supervision | Supervision | 69 |  | 3541 | 13750 | 14050 | -74.25% | -74.8% | 0.62727 | 32.1909
2047 | Done | V2.2 | 70 | 100 | labor | supervision | Supervision | 49.5 |  | 2402 | 4200 | 4250 | -42.81% | -43.48% | 0.70714 | 34.3143
2048 | Done | V2.2 | 72 | 100 | labor | supervision | Supervision | 63.5 |  | 3089.5 | 4320 | 4420 | -28.48% | -30.1% | 0.88194 | 42.9097
2049 | Done | V2.2 | 296 | 100 | labor | supervision | Supervision | 77.5 |  | 3977.5 | 15000 | 15200 | -73.48% | -73.83% | 0.26182 | 13.4375
2050 | Done | V2.2 | 50 | 100 | labor | supervision | Supervision | 26 |  | 1419.75 | 7000 | 7050 | -79.72% | -79.86% | 0.52 | 28.395
2051 | Done | V2.2 | 163 | 100 | labor | supervision | Supervision | 115.5 |  | 6172.5 | 16300 | 16550 | -62.13% | -62.7% | 0.70859 | 37.8681
2052 | Done | V2.2 | 107 | 100 | labor | supervision | Supervision |  |  | 5783 | 10700 | 11000 | -45.95% | -47.43% |  | 54.0467
2053 | Done | V2.2 | 136 | 100 | labor | supervision | Supervision | 27 |  | 1448.5 | 10800 | 10900 | -86.59% | -86.71% | 0.19853 | 10.6507
2054 | Done | V2.2 | 68 | 100 | labor | supervision | Supervision | 54 |  | 2903.5 | 6120 | 6220 | -52.56% | -53.32% | 0.79412 | 42.6985
2055 | Done | V2.2 | 98 | 100 | labor | supervision | Supervision | 27 |  | 1582 | 7920 | 8920 | -80.03% | -82.26% | 0.27551 | 16.1429
2056 | Done | V2.2 | 321 | 100 | labor | supervision | Supervision | 150 |  | 8525.5 | 38520 | 38620 | -77.87% | -77.92% | 0.46729 | 26.5592
2057 | Done | V2.2 | 111 | 100 | labor | supervision | Supervision | 65 |  | 3488.5 | 9630 | 9980 | -63.77% | -65.05% | 0.58559 | 31.4279
2058 | Done | V2.2 | 77 | 100 | labor | supervision | Supervision | 30.5 |  | 1731.5 | 6930 | 6980 | -75.01% | -75.19% | 0.3961 | 22.487
2059 | Done | V2.2 | 365 | 100 | labor | supervision | Supervision | 194.5 |  | 10931.5 | 24225 | 24225 | -54.88% | -54.88% | 0.53288 | 29.9493
2060 | Done | V2.2 | 270 | 100 | labor | supervision | Supervision | 20 |  | 1166 | 39900 | 39900 | -97.08% | -97.08% | 0.074074 | 4.3185
2098 | LIVE | V2.2 | 170 | 100 | labor | supervision | Supervision | 149.5 |  | 10219 | 12750 | 13000 | -19.85% | -21.39% | 0.87941 | 60.1118
2103 | LIVE | V2.2 | 234 | 100 | labor | supervision | Supervision | 171 |  | 11762 | 15210 | 16210 | -22.67% | -27.44% | 0.73077 | 50.265
2104 | LIVE | V2.2 | 24 | 100 | labor | supervision | Supervision | 63.5 |  | 4363.5 | 2400 | 2400 | 81.81% | 81.81% | 2.6458 | 181.8125
2106 | LIVE | V2.2 | 146 | 100 | labor | supervision | Supervision | 1 |  | 69 |  |  |  |  | 0.0068493 | 0.4726
2107 | LIVE | V2.2 | 244 | 100 | labor | supervision | Supervision | 136 |  | 9357 | 12200 | 12700 | -23.3% | -26.32% | 0.55738 | 38.3484
2111 | LIVE | V_TX | 186 | 100 | labor | supervision | Supervision | 35 |  | 2415 | 12090 | 12090 | -80.02% | -80.02% | 0.18817 | 12.9839
2112 | LIVE | V_TX | 20 | 100 | labor | supervision | Supervision | 53 |  | 3612 | 2000 | 2000 | 80.6% | 80.6% | 2.65 | 180.6
2116 | LIVE | V2.2 | 166 | 100 | labor | supervision | Supervision | 1 |  | 69 | 9628 | 9628 | -99.28% | -99.28% | 0.0060241 | 0.41566
2001 | Done | SUPABASE | 234 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor |  |  | 1227.8 | 11000 | 11000 | -88.84% | -88.84% |  | 5.247
2008 | Done | SUPABASE | 258 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor |  |  | 15093.5 | 10300 | 11560 | 46.54% | 30.57% |  | 58.5019
2009 | Done | SUPABASE | 56 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor |  |  | 1324 | 2500 | 2500 | -47.04% | -47.04% |  | 23.6429
2010 | Done | SUPABASE | 149 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor |  |  | 4286 | 7450 | 7450 | -42.47% | -42.47% |  | 28.7651
2011 | Done | SUPABASE | 117 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor |  |  | 3513 | 5850 | 5850 | -39.95% | -39.95% |  | 30.0256
2012 | Done | SUPABASE | 162 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 172.5 |  | 6161.5 | 12150 | 12150 | -49.29% | -49.29% | 1.0648 | 38.034
2015 | Done | SUPABASE | 197 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor |  |  | 16582.5 | 13790 | 15790 | 20.25% | 5.019% |  | 84.1751
2017 | Done | SUPABASE | 119 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor |  |  | 7873 | 6500 | 7300 | 21.12% | 7.849% |  | 66.1597
2018 | Done | SUPABASE | 211 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor |  |  | 9680 | 10000 | 10440 | -3.2% | -7.28% |  | 45.8768
2019 | Done | SUPABASE | 211 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor |  |  | 27212.5 | 14700 | 26068 | 85.12% | 4.39% |  | 128.9692
2020 | Done | SUPABASE | 256 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor |  |  | 18552.5 | 15360 | 17310 | 20.78% | 7.178% |  | 72.4707
2021 | Done | SUPABASE | 136 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor |  |  | 19430.5 | 12920 | 13887 | 50.39% | 39.92% |  | 142.8713
2022 | Done | SUPABASE | 18 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor |  |  | 2957.5 | 5100 | 5450 | -42.01% | -45.73% |  | 164.3056
2023 | Done | V1 | 209 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 683.5 |  | 29564 | 14630 | 19827 | 102.1% | 49.11% | 3.2703 | 141.4545
2024 | Done | V1 | 117 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 471.5 |  | 20381.5 | 20800 | 21407 | -2.012% | -4.79% | 4.0299 | 174.2009
2025 | Done | V1 | 75 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 255 |  | 11865 | 11250 | 11820 | 5.467% | 0.3807% | 3.4 | 158.2
2026 | Done | V1 | 49 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 130 |  | 5998 | 7840 | 7840 | -23.49% | -23.49% | 2.6531 | 122.4082
2027 | Done | V1 | 170 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 289.5 |  | 13422.5 | 20400 | 20823 | -34.2% | -35.54% | 1.7029 | 78.9559
2028 | Done | V1 | 296 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 380 |  | 17076 | 35400 | 18154 | -51.76% | -5.938% | 1.2838 | 57.6892
2029 | Done | V1 | 83 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 203.5 |  | 9512.5 | 13700 | 13896 | -30.57% | -31.55% | 2.4518 | 114.6084
2030 | Done | V1 | 144 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 392 |  | 19747 | 23040 | 25090 | -14.29% | -21.3% | 2.7222 | 137.1319
2031 | Done | V1 | 398 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 661.5 |  | 32080.5 | 79800 | 85062 | -59.8% | -62.29% | 1.6621 | 80.6043
2032 | Done | V1 | 71 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 166 |  | 8067.5 | 10295 | 10765 | -21.64% | -25.06% | 2.338 | 113.6268
2033 | Done | V1 | 139 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 271.5 |  | 13253 | 20155 | 22018 | -34.24% | -39.81% | 1.9532 | 95.3453
2034 | Done | V1 | 128 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 286.5 |  | 14099 | 21120 | 22880 | -33.24% | -38.38% | 2.2383 | 110.1484
2035 | Done | V1 | 92 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 197.5 |  | 9333 | 9200 | 9450 | 1.446% | -1.238% | 2.1467 | 101.4457
2036 | Done | V1 | 31 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 123 |  | 6121.5 | 5760 | 6060 | 6.276% | 1.015% | 3.9677 | 197.4677
2037 | Done | V1 | 122 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 279.5 |  | 15008.5 | 18425 | 20125 | -18.54% | -25.42% | 2.291 | 123.0205
2038 | Done | V1 | 80 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 228 |  | 11937.5 | 11600 | 12550 | 2.909% | -4.88% | 2.85 | 149.2188
2039 | Done | V1 |  | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 7 |  | 341 | 1128 | 1128 | -69.77% | -69.77%
2040 | Done | V1 | 55 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 96 |  | 5076.5 | 8250 | 8250 | -38.47% | -38.47% | 1.7455 | 92.3
2041 | Done | V2.2 | 108 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 297 |  | 16934 | 15120 | 16020 | 12% | 5.705% | 2.75 | 156.7963
2042 | Done | V2.2 | 75 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 147 |  | 7902.5 | 10440 | 10440 | -24.31% | -24.31% | 1.96 | 105.3667
2043 | Done | V2.2 | 89 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 277.5 |  | 15398 | 20900 | 21200 | -26.33% | -27.37% | 3.118 | 173.0112
2044 | Done | V2.2 | 78 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 85 |  | 4858 | 10875 | 10875 | -55.33% | -55.33% | 1.0897 | 62.2821
2045 | Done | V2.2 | 158 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 254.5 |  | 13778 | 19750 | 20150 | -30.24% | -31.62% | 1.6108 | 87.2025
2046 | Done | V2.2 | 110 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 172 |  | 9717 | 19250 | 19700 | -49.52% | -50.68% | 1.5636 | 88.3364
2047 | Done | V2.2 | 70 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 102 |  | 5375 | 8750 | 9000 | -38.57% | -40.28% | 1.4571 | 76.7857
2048 | Done | V2.2 | 72 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 91 |  | 4715.5 | 9000 | 9200 | -47.61% | -48.74% | 1.2639 | 65.4931
2049 | Done | V2.2 | 296 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 165 |  | 9262.5 | 25000 | 25500 | -62.95% | -63.68% | 0.55743 | 31.2922
2050 | Done | V2.2 | 50 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 149 |  | 8937.5 | 9000 | 9050 | -0.6944% | -1.243% | 2.98 | 178.75
2051 | Done | V2.2 | 163 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 335 |  | 19701 | 24400 | 25450 | -19.26% | -22.59% | 2.0552 | 120.865
2052 | Done | V2.2 | 107 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 225.5 |  | 12636.5 | 18190 | 20540 | -30.53% | -38.48% | 2.1075 | 118.0981
2053 | Done | V2.2 | 136 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 281 |  | 16497 | 19575 | 19675 | -15.72% | -16.15% | 2.0662 | 121.3015
2054 | Done | V2.2 | 68 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 72 |  | 4181.5 | 9860 | 9960 | -57.59% | -58.02% | 1.0588 | 61.4926
2055 | Done | V2.2 | 98 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 102.5 |  | 6150.5 | 13200 | 14700 | -53.41% | -58.16% | 1.0459 | 62.7602
2056 | Done | V2.2 | 321 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 531 |  | 31609 | 64200 | 64300 | -50.76% | -50.84% | 1.6542 | 98.4704
2057 | Done | V2.2 | 111 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 169 |  | 9538 | 13910 | 14210 | -31.43% | -32.88% | 1.5225 | 85.9279
2058 | Done | V2.2 | 77 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 105 |  | 6184.5 | 11165 | 11215 | -44.61% | -44.86% | 1.3636 | 80.3182
2059 | Done | V2.2 | 365 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 347 |  | 19998 | 30200 | 30200 | -33.78% | -33.78% | 0.95068 | 54.789
2060 | Done | V2.2 | 270 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 504.5 |  | 30723 | 66500 | 81000 | -53.8% | -62.07% | 1.8685 | 113.7889
2098 | LIVE | V2.2 | 170 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 480 |  | 28199 | 29750 | 30000 | -5.213% | -6.003% | 2.8235 | 165.8765
2103 | LIVE | V2.2 | 234 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 855.25 |  | 52674 | 40950 | 50300 | 28.63% | 4.72% | 3.6549 | 225.1026
2104 | LIVE | V2.2 | 24 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 153.5 |  | 9215 | 4800 | 4800 | 91.98% | 91.98% | 6.3958 | 383.9583
2105 | LIVE | V2.2 | 219 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 43.5 | 1 | 3014 |  |  |  |  | 0.19863 | 13.7626
2106 | LIVE | V2.2 | 146 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 151 |  | 9913.25 |  |  |  |  | 1.0342 | 67.899
2107 | LIVE | V2.2 | 244 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 763 |  | 48115.5 | 40260 | 45160 | 19.51% | 6.545% | 3.127 | 197.1947
2111 | LIVE | V_TX | 186 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 428 |  | 26982.5 | 32550 | 36150 | -17.1% | -25.36% | 2.3011 | 145.0672
2112 | LIVE | V_TX | 20 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 171 |  | 10619.25 | 6000 | 7000 | 76.99% | 51.7% | 8.55 | 530.9625
2114 | LIVE | V2.2 | 239 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 114.25 |  | 7372.25 |  |  |  |  | 0.47803 | 30.8462
2115 | LIVE | V2.2 | 201 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 26.25 |  | 1653.75 |  |  |  |  | 0.1306 | 8.2276
2116 | LIVE | V2.2 | 166 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 100 |  | 6420 | 25398 | 25398 | -74.72% | -74.72% | 0.60241 | 38.6747
2117 | LIVE | V2.2 | 104 | 101 | labor | takeoff_purchase | Takeoff & Purchase Labor | 3 |  | 197 |  |  |  |  | 0.028846 | 1.8942
2001 | Done | SUPABASE | 234 | 110 | labor | underground | Underground Labor |  |  | 5128.27 | 6500 | 6500 | -21.1% | -21.1% |  | 21.9157
2008 | Done | SUPABASE | 258 | 110 | labor | underground | Underground Labor |  |  | 7757.5 | 5440 | 5440 | 42.6% | 42.6% |  | 30.0678
2009 | Done | SUPABASE | 56 | 110 | labor | underground | Underground Labor |  |  | 4209 | 5350 | 5350 | -21.33% | -21.33% |  | 75.1607
2010 | Done | SUPABASE | 149 | 110 | labor | underground | Underground Labor |  |  | 959 | 3820 | 3820 | -74.9% | -74.9% |  | 6.4362
2011 | Done | SUPABASE | 117 | 110 | labor | underground | Underground Labor |  |  | 6703 | 13150 | 13150 | -49.03% | -49.03% |  | 57.2906
2012 | Done | SUPABASE | 162 | 110 | labor | underground | Underground Labor | 145.5 |  | 3184.25 | 5800 | 5800 | -45.1% | -45.1% | 0.89815 | 19.6559
2015 | Done | SUPABASE | 197 | 110 | labor | underground | Underground Labor |  |  | 7731 | 6080 | 7830 | 27.15% | -1.264% |  | 39.2437
2017 | Done | SUPABASE | 119 | 110 | labor | underground | Underground Labor |  |  | 6900 | 8538 | 8538 | -19.18% | -19.18% |  | 57.9832
2018 | Done | SUPABASE | 211 | 110 | labor | underground | Underground Labor |  |  | 8108.75 | 9330 | 9330 | -13.09% | -13.09% |  | 38.4301
2019 | Done | SUPABASE | 211 | 110 | labor | underground | Underground Labor |  |  | 11835 | 12700 | 12700 | -6.811% | -6.811% |  | 56.09
2020 | Done | SUPABASE | 256 | 110 | labor | underground | Underground Labor |  |  | 16803.75 | 16160 | 16760 | 3.984% | 0.261% |  | 65.6396
2021 | Done | SUPABASE | 136 | 110 | labor | underground | Underground Labor |  |  | 21121.15 | 12625 | 18310 | 67.3% | 15.35% |  | 155.3026
2022 | Done | SUPABASE | 18 | 110 | labor | underground | Underground Labor |  |  | 8667 | 6210 | 6910 | 39.57% | 25.43% |  | 481.5
2023 | Done | V1 | 209 | 110 | labor | underground | Underground Labor | 1086.5 | 19 | 25629.12 | 18865 | 27189 | 35.86% | -5.737% | 5.1986 | 122.6274
2024 | Done | V1 | 117 | 110 | labor | underground | Underground Labor | 297 | 37 | 7558 | 13300 | 13300 | -43.17% | -43.17% | 2.5385 | 64.5983
2025 | Done | V1 | 75 | 110 | labor | underground | Underground Labor | 211 | 1 | 6790.5 | 12250 | 13447.5 | -44.57% | -49.5% | 2.8133 | 90.54
2026 | Done | V1 | 49 | 110 | labor | underground | Underground Labor | 104 |  | 2899.5 | 5450 | 5450 | -46.8% | -46.8% | 2.1224 | 59.1735
2027 | Done | V1 | 170 | 110 | labor | underground | Underground Labor | 264 |  | 7711 | 12100 | 12017 | -36.27% | -35.83% | 1.5529 | 45.3588
2028 | Done | V1 | 296 | 110 | labor | underground | Underground Labor | 962 |  | 24769 | 54560 | 53331 | -54.6% | -53.56% | 3.25 | 83.6791
2029 | Done | V1 | 83 | 110 | labor | underground | Underground Labor | 450 |  | 12604 | 11700 | 12114.5 | 7.726% | 4.041% | 5.4217 | 151.8554
2030 | Done | V1 | 144 | 110 | labor | underground | Underground Labor | 143.5 |  | 4496.5 | 9400 | 10618 | -52.16% | -57.65% | 0.99653 | 31.2257
2031 | Done | V1 | 398 | 110 | labor | underground | Underground Labor | 238.5 |  | 5913 | 34660 | 35728 | -82.94% | -83.45% | 0.59925 | 14.8568
2032 | Done | V1 | 71 | 110 | labor | underground | Underground Labor | 231 |  | 6693 | 6720 | 8170 | -0.4018% | -18.08% | 3.2535 | 94.2676
2033 | Done | V1 | 139 | 110 | labor | underground | Underground Labor | 761.5 |  | 24211 | 18900 | 20923 | 28.1% | 15.71% | 5.4784 | 174.1799
2034 | Done | V1 | 128 | 110 | labor | underground | Underground Labor | 161.5 |  | 5597 | 5200 | 6576 | 7.635% | -14.89% | 1.2617 | 43.7266
2035 | Done | V1 | 92 | 110 | labor | underground | Underground Labor | 174.5 |  | 5630.5 | 12690 | 12690 | -55.63% | -55.63% | 1.8967 | 61.2011
2036 | Done | V1 | 31 | 110 | labor | underground | Underground Labor | 400.5 | 1.5 | 11913.5 | 6800 | 10340 | 75.2% | 15.22% | 12.9194 | 384.3065
2037 | Done | V1 | 122 | 110 | labor | underground | Underground Labor | 390 |  | 12034.5 | 15920 | 20680 | -24.41% | -41.81% | 3.1967 | 98.6434
2038 | Done | V1 | 80 | 110 | labor | underground | Underground Labor | 169.25 | 2.25 | 5314.5 | 10620 | 11115 | -49.96% | -52.19% | 2.1156 | 66.4313
2040 | Done | V1 | 55 | 110 | labor | underground | Underground Labor | 80 |  | 2443 | 5515 | 5515 | -55.7% | -55.7% | 1.4545 | 44.4182
2041 | Done | V2.2 | 108 | 110 | labor | underground | Underground Labor | 312.5 | 12 | 11895 | 14780 | 17300 | -19.52% | -31.24% | 2.8935 | 110.1389
2042 | Done | V2.2 | 75 | 110 | labor | underground | Underground Labor | 249 |  | 8776.5 | 20608 | 20608 | -57.41% | -57.41% | 3.32 | 117.02
2043 | Done | V2.2 | 89 | 110 | labor | underground | Underground Labor | 596 | 16.5 | 20109.5 | 35740 | 39130 | -43.73% | -48.61% | 6.6966 | 225.9494
2044 | Done | V2.2 | 78 | 110 | labor | underground | Underground Labor | 97 | 1 | 3411.5 | 17585 | 17585 | -80.6% | -80.6% | 1.2436 | 43.7372
2045 | Done | V2.2 | 158 | 110 | labor | underground | Underground Labor | 1098 | 44.5 | 31316 | 23250 | 44430 | 34.69% | -29.52% | 6.9494 | 198.2025
2046 | Done | V2.2 | 110 | 110 | labor | underground | Underground Labor | 82.5 |  | 2915 | 15775 | 16585 | -81.52% | -82.42% | 0.75 | 26.5
2049 | Done | V2.2 | 296 | 110 | labor | underground | Underground Labor | 436.5 | 13 | 12882 | 12900 | 20040 | -0.1395% | -35.72% | 1.4747 | 43.5203
2050 | Done | V2.2 | 50 | 110 | labor | underground | Underground Labor | 131.5 | 4 | 4762.5 | 10200 | 11310 | -53.31% | -57.89% | 2.63 | 95.25
2051 | Done | V2.2 | 163 | 110 | labor | underground | Underground Labor | 520 | 12 | 17320 | 21500 | 18940 | -19.44% | -8.553% | 3.1902 | 106.2577
2052 | Done | V2.2 | 107 | 110 | labor | underground | Underground Labor | 382.5 | 7 | 13156 | 25825 | 27925 | -49.06% | -52.89% | 3.5748 | 122.9533
2053 | Done | V2.2 | 136 | 110 | labor | underground | Underground Labor | 470.5 |  | 16111.5 | 13206 | 15488 | 22% | 4.026% | 3.4596 | 118.4669
2054 | Done | V2.2 | 68 | 110 | labor | underground | Underground Labor | 185.5 | 7 | 7369 | 12885 | 14055 | -42.81% | -47.57% | 2.7279 | 108.3676
2055 | Done | V2.2 | 98 | 110 | labor | underground | Underground Labor | 262.5 |  | 11833.5 | 9150 | 9150 | 29.33% | 29.33% | 2.6786 | 120.75
2056 | Done | V2.2 | 321 | 110 | labor | underground | Underground Labor | 1020 | 46 | 37974.25 | 38820 | 44224 | -2.179% | -14.13% | 3.1776 | 118.2998
2057 | Done | V2.2 | 111 | 110 | labor | underground | Underground Labor | 81 |  | 2949 | 9000 | 9000 | -67.23% | -67.23% | 0.72973 | 26.5676
2058 | Done | V2.2 | 77 | 110 | labor | underground | Underground Labor | 93 | 9 | 3766 | 3760 | 4280 | 0.1596% | -12.01% | 1.2078 | 48.9091
2059 | Done | V2.2 | 365 | 110 | labor | underground | Underground Labor | 2167 | 126 | 78123 | 76650 | 83790 | 1.922% | -6.763% | 5.937 | 214.0356
2060 | Done | V2.2 | 270 | 110 | labor | underground | Underground Labor | 678.5 | 5 | 27494.5 | 63020 | 67110 | -56.37% | -59.03% | 2.513 | 101.8315
2098 | LIVE | V2.2 | 170 | 110 | labor | underground | Underground Labor | 1516 | 6 | 71186.76 | 100467 | 100967 | -29.14% | -29.5% | 8.9176 | 418.7456
2103 | LIVE | V2.2 | 234 | 110 | labor | underground | Underground Labor | 2149.25 |  | 95456 | 53163 | 75888 | 79.55% | 25.79% | 9.1848 | 407.9316
2104 | LIVE | V2.2 | 24 | 110 | labor | underground | Underground Labor | 164.5 |  | 8973.5 | 7125 | 7125 | 25.94% | 25.94% | 6.8542 | 373.8958
2105 | LIVE | V2.2 | 219 | 110 | labor | underground | Underground Labor | 3 |  | 204 |  |  |  |  | 0.013699 | 0.93151
2107 | LIVE | V2.2 | 244 | 110 | labor | underground | Underground Labor | 708 |  | 31475 | 28400 | 30400 | 10.83% | 3.536% | 2.9016 | 128.9959
2111 | LIVE | V_TX | 186 | 110 | labor | underground | Underground Labor | 1619 | 1.25 | 67299.13 | 43000 | 48100 | 56.51% | 39.92% | 8.7043 | 361.8233
2112 | LIVE | V_TX | 20 | 110 | labor | underground | Underground Labor | 186.5 |  | 8197.5 | 4950 | 4950 | 65.61% | 65.61% | 9.325 | 409.875
2001 | Done | SUPABASE | 234 | 111 | labor | underground | Garage Labor |  |  | 51832.47 | 37860 | 37860 | 36.91% | 36.91% |  | 221.5063
2008 | Done | SUPABASE | 258 | 111 | labor | underground | Garage Labor |  |  | 38324.13 | 44625 | 44625 | -14.12% | -14.12% |  | 148.5431
2009 | Done | SUPABASE | 56 | 111 | labor | underground | Garage Labor |  |  | 9872 | 8960 | 8960 | 10.18% | 10.18% |  | 176.2857
2010 | Done | SUPABASE | 149 | 111 | labor | underground | Garage Labor |  |  | 28821.5 | 39100 | 39100 | -26.29% | -26.29% |  | 193.4329
2011 | Done | SUPABASE | 117 | 111 | labor | underground | Garage Labor |  |  | 10199 | 16200 | 16200 | -37.04% | -37.04% |  | 87.1709
2012 | Done | SUPABASE | 162 | 111 | labor | underground | Garage Labor | 872 |  | 19353.5 | 14600 | 14600 | 32.56% | 32.56% | 5.3827 | 119.466
2015 | Done | SUPABASE | 197 | 111 | labor | underground | Garage Labor |  |  | 50128.5 | 55870 | 67410 | -10.28% | -25.64% |  | 254.4594
2017 | Done | SUPABASE | 119 | 111 | labor | underground | Garage Labor |  |  | 29981 | 38180 | 38670 | -21.47% | -22.47% |  | 251.9412
2018 | Done | SUPABASE | 211 | 111 | labor | underground | Garage Labor |  |  | 33852.25 | 71700 | 71700 | -52.79% | -52.79% |  | 160.4372
2019 | Done | SUPABASE | 211 | 111 | labor | underground | Garage Labor |  |  | 65168.5 | 80400 | 84100 | -18.94% | -22.51% |  | 308.8555
2020 | Done | SUPABASE | 256 | 111 | labor | underground | Garage Labor |  |  | 142441 | 114350 | 118946 | 24.57% | 19.75% |  | 556.4102
2021 | Done | SUPABASE | 136 | 111 | labor | underground | Garage Labor |  |  | 40673.76 | 46180 | 48780 | -11.92% | -16.62% |  | 299.0718
2023 | Done | V1 | 209 | 111 | labor | underground | Garage Labor | 4461 | 1 | 84983.82 | 121140 | 123844 | -29.85% | -31.38% | 21.3445 | 406.6211
2024 | Done | V1 | 117 | 111 | labor | underground | Garage Labor | 2754 |  | 66691 | 85500 | 91072 | -22% | -26.77% | 23.5385 | 570.0085
2025 | Done | V1 | 75 | 111 | labor | underground | Garage Labor | 1617 |  | 41214 | 34540 | 35841 | 19.32% | 14.99% | 21.56 | 549.52
2026 | Done | V1 | 49 | 111 | labor | underground | Garage Labor | 870 |  | 22565 | 13550 | 13550 | 66.53% | 66.53% | 17.7551 | 460.5102
2027 | Done | V1 | 170 | 111 | labor | underground | Garage Labor | 1976.5 |  | 53390.5 | 62140 | 62140 | -14.08% | -14.08% | 11.6265 | 314.0618
2028 | Done | V1 | 296 | 111 | labor | underground | Garage Labor | 1862 |  | 46509 | 108000 | 109292 | -56.94% | -57.45% | 6.2905 | 157.125
2029 | Done | V1 | 83 | 111 | labor | underground | Garage Labor | 34 |  | 848 |  |  |  |  | 0.40964 | 10.2169
2030 | Done | V1 | 144 | 111 | labor | underground | Garage Labor | 3139.5 | 57.5 | 83224.5 | 110300 | 123843 | -24.55% | -32.8% | 21.8021 | 577.9479
2031 | Done | V1 | 398 | 111 | labor | underground | Garage Labor | 2482 | 4 | 62078.5 | 38740 | 38740 | 60.24% | 60.24% | 6.2362 | 155.9761
2033 | Done | V1 | 139 | 111 | labor | underground | Garage Labor | 1826.5 | 6 | 49382 | 62725 | 53811 | -21.27% | -8.231% | 13.1403 | 355.2662
2034 | Done | V1 | 128 | 111 | labor | underground | Garage Labor | 4024.5 |  | 99278.5 | 53325 | 58468 | 86.18% | 69.8% | 31.4414 | 775.6133
2035 | Done | V1 | 92 | 111 | labor | underground | Garage Labor | 521.75 | 2.75 | 15337 | 16050 | 16050 | -4.442% | -4.442% | 5.6712 | 166.7065
2037 | Done | V1 | 122 | 111 | labor | underground | Garage Labor | 2025 | 0.5 | 57346.75 | 55665 | 57225 | 3.021% | 0.2128% | 16.5984 | 470.0553
2038 | Done | V1 | 80 | 111 | labor | underground | Garage Labor | 1695 | 8.5 | 44370.5 | 34205 | 39485 | 29.72% | 12.37% | 21.1875 | 554.6313
2040 | Done | V1 | 55 | 111 | labor | underground | Garage Labor | 274 | 13 | 8649.5 |  | 850 |  | 917.6% | 4.9818 | 157.2636
2041 | Done | V2.2 | 108 | 111 | labor | underground | Garage Labor | 3647.5 | 147 | 120082.91 | 92270 | 107770 | 30.14% | 11.43% | 33.7731 | 1111.8788
2043 | Done | V2.2 | 89 | 111 | labor | underground | Garage Labor | 863.5 | 8 | 25234.5 | 51800 | 53120 | -51.28% | -52.5% | 9.7022 | 283.5337
2044 | Done | V2.2 | 78 | 111 | labor | underground | Garage Labor | 4 |  | 200 |  |  |  |  | 0.051282 | 2.5641
2045 | Done | V2.2 | 158 | 111 | labor | underground | Garage Labor | 937.5 | 49.5 | 24709.25 | 31020 | 42943 | -20.34% | -42.46% | 5.9335 | 156.3877
2046 | Done | V2.2 | 110 | 111 | labor | underground | Garage Labor | 749 | 4 | 21002 | 28850 | 31010 | -27.2% | -32.27% | 6.8091 | 190.9273
2047 | Done | V2.2 | 70 | 111 | labor | underground | Garage Labor
2049 | Done | V2.2 | 296 | 111 | labor | underground | Garage Labor | 645.5 | 3 | 17823 | 109290 | 109830 | -83.69% | -83.77% | 2.1807 | 60.2128
2050 | Done | V2.2 | 50 | 111 | labor | underground | Garage Labor | 1010 | 12 | 28655 | 30780 | 32040 | -6.904% | -10.56% | 20.2 | 573.1
2051 | Done | V2.2 | 163 | 111 | labor | underground | Garage Labor | 2309.5 | 109 | 70146.5 | 123400 | 102722 | -43.16% | -31.71% | 14.1687 | 430.3466
2052 | Done | V2.2 | 107 | 111 | labor | underground | Garage Labor | 1168.5 | 58 | 33231 | 110040 | 113215 | -69.8% | -70.65% | 10.9206 | 310.5701
2053 | Done | V2.2 | 136 | 111 | labor | underground | Garage Labor | 1955 | 15 | 63370.5 | 67077 | 67077 | -5.526% | -5.526% | 14.375 | 465.9596
2054 | Done | V2.2 | 68 | 111 | labor | underground | Garage Labor | 117 | 6 | 3588 | 7113 | 7113 | -49.56% | -49.56% | 1.7206 | 52.7647
2055 | Done | V2.2 | 98 | 111 | labor | underground | Garage Labor | 679 |  | 22091 | 18890 | 21890 | 16.95% | 0.9182% | 6.9286 | 225.4184
2056 | Done | V2.2 | 321 | 111 | labor | underground | Garage Labor | 4350 |  | 135710.5 | 191150 | 192900 | -29% | -29.65% | 13.5514 | 422.7741
2057 | Done | V2.2 | 111 | 111 | labor | underground | Garage Labor | 1063.5 |  | 32824 | 31350 | 36848 | 4.702% | -10.92% | 9.5811 | 295.7117
2058 | Done | V2.2 | 77 | 111 | labor | underground | Garage Labor | 41 |  | 1242 | 12325 | 12815 | -89.92% | -90.31% | 0.53247 | 16.1299
2059 | Done | V2.2 | 365 | 111 | labor | underground | Garage Labor | 2919 |  | 96984.5 | 94950 | 96520 | 2.143% | 0.4812% | 7.9973 | 265.711
2060 | Done | V2.2 | 270 | 111 | labor | underground | Garage Labor | 3027 | 1.5 | 110765.25 | 271830 | 291758 | -59.25% | -62.04% | 11.2111 | 410.2417
2098 | LIVE | V2.2 | 170 | 111 | labor | underground | Garage Labor | 2639.5 |  | 112004.5 | 116833 | 117133 | -4.133% | -4.378% | 15.5265 | 658.85
2103 | LIVE | V2.2 | 234 | 111 | labor | underground | Garage Labor | 3498.5 |  | 167884.75 | 109938 | 136288 | 52.71% | 23.18% | 14.9509 | 717.4562
2104 | LIVE | V2.2 | 24 | 111 | labor | underground | Garage Labor | 56 |  | 2268 | 5000 | 5000 | -54.64% | -54.64% | 2.3333 | 94.5
2107 | LIVE | V2.2 | 244 | 111 | labor | underground | Garage Labor | 3508.75 |  | 153773.75 | 74554 | 90954 | 106.3% | 69.07% | 14.3801 | 630.2203
2111 | LIVE | V_TX | 186 | 111 | labor | underground | Garage Labor | 228.25 |  | 12122.25 | 38250 | 43250 | -68.31% | -71.97% | 1.2272 | 65.1734
2001 | Done | SUPABASE | 234 | 112 | labor | underground | Canout Labor |  |  | 9995.05 | 12751 | 12751 | -21.61% | -21.61% |  | 42.7139
2008 | Done | SUPABASE | 258 | 112 | labor | underground | Canout Labor |  |  | 29831.5 | 42255 | 42255 | -29.4% | -29.4% |  | 115.626
2009 | Done | SUPABASE | 56 | 112 | labor | underground | Canout Labor |  |  | 1485.5 | 2000 | 2000 | -25.72% | -25.72% |  | 26.5268
2010 | Done | SUPABASE | 149 | 112 | labor | underground | Canout Labor |  |  | 2982.25 | 6650 | 6650 | -55.15% | -55.15% |  | 20.0151
2011 | Done | SUPABASE | 117 | 112 | labor | underground | Canout Labor |  |  | 2062 | 3640 | 3640 | -43.35% | -43.35% |  | 17.6239
2012 | Done | SUPABASE | 162 | 112 | labor | underground | Canout Labor | 238 |  | 5424 | 11700 | 11700 | -53.64% | -53.64% | 1.4691 | 33.4815
2015 | Done | SUPABASE | 197 | 112 | labor | underground | Canout Labor |  |  | 10087.5 | 12300 | 12860 | -17.99% | -21.56% |  | 51.2056
2017 | Done | SUPABASE | 119 | 112 | labor | underground | Canout Labor |  |  | 4602 | 5130 | 5130 | -10.29% | -10.29% |  | 38.6723
2018 | Done | SUPABASE | 211 | 112 | labor | underground | Canout Labor |  |  | 5609.75 | 10400 | 10400 | -46.06% | -46.06% |  | 26.5865
2019 | Done | SUPABASE | 211 | 112 | labor | underground | Canout Labor |  |  | 47229 | 44800 | 48150 | 5.422% | -1.913% |  | 223.8341
2020 | Done | SUPABASE | 256 | 112 | labor | underground | Canout Labor |  |  | 16515.5 | 16000 | 16100 | 3.222% | 2.581% |  | 64.5137
2021 | Done | SUPABASE | 136 | 112 | labor | underground | Canout Labor |  |  | 9421.18 | 8500 | 8500 | 10.84% | 10.84% |  | 69.2734
2023 | Done | V1 | 209 | 112 | labor | underground | Canout Labor | 825 | 14 | 16227.22 | 15000 | 15000 | 8.181% | 8.181% | 3.9474 | 77.6422
2024 | Done | V1 | 117 | 112 | labor | underground | Canout Labor | 231 |  | 5878.5 | 9400 | 9400 | -37.46% | -37.46% | 1.9744 | 50.2436
2025 | Done | V1 | 75 | 112 | labor | underground | Canout Labor | 278.5 |  | 8821 | 6950 | 6950 | 26.92% | 26.92% | 3.7133 | 117.6133
2026 | Done | V1 | 49 | 112 | labor | underground | Canout Labor | 327 |  | 9448.5 | 4375 | 4375 | 116% | 116% | 6.6735 | 192.8265
2027 | Done | V1 | 170 | 112 | labor | underground | Canout Labor | 573 |  | 16373 | 15450 | 15450 | 5.974% | 5.974% | 3.3706 | 96.3118
2028 | Done | V1 | 296 | 112 | labor | underground | Canout Labor | 469 |  | 12283 | 11700 | 11775 | 4.983% | 4.314% | 1.5845 | 41.4966
2029 | Done | V1 | 83 | 112 | labor | underground | Canout Labor | 188 |  | 5435 | 6800 | 6800 | -20.07% | -20.07% | 2.2651 | 65.4819
2030 | Done | V1 | 144 | 112 | labor | underground | Canout Labor | 373.75 | 3.75 | 10888 | 13900 | 20455 | -21.67% | -46.77% | 2.5955 | 75.6111
2031 | Done | V1 | 398 | 112 | labor | underground | Canout Labor | 380 |  | 11258.5 | 9310 | 9310 | 20.93% | 20.93% | 0.95477 | 28.2877
2033 | Done | V1 | 139 | 112 | labor | underground | Canout Labor | 414 |  | 12268.5 | 6450 | 6533 | 90.21% | 87.79% | 2.9784 | 88.2626
2034 | Done | V1 | 128 | 112 | labor | underground | Canout Labor | 439 |  | 13910 | 6250 | 7465 | 122.6% | 86.34% | 3.4297 | 108.6719
2035 | Done | V1 | 92 | 112 | labor | underground | Canout Labor | 125 |  | 4060 | 5120 | 5120 | -20.7% | -20.7% | 1.3587 | 44.1304
2037 | Done | V1 | 122 | 112 | labor | underground | Canout Labor | 508.5 |  | 16173.5 | 15875 | 17510 | 1.88% | -7.633% | 4.168 | 132.5697
2038 | Done | V1 | 80 | 112 | labor | underground | Canout Labor | 277 |  | 9423.5 | 4250 | 4895 | 121.7% | 92.51% | 3.4625 | 117.7938
2039 | Done | V1 |  | 112 | labor | underground | Canout Labor | 2 |  | 72 | 360 | 360 | -80% | -80%
2040 | Done | V1 | 55 | 112 | labor | underground | Canout Labor | 87 |  | 3009.5 | 3150 | 3300 | -4.46% | -8.803% | 1.5818 | 54.7182
2041 | Done | V2.2 | 108 | 112 | labor | underground | Canout Labor | 379 |  | 13665 | 22500 | 22590 | -39.27% | -39.51% | 3.5093 | 126.5278
2042 | Done | V2.2 | 75 | 112 | labor | underground | Canout Labor | 112 | 5.5 | 3698.5 | 3110 | 3550 | 18.92% | 4.183% | 1.4933 | 49.3133
2043 | Done | V2.2 | 89 | 112 | labor | underground | Canout Labor | 290 |  | 10065 | 6960 | 7380 | 44.61% | 36.38% | 3.2584 | 113.0899
2044 | Done | V2.2 | 78 | 112 | labor | underground | Canout Labor | 94.5 |  | 3108.5 | 6850 | 6850 | -54.62% | -54.62% | 1.2115 | 39.8526
2045 | Done | V2.2 | 158 | 112 | labor | underground | Canout Labor | 155 |  | 5231 | 5250 | 6120 | -0.3619% | -14.53% | 0.98101 | 33.1076
2046 | Done | V2.2 | 110 | 112 | labor | underground | Canout Labor | 177.5 | 18.5 | 6188.5 | 11285 | 11585 | -45.16% | -46.58% | 1.6136 | 56.2591
2048 | Done | V2.2 | 72 | 112 | labor | underground | Canout Labor
2050 | Done | V2.2 | 50 | 112 | labor | underground | Canout Labor | 91 |  | 3287 | 4500 | 4500 | -26.96% | -26.96% | 1.82 | 65.74
2051 | Done | V2.2 | 163 | 112 | labor | underground | Canout Labor | 421 | 4 | 13477.82 | 21400 | 21796 | -37.02% | -38.16% | 2.5828 | 82.686
2052 | Done | V2.2 | 107 | 112 | labor | underground | Canout Labor | 289 | 2 | 9800 | 21300 | 22040 | -53.99% | -55.54% | 2.7009 | 91.5888
2053 | Done | V2.2 | 136 | 112 | labor | underground | Canout Labor | 627.5 |  | 21073.5 | 39340 | 39790 | -46.43% | -47.04% | 4.614 | 154.9522
2054 | Done | V2.2 | 68 | 112 | labor | underground | Canout Labor | 59 | 2 | 2258.5 | 4350 | 4350 | -48.08% | -48.08% | 0.86765 | 33.2132
2055 | Done | V2.2 | 98 | 112 | labor | underground | Canout Labor | 114 |  | 4742 | 8370 | 9170 | -43.35% | -48.29% | 1.1633 | 48.3878
2056 | Done | V2.2 | 321 | 112 | labor | underground | Canout Labor | 900.5 | 1 | 31518 | 50640 | 50830 | -37.76% | -37.99% | 2.8053 | 98.1869
2057 | Done | V2.2 | 111 | 112 | labor | underground | Canout Labor | 256.5 |  | 9569 | 9176 | 9601 | 4.283% | -0.3333% | 2.3108 | 86.2072
2058 | Done | V2.2 | 77 | 112 | labor | underground | Canout Labor | 73 |  | 3080 | 12054 | 12154 | -74.45% | -74.66% | 0.94805 | 40
2059 | Done | V2.2 | 365 | 112 | labor | underground | Canout Labor |  |  | 27669 | 27000 | 27000 | 2.478% | 2.478% |  | 75.8055
2060 | Done | V2.2 | 270 | 112 | labor | underground | Canout Labor | 1085.5 | 63 | 41968 | 54450 | 56815 | -22.92% | -26.13% | 4.0204 | 155.437
2098 | LIVE | V2.2 | 170 | 112 | labor | underground | Canout Labor | 808 | 21 | 37993.5 | 48144 | 48994 | -21.08% | -22.45% | 4.7529 | 223.4912
2103 | LIVE | V2.2 | 234 | 112 | labor | underground | Canout Labor | 935.25 |  | 41039 | 51050 | 52600 | -19.61% | -21.98% | 3.9968 | 175.3803
2104 | LIVE | V2.2 | 24 | 112 | labor | underground | Canout Labor | 70 |  | 3928 | 4100 | 4100 | -4.195% | -4.195% | 2.9167 | 163.6667
2107 | LIVE | V2.2 | 244 | 112 | labor | underground | Canout Labor | 1455.5 |  | 66406.5 | 59715 | 59715 | 11.21% | 11.21% | 5.9652 | 272.1578
2111 | LIVE | V_TX | 186 | 112 | labor | underground | Canout Labor | 393.75 |  | 16891 | 41100 | 41200 | -58.9% | -59% | 2.1169 | 90.8118
2001 | Done | SUPABASE | 234 | 113 | labor | underground | Foundation Drain Labor |  |  | 3190.16 | 9000 | 9000 | -64.55% | -64.55% |  | 13.6332
2008 | Done | SUPABASE | 258 | 113 | labor | underground | Foundation Drain Labor |  |  | 2454 | 3400 | 3400 | -27.82% | -27.82% |  | 9.5116
2011 | Done | SUPABASE | 117 | 113 | labor | underground | Foundation Drain Labor |  |  | 2115 |  | 5650 |  | -62.57% |  | 18.0769
2012 | Done | SUPABASE | 162 | 113 | labor | underground | Foundation Drain Labor | 50 |  | 984 | 2700 | 2700 | -63.56% | -63.56% | 0.30864 | 6.0741
2015 | Done | SUPABASE | 197 | 113 | labor | underground | Foundation Drain Labor |  |  | 520.5 | 520 | 520 | 0.09615% | 0.09615% |  | 2.6421
2017 | Done | SUPABASE | 119 | 113 | labor | underground | Foundation Drain Labor |  |  | 2012 | 2012 | 2012 | 0% | 0% |  | 16.9076
2018 | Done | SUPABASE | 211 | 113 | labor | underground | Foundation Drain Labor |  |  | 952 | 6625 | 6625 | -85.63% | -85.63% |  | 4.5118
2020 | Done | SUPABASE | 256 | 113 | labor | underground | Foundation Drain Labor |  |  | 2843 | 2843 | 2843 | 0% | 0% |  | 11.1055
2001 | Done | SUPABASE | 234 | 120 | labor | rough_in | Roughin Labor |  |  | 218574.15 | 185705 | 185705 | 17.7% | 17.7% |  | 934.0776
2008 | Done | SUPABASE | 258 | 120 | labor | rough_in | Roughin Labor |  |  | 303122.05 | 261585 | 269760 | 15.88% | 12.37% |  | 1174.8917
2009 | Done | SUPABASE | 56 | 120 | labor | rough_in | Roughin Labor |  |  | 46114 | 34500 | 37530 | 33.66% | 22.87% |  | 823.4643
2010 | Done | SUPABASE | 149 | 120 | labor | rough_in | Roughin Labor |  |  | 114688.38 | 204925 | 159525 | -44.03% | -28.11% |  | 769.7207
2011 | Done | SUPABASE | 117 | 120 | labor | rough_in | Roughin Labor |  |  | 81010.75 | 82535 | 82835 | -1.847% | -2.202% |  | 692.3996
2012 | Done | SUPABASE | 162 | 120 | labor | rough_in | Roughin Labor | 9319.5 |  | 177291.75 | 139800 | 139800 | 26.82% | 26.82% | 57.5278 | 1094.3935
2015 | Done | SUPABASE | 197 | 120 | labor | rough_in | Roughin Labor |  |  | 387658.09 | 244060 | 261060 | 58.84% | 48.49% |  | 1967.8076
2017 | Done | SUPABASE | 119 | 120 | labor | rough_in | Roughin Labor |  |  | 173312.75 | 138760 | 140370 | 24.9% | 23.47% |  | 1456.4097
2018 | Done | SUPABASE | 211 | 120 | labor | rough_in | Roughin Labor |  |  | 256945.47 | 207140 | 208010 | 24.04% | 23.53% |  | 1217.751
2019 | Done | SUPABASE | 211 | 120 | labor | rough_in | Roughin Labor |  |  | 301244.35 | 281500 | 294635 | 7.014% | 2.243% |  | 1427.6983
2020 | Done | SUPABASE | 256 | 120 | labor | rough_in | Roughin Labor |  |  | 348602.98 | 376600 | 266055 | -7.434% | 31.03% |  | 1361.7304
2021 | Done | SUPABASE | 136 | 120 | labor | rough_in | Roughin Labor |  |  | 232285.5 | 205015 | 208728 | 13.3% | 11.29% |  | 1707.9816
2022 | Done | SUPABASE | 18 | 120 | labor | rough_in | Roughin Labor |  |  | 39476.75 | 32400 | 32400 | 21.84% | 21.84% |  | 2193.1528
2023 | Done | V1 | 209 | 120 | labor | rough_in | Roughin Labor | 17765 | 2 | 373123.5 | 230840 | 304097 | 61.64% | 22.7% | 85 | 1785.2799
2024 | Done | V1 | 117 | 120 | labor | rough_in | Roughin Labor | 8731 |  | 164177 | 183700 | 190647 | -10.63% | -13.88% | 74.6239 | 1403.2222
2025 | Done | V1 | 75 | 120 | labor | rough_in | Roughin Labor | 6350 |  | 150592 | 125395 | 127266 | 20.09% | 18.33% | 84.6667 | 2007.8933
2026 | Done | V1 | 49 | 120 | labor | rough_in | Roughin Labor | 4901 |  | 116564.5 | 101805 | 101946 | 14.5% | 14.34% | 100.0204 | 2378.8673
2027 | Done | V1 | 170 | 120 | labor | rough_in | Roughin Labor | 12672 | 148 | 278595.5 | 301840 | 300990 | -7.701% | -7.44% | 74.5412 | 1638.7971
2028 | Done | V1 | 296 | 120 | labor | rough_in | Roughin Labor | 16225 |  | 366998.59 | 348060 | 350306 | 5.441% | 4.765% | 54.8142 | 1239.8601
2029 | Done | V1 | 83 | 120 | labor | rough_in | Roughin Labor | 4553.5 |  | 103433 | 148500 | 149251 | -30.35% | -30.7% | 54.8614 | 1246.1807
2030 | Done | V1 | 144 | 120 | labor | rough_in | Roughin Labor | 9692.25 | 212.5 | 255360.5 | 246760 | 245447 | 3.485% | 4.039% | 67.3073 | 1773.3368
2031 | Done | V1 | 398 | 120 | labor | rough_in | Roughin Labor | 12464.75 | 14.25 | 289348.75 | 239070 | 261460 | 21.03% | 10.67% | 31.3185 | 727.0069
2032 | Done | V1 | 71 | 120 | labor | rough_in | Roughin Labor | 3132 |  | 77199.5 | 86310 | 87991 | -10.56% | -12.26% | 44.1127 | 1087.3169
2033 | Done | V1 | 139 | 120 | labor | rough_in | Roughin Labor | 11450.5 | 3 | 299136 | 373450 | 329577 | -19.9% | -9.236% | 82.3777 | 2152.0576
2034 | Done | V1 | 128 | 120 | labor | rough_in | Roughin Labor | 10611.5 |  | 248837 | 244245 | 255005 | 1.88% | -2.419% | 82.9023 | 1944.0391
2035 | Done | V1 | 92 | 120 | labor | rough_in | Roughin Labor | 2891 | 5.5 | 65658 | 83320 | 83320 | -21.2% | -21.2% | 31.4239 | 713.6739
2036 | Done | V1 | 31 | 120 | labor | rough_in | Roughin Labor | 2582.5 | 2 | 66604.5 | 66670 | 66670 | -0.09825% | -0.09825% | 83.3065 | 2148.5323
2037 | Done | V1 | 122 | 120 | labor | rough_in | Roughin Labor | 8156.5 | 419 | 240637.46 | 263000 | 265970 | -8.503% | -9.525% | 66.8566 | 1972.4382
2038 | Done | V1 | 80 | 120 | labor | rough_in | Roughin Labor | 7100 | 88 | 181998 | 136655 | 143435 | 33.18% | 26.89% | 88.75 | 2274.975
2040 | Done | V1 | 55 | 120 | labor | rough_in | Roughin Labor | 3429.75 | 121.5 | 86788 | 74440 | 75910 | 16.59% | 14.33% | 62.3591 | 1577.9636
2041 | Done | V2.2 | 108 | 120 | labor | rough_in | Roughin Labor | 6131 | 632 | 187351.59 | 155820 | 150920 | 20.24% | 24.14% | 56.7685 | 1734.7369
2042 | Done | V2.2 | 75 | 120 | labor | rough_in | Roughin Labor | 4990 | 71.5 | 128045 | 105400 | 106060 | 21.48% | 20.73% | 66.5333 | 1707.2667
2043 | Done | V2.2 | 89 | 120 | labor | rough_in | Roughin Labor | 5253 | 136.5 | 146478 | 139140 | 143130 | 5.274% | 2.339% | 59.0225 | 1645.8202
2044 | Done | V2.2 | 78 | 120 | labor | rough_in | Roughin Labor | 5294.75 | 67 | 150429.23 | 96130 | 98690 | 56.49% | 52.43% | 67.8814 | 1928.5799
2045 | Done | V2.2 | 158 | 120 | labor | rough_in | Roughin Labor | 8560.5 | 273.5 | 227602.48 | 342805 | 360476 | -33.61% | -36.86% | 54.1804 | 1440.522
2046 | Done | V2.2 | 110 | 120 | labor | rough_in | Roughin Labor | 7414.5 | 326 | 199226.75 | 244210 | 248785 | -18.42% | -19.92% | 67.4045 | 1811.1523
2047 | Done | V2.2 | 70 | 120 | labor | rough_in | Roughin Labor | 4762 | 171.5 | 119374 | 88827 | 105859 | 34.39% | 12.77% | 68.0286 | 1705.3429
2048 | Done | V2.2 | 72 | 120 | labor | rough_in | Roughin Labor | 3279.5 | 285 | 82885.25 | 98181 | 104646 | -15.58% | -20.79% | 45.5486 | 1151.184
2049 | Done | V2.2 | 296 | 120 | labor | rough_in | Roughin Labor | 14406 | 826 | 361459.35 | 404800 | 432470 | -10.71% | -16.42% | 48.6689 | 1221.1465
2050 | Done | V2.2 | 50 | 120 | labor | rough_in | Roughin Labor | 2862.5 | 101 | 78450 | 87940 | 91025 | -10.79% | -13.81% | 57.25 | 1569
2051 | Done | V2.2 | 163 | 120 | labor | rough_in | Roughin Labor | 10088 | 88.5 | 261842.25 | 387125 | 326457 | -32.36% | -19.79% | 61.8896 | 1606.3942
2052 | Done | V2.2 | 107 | 120 | labor | rough_in | Roughin Labor | 7137.5 | 303.5 | 201052.75 | 195065 | 211765 | 3.07% | -5.059% | 66.7056 | 1878.9977
2053 | Done | V2.2 | 136 | 120 | labor | rough_in | Roughin Labor | 11273.5 | 338 | 301988 | 243255 | 247365 | 24.14% | 22.08% | 82.8934 | 2220.5
2054 | Done | V2.2 | 68 | 120 | labor | rough_in | Roughin Labor | 4894.5 | 245 | 147001.5 | 91743 | 94273 | 60.23% | 55.93% | 71.9779 | 2161.7868
2055 | Done | V2.2 | 98 | 120 | labor | rough_in | Roughin Labor | 5631 | 88.5 | 182281.5 | 143615 | 178365 | 26.92% | 2.196% | 57.4592 | 1860.0153
2056 | Done | V2.2 | 321 | 120 | labor | rough_in | Roughin Labor |  |  | 802553.37 | 688305 | 692715 | 16.6% | 15.86% |  | 2500.1663
2057 | Done | V2.2 | 111 | 120 | labor | rough_in | Roughin Labor | 3219.5 | 126 | 96775 | 98240 | 98240 | -1.491% | -1.491% | 29.0045 | 871.8468
2058 | Done | V2.2 | 77 | 120 | labor | rough_in | Roughin Labor | 6483.5 | 1 | 195332 | 93340 | 102640 | 109.3% | 90.31% | 84.2013 | 2536.7792
2059 | Done | V2.2 | 365 | 120 | labor | rough_in | Roughin Labor | 21647.5 | 5 | 700399 | 559540 | 594524 | 25.17% | 17.81% | 59.3082 | 1918.9014
2060 | Done | V2.2 | 270 | 120 | labor | rough_in | Roughin Labor | 13201 | 646 | 422639.89 | 479570 | 618308 | -11.87% | -31.65% | 48.8926 | 1565.3329
2098 | LIVE | V2.2 | 170 | 120 | labor | rough_in | Roughin Labor | 22746.25 | 0.5 | 797900.1 | 1037606 | 1069806 | -23.1% | -25.42% | 133.8015 | 4693.53
2103 | LIVE | V2.2 | 234 | 120 | labor | rough_in | Roughin Labor | 24970.5 | 0.25 | 1041296.25 | 890865 | 936025 | 16.89% | 11.25% | 106.7115 | 4449.984
2104 | LIVE | V2.2 | 24 | 120 | labor | rough_in | Roughin Labor | 3215.75 |  | 132816 | 86380 | 91880 | 53.76% | 44.55% | 133.9896 | 5534
2107 | LIVE | V2.2 | 244 | 120 | labor | rough_in | Roughin Labor | 14998 | 2.5 | 646310.26 | 542930 | 565930 | 19.04% | 14.2% | 61.4672 | 2648.8125
2111 | LIVE | V_TX | 186 | 120 | labor | rough_in | Roughin Labor | 5618.75 | 6 | 236097 | 680615 | 682015 | -65.31% | -65.38% | 30.2083 | 1269.3387
2112 | LIVE | V_TX | 20 | 120 | labor | rough_in | Roughin Labor | 1689 | 2.25 | 67991 | 55760 | 60410 | 21.94% | 12.55% | 84.45 | 3399.55
2001 | Done | SUPABASE | 234 | 130 | labor | trim_finish | Finish Labor |  |  | 46024.72 | 37212 | 37212 | 23.68% | 23.68% |  | 196.6868
2008 | Done | SUPABASE | 258 | 130 | labor | trim_finish | Finish Labor |  |  | 76368.5 | 43650 | 49430 | 74.96% | 54.5% |  | 296.0019
2009 | Done | SUPABASE | 56 | 130 | labor | trim_finish | Finish Labor |  |  | 11391.5 | 10250 | 10320 | 11.14% | 10.38% |  | 203.4196
2010 | Done | SUPABASE | 149 | 130 | labor | trim_finish | Finish Labor |  |  | 29825 | 31000 | 31500 | -3.79% | -5.317% |  | 200.1678
2011 | Done | SUPABASE | 117 | 130 | labor | trim_finish | Finish Labor |  |  | 21869 | 24770 | 24770 | -11.71% | -11.71% |  | 186.9145
2012 | Done | SUPABASE | 162 | 130 | labor | trim_finish | Finish Labor | 1840.75 |  | 34658.38 | 31000 | 31000 | 11.8% | 11.8% | 11.3627 | 213.9406
2015 | Done | SUPABASE | 197 | 130 | labor | trim_finish | Finish Labor |  |  | 45395.28 | 41255 | 45665 | 10.04% | -0.5906% |  | 230.4329
2017 | Done | SUPABASE | 119 | 130 | labor | trim_finish | Finish Labor |  |  | 36292.5 | 23400 | 25520 | 55.1% | 42.21% |  | 304.979
2018 | Done | SUPABASE | 211 | 130 | labor | trim_finish | Finish Labor |  |  | 58292.75 | 43900 | 44800 | 32.79% | 30.12% |  | 276.269
2019 | Done | SUPABASE | 211 | 130 | labor | trim_finish | Finish Labor |  |  | 36001.25 | 54000 | 55373 | -33.33% | -34.98% |  | 170.622
2020 | Done | SUPABASE | 256 | 130 | labor | trim_finish | Finish Labor |  |  | 64250.9 | 51400 | 58664 | 25% | 9.524% |  | 250.9801
2021 | Done | SUPABASE | 136 | 130 | labor | trim_finish | Finish Labor |  |  | 30179 | 32520 | 32580 | -7.199% | -7.37% |  | 221.9044
2022 | Done | SUPABASE | 18 | 130 | labor | trim_finish | Finish Labor |  |  | 5302 | 4480 | 4480 | 18.35% | 18.35% |  | 294.5556
2023 | Done | V1 | 209 | 130 | labor | trim_finish | Finish Labor | 2906.5 |  | 62630.5 | 46160 | 48864 | 35.68% | 28.17% | 13.9067 | 299.6675
2024 | Done | V1 | 117 | 130 | labor | trim_finish | Finish Labor | 1150.5 |  | 28250.5 | 29900 | 31289 | -5.517% | -9.711% | 9.8333 | 241.4573
2025 | Done | V1 | 75 | 130 | labor | trim_finish | Finish Labor | 1069 |  | 23808 | 24190 | 24692 | -1.579% | -3.58% | 14.2533 | 317.44
2026 | Done | V1 | 49 | 130 | labor | trim_finish | Finish Labor | 625.5 |  | 12520 | 16920 | 16920 | -26% | -26% | 12.7653 | 255.5102
2027 | Done | V1 | 170 | 130 | labor | trim_finish | Finish Labor | 2157.5 | 55 | 48849.27 | 52080 | 53079 | -6.203% | -7.969% | 12.6912 | 287.3486
2028 | Done | V1 | 296 | 130 | labor | trim_finish | Finish Labor | 19 |  | 719 | 83600 | 719.5 | -99.14% | -0.06949% | 0.064189 | 2.4291
2029 | Done | V1 | 83 | 130 | labor | trim_finish | Finish Labor | 979 |  | 25915.5 | 26200 | 26808 | -1.086% | -3.329% | 11.7952 | 312.2349
2030 | Done | V1 | 144 | 130 | labor | trim_finish | Finish Labor | 1737.5 | 126.5 | 47557.25 | 48300 | 48437 | -1.538% | -1.816% | 12.066 | 330.2587
2031 | Done | V1 | 398 | 130 | labor | trim_finish | Finish Labor | 2669.5 | 200.5 | 69830.75 | 62435 | 64440 | 11.85% | 8.366% | 6.7073 | 175.4541
2032 | Done | V1 | 71 | 130 | labor | trim_finish | Finish Labor | 682.5 | 19.5 | 15430.25 | 23215 | 24174 | -33.53% | -36.17% | 9.6127 | 217.3275
2033 | Done | V1 | 139 | 130 | labor | trim_finish | Finish Labor | 1845 | 84 | 42783.5 | 50580 | 51098 | -15.41% | -16.27% | 13.2734 | 307.795
2034 | Done | V1 | 128 | 130 | labor | trim_finish | Finish Labor | 1468.75 | 20.5 | 37411.5 | 41700 | 43230 | -10.28% | -13.46% | 11.4746 | 292.2773
2035 | Done | V1 | 92 | 130 | labor | trim_finish | Finish Labor | 590 |  | 15449 | 19110 | 19284 | -19.16% | -19.89% | 6.413 | 167.9239
2036 | Done | V1 | 31 | 130 | labor | trim_finish | Finish Labor | 731.5 | 14.5 | 18527.25 | 17520 | 17520 | 5.749% | 5.749% | 23.5968 | 597.6532
2037 | Done | V1 | 122 | 130 | labor | trim_finish | Finish Labor | 1644 | 127 | 41886.75 | 43380 | 44150 | -3.442% | -5.126% | 13.4754 | 343.334
2038 | Done | V1 | 80 | 130 | labor | trim_finish | Finish Labor | 872.5 | 6 | 20959 | 25860 | 26050 | -18.95% | -19.54% | 10.9062 | 261.9875
2040 | Done | V1 | 55 | 130 | labor | trim_finish | Finish Labor | 531.75 | 41.25 | 13510.25 | 16860 | 16920 | -19.87% | -20.15% | 9.6682 | 245.6409
2041 | Done | V2.2 | 108 | 130 | labor | trim_finish | Finish Labor | 1290 |  | 33336 | 42870 | 43420 | -22.24% | -23.22% | 11.9444 | 308.6667
2042 | Done | V2.2 | 75 | 130 | labor | trim_finish | Finish Labor | 651 | 33.5 | 16956.5 | 21840 | 22595 | -22.36% | -24.95% | 8.68 | 226.0867
2043 | Done | V2.2 | 89 | 130 | labor | trim_finish | Finish Labor | 922.5 | 164.5 | 25473 | 30640 | 28735 | -16.86% | -11.35% | 10.3652 | 286.2135
2044 | Done | V2.2 | 78 | 130 | labor | trim_finish | Finish Labor | 741.5 |  | 17219.5 | 23100 | 22970 | -25.46% | -25.03% | 9.5064 | 220.7628
2045 | Done | V2.2 | 158 | 130 | labor | trim_finish | Finish Labor | 2528.5 |  | 67247 | 70680 | 71030 | -4.857% | -5.326% | 16.0032 | 425.6139
2046 | Done | V2.2 | 110 | 130 | labor | trim_finish | Finish Labor | 1052.5 | 50 | 36570 | 35160 | 35880 | 4.01% | 1.923% | 9.5682 | 332.4545
2047 | Done | V2.2 | 70 | 130 | labor | trim_finish | Finish Labor | 923.5 | 47.5 | 23539.75 | 25980 | 26220 | -9.393% | -10.22% | 13.1929 | 336.2821
2048 | Done | V2.2 | 72 | 130 | labor | trim_finish | Finish Labor | 1224.5 | 49 | 26670.5 | 26460 | 27252 | 0.7955% | -2.134% | 17.0069 | 370.4236
2049 | Done | V2.2 | 296 | 130 | labor | trim_finish | Finish Labor | 3028.5 | 303.5 | 83036.25 | 83990 | 84050 | -1.136% | -1.206% | 10.2314 | 280.5279
2050 | Done | V2.2 | 50 | 130 | labor | trim_finish | Finish Labor | 503 | 1.5 | 12091.25 | 15480 | 15750 | -21.89% | -23.23% | 10.06 | 241.825
2051 | Done | V2.2 | 163 | 130 | labor | trim_finish | Finish Labor | 2738.5 |  | 74007.5 | 59000 | 59314 | 25.44% | 24.77% | 16.8006 | 454.0337
2052 | Done | V2.2 | 107 | 130 | labor | trim_finish | Finish Labor | 1130 |  | 34751 | 35640 | 35780 | -2.494% | -2.876% | 10.5607 | 324.7757
2053 | Done | V2.2 | 136 | 130 | labor | trim_finish | Finish Labor | 2180.5 | 6 | 58885.5 | 46860 | 47430 | 25.66% | 24.15% | 16.0331 | 432.9816
2054 | Done | V2.2 | 68 | 130 | labor | trim_finish | Finish Labor |  |  | 21750 | 20700 | 20700 | 5.072% | 5.072% |  | 319.8529
2055 | Done | V2.2 | 98 | 130 | labor | trim_finish | Finish Labor | 1020.5 |  | 32494.5 | 29055 | 32055 | 11.84% | 1.371% | 10.4133 | 331.5765
2056 | Done | V2.2 | 321 | 130 | labor | trim_finish | Finish Labor | 3715 |  | 119715 | 105170 | 105765 | 13.83% | 13.19% | 11.5732 | 372.9439
2057 | Done | V2.2 | 111 | 130 | labor | trim_finish | Finish Labor | 685.5 |  | 17090.5 | 23058 | 23938 | -25.88% | -28.61% | 6.1757 | 153.9685
2058 | Done | V2.2 | 77 | 130 | labor | trim_finish | Finish Labor | 708 |  | 25477 | 23100 | 23310 | 10.29% | 9.296% | 9.1948 | 330.8701
2059 | Done | V2.2 | 365 | 130 | labor | trim_finish | Finish Labor | 5104 | 34.5 | 171108.5 | 184290 | 189240 | -7.153% | -9.581% | 13.9836 | 468.7904
2060 | Done | V2.2 | 270 | 130 | labor | trim_finish | Finish Labor | 3366.5 | 4 | 107754 | 110025 | 129670 | -2.064% | -16.9% | 12.4685 | 399.0889
2098 | LIVE | V2.2 | 170 | 130 | labor | trim_finish | Finish Labor | 5979 |  | 222921 | 196840 | 197570 | 13.25% | 12.83% | 35.1706 | 1311.3
2103 | LIVE | V2.2 | 234 | 130 | labor | trim_finish | Finish Labor | 2992 | 0.25 | 132682.75 | 136060 | 185910 | -2.482% | -28.63% | 12.7863 | 567.0203
2104 | LIVE | V2.2 | 24 | 130 | labor | trim_finish | Finish Labor | 222.25 |  | 10320.5 | 12080 | 12080 | -14.57% | -14.57% | 9.2604 | 430.0208
2107 | LIVE | V2.2 | 244 | 130 | labor | trim_finish | Finish Labor | 1 |  | 65 | 135784 | 135784 | -99.95% | -99.95% | 0.0040984 | 0.26639
2112 | LIVE | V_TX | 20 | 130 | labor | trim_finish | Finish Labor | 49.75 |  | 2682.5 | 9200 | 9200 | -70.84% | -70.84% | 2.4875 | 134.125
2001 | Done | SUPABASE | 234 | 140 | labor | gas | Gas Labor |  |  | 14211.67 | 9450 | 9450 | 50.39% | 50.39% |  | 60.7336
2008 | Done | SUPABASE | 258 | 140 | labor | gas | Gas Labor |  |  | 21795.5 | 18000 | 18200 | 21.09% | 19.76% |  | 84.4787
2010 | Done | SUPABASE | 149 | 140 | labor | gas | Gas Labor |  |  | 1712 | 3600 | 3600 | -52.44% | -52.44% |  | 11.4899
2012 | Done | SUPABASE | 162 | 140 | labor | gas | Gas Labor | 104 |  | 2168 | 3300 | 3300 | -34.3% | -34.3% | 0.64198 | 13.3827
2015 | Done | SUPABASE | 197 | 140 | labor | gas | Gas Labor |  |  | 11582.5 | 7250 | 11400 | 59.76% | 1.601% |  | 58.7944
2017 | Done | SUPABASE | 119 | 140 | labor | gas | Gas Labor |  |  | 7448 | 6000 | 6300 | 24.13% | 18.22% |  | 62.5882
2018 | Done | SUPABASE | 211 | 140 | labor | gas | Gas Labor |  |  | 8626.5 | 7200 | 8390 | 19.81% | 2.819% |  | 40.8839
2019 | Done | SUPABASE | 211 | 140 | labor | gas | Gas Labor |  |  | 7665 | 14700 | 15325 | -47.86% | -49.98% |  | 36.327
2020 | Done | SUPABASE | 256 | 140 | labor | gas | Gas Labor |  |  | 32025.5 | 9000 | 13862 | 255.8% | 131% |  | 125.0996
2021 | Done | SUPABASE | 136 | 140 | labor | gas | Gas Labor |  |  | 10305.46 | 5500 | 7990 | 87.37% | 28.98% |  | 75.7754
2023 | Done | V1 | 209 | 140 | labor | gas | Gas Labor | 971 |  | 21481 | 7975 | 11915 | 169.4% | 80.29% | 4.6459 | 102.7799
2024 | Done | V1 | 117 | 140 | labor | gas | Gas Labor | 406.5 |  | 9547 | 8700 | 8700 | 9.736% | 9.736% | 3.4744 | 81.5983
2025 | Done | V1 | 75 | 140 | labor | gas | Gas Labor | 195.5 |  | 5854 | 5500 | 5986 | 6.436% | -2.205% | 2.6067 | 78.0533
2026 | Done | V1 | 49 | 140 | labor | gas | Gas Labor | 133.5 |  | 3916 | 6000 | 6000 | -34.73% | -34.73% | 2.7245 | 79.9184
2027 | Done | V1 | 170 | 140 | labor | gas | Gas Labor | 336.5 | 32 | 7836.5 | 6600 | 6600 | 18.73% | 18.73% | 1.9794 | 46.0971
2028 | Done | V1 | 296 | 140 | labor | gas | Gas Labor | 425.5 |  | 10210.5 | 14400 | 14400 | -29.09% | -29.09% | 1.4375 | 34.4949
2029 | Done | V1 | 83 | 140 | labor | gas | Gas Labor | 90.5 |  | 2133 | 2400 | 2856 | -11.12% | -25.32% | 1.0904 | 25.6988
2030 | Done | V1 | 144 | 140 | labor | gas | Gas Labor | 578 | 19 | 16593 | 9600 | 11720 | 72.84% | 41.58% | 4.0139 | 115.2292
2031 | Done | V1 | 398 | 140 | labor | gas | Gas Labor | 260.5 | 2 | 6952.5 | 8800 | 9370 | -20.99% | -25.8% | 0.65452 | 17.4686
2032 | Done | V1 | 71 | 140 | labor | gas | Gas Labor | 50.5 |  | 1836 | 5250 | 5250 | -65.03% | -65.03% | 0.71127 | 25.8592
2033 | Done | V1 | 139 | 140 | labor | gas | Gas Labor | 324.5 |  | 9941.5 | 3600 | 3600 | 176.2% | 176.2% | 2.3345 | 71.5216
2034 | Done | V1 | 128 | 140 | labor | gas | Gas Labor | 324 |  | 10151 | 2300 | 3067 | 341.3% | 231% | 2.5312 | 79.3047
2037 | Done | V1 | 122 | 140 | labor | gas | Gas Labor | 194 | 11 | 6410 | 7750 | 7750 | -17.29% | -17.29% | 1.5902 | 52.541
2038 | Done | V1 | 80 | 140 | labor | gas | Gas Labor | 91 | 5 | 2740 | 3000 | 3360 | -8.667% | -18.45% | 1.1375 | 34.25
2039 | Done | V1 |  | 140 | labor | gas | Gas Labor | 226 | 17.5 | 7599.75 | 7360 | 7360 | 3.257% | 3.257%
2040 | Done | V1 | 55 | 140 | labor | gas | Gas Labor | 83 | 2 | 2784 | 7500 | 7500 | -62.88% | -62.88% | 1.5091 | 50.6182
2041 | Done | V2.2 | 108 | 140 | labor | gas | Gas Labor | 217 |  | 7098 | 9750 | 10950 | -27.2% | -35.18% | 2.0093 | 65.7222
2042 | Done | V2.2 | 75 | 140 | labor | gas | Gas Labor | 41 | 1 | 1625.5 | 2400 | 2400 | -32.27% | -32.27% | 0.54667 | 21.6733
2043 | Done | V2.2 | 89 | 140 | labor | gas | Gas Labor | 275 | 10 | 9705 | 11900 | 11900 | -18.45% | -18.45% | 3.0899 | 109.0449
2044 | Done | V2.2 | 78 | 140 | labor | gas | Gas Labor | 135.5 | 4 | 4551.5 | 6000 | 6000 | -24.14% | -24.14% | 1.7372 | 58.3526
2046 | Done | V2.2 | 110 | 140 | labor | gas | Gas Labor | 136.5 | 9.5 | 5168.5 | 11000 | 11000 | -53.01% | -53.01% | 1.2409 | 46.9864
2049 | Done | V2.2 | 296 | 140 | labor | gas | Gas Labor | 391 | 19 | 11964.5 | 14400 | 16200 | -16.91% | -26.15% | 1.3209 | 40.4206
2050 | Done | V2.2 | 50 | 140 | labor | gas | Gas Labor | 178 | 11 | 5268.5 | 6050 | 6170 | -12.92% | -14.61% | 3.56 | 105.37
2051 | Done | V2.2 | 163 | 140 | labor | gas | Gas Labor |  |  | 10694 | 11900 | 14255 | -10.13% | -24.98% |  | 65.6074
2052 | Done | V2.2 | 107 | 140 | labor | gas | Gas Labor | 103 | 3 | 4126.5 | 9750 | 10050 | -57.68% | -58.94% | 0.96262 | 38.5654
2053 | Done | V2.2 | 136 | 140 | labor | gas | Gas Labor | 425.5 |  | 13994 | 8100 | 8550 | 72.77% | 63.67% | 3.1287 | 102.8971
2054 | Done | V2.2 | 68 | 140 | labor | gas | Gas Labor | 210 |  | 6735 | 7500 | 7500 | -10.2% | -10.2% | 3.0882 | 99.0441
2055 | Done | V2.2 | 98 | 140 | labor | gas | Gas Labor | 210.5 |  | 7800 | 9600 | 9600 | -18.75% | -18.75% | 2.148 | 79.5918
2056 | Done | V2.2 | 321 | 140 | labor | gas | Gas Labor | 365 |  | 12589 | 20250 | 22750 | -37.83% | -44.66% | 1.1371 | 39.2181
2057 | Done | V2.2 | 111 | 140 | labor | gas | Gas Labor | 255 |  | 8361 | 6750 | 7520 | 23.87% | 11.18% | 2.2973 | 75.3243
2058 | Done | V2.2 | 77 | 140 | labor | gas | Gas Labor | 201 |  | 5276 | 9750 | 10230 | -45.89% | -48.43% | 2.6104 | 68.5195
2059 | Done | V2.2 | 365 | 140 | labor | gas | Gas Labor | 183 |  | 7514 | 7300 | 7300 | 2.932% | 2.932% | 0.50137 | 20.5863
2060 | Done | V2.2 | 270 | 140 | labor | gas | Gas Labor | 435 | 14 | 17179.5 | 60000 | 55700 | -71.37% | -69.16% | 1.6111 | 63.6278
2098 | LIVE | V2.2 | 170 | 140 | labor | gas | Gas Labor | 490.5 | 1 | 23969.5 | 11400 | 13400 | 110.3% | 78.88% | 2.8853 | 140.9971
2103 | LIVE | V2.2 | 234 | 140 | labor | gas | Gas Labor | 430.75 |  | 21237.25 | 9550 | 25250 | 122.4% | -15.89% | 1.8408 | 90.7575
2104 | LIVE | V2.2 | 24 | 140 | labor | gas | Gas Labor | 82.25 |  | 3848 | 4000 | 4000 | -3.8% | -3.8% | 3.4271 | 160.3333
2107 | LIVE | V2.2 | 244 | 140 | labor | gas | Gas Labor | 211.75 |  | 7647.75 | 5400 | 11400 | 41.62% | -32.91% | 0.86783 | 31.3432
2001 | Done | SUPABASE | 234 | 141 | labor | water_main | Water Main/Insulation Lab |  |  | 36651.38 | 36300 | 36300 | 0.968% | 0.968% |  | 156.6298
2008 | Done | SUPABASE | 258 | 141 | labor | water_main | Water Main/Insulation Lab |  |  | 64816.03 | 40050 | 40050 | 61.84% | 61.84% |  | 251.2249
2009 | Done | SUPABASE | 56 | 141 | labor | water_main | Water Main/Insulation Lab
2010 | Done | SUPABASE | 149 | 141 | labor | water_main | Water Main/Insulation Lab |  |  | 3672 | 14900 | 33900 | -75.36% | -89.17% |  | 24.6443
2011 | Done | SUPABASE | 117 | 141 | labor | water_main | Water Main/Insulation Lab |  |  | 208 | [5 empty] | 1.7778
2012 | Done | SUPABASE | 162 | 141 | labor | water_main | Water Main/Insulation Lab | 800 |  | 15756 | 41000 | 41000 | -61.57% | -61.57% | 4.9383 | 97.2593
2015 | Done | SUPABASE | 197 | 141 | labor | water_main | Water Main/Insulation Lab |  |  | 37466.75 | 29805 | 35505 | 25.71% | 5.525% |  | 190.1865
2017 | Done | SUPABASE | 119 | 141 | labor | water_main | Water Main/Insulation Lab |  |  | 19505.5 | 32000 | 32000 | -39.05% | -39.05% |  | 163.9118
2018 | Done | SUPABASE | 211 | 141 | labor | water_main | Water Main/Insulation Lab |  |  | 31534.47 | 40550 | 40550 | -22.23% | -22.23% |  | 149.4525
2019 | Done | SUPABASE | 211 | 141 | labor | water_main | Water Main/Insulation Lab |  |  | 39821.52 | 74800 | 75430 | -46.76% | -47.21% |  | 188.7276
2020 | Done | SUPABASE | 256 | 141 | labor | water_main | Water Main/Insulation Lab |  |  | 85831.88 | 55600 | 57029 | 54.37% | 50.51% |  | 335.2808
2021 | Done | SUPABASE | 136 | 141 | labor | water_main | Water Main/Insulation Lab |  |  | 56135.73 | 34750 | 34890 | 61.54% | 60.89% |  | 412.7627
2022 | Done | SUPABASE | 18 | 141 | labor | water_main | Water Main/Insulation Lab |  |  | 472.5 | [5 empty] | 26.25
2023 | Done | V1 | 209 | 141 | labor | water_main | Water Main/Insulation Lab | 3214.5 | 4 | 54198.43 | 29430 | 35287 | 84.16% | 53.59% | 15.3804 | 259.3226
2024 | Done | V1 | 117 | 141 | labor | water_main | Water Main/Insulation Lab | 1554.5 |  | 33366.5 | 27000 | 27000 | 23.58% | 23.58% | 13.2863 | 285.1838
2025 | Done | V1 | 75 | 141 | labor | water_main | Water Main/Insulation Lab | 921 |  | 20707 | 34110 | 34596 | -39.29% | -40.15% | 12.28 | 276.0933
2026 | Done | V1 | 49 | 141 | labor | water_main | Water Main/Insulation Lab | 967 |  | 20543 | 18820 | 18820 | 9.155% | 9.155% | 19.7347 | 419.2449
2027 | Done | V1 | 170 | 141 | labor | water_main | Water Main/Insulation Lab | 2208 | 16 | 46631.5 | 65315 | 66415 | -28.61% | -29.79% | 12.9882 | 274.3029
2028 | Done | V1 | 296 | 141 | labor | water_main | Water Main/Insulation Lab | 2837 |  | 60276 | 124740 | 124740 | -51.68% | -51.68% | 9.5845 | 203.6351
2029 | Done | V1 | 83 | 141 | labor | water_main | Water Main/Insulation Lab | 553 |  | 12249 | 28200 | 28756 | -56.56% | -57.4% | 6.6627 | 147.5783
2030 | Done | V1 | 144 | 141 | labor | water_main | Water Main/Insulation Lab | 1889 | 17 | 42757 | 44785 | 49085 | -4.528% | -12.89% | 13.1181 | 296.9236
2031 | Done | V1 | 398 | 141 | labor | water_main | Water Main/Insulation Lab | 1450.25 | 11.75 | 31378.38 | 52870 | 57700 | -40.65% | -45.62% | 3.6438 | 78.8402
2032 | Done | V1 | 71 | 141 | labor | water_main | Water Main/Insulation Lab | 558.5 |  | 12390 | 25980 | 25980 | -52.31% | -52.31% | 7.8662 | 174.507
2033 | Done | V1 | 139 | 141 | labor | water_main | Water Main/Insulation Lab | 1096 | 4 | 29860.13 | 45780 | 47220 | -34.77% | -36.76% | 7.8849 | 214.8211
2034 | Done | V1 | 128 | 141 | labor | water_main | Water Main/Insulation Lab | 3006.5 | 1.5 | 74191.25 | 44470 | 46169 | 66.83% | 60.69% | 23.4883 | 579.6191
2035 | Done | V1 | 92 | 141 | labor | water_main | Water Main/Insulation Lab | 596 |  | 12963 | 25000 | 25960 | -48.15% | -50.07% | 6.4783 | 140.9022
2036 | Done | V1 | 31 | 141 | labor | water_main | Water Main/Insulation Lab | 180 |  | 5620 | 2960 | 4004 | 89.86% | 40.36% | 5.8065 | 181.2903
2037 | Done | V1 | 122 | 141 | labor | water_main | Water Main/Insulation Lab | 983.5 | 52 | 25492.04 | 51720 | 51720 | -50.71% | -50.71% | 8.0615 | 208.9511
2038 | Done | V1 | 80 | 141 | labor | water_main | Water Main/Insulation Lab | 1339 | 9 | 38061 | 31600 | 31700 | 20.45% | 20.07% | 16.7375 | 475.7625
2039 | Done | V1 |  | 141 | labor | water_main | Water Main/Insulation Lab
2040 | Done | V1 | 55 | 141 | labor | water_main | Water Main/Insulation Lab | 635.5 | 14 | 15056.5 | 21435 | 21435 | -29.76% | -29.76% | 11.5545 | 273.7545
2041 | Done | V2.2 | 108 | 141 | labor | water_main | Water Main/Insulation Lab | 1697.5 | 74 | 53432 | 52850 | 53000 | 1.101% | 0.8151% | 15.7176 | 494.7407
2042 | Done | V2.2 | 75 | 141 | labor | water_main | Water Main/Insulation Lab | 585.5 | 23 | 13633.5 | 26080 | 26080 | -47.72% | -47.72% | 7.8067 | 181.78
2043 | Done | V2.2 | 89 | 141 | labor | water_main | Water Main/Insulation Lab | 1645 | 62 | 45112 | 38260 | 39220 | 17.91% | 15.02% | 18.4831 | 506.8764
2044 | Done | V2.2 | 78 | 141 | labor | water_main | Water Main/Insulation Lab | 991 | 25 | 23970.37 | 25485 | 25485 | -5.943% | -5.943% | 12.7051 | 307.3124
2045 | Done | V2.2 | 158 | 141 | labor | water_main | Water Main/Insulation Lab | 698.5 | 12 | 21040.5 | 23050 | 29480 | -8.718% | -28.63% | 4.4209 | 133.1677
2046 | Done | V2.2 | 110 | 141 | labor | water_main | Water Main/Insulation Lab | 2333 | 110 | 54625.61 | 32855 | 34835 | 66.26% | 56.81% | 21.2091 | 496.5965
2047 | Done | V2.2 | 70 | 141 | labor | water_main | Water Main/Insulation Lab
2049 | Done | V2.2 | 296 | 141 | labor | water_main | Water Main/Insulation Lab | 2253 | 165.5 | 55727.75 | 124740 | 124740 | -55.32% | -55.32% | 7.6115 | 188.2694
2050 | Done | V2.2 | 50 | 141 | labor | water_main | Water Main/Insulation Lab | 473 | 15 | 11432.5 | 22280 | 22730 | -48.69% | -49.7% | 9.46 | 228.65
2051 | Done | V2.2 | 163 | 141 | labor | water_main | Water Main/Insulation Lab | 1721.5 | 34 | 46255 | 55300 | 55500 | -16.36% | -16.66% | 10.5613 | 283.773
2052 | Done | V2.2 | 107 | 141 | labor | water_main | Water Main/Insulation Lab | 4536.5 | 15 | 117138.5 | 49650 | 49650 | 135.9% | 135.9% | 42.3972 | 1094.7523
2053 | Done | V2.2 | 136 | 141 | labor | water_main | Water Main/Insulation Lab | 1563.5 | 48 | 46415.5 | 50660 | 51080 | -8.378% | -9.132% | 11.4963 | 341.2904
2054 | Done | V2.2 | 68 | 141 | labor | water_main | Water Main/Insulation Lab | 2949.5 | 1 | 74881.5 | 26735 | 26735 | 180.1% | 180.1% | 43.375 | 1101.1985
2055 | Done | V2.2 | 98 | 141 | labor | water_main | Water Main/Insulation Lab | 1130 | 48 | 37064.5 | 36080 | 39780 | 2.729% | -6.826% | 11.5306 | 378.2092
2056 | Done | V2.2 | 321 | 141 | labor | water_main | Water Main/Insulation Lab | 4485.5 | 85.5 | 142511.29 | 172094 | 181004 | -17.19% | -21.27% | 13.9735 | 443.9604
2057 | Done | V2.2 | 111 | 141 | labor | water_main | Water Main/Insulation Lab | 1157.5 |  | 35756 | 44440 | 46100 | -19.54% | -22.44% | 10.4279 | 322.1261
2058 | Done | V2.2 | 77 | 141 | labor | water_main | Water Main/Insulation Lab | 817 |  | 22890 | 32180 | 32180 | -28.87% | -28.87% | 10.6104 | 297.2727
2059 | Done | V2.2 | 365 | 141 | labor | water_main | Water Main/Insulation Lab | 4536.75 |  | 131285.25 | 73190 | 73190 | 79.38% | 79.38% | 12.4295 | 359.6856
2060 | Done | V2.2 | 270 | 141 | labor | water_main | Water Main/Insulation Lab | 3846 | 170.5 | 114150.95 | 151330 | 159280 | -24.57% | -28.33% | 14.2444 | 422.7813
2098 | LIVE | V2.2 | 170 | 141 | labor | water_main | Water Main/Insulation Lab | 3297 | 138 | 120399.72 | 141720 | 142820 | -15.04% | -15.7% | 19.3941 | 708.2336
2103 | LIVE | V2.2 | 234 | 141 | labor | water_main | Water Main/Insulation Lab | 4098.75 | 123.75 | 185051 | 181470 | 193670 | 1.973% | -4.45% | 17.516 | 790.8162
2104 | LIVE | V2.2 | 24 | 141 | labor | water_main | Water Main/Insulation Lab | 438.75 | 0.5 | 17012.5 | 22570 | 23420 | -24.62% | -27.36% | 18.2812 | 708.8542
2107 | LIVE | V2.2 | 244 | 141 | labor | water_main | Water Main/Insulation Lab | 2553 |  | 108097.75 | 172570 | 184270 | -37.36% | -41.34% | 10.4631 | 443.0236
2111 | LIVE | V_TX | 186 | 141 | labor | water_main | Water Main/Insulation Lab | 413.75 |  | 16804.5 | 129370 | 136370 | -87.01% | -87.68% | 2.2245 | 90.3468
2112 | LIVE | V_TX | 20 | 141 | labor | water_main | Water Main/Insulation Lab | 190 |  | 9882.75 | 14420 | 15570 | -31.46% | -36.53% | 9.5 | 494.1375
2001 | Done | SUPABASE | 234 | 142 | labor | mech_room | Mech Room Labor |  |  | 12626.53 | 6250 | 6250 | 102% | 102% |  | 53.9595
2008 | Done | SUPABASE | 258 | 142 | labor | mech_room | Mech Room Labor |  |  | 13633.25 | 8100 | 8100 | 68.31% | 68.31% |  | 52.8421
2009 | Done | SUPABASE | 56 | 142 | labor | mech_room | Mech Room Labor |  |  | 1730 | 1430 | 1430 | 20.98% | 20.98% |  | 30.8929
2010 | Done | SUPABASE | 149 | 142 | labor | mech_room | Mech Room Labor |  |  | 1871 | [5 empty] | 12.557
2011 | Done | SUPABASE | 117 | 142 | labor | mech_room | Mech Room Labor |  |  | 1007 | 1760 | 1760 | -42.78% | -42.78% |  | 8.6068
2012 | Done | SUPABASE | 162 | 142 | labor | mech_room | Mech Room Labor | 379 |  | 9784 | 3525 | 3525 | 177.6% | 177.6% | 2.3395 | 60.3951
2015 | Done | SUPABASE | 197 | 142 | labor | mech_room | Mech Room Labor |  |  | 8975 | 5280 | 8650 | 69.98% | 3.757% |  | 45.5584
2017 | Done | SUPABASE | 119 | 142 | labor | mech_room | Mech Room Labor |  |  | 85 | [5 empty] | 0.71429
2018 | Done | SUPABASE | 211 | 142 | labor | mech_room | Mech Room Labor |  |  | 14152 | 8400 | 8400 | 68.48% | 68.48% |  | 67.0711
2019 | Done | SUPABASE | 211 | 142 | labor | mech_room | Mech Room Labor |  |  | 814 | [5 empty] | 3.8578
2020 | Done | SUPABASE | 256 | 142 | labor | mech_room | Mech Room Labor |  |  | 26035.5 | 9900 | 12705 | 163% | 104.9% |  | 101.7012
2021 | Done | SUPABASE | 136 | 142 | labor | mech_room | Mech Room Labor |  |  | 1144.5 | [5 empty] | 8.4154
2023 | Done | V1 | 209 | 142 | labor | mech_room | Mech Room Labor | 875.5 |  | 21196.26 | 7200 | 7200 | 194.4% | 194.4% | 4.189 | 101.4175
2024 | Done | V1 | 117 | 142 | labor | mech_room | Mech Room Labor | 343.5 |  | 10740.5 | 7000 | 7097 | 53.44% | 51.34% | 2.9359 | 91.7991
2025 | Done | V1 | 75 | 142 | labor | mech_room | Mech Room Labor | 494.5 |  | 13230 | 6900 | 6900 | 91.74% | 91.74% | 6.5933 | 176.4
2026 | Done | V1 | 49 | 142 | labor | mech_room | Mech Room Labor | 435 |  | 14056.5 | 9180 | 9180 | 53.12% | 53.12% | 8.8776 | 286.8673
2027 | Done | V1 | 170 | 142 | labor | mech_room | Mech Room Labor | 412.5 | 6 | 12684.5 | 11000 | 11000 | 15.31% | 15.31% | 2.4265 | 74.6147
2028 | Done | V1 | 296 | 142 | labor | mech_room | Mech Room Labor | 664.5 |  | 18210 | 12500 | 14310 | 45.68% | 27.25% | 2.2449 | 61.5203
2029 | Done | V1 | 83 | 142 | labor | mech_room | Mech Room Labor | 465 |  | 12326 | 11400 | 11400 | 8.123% | 8.123% | 5.6024 | 148.506
2030 | Done | V1 | 144 | 142 | labor | mech_room | Mech Room Labor | 617 | 93 | 18473 | 21000 | 24886 | -12.03% | -25.77% | 4.2847 | 128.2847
2031 | Done | V1 | 398 | 142 | labor | mech_room | Mech Room Labor | 920 | 3 | 32815 | 23440 | 27517 | 40% | 19.25% | 2.3116 | 82.4497
2032 | Done | V1 | 71 | 142 | labor | mech_room | Mech Room Labor | 274 |  | 9868.5 | 12060 | 12762 | -18.17% | -22.67% | 3.8592 | 138.993
2033 | Done | V1 | 139 | 142 | labor | mech_room | Mech Room Labor | 355 | 10 | 13827 | 18900 | 19400 | -26.84% | -28.73% | 2.554 | 99.4748
2034 | Done | V1 | 128 | 142 | labor | mech_room | Mech Room Labor | 206 |  | 8618.5 | 16650 | 16882 | -48.24% | -48.95% | 1.6094 | 67.332
2035 | Done | V1 | 92 | 142 | labor | mech_room | Mech Room Labor | 14 |  | 588 | 4200 | 4200 | -86% | -86% | 0.15217 | 6.3913
2036 | Done | V1 | 31 | 142 | labor | mech_room | Mech Room Labor | 9.5 |  | 405 | 2600 | 2600 | -84.42% | -84.42% | 0.30645 | 13.0645
2037 | Done | V1 | 122 | 142 | labor | mech_room | Mech Room Labor | 446.5 | 0.5 | 17394.75 | 13000 | 24060 | 33.81% | -27.7% | 3.6598 | 142.5799
2038 | Done | V1 | 80 | 142 | labor | mech_room | Mech Room Labor |  |  | 7634.5 | 20000 | 20300 | -61.83% | -62.39% |  | 95.4313
2040 | Done | V1 | 55 | 142 | labor | mech_room | Mech Room Labor | 192 |  | 7174 | 12060 | 12060 | -40.51% | -40.51% | 3.4909 | 130.4364
2041 | Done | V2.2 | 108 | 142 | labor | mech_room | Mech Room Labor | 424.5 |  | 15740.5 | 17500 | 17500 | -10.05% | -10.05% | 3.9306 | 145.7454
2042 | Done | V2.2 | 75 | 142 | labor | mech_room | Mech Room Labor | 284.5 |  | 12026.5 | 17500 | 17750 | -31.28% | -32.25% | 3.7933 | 160.3533
2043 | Done | V2.2 | 89 | 142 | labor | mech_room | Mech Room Labor | 288 | 3 | 10649.5 | 10600 | 11140 | 0.467% | -4.403% | 3.236 | 119.6573
2044 | Done | V2.2 | 78 | 142 | labor | mech_room | Mech Room Labor | 249 |  | 9685 | 13400 | 13400 | -27.72% | -27.72% | 3.1923 | 124.1667
2045 | Done | V2.2 | 158 | 142 | labor | mech_room | Mech Room Labor | 125 |  | 4376 | 5250 | 8250 | -16.65% | -46.96% | 0.79114 | 27.6962
2046 | Done | V2.2 | 110 | 142 | labor | mech_room | Mech Room Labor | 272.5 | 2 | 9940.82 | 14740 | 15760 | -32.56% | -36.92% | 2.4773 | 90.3711
2047 | Done | V2.2 | 70 | 142 | labor | mech_room | Mech Room Labor
2049 | Done | V2.2 | 296 | 142 | labor | mech_room | Mech Room Labor | 371.25 | 41.25 | 11736.7 | 20000 | 20880 | -41.32% | -43.79% | 1.2542 | 39.651
2050 | Done | V2.2 | 50 | 142 | labor | mech_room | Mech Room Labor | 254.5 |  | 9014 | 7800 | 7800 | 15.56% | 15.56% | 5.09 | 180.28
2051 | Done | V2.2 | 163 | 142 | labor | mech_room | Mech Room Labor | 455.5 |  | 16058 | 17000 | 17000 | -5.541% | -5.541% | 2.7945 | 98.5153
2052 | Done | V2.2 | 107 | 142 | labor | mech_room | Mech Room Labor | 320 |  | 11567 | 16000 | 19000 | -27.71% | -39.12% | 2.9907 | 108.1028
2053 | Done | V2.2 | 136 | 142 | labor | mech_room | Mech Room Labor | 527 | 1.5 | 17521.5 | 18150 | 18150 | -3.463% | -3.463% | 3.875 | 128.8346
2054 | Done | V2.2 | 68 | 142 | labor | mech_room | Mech Room Labor | 320 |  | 12228 | 12000 | 12000 | 1.9% | 1.9% | 4.7059 | 179.8235
2055 | Done | V2.2 | 98 | 142 | labor | mech_room | Mech Room Labor | 673.5 |  | 28376 | 15600 | 15600 | 81.9% | 81.9% | 6.8724 | 289.551
2056 | Done | V2.2 | 321 | 142 | labor | mech_room | Mech Room Labor | 814.5 |  | 35212 | 115500 | 115500 | -69.51% | -69.51% | 2.5374 | 109.6947
2057 | Done | V2.2 | 111 | 142 | labor | mech_room | Mech Room Labor | 138.5 |  | 5049.5 | 7000 | 7300 | -27.86% | -30.83% | 1.2477 | 45.491
2058 | Done | V2.2 | 77 | 142 | labor | mech_room | Mech Room Labor | 332.5 |  | 12628.5 | 14400 | 14400 | -12.3% | -12.3% | 4.3182 | 164.0065
2060 | Done | V2.2 | 270 | 142 | labor | mech_room | Mech Room Labor | 966.5 | 6 | 47501.5 | 40000 | 40500 | 18.75% | 17.29% | 3.5796 | 175.9315
2098 | LIVE | V2.2 | 170 | 142 | labor | mech_room | Mech Room Labor |  |  | 80791 | 65600 | 65600 | 23.16% | 23.16% |  | 475.2412
2103 | LIVE | V2.2 | 234 | 142 | labor | mech_room | Mech Room Labor | 1081.25 | 9 | 61170.75 | 99200 | 107100 | -38.34% | -42.88% | 4.6207 | 261.4135
2104 | LIVE | V2.2 | 24 | 142 | labor | mech_room | Mech Room Labor | 136.75 |  | 9336 | 39600 | 42600 | -76.42% | -78.08% | 5.6979 | 389
2105 | LIVE | V2.2 | 219 | 142 | labor | mech_room | Mech Room Labor | 3 |  | 204 |  |  |  |  | 0.013699 | 0.93151
2107 | LIVE | V2.2 | 244 | 142 | labor | mech_room | Mech Room Labor | 642.25 |  | 28970 | 122400 | 122250 | -76.33% | -76.3% | 2.6322 | 118.7295
2112 | LIVE | V_TX | 20 | 142 | labor | mech_room | Mech Room Labor | 12.75 |  | 535.5 | 49500 | 50650 | -98.92% | -98.94% | 0.6375 | 26.775
2023 | Done | V1 | 209 | 143 | labor | condensation | Condensation Drains Labor | 7 |  | 175 |  |  |  |  | 0.033493 | 0.83732
2024 | Done | V1 | 117 | 143 | labor | condensation | Condensation Drains Labor | 854.5 |  | 20595.5 |  | 46 |  | 44673% | 7.3034 | 176.0299
2028 | Done | V1 | 296 | 143 | labor | condensation | Condensation Drains Labor | 37 |  | 905 |  |  |  |  | 0.125 | 3.0574
2031 | Done | V1 | 398 | 143 | labor | condensation | Condensation Drains Labor | 37 |  | 1419 |  |  |  |  | 0.092965 | 3.5653
2033 | Done | V1 | 139 | 143 | labor | condensation | Condensation Drains Labor | 1117 | 1 | 29278.5 |  | 2808 |  | 942.7% | 8.036 | 210.6367
2034 | Done | V1 | 128 | 143 | labor | condensation | Condensation Drains Labor | 1037.5 |  | 23734 |  | 2900 |  | 718.4% | 8.1055 | 185.4219
2037 | Done | V1 | 122 | 143 | labor | condensation | Condensation Drains Labor | 24 |  | 432 |  |  |  |  | 0.19672 | 3.541
2041 | Done | V2.2 | 108 | 143 | labor | condensation | Condensation Drains Labor | 69 |  | 2447 |  |  |  |  | 0.63889 | 22.6574
2043 | Done | V2.2 | 89 | 143 | labor | condensation | Condensation Drains Labor | 489 | 14 | 13291 |  |  |  |  | 5.4944 | 149.3371
2046 | Done | V2.2 | 110 | 143 | labor | condensation | Condensation Drains Labor | 20.5 |  | 722.5 |  |  |  |  | 0.18636 | 6.5682
2047 | Done | V2.2 | 70 | 143 | labor | condensation | Condensation Drains Labor
2049 | Done | V2.2 | 296 | 143 | labor | condensation | Condensation Drains Labor | 16 | 4 | 530 |  |  |  |  | 0.054054 | 1.7905
2051 | Done | V2.2 | 163 | 143 | labor | condensation | Condensation Drains Labor | 16 |  | 416 |  |  |  |  | 0.09816 | 2.5521
2053 | Done | V2.2 | 136 | 143 | labor | condensation | Condensation Drains Labor | 3 |  | 106 |  |  |  |  | 0.022059 | 0.77941
2059 | Done | V2.2 | 365 | 143 | labor | condensation | Condensation Drains Labor | 11 |  | 284 |  |  |  |  | 0.030137 | 0.77808
2098 | LIVE | V2.2 | 170 | 143 | labor | condensation | Condensation Drains Labor
2001 | Done | SUPABASE | 234 | 145 | labor | trim_finish | Tub/Shower Labor |  |  | 16.5 | [5 empty] | 0.070513
2008 | Done | SUPABASE | 258 | 145 | labor | trim_finish | Tub/Shower Labor |  |  | 101.5 | [5 empty] | 0.39341
2009 | Done | SUPABASE | 56 | 145 | labor | trim_finish | Tub/Shower Labor |  |  | 138.5 | [5 empty] | 2.4732
2010 | Done | SUPABASE | 149 | 145 | labor | trim_finish | Tub/Shower Labor |  |  | 373 | [5 empty] | 2.5034
2011 | Done | SUPABASE | 117 | 145 | labor | trim_finish | Tub/Shower Labor |  |  | 9024 | 9360 | 9360 | -3.59% | -3.59% |  | 77.1282
2012 | Done | SUPABASE | 162 | 145 | labor | trim_finish | Tub/Shower Labor | 338 |  | 6781 | 19800 | 19800 | -65.75% | -65.75% | 2.0864 | 41.858
2018 | Done | SUPABASE | 211 | 145 | labor | trim_finish | Tub/Shower Labor |  |  | 805 | 20485 | 20485 | -96.07% | -96.07% |  | 3.8152
2023 | Done | V1 | 209 | 150 | labor | warranty | Warranty Labor | 3 |  | 111 |  | 96 |  | 15.62% | 0.014354 | 0.5311
2024 | Done | V1 | 117 | 150 | labor | warranty | Warranty Labor | 9 |  | 343 |  |  |  |  | 0.076923 | 2.9316
2025 | Done | V1 | 75 | 150 | labor | warranty | Warranty Labor | 2 |  | 80 |  |  |  |  | 0.026667 | 1.0667
2026 | Done | V1 | 49 | 150 | labor | warranty | Warranty Labor | 3 |  | 126 |  |  |  |  | 0.061224 | 2.5714
2028 | Done | V1 | 296 | 150 | labor | warranty | Warranty Labor | 6.5 |  | 240.5 |  |  |  |  | 0.021959 | 0.8125
2029 | Done | V1 | 83 | 150 | labor | warranty | Warranty Labor | 8 |  | 320 |  |  |  |  | 0.096386 | 3.8554
2037 | Done | V1 | 122 | 150 | labor | warranty | Warranty Labor | 5 |  | 250 |  |  |  |  | 0.040984 | 2.0492
2038 | Done | V1 | 80 | 150 | labor | warranty | Warranty Labor | 10.5 | 10.5 | 719.25 |  |  |  |  | 0.13125 | 8.9906
2040 | Done | V1 | 55 | 150 | labor | warranty | Warranty Labor | 1 |  | 48 |  |  |  |  | 0.018182 | 0.87273
2041 | Done | V2.2 | 108 | 150 | labor | warranty | Warranty Labor | 1.5 |  | 73.5 |  |  |  |  | 0.013889 | 0.68056
2049 | Done | V2.2 | 296 | 150 | labor | warranty | Warranty Labor | 1 |  | 50 |  |  |  |  | 0.0033784 | 0.16892
2056 | Done | V2.2 | 321 | 150 | labor | warranty | Warranty Labor | 2.5 |  | 137.5 |  |  |  |  | 0.0077882 | 0.42835
2060 | Done | V2.2 | 270 | 150 | labor | warranty | Warranty Labor | 13.5 |  | 829 |  |  |  |  | 0.05 | 3.0704
2098 | LIVE | V2.2 | 170 | 150 | labor | warranty | Warranty Labor |  |  | 26715.88 | [5 empty] | 157.1522
2039 | Done | V1 |  | 151 | labor | unmapped_labor | T&M Labor |  |  | 178.25
2050 | Done | V2.2 | 50 | 151 | labor | unmapped_labor | T&M Labor | 3 |  | 187.5 |  |  |  |  | 0.06 | 3.75
2098 | LIVE | V2.2 | 170 | 151 | labor | unmapped_labor | T&M Labor | 8 |  | 224 |  |  |  |  | 0.047059 | 1.3176
2103 | LIVE | V2.2 | 234 | 151 | labor | unmapped_labor | T&M Labor | 19.75 |  | 869 |  |  |  |  | 0.084402 | 3.7137
2001 | Done | SUPABASE | 234 | 039 | material | underground | DS & RD Material |  |  | 10684.8 | 34350 | 34350 | -68.89% | -68.89% |  | 45.6615
2008 | Done | SUPABASE | 258 | 039 | material | underground | DS & RD Material |  |  | 26220.27 | 60420 | 60420 | -56.6% | -56.6% |  | 101.629
2009 | Done | SUPABASE | 56 | 039 | material | underground | DS & RD Material |  |  | 369.06 | 1250 | 1250 | -70.48% | -70.48% |  | 6.5904
2010 | Done | SUPABASE | 149 | 039 | material | underground | DS & RD Material |  |  | 1188.86 | 11500 | 11500 | -89.66% | -89.66% |  | 7.9789
2011 | Done | SUPABASE | 117 | 039 | material | underground | DS & RD Material |  |  | 1134.76 | 4725 | 4725 | -75.98% | -75.98% |  | 9.6988
2012 | Done | SUPABASE | 162 | 039 | material | underground | DS & RD Material |  |  | 5066.8 | 17900 | 17900 | -71.69% | -71.69% |  | 31.2765
2017 | Done | SUPABASE | 119 | 039 | material | underground | DS & RD Material |  |  | 2380.94 | [5 empty] | 20.0079
2001 | Done | SUPABASE | 234 | 210 | material | underground | Underground Material |  |  | 6150.1 | 5400 | 5400 | 13.89% | 13.89% |  | 26.2825
2008 | Done | SUPABASE | 258 | 210 | material | underground | Underground Material |  |  | 10852.76 | 3000 | 3000 | 261.8% | 261.8% |  | 42.065
2009 | Done | SUPABASE | 56 | 210 | material | underground | Underground Material |  |  | 2613.58 | 2800 | 2800 | -6.658% | -6.658% |  | 46.6711
2010 | Done | SUPABASE | 149 | 210 | material | underground | Underground Material |  |  | 1514.24 | 3000 | 3000 | -49.53% | -49.53% |  | 10.1627
2011 | Done | SUPABASE | 117 | 210 | material | underground | Underground Material |  |  | 5311 | 10300 | 10300 | -48.44% | -48.44% |  | 45.3932
2012 | Done | SUPABASE | 162 | 210 | material | underground | Underground Material |  |  | 1635.51 | 4300 | 4300 | -61.96% | -61.96% |  | 10.0957
2015 | Done | SUPABASE | 197 | 210 | material | underground | Underground Material |  |  | 7557.66 | 9825 | 9385 | -23.08% | -19.47% |  | 38.3638
2017 | Done | SUPABASE | 119 | 210 | material | underground | Underground Material |  |  | 3861 | 5685 | 5685 | -32.08% | -32.08% |  | 32.4454
2018 | Done | SUPABASE | 211 | 210 | material | underground | Underground Material |  |  | 3233.67 | 5900 | 5900 | -45.19% | -45.19% |  | 15.3255
2019 | Done | SUPABASE | 211 | 210 | material | underground | Underground Material |  |  | 9932.16 | 16500 | 16500 | -39.81% | -39.81% |  | 47.0718
2020 | Done | SUPABASE | 256 | 210 | material | underground | Underground Material |  |  | 24415.78 | 23100 | 23300 | 5.696% | 4.789% |  | 95.3741
2021 | Done | SUPABASE | 136 | 210 | material | underground | Underground Material |  |  | 21743.86 | 13250 | 13550 | 64.1% | 60.47% |  | 159.8813
2022 | Done | SUPABASE | 18 | 210 | material | underground | Underground Material |  |  | 3879.67 | 5550 | 5550 | -30.1% | -30.1% |  | 215.5372
2023 | Done | V1 | 209 | 210 | material | underground | Underground Material |  |  | 45918.24 | 23150 | 38304 | 98.35% | 19.88% |  | 219.7045
2024 | Done | V1 | 117 | 210 | material | underground | Underground Material |  |  | 22920.93 | 17800 | 17800 | 28.77% | 28.77% |  | 195.9054
2025 | Done | V1 | 75 | 210 | material | underground | Underground Material |  |  | 12323.48 | 23000 | 27199 | -46.42% | -54.69% |  | 164.3131
2026 | Done | V1 | 49 | 210 | material | underground | Underground Material |  |  | 6574.76 | 11900 | 11900 | -44.75% | -44.75% |  | 134.1788
2027 | Done | V1 | 170 | 210 | material | underground | Underground Material |  |  | 13388.88 | 18300 | 15078 | -26.84% | -11.2% |  | 78.7581
2028 | Done | V1 | 296 | 210 | material | underground | Underground Material |  |  | 19678.27 | 62400 | 58475 | -68.46% | -66.35% |  | 66.4806
2029 | Done | V1 | 83 | 210 | material | underground | Underground Material |  |  | 10418.9 | 13900 | 14089 | -25.04% | -26.05% |  | 125.5289
2030 | Done | V1 | 144 | 210 | material | underground | Underground Material |  |  | 14590.94 | 19300 | 23202 | -24.4% | -37.11% |  | 101.326
2031 | Done | V1 | 398 | 210 | material | underground | Underground Material |  |  | 10306.12 | 38085 | 40845 | -72.94% | -74.77% |  | 25.8948
2032 | Done | V1 | 71 | 210 | material | underground | Underground Material |  |  | 7410.05 | 7845 | 12333 | -5.544% | -39.92% |  | 104.3669
2033 | Done | V1 | 139 | 210 | material | underground | Underground Material |  |  | 25541.27 | 35500 | 42333 | -28.05% | -39.67% |  | 183.7501
2034 | Done | V1 | 128 | 210 | material | underground | Underground Material |  |  | 10119.25 | 13950 | 14603 | -27.46% | -30.7% |  | 79.0566
2035 | Done | V1 | 92 | 210 | material | underground | Underground Material |  |  | 8289.11 | 12700 | 12700 | -34.73% | -34.73% |  | 90.099
2036 | Done | V1 | 31 | 210 | material | underground | Underground Material |  |  | 7669.29 | 6300 | 7778 | 21.73% | -1.398% |  | 247.3965
2037 | Done | V1 | 122 | 210 | material | underground | Underground Material |  |  | 15243.5 | 37500 | 27000 | -59.35% | -43.54% |  | 124.9467
2038 | Done | V1 | 80 | 210 | material | underground | Underground Material |  |  | 11448.44 | 26470 | 26903 | -56.75% | -57.45% |  | 143.1055
2040 | Done | V1 | 55 | 210 | material | underground | Underground Material |  |  | 2062.26 | 11800 | 11800 | -82.52% | -82.52% |  | 37.4956
2041 | Done | V2.2 | 108 | 210 | material | underground | Underground Material |  |  | 6296.57 | 9540 | 14690 | -34% | -57.14% |  | 58.3016
2042 | Done | V2.2 | 75 | 210 | material | underground | Underground Material |  |  | 5226.84 | 15383 | 15383 | -66.02% | -66.02% |  | 69.6912
2043 | Done | V2.2 | 89 | 210 | material | underground | Underground Material |  |  | 11843.79 | 33850 | 34823 | -65.01% | -65.99% |  | 133.0763
2044 | Done | V2.2 | 78 | 210 | material | underground | Underground Material |  |  | 1317.75 | 16585 | 16585 | -92.05% | -92.05% |  | 16.8942
2045 | Done | V2.2 | 158 | 210 | material | underground | Underground Material |  |  | 14535.79 | 15530 | 29830 | -6.402% | -51.27% |  | 91.9987
2046 | Done | V2.2 | 110 | 210 | material | underground | Underground Material |  |  | 3400.09 | 10575 | 10900 | -67.85% | -68.81% |  | 30.9099
2049 | Done | V2.2 | 296 | 210 | material | underground | Underground Material |  |  | 3633.46 | 2600 | 8465 | 39.75% | -57.08% |  | 12.2752
2050 | Done | V2.2 | 50 | 210 | material | underground | Underground Material |  |  | 2906.23 | 8700 | 10253 | -66.6% | -71.65% |  | 58.1246
2051 | Done | V2.2 | 163 | 210 | material | underground | Underground Material |  |  | 9764.8 | 13000 | 10100 | -24.89% | -3.319% |  | 59.9067
2052 | Done | V2.2 | 107 | 210 | material | underground | Underground Material |  |  | 13998.46 | 20325 | 20325 | -31.13% | -31.13% |  | 130.8267
2053 | Done | V2.2 | 136 | 210 | material | underground | Underground Material |  |  | 8316.84 | 10664 | 13531 | -22.01% | -38.53% |  | 61.1532
2054 | Done | V2.2 | 68 | 210 | material | underground | Underground Material |  |  | 3063.5 | 10925 | 11575 | -71.96% | -73.53% |  | 45.0515
2055 | Done | V2.2 | 98 | 210 | material | underground | Underground Material |  |  | 5959.91 | 6825 | 6825 | -12.68% | -12.68% |  | 60.8154
2056 | Done | V2.2 | 321 | 210 | material | underground | Underground Material |  |  | 31760.07 | 57667 | 59247 | -44.93% | -46.39% |  | 98.941
2057 | Done | V2.2 | 111 | 210 | material | underground | Underground Material |  |  | 648.12 | 9500 | 9500 | -93.18% | -93.18% |  | 5.8389
2058 | Done | V2.2 | 77 | 210 | material | underground | Underground Material |  |  | 2678.61 | 2880 | 3580 | -6.993% | -25.18% |  | 34.7871
2059 | Done | V2.2 | 365 | 210 | material | underground | Underground Material |  |  | 26908.83 | 63600 | 63800 | -57.69% | -57.82% |  | 73.7228
2060 | Done | V2.2 | 270 | 210 | material | underground | Underground Material |  |  | 26001.45 | 50000 | 50750 | -48% | -48.77% |  | 96.3017
2098 | LIVE | V2.2 | 170 | 210 | material | underground | Underground Material | 310 |  | 101624.25 | 85150 | 85650 | 19.35% | 18.65% | 1.8235 | 597.7897
2103 | LIVE | V2.2 | 234 | 210 | material | underground | Underground Material | 152 |  | 49664.33 | 64300 | 75460 | -22.76% | -34.18% | 0.64957 | 212.2407
2104 | LIVE | V2.2 | 24 | 210 | material | underground | Underground Material |  |  | 4029.94 | 8500 | 8500 | -52.59% | -52.59% |  | 167.9142
2107 | LIVE | V2.2 | 244 | 210 | material | underground | Underground Material |  |  | 13857.07 | 28700 | 29000 | -51.72% | -52.22% |  | 56.7913
2111 | LIVE | V_TX | 186 | 210 | material | underground | Underground Material |  |  | 28949.16 | 62600 | 67600 | -53.76% | -57.18% |  | 155.6406
2112 | LIVE | V_TX | 20 | 210 | material | underground | Underground Material |  |  | 4486.52 | 5850 | 5850 | -23.31% | -23.31% |  | 224.326
2001 | Done | SUPABASE | 234 | 211 | material | underground | Garage Material |  |  | 36037.82 | 35055 | 35055 | 2.804% | 2.804% |  | 154.0078
2008 | Done | SUPABASE | 258 | 211 | material | underground | Garage Material |  |  | 15831.2 | 33750 | 33750 | -53.09% | -53.09% |  | 61.3612
2009 | Done | SUPABASE | 56 | 211 | material | underground | Garage Material |  |  | 3972.94 | 10570 | 10570 | -62.41% | -62.41% |  | 70.9454
2010 | Done | SUPABASE | 149 | 211 | material | underground | Garage Material |  |  | 11302.9 | 63370 | 63370 | -82.16% | -82.16% |  | 75.8584
2011 | Done | SUPABASE | 117 | 211 | material | underground | Garage Material |  |  | 6465.89 | 14000 | 14000 | -53.82% | -53.82% |  | 55.264
2012 | Done | SUPABASE | 162 | 211 | material | underground | Garage Material |  |  | 6599.03 | 11970 | 11970 | -44.87% | -44.87% |  | 40.7348
2015 | Done | SUPABASE | 197 | 211 | material | underground | Garage Material |  |  | 41623.99 | 59640 | 63870 | -30.21% | -34.83% |  | 211.2893
2017 | Done | SUPABASE | 119 | 211 | material | underground | Garage Material |  |  | 3724.79 | 29760 | 29800 | -87.48% | -87.5% |  | 31.3008
2018 | Done | SUPABASE | 211 | 211 | material | underground | Garage Material |  |  | 74066.35 | 45820 | 45820 | 61.65% | 61.65% |  | 351.0254
2019 | Done | SUPABASE | 211 | 211 | material | underground | Garage Material |  |  | 22168.78 | 55800 | 57063 | -60.27% | -61.15% |  | 105.0653
2020 | Done | SUPABASE | 256 | 211 | material | underground | Garage Material |  |  | 54034.99 | 95600 | 92894 | -43.48% | -41.83% |  | 211.0742
2021 | Done | SUPABASE | 136 | 211 | material | underground | Garage Material |  |  | 39526.02 | 36150 | 37700 | 9.339% | 4.844% |  | 290.6325
2023 | Done | V1 | 209 | 211 | material | underground | Garage Material |  |  | 33922.59 | 101825 | 102635 | -66.69% | -66.95% |  | 162.309
2024 | Done | V1 | 117 | 211 | material | underground | Garage Material |  |  | 25579.57 | 57600 | 57951 | -55.59% | -55.86% |  | 218.6288
2025 | Done | V1 | 75 | 211 | material | underground | Garage Material |  |  | 19383.8 | 27270 | 28626 | -28.92% | -32.29% |  | 258.4507
2026 | Done | V1 | 49 | 211 | material | underground | Garage Material |  |  | 16318.46 | 16750 | 16750 | -2.576% | -2.576% |  | 333.0298
2027 | Done | V1 | 170 | 211 | material | underground | Garage Material |  |  | 37284.47 | 64290 | 64290 | -42.01% | -42.01% |  | 219.3204
2028 | Done | V1 | 296 | 211 | material | underground | Garage Material |  |  | 41996.33 | 79425 | 80707 | -47.12% | -47.96% |  | 141.8795
2029 | Done | V1 | 83 | 211 | material | underground | Garage Material |  |  | 467.8 | [5 empty] | 5.6361
2030 | Done | V1 | 144 | 211 | material | underground | Garage Material |  |  | 72845.97 | 108050 | 126594 | -32.58% | -42.46% |  | 505.8748
2031 | Done | V1 | 398 | 211 | material | underground | Garage Material |  |  | 14259.91 | 30580 | 30580 | -53.37% | -53.37% |  | 35.8289
2032 | Done | V1 | 71 | 211 | material | underground | Garage Material |  |  | 203.65 | [5 empty] | 2.8683
2033 | Done | V1 | 139 | 211 | material | underground | Garage Material |  |  | 19980.4 | 93500 | 71296 | -78.63% | -71.98% |  | 143.7439
2034 | Done | V1 | 128 | 211 | material | underground | Garage Material |  |  | 33009.22 | 42025 | 49734 | -21.45% | -33.63% |  | 257.8845
2035 | Done | V1 | 92 | 211 | material | underground | Garage Material |  |  | 7036.09 | 20700 | 20700 | -66.01% | -66.01% |  | 76.4792
2036 | Done | V1 | 31 | 211 | material | underground | Garage Material |  |  | 65 | [5 empty] | 2.0968
2037 | Done | V1 | 122 | 211 | material | underground | Garage Material |  |  | 17635.16 | 58095 | 56631 | -69.64% | -68.86% |  | 144.5505
2038 | Done | V1 | 80 | 211 | material | underground | Garage Material |  |  | 26750.81 | 34080 | 37555 | -21.51% | -28.77% |  | 334.3851
2040 | Done | V1 | 55 | 211 | material | underground | Garage Material |  |  | 1763.95 | [5 empty] | 32.0718
2041 | Done | V2.2 | 108 | 211 | material | underground | Garage Material |  |  | 71058.87 | 86250 | 95533 | -17.61% | -25.62% |  | 657.9525
2042 | Done | V2.2 | 75 | 211 | material | underground | Garage Material |  |  | 1607.11 | [5 empty] | 21.4281
2043 | Done | V2.2 | 89 | 211 | material | underground | Garage Material |  |  | 22375.47 | 28205 | 31448 | -20.67% | -28.85% |  | 251.4098
2044 | Done | V2.2 | 78 | 211 | material | underground | Garage Material |  |  | 2172.87 | [5 empty] | 27.8573
2045 | Done | V2.2 | 158 | 211 | material | underground | Garage Material |  |  | 15918.41 | 30440 | 34850 | -47.71% | -54.32% |  | 100.7494
2046 | Done | V2.2 | 110 | 211 | material | underground | Garage Material |  |  | 10464.66 | 26950 | 28736 | -61.17% | -63.58% |  | 95.1333
2047 | Done | V2.2 | 70 | 211 | material | underground | Garage Material |  |  | 10.6 | [5 empty] | 0.15143
2048 | Done | V2.2 | 72 | 211 | material | underground | Garage Material |  |  |  |  | 1644 |  | -100%
2049 | Done | V2.2 | 296 | 211 | material | underground | Garage Material |  |  | 3799.24 | 63000 | 63600 | -93.97% | -94.03% |  | 12.8353
2050 | Done | V2.2 | 50 | 211 | material | underground | Garage Material |  |  | 13959.12 | 21850 | 23310 | -36.11% | -40.12% |  | 279.1824
2051 | Done | V2.2 | 163 | 211 | material | underground | Garage Material |  |  | 9727.46 | 75760 | 59835 | -87.16% | -83.74% |  | 59.6777
2052 | Done | V2.2 | 107 | 211 | material | underground | Garage Material |  |  | 30100.97 | 70875 | 73930 | -57.53% | -59.28% |  | 281.3175
2053 | Done | V2.2 | 136 | 211 | material | underground | Garage Material |  |  | 22525.24 | 97667 | 97667 | -76.94% | -76.94% |  | 165.6268
2054 | Done | V2.2 | 68 | 211 | material | underground | Garage Material |  |  | 26287.7 | 7500 | 7500 | 250.5% | 250.5% |  | 386.5838
2055 | Done | V2.2 | 98 | 211 | material | underground | Garage Material |  |  | 28292.22 | 5175 | 6675 | 446.7% | 323.9% |  | 288.6961
2056 | Done | V2.2 | 321 | 211 | material | underground | Garage Material |  |  | 92755.74 | 172517 | 173467 | -46.23% | -46.53% |  | 288.9587
2057 | Done | V2.2 | 111 | 211 | material | underground | Garage Material |  |  | 17156.73 | 30850 | 33497 | -44.39% | -48.78% |  | 154.5651
2058 | Done | V2.2 | 77 | 211 | material | underground | Garage Material |  |  | 16428.12 | 13510 | 13960 | 21.6% | 17.68% |  | 213.3522
2059 | Done | V2.2 | 365 | 211 | material | underground | Garage Material |  |  | 31688.57 | 98250 | 98250 | -67.75% | -67.75% |  | 86.818
2060 | Done | V2.2 | 270 | 211 | material | underground | Garage Material |  |  | 39400.27 | 246784 | 250234 | -84.03% | -84.25% |  | 145.9269
2098 | LIVE | V2.2 | 170 | 211 | material | underground | Garage Material |  |  | 17998.09 | 106000 | 106150 | -83.02% | -83.04% |  | 105.8711
2103 | LIVE | V2.2 | 234 | 211 | material | underground | Garage Material |  |  | 169337.63 | 105025 | 122695 | 61.24% | 38.02% |  | 723.6651
2104 | LIVE | V2.2 | 24 | 211 | material | underground | Garage Material |  |  | 2904.28 | 4000 | 4000 | -27.39% | -27.39% |  | 121.0117
2107 | LIVE | V2.2 | 244 | 211 | material | underground | Garage Material |  |  | 54729.07 | 68005 | 78105 | -19.52% | -29.93% |  | 224.2995
2111 | LIVE | V_TX | 186 | 211 | material | underground | Garage Material |  |  | 15686.54 | 37500 | 40900 | -58.17% | -61.65% |  | 84.3362
2001 | Done | SUPABASE | 234 | 212 | material | underground | Canout Material |  |  | 16844.65 | 19308 | 19308 | -12.76% | -12.76% |  | 71.9857
2008 | Done | SUPABASE | 258 | 212 | material | underground | Canout Material |  |  | 58265.64 | 70425 | 70425 | -17.27% | -17.27% |  | 225.8358
2009 | Done | SUPABASE | 56 | 212 | material | underground | Canout Material |  |  | 2749.23 | 2800 | 2800 | -1.813% | -1.813% |  | 49.0934
2010 | Done | SUPABASE | 149 | 212 | material | underground | Canout Material |  |  | 5720.08 | 7980 | 7980 | -28.32% | -28.32% |  | 38.3898
2011 | Done | SUPABASE | 117 | 212 | material | underground | Canout Material |  |  | 5222.75 | 5460 | 5460 | -4.345% | -4.345% |  | 44.6389
2012 | Done | SUPABASE | 162 | 212 | material | underground | Canout Material |  |  | 8579.19 | 13130 | 13130 | -34.66% | -34.66% |  | 52.958
2015 | Done | SUPABASE | 197 | 212 | material | underground | Canout Material |  |  | 13825.36 | 17220 | 17700 | -19.71% | -21.89% |  | 70.1795
2017 | Done | SUPABASE | 119 | 212 | material | underground | Canout Material |  |  | 6453.36 | 5700 | 5740 | 13.22% | 12.43% |  | 54.2299
2018 | Done | SUPABASE | 211 | 212 | material | underground | Canout Material |  |  | 5771.34 | 18200 | 18200 | -68.29% | -68.29% |  | 27.3523
2019 | Done | SUPABASE | 211 | 212 | material | underground | Canout Material |  |  | 40231.97 | 69200 | 69350 | -41.86% | -41.99% |  | 190.6728
2020 | Done | SUPABASE | 256 | 212 | material | underground | Canout Material |  |  | 24723.82 | 26400 | 26700 | -6.349% | -7.401% |  | 96.5774
2021 | Done | SUPABASE | 136 | 212 | material | underground | Canout Material |  |  | 6538.72 | 9520 | 9520 | -31.32% | -31.32% |  | 48.0788
2023 | Done | V1 | 209 | 212 | material | underground | Canout Material |  |  | 11617.32 | 17500 | 17660 | -33.62% | -34.22% |  | 55.5853
2024 | Done | V1 | 117 | 212 | material | underground | Canout Material |  |  | 8927.31 | 14100 | 14100 | -36.69% | -36.69% |  | 76.3018
2025 | Done | V1 | 75 | 212 | material | underground | Canout Material |  |  | 4759.86 | 7780 | 7780 | -38.82% | -38.82% |  | 63.4648
2026 | Done | V1 | 49 | 212 | material | underground | Canout Material |  |  | 5237.21 | 4375 | 4375 | 19.71% | 19.71% |  | 106.8818
2027 | Done | V1 | 170 | 212 | material | underground | Canout Material |  |  | 14050.89 | 15450 | 15450 | -9.056% | -9.056% |  | 82.6523
2028 | Done | V1 | 296 | 212 | material | underground | Canout Material |  |  | 9133.37 | 17700 | 17954 | -48.4% | -49.13% |  | 30.856
2029 | Done | V1 | 83 | 212 | material | underground | Canout Material |  |  | 6161.22 | 7500 | 7500 | -17.85% | -17.85% |  | 74.2316
2030 | Done | V1 | 144 | 212 | material | underground | Canout Material |  |  | 9952.79 | 16650 | 19740 | -40.22% | -49.58% |  | 69.1166
2031 | Done | V1 | 398 | 212 | material | underground | Canout Material |  |  | 7891.24 | 9310 | 9310 | -15.24% | -15.24% |  | 19.8272
2032 | Done | V1 | 71 | 212 | material | underground | Canout Material |  |  | 80.8 | [5 empty] | 1.138
2033 | Done | V1 | 139 | 212 | material | underground | Canout Material |  |  | 11279.69 | 7740 | 8272 | 45.73% | 36.36% |  | 81.1488
2034 | Done | V1 | 128 | 212 | material | underground | Canout Material |  |  | 9058.05 | 7500 | 8771 | 20.77% | 3.273% |  | 70.766
2035 | Done | V1 | 92 | 212 | material | underground | Canout Material |  |  | 5117.23 | 4800 | 4800 | 6.609% | 6.609% |  | 55.6221
2037 | Done | V1 | 122 | 212 | material | underground | Canout Material |  |  | 11652.7 | 17575 | 17575 | -33.7% | -33.7% |  | 95.5139
2038 | Done | V1 | 80 | 212 | material | underground | Canout Material |  |  | 4514.39 | 5100 | 6316 | -11.48% | -28.52% |  | 56.4299
2040 | Done | V1 | 55 | 212 | material | underground | Canout Material |  |  | 2644.13 | 3150 | 3605 | -16.06% | -26.65% |  | 48.0751
2041 | Done | V2.2 | 108 | 212 | material | underground | Canout Material |  |  | 8465.53 | 22500 | 22695 | -62.38% | -62.7% |  | 78.3845
2042 | Done | V2.2 | 75 | 212 | material | underground | Canout Material |  |  | 2967.63 | 3480 | 3480 | -14.72% | -14.72% |  | 39.5684
2043 | Done | V2.2 | 89 | 212 | material | underground | Canout Material |  |  | 6739.32 | 8700 | 9582 | -22.54% | -29.67% |  | 75.7227
2044 | Done | V2.2 | 78 | 212 | material | underground | Canout Material |  |  | 5102.82 | 8220 | 8220 | -37.92% | -37.92% |  | 65.4208
2045 | Done | V2.2 | 158 | 212 | material | underground | Canout Material |  |  | 4323.42 | 4500 | 5718 | -3.924% | -24.39% |  | 27.3634
2046 | Done | V2.2 | 110 | 212 | material | underground | Canout Material |  |  | 7542.97 | 9150 | 9450 | -17.56% | -20.18% |  | 68.5725
2047 | Done | V2.2 | 70 | 212 | material | underground | Canout Material
2049 | Done | V2.2 | 296 | 212 | material | underground | Canout Material |  |  | 74.33 | 7000 | 7000 | -98.94% | -98.94% |  | 0.25111
2050 | Done | V2.2 | 50 | 212 | material | underground | Canout Material |  |  | 3121.63 | 5040 | 5040 | -38.06% | -38.06% |  | 62.4326
2051 | Done | V2.2 | 163 | 212 | material | underground | Canout Material |  |  | 13552.21 | 21400 | 21996 | -36.67% | -38.39% |  | 83.1424
2052 | Done | V2.2 | 107 | 212 | material | underground | Canout Material |  |  | 11577.93 | 21300 | 22040 | -45.64% | -47.47% |  | 108.205
2053 | Done | V2.2 | 136 | 212 | material | underground | Canout Material |  |  | 12046.87 | 22085 | 22585 | -45.45% | -46.66% |  | 88.5799
2054 | Done | V2.2 | 68 | 212 | material | underground | Canout Material |  |  | 9124.86 | 5220 | 5220 | 74.81% | 74.81% |  | 134.1891
2055 | Done | V2.2 | 98 | 212 | material | underground | Canout Material |  |  | 4336.58 | 7254 | 7654 | -40.22% | -43.34% |  | 44.2508
2056 | Done | V2.2 | 321 | 212 | material | underground | Canout Material |  |  | 32821.74 | 68227 | 68417 | -51.89% | -52.03% |  | 102.2484
2057 | Done | V2.2 | 111 | 212 | material | underground | Canout Material |  |  | 8186.91 | 7440 | 7915 | 10.04% | 3.435% |  | 73.7559
2058 | Done | V2.2 | 77 | 212 | material | underground | Canout Material |  |  | 4845.32 | 11466 | 11566 | -57.74% | -58.11% |  | 62.9262
2059 | Done | V2.2 | 365 | 212 | material | underground | Canout Material |  |  | 15350.72 | 31500 | 31500 | -51.27% | -51.27% |  | 42.0568
2060 | Done | V2.2 | 270 | 212 | material | underground | Canout Material |  |  | 24014.23 | 54450 | 54950 | -55.9% | -56.3% |  | 88.9416
2098 | LIVE | V2.2 | 170 | 212 | material | underground | Canout Material |  |  | 23927.32 | 47200 | 47200 | -49.31% | -49.31% |  | 140.7489
2103 | LIVE | V2.2 | 234 | 212 | material | underground | Canout Material |  |  | 22272.59 | 51050 | 52900 | -56.37% | -57.9% |  | 95.182
2104 | LIVE | V2.2 | 24 | 212 | material | underground | Canout Material |  |  | 1262.92 | 4018 | 4018 | -68.57% | -68.57% |  | 52.6217
2107 | LIVE | V2.2 | 244 | 212 | material | underground | Canout Material |  |  | 47833.93 | 51753 | 51753 | -7.573% | -7.573% |  | 196.0407
2111 | LIVE | V_TX | 186 | 212 | material | underground | Canout Material |  |  | 17136.45 | 41100 | 41400 | -58.31% | -58.61% |  | 92.1315
2112 | LIVE | V_TX | 20 | 212 | material | underground | Canout Material
2001 | Done | SUPABASE | 234 | 213 | material | underground | Foundation Material |  |  | 3564.14 | 10000 | 10000 | -64.36% | -64.36% |  | 15.2314
2008 | Done | SUPABASE | 258 | 213 | material | underground | Foundation Material |  |  | 2839.07 | 10550 | 10550 | -73.09% | -73.09% |  | 11.0041
2011 | Done | SUPABASE | 117 | 213 | material | underground | Foundation Material |  |  | 3664.54 |  | 6000 |  | -38.92% |  | 31.3209
2012 | Done | SUPABASE | 162 | 213 | material | underground | Foundation Material |  |  | 1789.12 | 2700 | 2700 | -33.74% | -33.74% |  | 11.044
2015 | Done | SUPABASE | 197 | 213 | material | underground | Foundation Material |  |  | 1275.6 | 1275 | 1275 | 0.04706% | 0.04706% |  | 6.4751
2017 | Done | SUPABASE | 119 | 213 | material | underground | Foundation Material |  |  | 13364.65 | 15065 | 13365 | -11.29% | -0.002619% |  | 112.308
2018 | Done | SUPABASE | 211 | 213 | material | underground | Foundation Material |  |  | 5372.56 | 10600 | 10600 | -49.32% | -49.32% |  | 25.4624
2022 | Done | SUPABASE | 18 | 213 | material | underground | Foundation Material |  |  | 829 | [5 empty] | 46.0556
2024 | Done | V1 | 117 | 213 | material | underground | Foundation Material |  |  | 9.84 | [5 empty] | 0.084103
2001 | Done | SUPABASE | 234 | 220 | material | rough_in | Roughin Material |  |  | 148282.22 | 197530 | 197530 | -24.93% | -24.93% |  | 633.6847
2008 | Done | SUPABASE | 258 | 220 | material | rough_in | Roughin Material |  |  | 178543.02 | 247610 | 250830 | -27.89% | -28.82% |  | 692.0272
2009 | Done | SUPABASE | 56 | 220 | material | rough_in | Roughin Material |  |  | 30742.47 | 33560 | 32510 | -8.396% | -5.437% |  | 548.9727
2010 | Done | SUPABASE | 149 | 220 | material | rough_in | Roughin Material |  |  | 66457.52 | 204925 | 130025 | -67.57% | -48.89% |  | 446.0236
2011 | Done | SUPABASE | 117 | 220 | material | rough_in | Roughin Material |  |  | 48840.52 | 82540 | 82840 | -40.83% | -41.04% |  | 417.4403
2012 | Done | SUPABASE | 162 | 220 | material | rough_in | Roughin Material |  |  | 94000.7 | 161200 | 161200 | -41.69% | -41.69% |  | 580.2512
2015 | Done | SUPABASE | 197 | 220 | material | rough_in | Roughin Material |  |  | 176561.56 | 210065 | 212365 | -15.95% | -16.86% |  | 896.2516
2017 | Done | SUPABASE | 119 | 220 | material | rough_in | Roughin Material |  |  | 98571.05 | 138250 | 132050 | -28.7% | -25.35% |  | 828.3282
2018 | Done | SUPABASE | 211 | 220 | material | rough_in | Roughin Material |  |  | 141396.65 | 201680 | 201680 | -29.89% | -29.89% |  | 670.1263
2019 | Done | SUPABASE | 211 | 220 | material | rough_in | Roughin Material |  |  | 176444.92 | 212400 | 215686 | -16.93% | -18.19% |  | 836.2318
2020 | Done | SUPABASE | 256 | 220 | material | rough_in | Roughin Material |  |  | 87900.72 | 363580 | 213718 | -75.82% | -58.87% |  | 343.3622
2021 | Done | SUPABASE | 136 | 220 | material | rough_in | Roughin Material |  |  | 99695.01 | 145590 | 120660 | -31.52% | -17.38% |  | 733.0515
2022 | Done | SUPABASE | 18 | 220 | material | rough_in | Roughin Material |  |  | 20929.54 | 24340 | 24340 | -14.01% | -14.01% |  | 1162.7522
2023 | Done | V1 | 209 | 220 | material | rough_in | Roughin Material |  |  | 158305.23 | 156630 | 224127 | 1.07% | -29.37% |  | 757.4413
2024 | Done | V1 | 117 | 220 | material | rough_in | Roughin Material |  |  | 75249.36 | 122600 | 124334 | -38.62% | -39.48% |  | 643.1569
2025 | Done | V1 | 75 | 220 | material | rough_in | Roughin Material |  |  | 58515.95 | 76655 | 77101 | -23.66% | -24.1% |  | 780.2127
2026 | Done | V1 | 49 | 220 | material | rough_in | Roughin Material |  |  | 42655.4 | 60210 | 60210 | -29.16% | -29.16% |  | 870.5184
2027 | Done | V1 | 170 | 220 | material | rough_in | Roughin Material |  |  | 91274.89 | 153325 | 151625 | -40.47% | -39.8% |  | 536.9111
2028 | Done | V1 | 296 | 220 | material | rough_in | Roughin Material |  |  | 77241.99 | 149440 | 151272 | -48.31% | -48.94% |  | 260.9527
2029 | Done | V1 | 83 | 220 | material | rough_in | Roughin Material |  |  | 63196.04 | 79600 | 80398 | -20.61% | -21.4% |  | 761.3981
2030 | Done | V1 | 144 | 220 | material | rough_in | Roughin Material |  |  | 104992.07 | 141080 | 130320 | -25.58% | -19.44% |  | 729.1116
2031 | Done | V1 | 398 | 220 | material | rough_in | Roughin Material |  |  | 90966.27 | 142470 | 145264 | -36.15% | -37.38% |  | 228.5585
2032 | Done | V1 | 71 | 220 | material | rough_in | Roughin Material |  |  | 27891.8 | 48085 | 49835 | -41.99% | -44.03% |  | 392.8423
2033 | Done | V1 | 139 | 220 | material | rough_in | Roughin Material |  |  | 67263.77 | 294400 | 171617 | -77.15% | -60.81% |  | 483.912
2034 | Done | V1 | 128 | 220 | material | rough_in | Roughin Material |  |  | 100919.24 | 197820 | 201155 | -48.98% | -49.83% |  | 788.4316
2035 | Done | V1 | 92 | 220 | material | rough_in | Roughin Material |  |  | 17359.05 | 35575 | 35575 | -51.2% | -51.2% |  | 188.6853
2036 | Done | V1 | 31 | 220 | material | rough_in | Roughin Material |  |  | 21242.97 | 30375 | 30375 | -30.06% | -30.06% |  | 685.2571
2037 | Done | V1 | 122 | 220 | material | rough_in | Roughin Material |  |  | 106312.24 | 101645 | 105468 | 4.592% | 0.8005% |  | 871.4118
2038 | Done | V1 | 80 | 220 | material | rough_in | Roughin Material |  |  | 61984.15 | 83800 | 88698 | -26.03% | -30.12% |  | 774.8019
2039 | Done | V1 |  | 220 | material | rough_in | Roughin Material |  |  | 30.2
2040 | Done | V1 | 55 | 220 | material | rough_in | Roughin Material |  |  | 24915.98 | 32500 | 32895 | -23.34% | -24.26% |  | 453.0178
2041 | Done | V2.2 | 108 | 220 | material | rough_in | Roughin Material |  |  | 79004.39 | 90850 | 90170 | -13.04% | -12.38% |  | 731.5221
2042 | Done | V2.2 | 75 | 220 | material | rough_in | Roughin Material |  |  | 62128.4 | 74450 | 74650 | -16.55% | -16.77% |  | 828.3787
2043 | Done | V2.2 | 89 | 220 | material | rough_in | Roughin Material |  |  | 30692.52 | 53365 | 54365 | -42.49% | -43.54% |  | 344.8598
2044 | Done | V2.2 | 78 | 220 | material | rough_in | Roughin Material |  |  | 42382.13 | 44200 | 45350 | -4.113% | -6.544% |  | 543.3606
2045 | Done | V2.2 | 158 | 220 | material | rough_in | Roughin Material |  |  | 97191 | 153390 | 158260 | -36.64% | -38.59% |  | 615.1329
2046 | Done | V2.2 | 110 | 220 | material | rough_in | Roughin Material |  |  | 91683.71 | 129520 | 130335 | -29.21% | -29.66% |  | 833.4883
2047 | Done | V2.2 | 70 | 220 | material | rough_in | Roughin Material |  |  | 56003.99 | 59765 | 67358 | -6.293% | -16.86% |  | 800.057
2048 | Done | V2.2 | 72 | 220 | material | rough_in | Roughin Material |  |  | 51415.82 | 62505 | 63290 | -17.74% | -18.76% |  | 714.1086
2049 | Done | V2.2 | 296 | 220 | material | rough_in | Roughin Material |  |  | 140166.18 | 96000 | 96762 | 46.01% | 44.86% |  | 473.5344
2050 | Done | V2.2 | 50 | 220 | material | rough_in | Roughin Material |  |  | 40315.08 | 49945 | 50270 | -19.28% | -19.8% |  | 806.3016
2051 | Done | V2.2 | 163 | 220 | material | rough_in | Roughin Material |  |  | 47851.97 | 230840 | 145597 | -79.27% | -67.13% |  | 293.5704
2052 | Done | V2.2 | 107 | 220 | material | rough_in | Roughin Material |  |  | 87583.59 | 112170 | 118820 | -21.92% | -26.29% |  | 818.5382
2053 | Done | V2.2 | 136 | 220 | material | rough_in | Roughin Material |  |  | 74601.11 | 163620 | 166602 | -54.41% | -55.22% |  | 548.5376
2054 | Done | V2.2 | 68 | 220 | material | rough_in | Roughin Material |  |  | 34199.43 | 46890 | 49582 | -27.06% | -31.02% |  | 502.9328
2055 | Done | V2.2 | 98 | 220 | material | rough_in | Roughin Material |  |  | 84940.23 | 63421 | 70041 | 33.93% | 21.27% |  | 866.737
2056 | Done | V2.2 | 321 | 220 | material | rough_in | Roughin Material |  |  | 239543.21 | 429928 | 431128 | -44.28% | -44.44% |  | 746.2405
2057 | Done | V2.2 | 111 | 220 | material | rough_in | Roughin Material |  |  | 25828.61 | 53020 | 53020 | -51.29% | -51.29% |  | 232.6902
2058 | Done | V2.2 | 77 | 220 | material | rough_in | Roughin Material |  |  | 32023.13 | 43040 | 44540 | -25.6% | -28.1% |  | 415.8848
2059 | Done | V2.2 | 365 | 220 | material | rough_in | Roughin Material |  |  | 205612.27 | 342245 | 342415 | -39.92% | -39.95% |  | 563.3213
2060 | Done | V2.2 | 270 | 220 | material | rough_in | Roughin Material |  |  | 162471.68 | 205194 | 376194 | -20.82% | -56.81% |  | 601.747
2098 | LIVE | V2.2 | 170 | 220 | material | rough_in | Roughin Material |  |  | 266624.03 | 611575 | 623175 | -56.4% | -57.22% |  | 1568.3766
2103 | LIVE | V2.2 | 234 | 220 | material | rough_in | Roughin Material |  |  | 429974.35 | 636571 | 657496 | -32.45% | -34.6% |  | 1837.4972
2104 | LIVE | V2.2 | 24 | 220 | material | rough_in | Roughin Material |  |  | 18939.04 | 53635 | 53835 | -64.69% | -64.82% |  | 789.1267
2107 | LIVE | V2.2 | 244 | 220 | material | rough_in | Roughin Material |  |  | 209687.42 | 381860 | 392310 | -45.09% | -46.55% |  | 859.3747
2111 | LIVE | V_TX | 186 | 220 | material | rough_in | Roughin Material |  |  | 224000.12 | 465420 | 466720 | -51.87% | -52.01% |  | 1204.3017
2112 | LIVE | V_TX | 20 | 220 | material | rough_in | Roughin Material |  |  | 32236.67 | 37330 | 37810 | -13.64% | -14.74% |  | 1611.8335
2001 | Done | SUPABASE | 234 | 230 | material | trim_finish | Finish Material |  |  | 327741.23 | 372749 | 372749 | -12.07% | -12.07% |  | 1400.6035
2008 | Done | SUPABASE | 258 | 230 | material | trim_finish | Finish Material |  |  | 428881.3 | 498050 | 521715 | -13.89% | -17.79% |  | 1662.3306
2009 | Done | SUPABASE | 56 | 230 | material | trim_finish | Finish Material |  |  | 109975.66 | 143270 | 143381 | -23.24% | -23.3% |  | 1963.8511
2010 | Done | SUPABASE | 149 | 230 | material | trim_finish | Finish Material |  |  | 173652.72 | 261700 | 251305 | -33.64% | -30.9% |  | 1165.4545
2011 | Done | SUPABASE | 117 | 230 | material | trim_finish | Finish Material |  |  | 207101.2 | 231620 | 259734 | -10.59% | -20.26% |  | 1770.0957
2012 | Done | SUPABASE | 162 | 230 | material | trim_finish | Finish Material |  |  | 210145.22 | 261600 | 269866 | -19.67% | -22.13% |  | 1297.1927
2015 | Done | SUPABASE | 197 | 230 | material | trim_finish | Finish Material |  |  | 337546.71 | 466740 | 483149 | -27.68% | -30.14% |  | 1713.4351
2017 | Done | SUPABASE | 119 | 230 | material | trim_finish | Finish Material |  |  | 192296.61 | 273100 | 248951 | -29.59% | -22.76% |  | 1615.9379
2018 | Done | SUPABASE | 211 | 230 | material | trim_finish | Finish Material |  |  | 272549.22 | 390477 | 336907 | -30.2% | -19.1% |  | 1291.7025
2019 | Done | SUPABASE | 211 | 230 | material | trim_finish | Finish Material |  |  | 313722.19 | 461500 | 488611 | -32.02% | -35.79% |  | 1486.835
2020 | Done | SUPABASE | 256 | 230 | material | trim_finish | Finish Material |  |  | 411991.97 | 478500 | 526401 | -13.9% | -21.73% |  | 1609.3436
2021 | Done | SUPABASE | 136 | 230 | material | trim_finish | Finish Material |  |  | 202739.69 | 256900 | 260675 | -21.08% | -22.23% |  | 1490.733
2022 | Done | SUPABASE | 18 | 230 | material | trim_finish | Finish Material |  |  | 32656.07 | 52590 | 59219 | -37.9% | -44.86% |  | 1814.2261
2023 | Done | V1 | 209 | 230 | material | trim_finish | Finish Material |  |  | 287126.83 | 496970 | 491330 | -42.22% | -41.56% |  | 1373.8126
2024 | Done | V1 | 117 | 230 | material | trim_finish | Finish Material |  |  | 70943.89 | 267000 | 276405 | -73.43% | -74.33% |  | 606.358
2025 | Done | V1 | 75 | 230 | material | trim_finish | Finish Material |  |  | 110946.04 | 105200 | 104606.5 | 5.462% | 6.06% |  | 1479.2805
2026 | Done | V1 | 49 | 230 | material | trim_finish | Finish Material |  |  | 68397.28 | 78595 | 82765 | -12.98% | -17.36% |  | 1395.8629
2027 | Done | V1 | 170 | 230 | material | trim_finish | Finish Material |  |  | 220048.68 | 224100 | 238053 | -1.808% | -7.563% |  | 1294.404
2028 | Done | V1 | 296 | 230 | material | trim_finish | Finish Material |  |  | 140999.27 | 283585 | 143340 | -50.28% | -1.633% |  | 476.3489
2029 | Done | V1 | 83 | 230 | material | trim_finish | Finish Material |  |  | 82322 | 94600 | 95549.5 | -12.98% | -13.84% |  | 991.8313
2030 | Done | V1 | 144 | 230 | material | trim_finish | Finish Material |  |  | 290680.64 | 209900 | 321508 | 38.49% | -9.588% |  | 2018.6156
2031 | Done | V1 | 398 | 230 | material | trim_finish | Finish Material |  |  | 268692.84 | 264020 | 230010 | 1.77% | 16.82% |  | 675.1076
2032 | Done | V1 | 71 | 230 | material | trim_finish | Finish Material |  |  | 98389.06 | 79470 | 92626 | 23.81% | 6.222% |  | 1385.7614
2033 | Done | V1 | 139 | 230 | material | trim_finish | Finish Material |  |  | 219513.43 | 222560 | 197050 | -1.369% | 11.4% |  | 1579.2333
2034 | Done | V1 | 128 | 230 | material | trim_finish | Finish Material |  |  | 181853.14 | 195710 | 188997 | -7.08% | -3.78% |  | 1420.7277
2035 | Done | V1 | 92 | 230 | material | trim_finish | Finish Material |  |  | 96906.5 | 96100 | 94265 | 0.8392% | 2.802% |  | 1053.3315
2036 | Done | V1 | 31 | 230 | material | trim_finish | Finish Material |  |  | 65661.22 | 62775 | 73757 | 4.598% | -10.98% |  | 2118.1039
2037 | Done | V1 | 122 | 230 | material | trim_finish | Finish Material |  |  | 273944.52 | 187500 | 331860 | 46.1% | -17.45% |  | 2245.4469
2038 | Done | V1 | 80 | 230 | material | trim_finish | Finish Material |  |  | 116427.88 | 137370 | 109090 | -15.25% | 6.726% |  | 1455.3485
2040 | Done | V1 | 55 | 230 | material | trim_finish | Finish Material |  |  | 88855.74 | 68220 | 79636 | 30.25% | 11.58% |  | 1615.5589
2041 | Done | V2.2 | 108 | 230 | material | trim_finish | Finish Material |  |  | 251663.7 | 311040 | 337431 | -19.09% | -25.42% |  | 2330.2194
2042 | Done | V2.2 | 75 | 230 | material | trim_finish | Finish Material |  |  | 148333.68 | 162699 | 168539 | -8.829% | -11.99% |  | 1977.7824
2043 | Done | V2.2 | 89 | 230 | material | trim_finish | Finish Material |  |  | 200687.65 | 328175 | 321400 | -38.85% | -37.56% |  | 2254.9174
2044 | Done | V2.2 | 78 | 230 | material | trim_finish | Finish Material |  |  | 133693.08 | 147457 | 163316 | -9.334% | -18.14% |  | 1714.0138
2045 | Done | V2.2 | 158 | 230 | material | trim_finish | Finish Material |  |  | 293213.41 | 274850 | 325525 | 6.681% | -9.926% |  | 1855.7811
2046 | Done | V2.2 | 110 | 230 | material | trim_finish | Finish Material |  |  | 199016.45 | 226119 | 255231 | -11.99% | -22.02% |  | 1809.2405
2047 | Done | V2.2 | 70 | 230 | material | trim_finish | Finish Material |  |  | 77180.43 | 89920 | 105538 | -14.17% | -26.87% |  | 1102.5776
2048 | Done | V2.2 | 72 | 230 | material | trim_finish | Finish Material |  |  | 64020.72 | 81287 | 86964 | -21.24% | -26.38% |  | 889.1767
2049 | Done | V2.2 | 296 | 230 | material | trim_finish | Finish Material |  |  | 335404.06 | 334600 | 347595 | 0.2403% | -3.507% |  | 1133.1218
2050 | Done | V2.2 | 50 | 230 | material | trim_finish | Finish Material |  |  | 111207.3 | 180170 | 182982 | -38.28% | -39.23% |  | 2224.146
2051 | Done | V2.2 | 163 | 230 | material | trim_finish | Finish Material |  |  | 281538.12 | 332585 | 352190 | -15.35% | -20.06% |  | 1727.2277
2052 | Done | V2.2 | 107 | 230 | material | trim_finish | Finish Material |  |  | 273004.96 | 404000 | 419844 | -32.42% | -34.97% |  | 2551.4482
2053 | Done | V2.2 | 136 | 230 | material | trim_finish | Finish Material |  |  | 287966.65 | 371637 | 366745 | -22.51% | -21.48% |  | 2117.4018
2054 | Done | V2.2 | 68 | 230 | material | trim_finish | Finish Material |  |  | 147852.36 | 129526 | 169700 | 14.15% | -12.87% |  | 2174.2994
2055 | Done | V2.2 | 98 | 230 | material | trim_finish | Finish Material |  |  | 216460.37 | 238986 | 255066 | -9.426% | -15.14% |  | 2208.7793
2056 | Done | V2.2 | 321 | 230 | material | trim_finish | Finish Material |  |  | 650099 | 867882 | 870472 | -25.09% | -25.32% |  | 2025.2305
2057 | Done | V2.2 | 111 | 230 | material | trim_finish | Finish Material |  |  | 141842.79 | 253455 | 260209 | -44.04% | -45.49% |  | 1277.863
2058 | Done | V2.2 | 77 | 230 | material | trim_finish | Finish Material |  |  | 150779.38 | 159654 | 169208 | -5.559% | -10.89% |  | 1958.1738
2059 | Done | V2.2 | 365 | 230 | material | trim_finish | Finish Material |  |  | 682969.44 | 828580 | 866635 | -17.57% | -21.19% |  | 1871.1492
2060 | Done | V2.2 | 270 | 230 | material | trim_finish | Finish Material |  |  | 539813.97 | 875550 | 998490 | -38.35% | -45.94% |  | 1999.311
2098 | LIVE | V2.2 | 170 | 230 | material | trim_finish | Finish Material |  |  | 912915.01 | 1131147 | 1114762 | -19.29% | -18.11% |  | 5370.0883
2103 | LIVE | V2.2 | 234 | 230 | material | trim_finish | Finish Material |  |  | 971188.26 | 1011650 | 1140441 | -4% | -14.84% |  | 4150.3772
2104 | LIVE | V2.2 | 24 | 230 | material | trim_finish | Finish Material |  |  | 343464.97 | 384025 | 411659 | -10.56% | -16.57% |  | 14311.0404
2107 | LIVE | V2.2 | 244 | 230 | material | trim_finish | Finish Material |  |  | 546778.65 | 1068397 | 1055804 | -48.82% | -48.21% |  | 2240.8961
2111 | LIVE | V_TX | 186 | 230 | material | trim_finish | Finish Material |  |  | 43213.45 | 835905 | 841755 | -94.83% | -94.87% |  | 232.3304
2112 | LIVE | V_TX | 20 | 230 | material | trim_finish | Finish Material |  |  | 42798.91 | 198762 | 213937 | -78.47% | -79.99% |  | 2139.9455
2001 | Done | SUPABASE | 234 | 240 | material | gas | Gas Material |  |  | 10163.67 | 7500 | 7500 | 35.52% | 35.52% |  | 43.4345
2008 | Done | SUPABASE | 258 | 240 | material | gas | Gas Material |  |  | 11391.29 | 18000 | 18300 | -36.72% | -37.75% |  | 44.1523
2010 | Done | SUPABASE | 149 | 240 | material | gas | Gas Material |  |  | 1080.05 | 3600 | 3600 | -70% | -70% |  | 7.2487
2012 | Done | SUPABASE | 162 | 240 | material | gas | Gas Material |  |  | 996.32 | 3000 | 3000 | -66.79% | -66.79% |  | 6.1501
2015 | Done | SUPABASE | 197 | 240 | material | gas | Gas Material |  |  | 6984.66 | 3350 | 6250 | 108.5% | 11.75% |  | 35.4551
2017 | Done | SUPABASE | 119 | 240 | material | gas | Gas Material |  |  | 2769 | 3600 | 3600 | -23.08% | -23.08% |  | 23.2689
2018 | Done | SUPABASE | 211 | 240 | material | gas | Gas Material |  |  | 3578.52 | 10800 | 10800 | -66.87% | -66.87% |  | 16.9598
2019 | Done | SUPABASE | 211 | 240 | material | gas | Gas Material |  |  | 4568.01 | 10300 | 10532 | -55.65% | -56.63% |  | 21.6493
2020 | Done | SUPABASE | 256 | 240 | material | gas | Gas Material |  |  | 8263.12 | 12600 | 12800 | -34.42% | -35.44% |  | 32.2778
2021 | Done | SUPABASE | 136 | 240 | material | gas | Gas Material |  |  | 3604.09 | 5500 | 7369 | -34.47% | -51.09% |  | 26.5007
2023 | Done | V1 | 209 | 240 | material | gas | Gas Material |  |  | 4873.37 | 5500 | 8897 | -11.39% | -45.22% |  | 23.3176
2024 | Done | V1 | 117 | 240 | material | gas | Gas Material |  |  | 4159.94 | 7200 | 7200 | -42.22% | -42.22% |  | 35.555
2025 | Done | V1 | 75 | 240 | material | gas | Gas Material |  |  | 1507.91 | 5500 | 6088 | -72.58% | -75.23% |  | 20.1055
2026 | Done | V1 | 49 | 240 | material | gas | Gas Material |  |  | 625.77 | 3600 | 3600 | -82.62% | -82.62% |  | 12.7708
2027 | Done | V1 | 170 | 240 | material | gas | Gas Material |  |  | 1363.51 | 7800 | 7800 | -82.52% | -82.52% |  | 8.0206
2028 | Done | V1 | 296 | 240 | material | gas | Gas Material |  |  | 4382.08 | 9600 | 9600 | -54.35% | -54.35% |  | 14.8043
2029 | Done | V1 | 83 | 240 | material | gas | Gas Material |  |  | 1057.3 | 2400 | 2987 | -55.95% | -64.6% |  | 12.7386
2030 | Done | V1 | 144 | 240 | material | gas | Gas Material |  |  | 3056.66 | 9400 | 12033 | -67.48% | -74.6% |  | 21.2268
2031 | Done | V1 | 398 | 240 | material | gas | Gas Material |  |  | 5822.71 | 10400 | 10930 | -44.01% | -46.73% |  | 14.6299
2032 | Done | V1 | 71 | 240 | material | gas | Gas Material |  |  | 1008.16 | 3500 | 3500 | -71.2% | -71.2% |  | 14.1994
2033 | Done | V1 | 139 | 240 | material | gas | Gas Material |  |  | 2339.62 | 11600 | 11600 | -79.83% | -79.83% |  | 16.8318
2034 | Done | V1 | 128 | 240 | material | gas | Gas Material |  |  | 3977.41 | 9450 | 10350 | -57.91% | -61.57% |  | 31.0735
2037 | Done | V1 | 122 | 240 | material | gas | Gas Material |  |  | 4633.76 | 5625 | 5625 | -17.62% | -17.62% |  | 37.9816
2038 | Done | V1 | 80 | 240 | material | gas | Gas Material |  |  | 1301.17 | 7000 | 7250 | -81.41% | -82.05% |  | 16.2646
2039 | Done | V1 |  | 240 | material | gas | Gas Material |  |  | 2667.14 | 10650 | 10650 | -74.96% | -74.96%
2040 | Done | V1 | 55 | 240 | material | gas | Gas Material |  |  | 1504.45 | 6750 | 6750 | -77.71% | -77.71% |  | 27.3536
2041 | Done | V2.2 | 108 | 240 | material | gas | Gas Material |  |  | 4155.07 | 5250 | 5580 | -20.86% | -25.54% |  | 38.4729
2042 | Done | V2.2 | 75 | 240 | material | gas | Gas Material |  |  | 665.67 | 7150 | 7150 | -90.69% | -90.69% |  | 8.8756
2043 | Done | V2.2 | 89 | 240 | material | gas | Gas Material |  |  | 3780.25 | 14400 | 14400 | -73.75% | -73.75% |  | 42.4747
2044 | Done | V2.2 | 78 | 240 | material | gas | Gas Material |  |  | 2098.38 | 6800 | 6800 | -69.14% | -69.14% |  | 26.9023
2045 | Done | V2.2 | 158 | 240 | material | gas | Gas Material |  |  | 63.72 | [5 empty] | 0.40329
2046 | Done | V2.2 | 110 | 240 | material | gas | Gas Material |  |  | 2670.82 | 4000 | 4000 | -33.23% | -33.23% |  | 24.2802
2049 | Done | V2.2 | 296 | 240 | material | gas | Gas Material |  |  | 11428.68 | 6000 | 7500 | 90.48% | 52.38% |  | 38.6104
2050 | Done | V2.2 | 50 | 240 | material | gas | Gas Material |  |  | 1913.88 | 6050 | 6150 | -68.37% | -68.88% |  | 38.2776
2051 | Done | V2.2 | 163 | 240 | material | gas | Gas Material |  |  | 5341.44 | 9800 | 12214 | -45.5% | -56.27% |  | 32.7696
2052 | Done | V2.2 | 107 | 240 | material | gas | Gas Material |  |  | 6559.15 | 7500 | 8425 | -12.54% | -22.15% |  | 61.3005
2053 | Done | V2.2 | 136 | 240 | material | gas | Gas Material |  |  | 6882.96 | 18450 | 18838 | -62.69% | -63.46% |  | 50.61
2054 | Done | V2.2 | 68 | 240 | material | gas | Gas Material |  |  | 3477.36 | 8500 | 8500 | -59.09% | -59.09% |  | 51.1376
2055 | Done | V2.2 | 98 | 240 | material | gas | Gas Material |  |  | 4654.15 | 6000 | 6000 | -22.43% | -22.43% |  | 47.4913
2056 | Done | V2.2 | 321 | 240 | material | gas | Gas Material |  |  | 8134.74 | 27000 | 28800 | -69.87% | -71.75% |  | 25.3419
2057 | Done | V2.2 | 111 | 240 | material | gas | Gas Material |  |  | 1138.79 | 10800 | 10972 | -89.46% | -89.62% |  | 10.2594
2058 | Done | V2.2 | 77 | 240 | material | gas | Gas Material |  |  | 3600.92 | 11050 | 11250 | -67.41% | -67.99% |  | 46.7652
2059 | Done | V2.2 | 365 | 240 | material | gas | Gas Material |  |  | 6691.94 | 7650 | 7650 | -12.52% | -12.52% |  | 18.3341
2060 | Done | V2.2 | 270 | 240 | material | gas | Gas Material |  |  | 13263.56 | 78000 | 71950 | -83% | -81.57% |  | 49.1243
2098 | LIVE | V2.2 | 170 | 240 | material | gas | Gas Material |  |  | 14686.12 | 10450 | 22400 | 40.54% | -34.44% |  | 86.3889
2103 | LIVE | V2.2 | 234 | 240 | material | gas | Gas Material |  |  | 14023.31 | 8463 | 21708 | 65.7% | -35.4% |  | 59.9287
2104 | LIVE | V2.2 | 24 | 240 | material | gas | Gas Material |  |  | 2063.38 | 7500 | 7500 | -72.49% | -72.49% |  | 85.9742
2107 | LIVE | V2.2 | 244 | 240 | material | gas | Gas Material |  |  | 7204.51 | 5400 | 8500 | 33.42% | -15.24% |  | 29.5267
2001 | Done | SUPABASE | 234 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 75553.36 | 30250 | 30250 | 149.8% | 149.8% |  | 322.8776
2008 | Done | SUPABASE | 258 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 80448.24 | 66750 | 66750 | 20.52% | 20.52% |  | 311.8149
2009 | Done | SUPABASE | 56 | 241 | material | water_main | Water Main/Insulation Mat
2010 | Done | SUPABASE | 149 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 20000.49 | 14900 | 33900 | 34.23% | -41% |  | 134.2315
2011 | Done | SUPABASE | 117 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 15147.02 | 7800 | 7800 | 94.19% | 94.19% |  | 129.4617
2012 | Done | SUPABASE | 162 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 36964.67 | 65600 | 65600 | -43.65% | -43.65% |  | 228.177
2015 | Done | SUPABASE | 197 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 46749.33 | 60900 | 60900 | -23.24% | -23.24% |  | 237.3062
2017 | Done | SUPABASE | 119 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 45904.61 | 51200 | 51200 | -10.34% | -10.34% |  | 385.753
2018 | Done | SUPABASE | 211 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 48338.27 | 87250 | 87250 | -44.6% | -44.6% |  | 229.0913
2019 | Done | SUPABASE | 211 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 69305.69 | 83500 | 83775 | -17% | -17.27% |  | 328.463
2020 | Done | SUPABASE | 256 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 122165.25 | 92600 | 93431 | 31.93% | 30.75% |  | 477.208
2021 | Done | SUPABASE | 136 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 49938.59 | 45175 | 45275 | 10.54% | 10.3% |  | 367.1955
2023 | Done | V1 | 209 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 77345.28 | 76300 | 76847 | 1.37% | 0.6484% |  | 370.0731
2024 | Done | V1 | 117 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 50657.33 | 59400 | 59400 | -14.72% | -14.72% |  | 432.9686
2025 | Done | V1 | 75 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 19584.74 | 42330 | 42330 | -53.73% | -53.73% |  | 261.1299
2026 | Done | V1 | 49 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 21103.03 | 32420 | 32420 | -34.91% | -34.91% |  | 430.6741
2027 | Done | V1 | 170 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 71604.01 | 79900 | 80900 | -10.38% | -11.49% |  | 421.2001
2028 | Done | V1 | 296 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 97106.59 | 148955 | 148955 | -34.81% | -34.81% |  | 328.0628
2029 | Done | V1 | 83 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 26177.22 | 40200 | 40200 | -34.88% | -34.88% |  | 315.3882
2030 | Done | V1 | 144 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 46541.31 | 79050 | 87248 | -41.12% | -46.66% |  | 323.2035
2031 | Done | V1 | 398 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 48502.22 | 59980 | 62068 | -19.14% | -21.86% |  | 121.8649
2032 | Done | V1 | 71 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 21425.26 | 33025 | 33025 | -35.12% | -35.12% |  | 301.7642
2033 | Done | V1 | 139 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 67464.44 | 59175 | 59933 | 14.01% | 12.57% |  | 485.3557
2034 | Done | V1 | 128 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 56230.79 | 55000 | 56140 | 2.238% | 0.1617% |  | 439.303
2035 | Done | V1 | 92 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 17346.53 | 36000 | 36300 | -51.82% | -52.21% |  | 188.5492
2036 | Done | V1 | 31 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 9614.37 | 3320 | 3917 | 189.6% | 145.5% |  | 310.141
2037 | Done | V1 | 122 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 33059.1 | 66355 | 66355 | -50.18% | -50.18% |  | 270.9762
2038 | Done | V1 | 80 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 32240.09 | 38115 | 36610 | -15.41% | -11.94% |  | 403.0011
2040 | Done | V1 | 55 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 17052.68 | 22530 | 22530 | -24.31% | -24.31% |  | 310.0487
2041 | Done | V2.2 | 108 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 62146.49 | 50200 | 51126 | 23.8% | 21.56% |  | 575.4305
2042 | Done | V2.2 | 75 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 13163.4 | 8935 | 8935 | 47.32% | 47.32% |  | 175.512
2043 | Done | V2.2 | 89 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 29819.24 | 51400 | 52597 | -41.99% | -43.31% |  | 335.0476
2044 | Done | V2.2 | 78 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 14099.66 | 26630 | 26630 | -47.05% | -47.05% |  | 180.7649
2045 | Done | V2.2 | 158 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 65243.62 | 34700 | 44525 | 88.02% | 46.53% |  | 412.9343
2046 | Done | V2.2 | 110 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 39917.5 | 39165 | 39740 | 1.921% | 0.4467% |  | 362.8864
2048 | Done | V2.2 | 72 | 241 | material | water_main | Water Main/Insulation Mat
2049 | Done | V2.2 | 296 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 96552.88 | 127400 | 127400 | -24.21% | -24.21% |  | 326.1922
2050 | Done | V2.2 | 50 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 20655.61 | 20400 | 20400 | 1.253% | 1.253% |  | 413.1122
2051 | Done | V2.2 | 163 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 43355.63 | 51400 | 51400 | -15.65% | -15.65% |  | 265.9855
2052 | Done | V2.2 | 107 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 41276.8 | 69550 | 69550 | -40.65% | -40.65% |  | 385.7645
2053 | Done | V2.2 | 136 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 45462.73 | 57400 | 57623 | -20.8% | -21.1% |  | 334.2848
2054 | Done | V2.2 | 68 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 18210.35 | 26265 | 26265 | -30.67% | -30.67% |  | 267.7993
2055 | Done | V2.2 | 98 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 32273.25 | 33530 | 37230 | -3.748% | -13.31% |  | 329.3189
2056 | Done | V2.2 | 321 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 103675.54 | 205659 | 206189 | -49.59% | -49.72% |  | 322.9768
2057 | Done | V2.2 | 111 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 30721.75 | 47140 | 48750 | -34.83% | -36.98% |  | 276.7725
2058 | Done | V2.2 | 77 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 16093.43 | 30640 | 30640 | -47.48% | -47.48% |  | 209.0056
2059 | Done | V2.2 | 365 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 57918.56 | 84760 | 84760 | -31.67% | -31.67% |  | 158.681
2060 | Done | V2.2 | 270 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 134603.6 | 189170 | 195680 | -28.85% | -31.21% |  | 498.5319
2098 | LIVE | V2.2 | 170 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 121627.31 | 136575 | 138575 | -10.94% | -12.23% |  | 715.4548
2103 | LIVE | V2.2 | 234 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 126781.38 | 192848 | 207528 | -34.26% | -38.91% |  | 541.8008
2104 | LIVE | V2.2 | 24 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 31392.49 | 24065 | 25015 | 30.45% | 25.49% |  | 1308.0204
2107 | LIVE | V2.2 | 244 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 137969.26 | 180900 | 189150 | -23.73% | -27.06% |  | 565.4478
2111 | LIVE | V_TX | 186 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 15782.52 | 147575 | 159775 | -89.31% | -90.12% |  | 84.8523
2112 | LIVE | V_TX | 20 | 241 | material | water_main | Water Main/Insulation Mat |  |  | 11818.6 | 15010 | 15240 | -21.26% | -22.45% |  | 590.93
2001 | Done | SUPABASE | 234 | 242 | material | mech_room | Mech Room Material |  |  | 2968.89 | 5000 | 5000 | -40.62% | -40.62% |  | 12.6876
2008 | Done | SUPABASE | 258 | 242 | material | mech_room | Mech Room Material |  |  | 2236.93 | 5400 | 5400 | -58.58% | -58.58% |  | 8.6703
2009 | Done | SUPABASE | 56 | 242 | material | mech_room | Mech Room Material |  |  | 641.45 | 2000 | 2000 | -67.93% | -67.93% |  | 11.4545
2010 | Done | SUPABASE | 149 | 242 | material | mech_room | Mech Room Material |  |  | 1098.46 | [5 empty] | 7.3722
2011 | Done | SUPABASE | 117 | 242 | material | mech_room | Mech Room Material |  |  | 1233.58 | 2500 | 2500 | -50.66% | -50.66% |  | 10.5434
2012 | Done | SUPABASE | 162 | 242 | material | mech_room | Mech Room Material |  |  | 22695.31 | 12000 | 12000 | 89.13% | 89.13% |  | 140.0945
2015 | Done | SUPABASE | 197 | 242 | material | mech_room | Mech Room Material |  |  | 29343.46 | 12000 | 12000 | 144.5% | 144.5% |  | 148.9516
2017 | Done | SUPABASE | 119 | 242 | material | mech_room | Mech Room Material |  |  | 8987.73 | 12000 | 12000 | -25.1% | -25.1% |  | 75.5271
2018 | Done | SUPABASE | 211 | 242 | material | mech_room | Mech Room Material |  |  | 1947.18 | 5520 | 5520 | -64.72% | -64.72% |  | 9.2283
2019 | Done | SUPABASE | 211 | 242 | material | mech_room | Mech Room Material |  |  | 24175.21 | 32500 | 32500 | -25.61% | -25.61% |  | 114.5745
2020 | Done | SUPABASE | 256 | 242 | material | mech_room | Mech Room Material |  |  | 2198.97 | 7000 | 7952 | -68.59% | -72.35% |  | 8.5897
2021 | Done | SUPABASE | 136 | 242 | material | mech_room | Mech Room Material |  |  | 5.44 | [5 empty] | 0.04
2022 | Done | SUPABASE | 18 | 242 | material | mech_room | Mech Room Material |  |  | 2510.08 | [5 empty] | 139.4489
2023 | Done | V1 | 209 | 242 | material | mech_room | Mech Room Material |  |  | 105558.69 | 22500 | 22500 | 369.1% | 369.1% |  | 505.0655
2024 | Done | V1 | 117 | 242 | material | mech_room | Mech Room Material |  |  | 76386.17 | 29000 | 30622 | 163.4% | 149.4% |  | 652.8732
2025 | Done | V1 | 75 | 242 | material | mech_room | Mech Room Material |  |  | 36585.89 | 82200 | 82926 | -55.49% | -55.88% |  | 487.8119
2026 | Done | V1 | 49 | 242 | material | mech_room | Mech Room Material |  |  | 33752.74 | 53250 | 53250 | -36.61% | -36.61% |  | 688.8314
2027 | Done | V1 | 170 | 242 | material | mech_room | Mech Room Material |  |  | 99306.42 | 123300 | 123300 | -19.46% | -19.46% |  | 584.1554
2028 | Done | V1 | 296 | 242 | material | mech_room | Mech Room Material |  |  | 68176.58 | 75350 | 84131 | -9.52% | -18.96% |  | 230.3263
2029 | Done | V1 | 83 | 242 | material | mech_room | Mech Room Material |  |  | 53061.22 | 68600 | 69326 | -22.65% | -23.46% |  | 639.2918
2030 | Done | V1 | 144 | 242 | material | mech_room | Mech Room Material |  |  | 27223.2 | 130300 | 50965 | -79.11% | -46.58% |  | 189.05
2031 | Done | V1 | 398 | 242 | material | mech_room | Mech Room Material |  |  | 38991.48 | 102264 | 113823 | -61.87% | -65.74% |  | 97.9685
2032 | Done | V1 | 71 | 242 | material | mech_room | Mech Room Material |  |  | 11291.75 | 32450 | 39250 | -65.2% | -71.23% |  | 159.0387
2033 | Done | V1 | 139 | 242 | material | mech_room | Mech Room Material |  |  | 43786.76 | 125650 | 127123 | -65.15% | -65.56% |  | 315.0127
2034 | Done | V1 | 128 | 242 | material | mech_room | Mech Room Material |  |  | 22432.91 | 92575 | 70135 | -75.77% | -68.01% |  | 175.2571
2035 | Done | V1 | 92 | 242 | material | mech_room | Mech Room Material |  |  | 7233.3 | 6000 | 6000 | 20.55% | 20.55% |  | 78.6228
2037 | Done | V1 | 122 | 242 | material | mech_room | Mech Room Material |  |  | 24688.69 | 102185 | 32687 | -75.84% | -24.47% |  | 202.3663
2038 | Done | V1 | 80 | 242 | material | mech_room | Mech Room Material |  |  | 13768.11 | 59460 | 59760 | -76.84% | -76.96% |  | 172.1014
2040 | Done | V1 | 55 | 242 | material | mech_room | Mech Room Material |  |  | 15297.78 | 28770 | 28770 | -46.83% | -46.83% |  | 278.1415
2041 | Done | V2.2 | 108 | 242 | material | mech_room | Mech Room Material |  |  | 19825.43 | 22500 | 22500 | -11.89% | -11.89% |  | 183.5688
2042 | Done | V2.2 | 75 | 242 | material | mech_room | Mech Room Material |  |  | 16059.71 | 38400 | 38653 | -58.18% | -58.45% |  | 214.1295
2043 | Done | V2.2 | 89 | 242 | material | mech_room | Mech Room Material |  |  | 12806.38 | 30800 | 33306 | -58.42% | -61.55% |  | 143.8919
2044 | Done | V2.2 | 78 | 242 | material | mech_room | Mech Room Material |  |  | 15511.19 | 12500 | 12500 | 24.09% | 24.09% |  | 198.8614
2045 | Done | V2.2 | 158 | 242 | material | mech_room | Mech Room Material |  |  | 7101 | 7000 | 10000 | 1.443% | -28.99% |  | 44.943
2046 | Done | V2.2 | 110 | 242 | material | mech_room | Mech Room Material |  |  | 24087.86 | 13750 | 15250 | 75.18% | 57.95% |  | 218.9805
2047 | Done | V2.2 | 70 | 242 | material | mech_room | Mech Room Material
2049 | Done | V2.2 | 296 | 242 | material | mech_room | Mech Room Material |  |  | 27383.35 | 33200 | 33500 | -17.52% | -18.26% |  | 92.5113
2050 | Done | V2.2 | 50 | 242 | material | mech_room | Mech Room Material |  |  | 10877.78 | 13500 | 13500 | -19.42% | -19.42% |  | 217.5556
2051 | Done | V2.2 | 163 | 242 | material | mech_room | Mech Room Material |  |  | 20399.37 | 20400 | 20400 | -0.003088% | -0.003088% |  | 125.1495
2052 | Done | V2.2 | 107 | 242 | material | mech_room | Mech Room Material |  |  | 15179.21 | 20000 | 22000 | -24.1% | -31% |  | 141.8618
2053 | Done | V2.2 | 136 | 242 | material | mech_room | Mech Room Material |  |  | 20788.7 | 44000 | 44000 | -52.75% | -52.75% |  | 152.8581
2054 | Done | V2.2 | 68 | 242 | material | mech_room | Mech Room Material |  |  | 22105.44 | 12500 | 12500 | 76.84% | 76.84% |  | 325.08
2055 | Done | V2.2 | 98 | 242 | material | mech_room | Mech Room Material |  |  | 29539.9 | 16250 | 16250 | 81.78% | 81.78% |  | 301.4276
2056 | Done | V2.2 | 321 | 242 | material | mech_room | Mech Room Material |  |  | 79516.1 | 94000 | 94000 | -15.41% | -15.41% |  | 247.7137
2057 | Done | V2.2 | 111 | 242 | material | mech_room | Mech Room Material |  |  | 7324.66 | 7000 | 7200 | 4.638% | 1.731% |  | 65.9879
2058 | Done | V2.2 | 77 | 242 | material | mech_room | Mech Room Material |  |  | 17680.02 | 15000 | 15000 | 17.87% | 17.87% |  | 229.6106
2059 | Done | V2.2 | 365 | 242 | material | mech_room | Mech Room Material |  |  | 7790.2 | 21500 | 21500 | -63.77% | -63.77% |  | 21.343
2060 | Done | V2.2 | 270 | 242 | material | mech_room | Mech Room Material |  |  | 69474.91 | 40000 | 40000 | 73.69% | 73.69% |  | 257.3145
2098 | LIVE | V2.2 | 170 | 242 | material | mech_room | Mech Room Material |  |  | 58031.73 | 71500 | 71500 | -18.84% | -18.84% |  | 341.3631
2103 | LIVE | V2.2 | 234 | 242 | material | mech_room | Mech Room Material |  |  | 71241.58 | 102300 | 109400 | -30.36% | -34.88% |  | 304.4512
2104 | LIVE | V2.2 | 24 | 242 | material | mech_room | Mech Room Material |  |  | 28522.36 | 44400 | 44400 | -35.76% | -35.76% |  | 1188.4317
2107 | LIVE | V2.2 | 244 | 242 | material | mech_room | Mech Room Material |  |  | 82317.36 | 126000 | 125800 | -34.67% | -34.56% |  | 337.3662
2023 | Done | V1 | 209 | 243 | material | condensation | Condensation Drains Mat |  |  | 182.88 | [5 empty] | 0.87502
2024 | Done | V1 | 117 | 243 | material | condensation | Condensation Drains Mat |  |  | 1704 |  | 45 |  | 3687% |  | 14.5641
2026 | Done | V1 | 49 | 243 | material | condensation | Condensation Drains Mat |  |  | 27.08 | [5 empty] | 0.55265
2027 | Done | V1 | 170 | 243 | material | condensation | Condensation Drains Mat |  |  | 15.84 | [5 empty] | 0.093176
2028 | Done | V1 | 296 | 243 | material | condensation | Condensation Drains Mat |  |  | 38.65 | [5 empty] | 0.13057
2029 | Done | V1 | 83 | 243 | material | condensation | Condensation Drains Mat |  |  | 13.2 | [5 empty] | 0.15904
2030 | Done | V1 | 144 | 243 | material | condensation | Condensation Drains Mat |  |  | 21.41 | [5 empty] | 0.14868
2031 | Done | V1 | 398 | 243 | material | condensation | Condensation Drains Mat |  |  | 6.64 | [5 empty] | 0.016683
2032 | Done | V1 | 71 | 243 | material | condensation | Condensation Drains Mat
2033 | Done | V1 | 139 | 243 | material | condensation | Condensation Drains Mat |  |  | 3093.95 |  | 2294 |  | 34.87% |  | 22.2586
2034 | Done | V1 | 128 | 243 | material | condensation | Condensation Drains Mat |  |  | 2280.11 |  | 2868 |  | -20.5% |  | 17.8134
2035 | Done | V1 | 92 | 243 | material | condensation | Condensation Drains Mat |  |  | 121.8 | [5 empty] | 1.3239
2037 | Done | V1 | 122 | 243 | material | condensation | Condensation Drains Mat |  |  | 106.54 | [5 empty] | 0.87328
2038 | Done | V1 | 80 | 243 | material | condensation | Condensation Drains Mat |  |  | 258.5 | [5 empty] | 3.2313
2040 | Done | V1 | 55 | 243 | material | condensation | Condensation Drains Mat |  |  | 7.2 | [5 empty] | 0.13091
2041 | Done | V2.2 | 108 | 243 | material | condensation | Condensation Drains Mat
2042 | Done | V2.2 | 75 | 243 | material | condensation | Condensation Drains Mat |  |  | 91.07 | [5 empty] | 1.2143
2043 | Done | V2.2 | 89 | 243 | material | condensation | Condensation Drains Mat |  |  | 1275 | [5 empty] | 14.3258
2044 | Done | V2.2 | 78 | 243 | material | condensation | Condensation Drains Mat
2045 | Done | V2.2 | 158 | 243 | material | condensation | Condensation Drains Mat
2049 | Done | V2.2 | 296 | 243 | material | condensation | Condensation Drains Mat
2050 | Done | V2.2 | 50 | 243 | material | condensation | Condensation Drains Mat |  |  | 2.16 | [5 empty] | 0.0432
2051 | Done | V2.2 | 163 | 243 | material | condensation | Condensation Drains Mat
2053 | Done | V2.2 | 136 | 243 | material | condensation | Condensation Drains Mat
2057 | Done | V2.2 | 111 | 243 | material | condensation | Condensation Drains Mat
2011 | Done | SUPABASE | 117 | 244 | material | fire_caulking | Fire Caulking Material
2019 | Done | SUPABASE | 211 | 244 | material | fire_caulking | Fire Caulking Material
2021 | Done | SUPABASE | 136 | 244 | material | fire_caulking | Fire Caulking Material |  |  | 133.04 | [5 empty] | 0.97824
2023 | Done | V1 | 209 | 244 | material | fire_caulking | Fire Caulking Material |  |  | 654.39 | [5 empty] | 3.1311
2026 | Done | V1 | 49 | 244 | material | fire_caulking | Fire Caulking Material |  |  | 178.63 | [5 empty] | 3.6455
2008 | Done | SUPABASE | 258 | 245 | material | trim_finish | Tub/Shower Material |  |  | 536.61 | 2600 | 2600 | -79.36% | -79.36% |  | 2.0799
2009 | Done | SUPABASE | 56 | 245 | material | trim_finish | Tub/Shower Material
2010 | Done | SUPABASE | 149 | 245 | material | trim_finish | Tub/Shower Material |  |  | 647.45 | [5 empty] | 4.3453
2011 | Done | SUPABASE | 117 | 245 | material | trim_finish | Tub/Shower Material |  |  | 884.62 | [5 empty] | 7.5609
2012 | Done | SUPABASE | 162 | 245 | material | trim_finish | Tub/Shower Material |  |  | 2278.99 | [5 empty] | 14.0678
2018 | Done | SUPABASE | 211 | 245 | material | trim_finish | Tub/Shower Material |  |  | 653.01 | [5 empty] | 3.0948
2098 | LIVE | V2.2 | 170 | 250 | material | unmapped_material | Warranty Material |  |  | 1481.84 | [5 empty] | 8.7167
2052 | Done | V2.2 | 107 | 251 | material | unmapped_material | T&M Material |  |  | 81.68 | [5 empty] | 0.76336
2103 | LIVE | V2.2 | 234 | 251 | material | unmapped_material | T&M Material
2112 | LIVE | V_TX | 20 | 251 | material | unmapped_material | T&M Material |  |  | 87.83 | 100 | 100 | -12.17% | -12.17% |  | 4.3915
2001 | Done | SUPABASE | 234 | 600 | overhead | overhead | Subcontractor |  |  | 5407 | 5500 | 5500 | -1.691% | -1.691% |  | 23.1068
2008 | Done | SUPABASE | 258 | 600 | overhead | overhead | Subcontractor |  |  | 16900.64 | 7870 | 9070 | 114.7% | 86.34% |  | 65.5064
2009 | Done | SUPABASE | 56 | 600 | overhead | overhead | Subcontractor |  |  | 2379 | 4800 | 4885 | -50.44% | -51.3% |  | 42.4821
2010 | Done | SUPABASE | 149 | 600 | overhead | overhead | Subcontractor |  |  | 1212 | 1000 | 1000 | 21.2% | 21.2% |  | 8.1342
2011 | Done | SUPABASE | 117 | 600 | overhead | overhead | Subcontractor |  |  | 6346.07 | 10000 | 13085 | -36.54% | -51.5% |  | 54.2399
2012 | Done | SUPABASE | 162 | 600 | overhead | overhead | Subcontractor |  |  | 186 | 1000 | 1000 | -81.4% | -81.4% |  | 1.1481
2015 | Done | SUPABASE | 197 | 600 | overhead | overhead | Subcontractor |  |  | 36287 | 25125 | 27425 | 44.43% | 32.31% |  | 184.198
2017 | Done | SUPABASE | 119 | 600 | overhead | overhead | Subcontractor |  |  | 15635 | 15970 | 16970 | -2.098% | -7.867% |  | 131.3866
2018 | Done | SUPABASE | 211 | 600 | overhead | overhead | Subcontractor |  |  | 691.7 | 3000 | 3000 | -76.94% | -76.94% |  | 3.2782
2019 | Done | SUPABASE | 211 | 600 | overhead | overhead | Subcontractor |  |  | 31086.35 | 21600 | 45850 | 43.92% | -32.2% |  | 147.3287
2020 | Done | SUPABASE | 256 | 600 | overhead | overhead | Subcontractor |  |  | 21589.36 | 4000 | 5000 | 439.7% | 331.8% |  | 84.3334
2021 | Done | SUPABASE | 136 | 600 | overhead | overhead | Subcontractor |  |  | 4501 | 21050 | 21550 | -78.62% | -79.11% |  | 33.0956
2022 | Done | SUPABASE | 18 | 600 | overhead | overhead | Subcontractor |  |  | 950 | 3400 | 3400 | -72.06% | -72.06% |  | 52.7778
2023 | Done | V1 | 209 | 600 | overhead | overhead | Subcontractor |  |  | 14130.5 | 500 | 11843 | 2726% | 19.32% |  | 67.61
2024 | Done | V1 | 117 | 600 | overhead | overhead | Subcontractor |  |  | 1711 | 1000 | 1000 | 71.1% | 71.1% |  | 14.6239
2025 | Done | V1 | 75 | 600 | overhead | overhead | Subcontractor |  |  | 4506.25 | 2000 | 2594.5 | 125.3% | 73.68% |  | 60.0833
2026 | Done | V1 | 49 | 600 | overhead | overhead | Subcontractor |  |  | 186 | 500 | 500 | -62.8% | -62.8% |  | 3.7959
2027 | Done | V1 | 170 | 600 | overhead | overhead | Subcontractor |  |  | 27855.92 | 2000 | 27261 | 1293% | 2.182% |  | 163.8584
2028 | Done | V1 | 296 | 600 | overhead | overhead | Subcontractor |  |  | 4405 | 2500 | 2500 | 76.2% | 76.2% |  | 14.8818
2029 | Done | V1 | 83 | 600 | overhead | overhead | Subcontractor |  |  | 1566 | 2500 | 2744.5 | -37.36% | -42.94% |  | 18.8675
2030 | Done | V1 | 144 | 600 | overhead | overhead | Subcontractor |  |  | 21749 | 1500 | 23000 | 1350% | -5.439% |  | 151.0347
2031 | Done | V1 | 398 | 600 | overhead | overhead | Subcontractor |  |  | 65165 |  | 58006 |  | 12.34% |  | 163.7312
2032 | Done | V1 | 71 | 600 | overhead | overhead | Subcontractor |  |  | 135 | 1000 | 1000 | -86.5% | -86.5% |  | 1.9014
2033 | Done | V1 | 139 | 600 | overhead | overhead | Subcontractor |  |  | 230 | 1000 | 1165 | -77% | -80.26% |  | 1.6547
2034 | Done | V1 | 128 | 600 | overhead | overhead | Subcontractor |  |  | 3044.35 | 1000 | 3255 | 204.4% | -6.472% |  | 23.784
2035 | Done | V1 | 92 | 600 | overhead | overhead | Subcontractor |  |  | 1400 | 1000 | 2200 | 40% | -36.36% |  | 15.2174
2037 | Done | V1 | 122 | 600 | overhead | overhead | Subcontractor |  |  | 4420.5 | 500 | 4225 | 784.1% | 4.627% |  | 36.2336
2038 | Done | V1 | 80 | 600 | overhead | overhead | Subcontractor |  |  | 2967 | 1000 | 1000 | 196.7% | 196.7% |  | 37.0875
2040 | Done | V1 | 55 | 600 | overhead | overhead | Subcontractor |  |  | 2304 | 500 | 650 | 360.8% | 254.5% |  | 41.8909
2041 | Done | V2.2 | 108 | 600 | overhead | overhead | Subcontractor |  |  | 33916.25 | 500 | 23850 | 6683% | 42.21% |  | 314.0394
2042 | Done | V2.2 | 75 | 600 | overhead | overhead | Subcontractor |  |  | 215 | 1000 | 1000 | -78.5% | -78.5% |  | 2.8667
2043 | Done | V2.2 | 89 | 600 | overhead | overhead | Subcontractor |  |  | 4122.5 | 1000 | 1000 | 312.2% | 312.2% |  | 46.3202
2044 | Done | V2.2 | 78 | 600 | overhead | overhead | Subcontractor |  |  | 3900 | 1000 | 1000 | 290% | 290% |  | 50
2045 | Done | V2.2 | 158 | 600 | overhead | overhead | Subcontractor |  |  | 3412 | 500 | 500 | 582.4% | 582.4% |  | 21.5949
2046 | Done | V2.2 | 110 | 600 | overhead | overhead | Subcontractor |  |  | 10409.7 | 2500 | 2500 | 316.4% | 316.4% |  | 94.6336
2047 | Done | V2.2 | 70 | 600 | overhead | overhead | Subcontractor |  |  | 155 | 500 | 500 | -69% | -69% |  | 2.2143
2048 | Done | V2.2 | 72 | 600 | overhead | overhead | Subcontractor |  |  | 115 | 500 | 500 | -77% | -77% |  | 1.5972
2049 | Done | V2.2 | 296 | 600 | overhead | overhead | Subcontractor |  |  | 22111.5 | 5000 | 6200 | 342.2% | 256.6% |  | 74.701
2050 | Done | V2.2 | 50 | 600 | overhead | overhead | Subcontractor |  |  | 6585 | 1000 | 1050 | 558.5% | 527.1% |  | 131.7
2051 | Done | V2.2 | 163 | 600 | overhead | overhead | Subcontractor |  |  | 33715 | 2500 | 31650 | 1249% | 6.524% |  | 206.8405
2052 | Done | V2.2 | 107 | 600 | overhead | overhead | Subcontractor |  |  | 13352 | 25500 | 25500 | -47.64% | -47.64% |  | 124.785
2053 | Done | V2.2 | 136 | 600 | overhead | overhead | Subcontractor |  |  | 9771.2 | 1000 | 4360 | 877.1% | 124.1% |  | 71.8471
2054 | Done | V2.2 | 68 | 600 | overhead | overhead | Subcontractor |  |  | 6041.25 | 1000 | 1000 | 504.1% | 504.1% |  | 88.8419
2055 | Done | V2.2 | 98 | 600 | overhead | overhead | Subcontractor |  |  | 9865 | 1000 | 1000 | 886.5% | 886.5% |  | 100.6633
2056 | Done | V2.2 | 321 | 600 | overhead | overhead | Subcontractor |  |  | 25977.47 | 55000 | 59850 | -52.77% | -56.6% |  | 80.9267
2057 | Done | V2.2 | 111 | 600 | overhead | overhead | Subcontractor |  |  | 4653.75 | 1000 | 1000 | 365.4% | 365.4% |  | 41.9257
2058 | Done | V2.2 | 77 | 600 | overhead | overhead | Subcontractor |  |  | 5000 | 1000 | 1000 | 400% | 400% |  | 64.9351
2059 | Done | V2.2 | 365 | 600 | overhead | overhead | Subcontractor |  |  | 5916 | 3000 | 3000 | 97.2% | 97.2% |  | 16.2082
2060 | Done | V2.2 | 270 | 600 | overhead | overhead | Subcontractor |  |  | 25781.65 | 2000 | 8300 | 1189% | 210.6% |  | 95.4876
2098 | LIVE | V2.2 | 170 | 600 | overhead | overhead | Subcontractor |  |  | 16200 | 25130 | 25130 | -35.54% | -35.54% |  | 95.2941
2103 | LIVE | V2.2 | 234 | 600 | overhead | overhead | Subcontractor |  |  | 17950 | 30983 | 35083 | -42.07% | -48.84% |  | 76.7094
2107 | LIVE | V2.2 | 244 | 600 | overhead | overhead | Subcontractor |  |  | 2272.1 | 29625 | 34125 | -92.33% | -93.34% |  | 9.3119
2111 | LIVE | V_TX | 186 | 600 | overhead | overhead | Subcontractor |  |  | 622.12 | 25345 | 25645 | -97.55% | -97.57% |  | 3.3447
2112 | LIVE | V_TX | 20 | 600 | overhead | overhead | Subcontractor |  |  | 60 | 12700 | 12700 | -99.53% | -99.53% |  | 3
2001 | Done | SUPABASE | 234 | 601 | overhead | overhead | Engineering/Plans |  |  | 1835.26 | 5500 | 5500 | -66.63% | -66.63% |  | 7.843
2008 | Done | SUPABASE | 258 | 601 | overhead | overhead | Engineering/Plans |  |  | 57119.45 | 35000 | 35500 | 63.2% | 60.9% |  | 221.3932
2009 | Done | SUPABASE | 56 | 601 | overhead | overhead | Engineering/Plans |  |  | 4990.08 | 6000 | 6000 | -16.83% | -16.83% |  | 89.1086
2010 | Done | SUPABASE | 149 | 601 | overhead | overhead | Engineering/Plans |  |  | 2404.21 | 4000 | 4000 | -39.89% | -39.89% |  | 16.1356
2011 | Done | SUPABASE | 117 | 601 | overhead | overhead | Engineering/Plans |  |  | 12573.03 | 25000 | 25000 | -49.71% | -49.71% |  | 107.4618
2012 | Done | SUPABASE | 162 | 601 | overhead | overhead | Engineering/Plans |  |  | 15682.03 | 22000 | 22000 | -28.72% | -28.72% |  | 96.8027
2015 | Done | SUPABASE | 197 | 601 | overhead | overhead | Engineering/Plans |  |  | 7038.38 | 2000 | 2000 | 251.9% | 251.9% |  | 35.7278
2017 | Done | SUPABASE | 119 | 601 | overhead | overhead | Engineering/Plans |  |  | 17974.5 | 22000 | 22500 | -18.3% | -20.11% |  | 151.0462
2018 | Done | SUPABASE | 211 | 601 | overhead | overhead | Engineering/Plans |  |  | 2252.62 | 3000 | 3000 | -24.91% | -24.91% |  | 10.6759
2019 | Done | SUPABASE | 211 | 601 | overhead | overhead | Engineering/Plans |  |  | 10226 | 5000 | 5000 | 104.5% | 104.5% |  | 48.4645
2021 | Done | SUPABASE | 136 | 601 | overhead | overhead | Engineering/Plans |  |  | 53259.5 | 38000 | 39000 | 40.16% | 36.56% |  | 391.614
2022 | Done | SUPABASE | 18 | 601 | overhead | overhead | Engineering/Plans |  |  | 4756.5 | 7000 | 7000 | -32.05% | -32.05% |  | 264.25
2023 | Done | V1 | 209 | 601 | overhead | overhead | Engineering/Plans |  |  | 28143.85 | 50000 | 50770 | -43.71% | -44.57% |  | 134.6596
2024 | Done | V1 | 117 | 601 | overhead | overhead | Engineering/Plans |  |  | 1218.23 | 20000 | 20000 | -93.91% | -93.91% |  | 10.4122
2025 | Done | V1 | 75 | 601 | overhead | overhead | Engineering/Plans |  |  | 27969.5 | 30000 | 30000 | -6.768% | -6.768% |  | 372.9267
2026 | Done | V1 | 49 | 601 | overhead | overhead | Engineering/Plans |  |  | 17344 | 35000 | 35000 | -50.45% | -50.45% |  | 353.9592
2027 | Done | V1 | 170 | 601 | overhead | overhead | Engineering/Plans |  |  | 39853.5 | 30000 | 35343 | 32.84% | 12.76% |  | 234.4324
2028 | Done | V1 | 296 | 601 | overhead | overhead | Engineering/Plans |  |  | 20232.56 | 25000 | 25000 | -19.07% | -19.07% |  | 68.3532
2029 | Done | V1 | 83 | 601 | overhead | overhead | Engineering/Plans |  |  | 20121 | 22000 | 22000 | -8.541% | -8.541% |  | 242.4217
2030 | Done | V1 | 144 | 601 | overhead | overhead | Engineering/Plans |  |  | 22272.25 | 25000 | 25100 | -10.91% | -11.27% |  | 154.6684
2031 | Done | V1 | 398 | 601 | overhead | overhead | Engineering/Plans |  |  | 3927.4 | 56720 | 56720 | -93.08% | -93.08% |  | 9.8678
2032 | Done | V1 | 71 | 601 | overhead | overhead | Engineering/Plans |  |  | 17538.5 | 21000 | 21000 | -16.48% | -16.48% |  | 247.0211
2033 | Done | V1 | 139 | 601 | overhead | overhead | Engineering/Plans |  |  | 60958.25 | 55000 | 57485 | 10.83% | 6.042% |  | 438.5486
2034 | Done | V1 | 128 | 601 | overhead | overhead | Engineering/Plans |  |  | 33606.25 | 55000 | 57200 | -38.9% | -41.25% |  | 262.5488
2037 | Done | V1 | 122 | 601 | overhead | overhead | Engineering/Plans |  |  | 44369.11 | 36000 | 39220 | 23.25% | 13.13% |  | 363.6812
2038 | Done | V1 | 80 | 601 | overhead | overhead | Engineering/Plans |  |  | 36872.75 | 40000 | 40000 | -7.818% | -7.818% |  | 460.9094
2039 | Done | V1 |  | 601 | overhead | overhead | Engineering/Plans |  |  | 3337.5 | 5000 | 5000 | -33.25% | -33.25%
2040 | Done | V1 | 55 | 601 | overhead | overhead | Engineering/Plans |  |  | 15976 | 16000 | 16000 | -0.15% | -0.15% |  | 290.4727
2041 | Done | V2.2 | 108 | 601 | overhead | overhead | Engineering/Plans |  |  | 57943.23 | 50000 | 50000 | 15.89% | 15.89% |  | 536.5114
2042 | Done | V2.2 | 75 | 601 | overhead | overhead | Engineering/Plans |  |  | 32640.89 | 27000 | 27000 | 20.89% | 20.89% |  | 435.2119
2043 | Done | V2.2 | 89 | 601 | overhead | overhead | Engineering/Plans |  |  | 29259.75 | 55000 | 55500 | -46.8% | -47.28% |  | 328.7612
2044 | Done | V2.2 | 78 | 601 | overhead | overhead | Engineering/Plans |  |  | 25725.44 | 21000 | 21000 | 22.5% | 22.5% |  | 329.8133
2045 | Done | V2.2 | 158 | 601 | overhead | overhead | Engineering/Plans |  |  | 16078.25 | 25000 | 25000 | -35.69% | -35.69% |  | 101.7611
2046 | Done | V2.2 | 110 | 601 | overhead | overhead | Engineering/Plans |  |  | 34504.78 | 42000 | 42000 | -17.85% | -17.85% |  | 313.6798
2047 | Done | V2.2 | 70 | 601 | overhead | overhead | Engineering/Plans |  |  | 772.5 | 1000 | 1000 | -22.75% | -22.75% |  | 11.0357
2048 | Done | V2.2 | 72 | 601 | overhead | overhead | Engineering/Plans |  |  | 772.5 | 1000 | 1000 | -22.75% | -22.75% |  | 10.7292
2049 | Done | V2.2 | 296 | 601 | overhead | overhead | Engineering/Plans |  |  | 103 | 4000 | 5000 | -97.42% | -97.94% |  | 0.34797
2050 | Done | V2.2 | 50 | 601 | overhead | overhead | Engineering/Plans |  |  | 17150.88 | 30000 | 30000 | -42.83% | -42.83% |  | 343.0176
2051 | Done | V2.2 | 163 | 601 | overhead | overhead | Engineering/Plans |  |  | 22226.25 | 45000 | 48022 | -50.61% | -53.72% |  | 136.3574
2052 | Done | V2.2 | 107 | 601 | overhead | overhead | Engineering/Plans |  |  | 35026.44 | 50000 | 51250 | -29.95% | -31.66% |  | 327.3499
2053 | Done | V2.2 | 136 | 601 | overhead | overhead | Engineering/Plans |  |  | 40070.75 | 70000 | 70000 | -42.76% | -42.76% |  | 294.6379
2054 | Done | V2.2 | 68 | 601 | overhead | overhead | Engineering/Plans |  |  | 17733.13 | 18500 | 18900 | -4.145% | -6.174% |  | 260.7813
2055 | Done | V2.2 | 98 | 601 | overhead | overhead | Engineering/Plans |  |  | 43959.25 | 32000 | 53044 | 37.37% | -17.13% |  | 448.5638
2056 | Done | V2.2 | 321 | 601 | overhead | overhead | Engineering/Plans |  |  | 93899.29 | 120000 | 120000 | -21.75% | -21.75% |  | 292.5212
2058 | Done | V2.2 | 77 | 601 | overhead | overhead | Engineering/Plans |  |  | 19206.32 | 30000 | 30000 | -35.98% | -35.98% |  | 249.4327
2059 | Done | V2.2 | 365 | 601 | overhead | overhead | Engineering/Plans |  |  | 54267.4 | 50000 | 50000 | 8.535% | 8.535% |  | 148.6778
2060 | Done | V2.2 | 270 | 601 | overhead | overhead | Engineering/Plans |  |  | 100995.25 | 90000 | 120000 | 12.22% | -15.84% |  | 374.0565
2098 | LIVE | V2.2 | 170 | 601 | overhead | overhead | Engineering/Plans |  |  | 106959.5 | 124500 | 124500 | -14.09% | -14.09% |  | 629.1735
2103 | LIVE | V2.2 | 234 | 601 | overhead | overhead | Engineering/Plans |  |  | 8252.5 | 99450 | 99450 | -91.7% | -91.7% |  | 35.2671
2105 | LIVE | V2.2 | 219 | 601 | overhead | overhead | Engineering/Plans |  |  | 131071.25 | [5 empty] | 598.4989
2106 | LIVE | V2.2 | 146 | 601 | overhead | overhead | Engineering/Plans |  |  | 30200 | [5 empty] | 206.8493
2107 | LIVE | V2.2 | 244 | 601 | overhead | overhead | Engineering/Plans |  |  | 9356.25 | 79300 | 79300 | -88.2% | -88.2% |  | 38.3453
2111 | LIVE | V_TX | 186 | 601 | overhead | overhead | Engineering/Plans |  |  | 123072.5 | 93000 | 99725 | 32.34% | 23.41% |  | 661.6801
2114 | LIVE | V2.2 | 239 | 601 | overhead | overhead | Engineering/Plans |  |  | 55000 | [5 empty] | 230.1255
2115 | LIVE | V2.2 | 201 | 601 | overhead | overhead | Engineering/Plans |  |  | 10407.5 | [5 empty] | 51.7786
2117 | LIVE | V2.2 | 104 | 601 | overhead | overhead | Engineering/Plans |  |  | 10701.25 | [5 empty] | 102.8966
2023 | Done | V1 | 209 | 602 | overhead | overhead | Rental Equipment |  |  | 6870.79 | 5000 | 5919 | 37.42% | 16.08% |  | 32.8746
2024 | Done | V1 | 117 | 602 | overhead | overhead | Rental Equipment |  |  | 2202.92 | 5000 | 5000 | -55.94% | -55.94% |  | 18.8284
2025 | Done | V1 | 75 | 602 | overhead | overhead | Rental Equipment |  |  | 1302.4 | 5000 | 5000 | -73.95% | -73.95% |  | 17.3653
2027 | Done | V1 | 170 | 602 | overhead | overhead | Rental Equipment |  |  | 527.56 | 5000 | 5000 | -89.45% | -89.45% |  | 3.1033
2028 | Done | V1 | 296 | 602 | overhead | overhead | Rental Equipment |  |  | 1758.76 | 6000 | 6000 | -70.69% | -70.69% |  | 5.9418
2030 | Done | V1 | 144 | 602 | overhead | overhead | Rental Equipment |  |  | 10037.15 | 10000 | 11500 | 0.3715% | -12.72% |  | 69.7024
2031 | Done | V1 | 398 | 602 | overhead | overhead | Rental Equipment |  |  | 5415.52 | 8060 | 6541 | -32.81% | -17.21% |  | 13.6068
2033 | Done | V1 | 139 | 602 | overhead | overhead | Rental Equipment |  |  | 316.54 | 3000 | 3117 | -89.45% | -89.84% |  | 2.2773
2034 | Done | V1 | 128 | 602 | overhead | overhead | Rental Equipment |  |  | 6832.2 | 3000 | 3000 | 127.7% | 127.7% |  | 53.3766
2037 | Done | V1 | 122 | 602 | overhead | overhead | Rental Equipment |  |  | 1208.69 | 4000 | 4000 | -69.78% | -69.78% |  | 9.9073
2038 | Done | V1 | 80 | 602 | overhead | overhead | Rental Equipment |  |  | 4897.67 | 4000 | 4000 | 22.44% | 22.44% |  | 61.2209
2041 | Done | V2.2 | 108 | 602 | overhead | overhead | Rental Equipment |  |  | 11181.2 | 6000 | 13696 | 86.35% | -18.36% |  | 103.5296
2043 | Done | V2.2 | 89 | 602 | overhead | overhead | Rental Equipment |  |  | 2579.5 | 10000 | 10000 | -74.2% | -74.2% |  | 28.9831
2044 | Done | V2.2 | 78 | 602 | overhead | overhead | Rental Equipment |  |  | 644.09 | 600 | 600 | 7.348% | 7.348% |  | 8.2576
2045 | Done | V2.2 | 158 | 602 | overhead | overhead | Rental Equipment |  |  | 4998.15 | 3500 | 3800 | 42.8% | 31.53% |  | 31.6339
2046 | Done | V2.2 | 110 | 602 | overhead | overhead | Rental Equipment |  |  | 199.25 | 4500 | 4500 | -95.57% | -95.57% |  | 1.8114
2047 | Done | V2.2 | 70 | 602 | overhead | overhead | Rental Equipment |  |  | 2109.22 | 1000 | 2046 | 110.9% | 3.09% |  | 30.1317
2049 | Done | V2.2 | 296 | 602 | overhead | overhead | Rental Equipment |  |  | 3071.92 | 10250 | 10250 | -70.03% | -70.03% |  | 10.3781
2050 | Done | V2.2 | 50 | 602 | overhead | overhead | Rental Equipment |  |  | 4110.62 | 5000 | 5000 | -17.79% | -17.79% |  | 82.2124
2052 | Done | V2.2 | 107 | 602 | overhead | overhead | Rental Equipment |  |  | 591.82 | 8000 | 8400 | -92.6% | -92.95% |  | 5.531
2053 | Done | V2.2 | 136 | 602 | overhead | overhead | Rental Equipment |  |  | 10709.84 | 9000 | 9000 | 19% | 19% |  | 78.7488
2054 | Done | V2.2 | 68 | 602 | overhead | overhead | Rental Equipment |  |  | 241.47 | 600 | 850 | -59.76% | -71.59% |  | 3.551
2055 | Done | V2.2 | 98 | 602 | overhead | overhead | Rental Equipment |  |  | 4238 | 600 | 600 | 606.3% | 606.3% |  | 43.2449
2056 | Done | V2.2 | 321 | 602 | overhead | overhead | Rental Equipment |  |  | 19433.38 | 12000 | 12000 | 61.94% | 61.94% |  | 60.5401
2057 | Done | V2.2 | 111 | 602 | overhead | overhead | Rental Equipment |  |  | 199.24 | 600 | 600 | -66.79% | -66.79% |  | 1.795
2058 | Done | V2.2 | 77 | 602 | overhead | overhead | Rental Equipment |  |  | 624.67 | 600 | 600 | 4.112% | 4.112% |  | 8.1126
2059 | Done | V2.2 | 365 | 602 | overhead | overhead | Rental Equipment |  |  | 2267.08 | [5 empty] | 6.2112
2060 | Done | V2.2 | 270 | 602 | overhead | overhead | Rental Equipment |  |  | 1673.84 | 10000 | 10000 | -83.26% | -83.26% |  | 6.1994
2098 | LIVE | V2.2 | 170 | 602 | overhead | overhead | Rental Equipment |  |  | 13081.86 | 18000 | 18000 | -27.32% | -27.32% |  | 76.9521
2103 | LIVE | V2.2 | 234 | 602 | overhead | overhead | Rental Equipment |  |  | 17684.58 | 15000 | 17990 | 17.9% | -1.698% |  | 75.5751
2107 | LIVE | V2.2 | 244 | 602 | overhead | overhead | Rental Equipment |  |  | 15185.12 | 12000 | 14700 | 26.54% | 3.3% |  | 62.2341
2111 | LIVE | V_TX | 186 | 602 | overhead | overhead | Rental Equipment |  |  | 2313.85 | 10000 | 10000 | -76.86% | -76.86% |  | 12.4401
2001 | Done | SUPABASE | 234 | 603 | overhead | overhead | Permits & Licenses |  |  | 101.56 | [5 empty] | 0.43402
2008 | Done | SUPABASE | 258 | 603 | overhead | overhead | Permits & Licenses |  |  | 6197.36 | 2000 | 2000 | 209.9% | 209.9% |  | 24.0208
2009 | Done | SUPABASE | 56 | 603 | overhead | overhead | Permits & Licenses |  |  | 141.44 | [5 empty] | 2.5257
2010 | Done | SUPABASE | 149 | 603 | overhead | overhead | Permits & Licenses |  |  | 34.46 | 3000 | 3000 | -98.85% | -98.85% |  | 0.23128
2011 | Done | SUPABASE | 117 | 603 | overhead | overhead | Permits & Licenses |  |  | 7291 | 7630 | 7640 | -4.443% | -4.568% |  | 62.3162
2012 | Done | SUPABASE | 162 | 603 | overhead | overhead | Permits & Licenses |  |  | 9741.88 | 10900 | 10900 | -10.62% | -10.62% |  | 60.1351
2015 | Done | SUPABASE | 197 | 603 | overhead | overhead | Permits & Licenses |  |  | 10 | 5000 | 5000 | -99.8% | -99.8% |  | 0.050761
2017 | Done | SUPABASE | 119 | 603 | overhead | overhead | Permits & Licenses |  |  | 246 | 3000 | 3000 | -91.8% | -91.8% |  | 2.0672
2018 | Done | SUPABASE | 211 | 603 | overhead | overhead | Permits & Licenses |  |  | 1998.96 | 2000 | 2150 | -0.052% | -7.025% |  | 9.4737
2019 | Done | SUPABASE | 211 | 603 | overhead | overhead | Permits & Licenses |  |  | 18668.95 | 15000 | 15000 | 24.46% | 24.46% |  | 88.4784
2020 | Done | SUPABASE | 256 | 603 | overhead | overhead | Permits & Licenses |  |  | 11677.83 | 1000 | 11000 | 1068% | 6.162% |  | 45.6165
2021 | Done | SUPABASE | 136 | 603 | overhead | overhead | Permits & Licenses |  |  | 8886 | 10770 | 10770 | -17.49% | -17.49% |  | 65.3382
2022 | Done | SUPABASE | 18 | 603 | overhead | overhead | Permits & Licenses |  |  | 1583 | 1850 | 1850 | -14.43% | -14.43% |  | 87.9444
2023 | Done | V1 | 209 | 603 | overhead | overhead | Permits & Licenses |  |  | 29245.43 | 28000 | 28000 | 4.448% | 4.448% |  | 139.9303
2024 | Done | V1 | 117 | 603 | overhead | overhead | Permits & Licenses |  |  | 7148 | 11000 | 11123 | -35.02% | -35.74% |  | 61.094
2025 | Done | V1 | 75 | 603 | overhead | overhead | Permits & Licenses |  |  | 5334 | 6830 | 6970 | -21.9% | -23.47% |  | 71.12
2026 | Done | V1 | 49 | 603 | overhead | overhead | Permits & Licenses |  |  | 3352 | 5420 | 5560 | -38.15% | -39.71% |  | 68.4082
2027 | Done | V1 | 170 | 603 | overhead | overhead | Permits & Licenses |  |  | 9694 | 13365 | 13365 | -27.47% | -27.47% |  | 57.0235
2028 | Done | V1 | 296 | 603 | overhead | overhead | Permits & Licenses |  |  | 22287.6 | 24000 | 24000 | -7.135% | -7.135% |  | 75.2959
2029 | Done | V1 | 83 | 603 | overhead | overhead | Permits & Licenses |  |  | 4247 | 5600 | 5740 | -24.16% | -26.01% |  | 51.1687
2030 | Done | V1 | 144 | 603 | overhead | overhead | Permits & Licenses |  |  | 10377.9 | 11500 | 11640 | -9.757% | -10.84% |  | 72.0687
2031 | Done | V1 | 398 | 603 | overhead | overhead | Permits & Licenses |  |  | 1959.3 |  | 2327 |  | -15.8% |  | 4.9229
2032 | Done | V1 | 71 | 603 | overhead | overhead | Permits & Licenses |  |  | 4198 | 5155 | 5165 | -18.56% | -18.72% |  | 59.1268
2033 | Done | V1 | 139 | 603 | overhead | overhead | Permits & Licenses |  |  | 21161 | 21300 | 22604 | -0.6526% | -6.384% |  | 152.2374
2034 | Done | V1 | 128 | 603 | overhead | overhead | Permits & Licenses |  |  | 18927.11 | 21850 | 21850 | -13.38% | -13.38% |  | 147.868
2035 | Done | V1 | 92 | 603 | overhead | overhead | Permits & Licenses |  |  | 109 | [5 empty] | 1.1848
2037 | Done | V1 | 122 | 603 | overhead | overhead | Permits & Licenses |  |  | 9138 | 11735 | 12335 | -22.13% | -25.92% |  | 74.9016
2038 | Done | V1 | 80 | 603 | overhead | overhead | Permits & Licenses |  |  | 5797 | 6710 | 6850 | -13.61% | -15.37% |  | 72.4625
2039 | Done | V1 |  | 603 | overhead | overhead | Permits & Licenses |  |  | 838.05 | 944 | 944 | -11.22% | -11.22%
2040 | Done | V1 | 55 | 603 | overhead | overhead | Permits & Licenses |  |  | 3518 | 4385 | 4385 | -19.77% | -19.77% |  | 63.9636
2041 | Done | V2.2 | 108 | 603 | overhead | overhead | Permits & Licenses |  |  | 8662 | 10000 | 10000 | -13.38% | -13.38% |  | 80.2037
2042 | Done | V2.2 | 75 | 603 | overhead | overhead | Permits & Licenses |  |  | 4774.5 | 5930 | 5930 | -19.49% | -19.49% |  | 63.66
2043 | Done | V2.2 | 89 | 603 | overhead | overhead | Permits & Licenses |  |  | 287.82 | 18000 | 3000 | -98.4% | -90.41% |  | 3.2339
2044 | Done | V2.2 | 78 | 603 | overhead | overhead | Permits & Licenses |  |  | 695 | 5370 | 5370 | -87.06% | -87.06% |  | 8.9103
2046 | Done | V2.2 | 110 | 603 | overhead | overhead | Permits & Licenses |  |  | 7501 | 6682 | 6682 | 12.26% | 12.26% |  | 68.1909
2047 | Done | V2.2 | 70 | 603 | overhead | overhead | Permits & Licenses |  |  | 954.5 |  | 922 |  | 3.525% |  | 13.6357
2049 | Done | V2.2 | 296 | 603 | overhead | overhead | Permits & Licenses |  |  | 20155.02 | 24000 | 25500 | -16.02% | -20.96% |  | 68.0913
2050 | Done | V2.2 | 50 | 603 | overhead | overhead | Permits & Licenses |  |  | 4165 | 6940 | 7080 | -39.99% | -41.17% |  | 83.3
2052 | Done | V2.2 | 107 | 603 | overhead | overhead | Permits & Licenses |  |  | 8631.5 | 16780 | 16780 | -48.56% | -48.56% |  | 80.6682
2053 | Done | V2.2 | 136 | 603 | overhead | overhead | Permits & Licenses |  |  | 21423 | 26800 | 26800 | -20.06% | -20.06% |  | 157.5221
2054 | Done | V2.2 | 68 | 603 | overhead | overhead | Permits & Licenses |  |  | 4539.5 | 8298 | 8298 | -45.29% | -45.29% |  | 66.7574
2055 | Done | V2.2 | 98 | 603 | overhead | overhead | Permits & Licenses |  |  | 6505 | 9362 | 9362 | -30.52% | -30.52% |  | 66.3776
2056 | Done | V2.2 | 321 | 603 | overhead | overhead | Permits & Licenses |  |  | 20109.95 | 26710 | 27010 | -24.71% | -25.55% |  | 62.6478
2058 | Done | V2.2 | 77 | 603 | overhead | overhead | Permits & Licenses |  |  | 4751 | 8858 | 8858 | -46.36% | -46.36% |  | 61.7013
2059 | Done | V2.2 | 365 | 603 | overhead | overhead | Permits & Licenses |  |  | 50576.78 | 59000 | 59000 | -14.28% | -14.28% |  | 138.5665
2060 | Done | V2.2 | 270 | 603 | overhead | overhead | Permits & Licenses |  |  | 29026.58 | 32000 | 35400 | -9.292% | -18% |  | 107.5059
2098 | LIVE | V2.2 | 170 | 603 | overhead | overhead | Permits & Licenses |  |  | 26503.77 | 40500 | 40500 | -34.56% | -34.56% |  | 155.9045
2103 | LIVE | V2.2 | 234 | 603 | overhead | overhead | Permits & Licenses |  |  | 22521.02 | 24660 | 31010 | -8.674% | -27.37% |  | 96.2437
2104 | LIVE | V2.2 | 24 | 603 | overhead | overhead | Permits & Licenses |  |  | 2505 | 8675 | 8675 | -71.12% | -71.12% |  | 104.375
2105 | LIVE | V2.2 | 219 | 603 | overhead | overhead | Permits & Licenses |  |  | 9636 | [5 empty] | 44
2107 | LIVE | V2.2 | 244 | 603 | overhead | overhead | Permits & Licenses |  |  | 16277 | 8000 | 24887 | 103.5% | -34.6% |  | 66.709
2111 | LIVE | V_TX | 186 | 603 | overhead | overhead | Permits & Licenses |  |  | 39594 | 47456 | 50316 | -16.57% | -21.31% |  | 212.871
2112 | LIVE | V_TX | 20 | 603 | overhead | overhead | Permits & Licenses |  |  | 3676 | 9262 | 9790 | -60.31% | -62.45% |  | 183.8
2012 | Done | SUPABASE | 162 | 604 | overhead | overhead | Backcharges |  |  | 1837.5 | [5 empty] | 11.3426
2030 | Done | V1 | 144 | 604 | overhead | overhead | Backcharges |  |  | 34043.21 | [5 empty] | 236.4112
2012 | Done | SUPABASE | 162 | 607 | overhead | overhead | Other Expenses |  |  | 70.71 | 25600 | 10000 | -99.72% | -99.29% |  | 0.43648
2023 | Done | V1 | 209 | 607 | overhead | overhead | Other Expenses |  |  | 49 | 10000 | 10000 | -99.51% | -99.51% |  | 0.23445
2024 | Done | V1 | 117 | 607 | overhead | overhead | Other Expenses |  |  | 123.75 | 10000 | 10000 | -98.76% | -98.76% |  | 1.0577
2025 | Done | V1 | 75 | 607 | overhead | overhead | Other Expenses |  |  | 7637.01 | 10000 | 10000 | -23.63% | -23.63% |  | 101.8268
2026 | Done | V1 | 49 | 607 | overhead | overhead | Other Expenses |  |  | 11995.82 | 15000 | 15000 | -20.03% | -20.03% |  | 244.8127
2027 | Done | V1 | 170 | 607 | overhead | overhead | Other Expenses |  |  | 10135.59 | 17000 | 17000 | -40.38% | -40.38% |  | 59.6211
2028 | Done | V1 | 296 | 607 | overhead | overhead | Other Expenses |  |  | 226 | 10000 | 300 | -97.74% | -24.67% |  | 0.76351
2029 | Done | V1 | 83 | 607 | overhead | overhead | Other Expenses |  |  | 8952.41 | 14500 | 14500 | -38.26% | -38.26% |  | 107.8604
2030 | Done | V1 | 144 | 607 | overhead | overhead | Other Expenses |  |  | 2825.11 | 12800 | 12800 | -77.93% | -77.93% |  | 19.6188
2031 | Done | V1 | 398 | 607 | overhead | overhead | Other Expenses |  |  | 2737.5 | 9900 | 9900 | -72.35% | -72.35% |  | 6.8781
2032 | Done | V1 | 71 | 607 | overhead | overhead | Other Expenses |  |  | 4239.36 | 7000 | 7000 | -39.44% | -39.44% |  | 59.7093
2033 | Done | V1 | 139 | 607 | overhead | overhead | Other Expenses |  |  | 13617.45 | 11000 | 11000 | 23.79% | 23.79% |  | 97.9673
2034 | Done | V1 | 128 | 607 | overhead | overhead | Other Expenses |  |  | 2446 | 4500 | 4500 | -45.64% | -45.64% |  | 19.1094
2036 | Done | V1 | 31 | 607 | overhead | overhead | Other Expenses |  |  | 825.48 | 2500 | 2500 | -66.98% | -66.98% |  | 26.6284
2037 | Done | V1 | 122 | 607 | overhead | overhead | Other Expenses |  |  | 71.1 | 10000 | 10000 | -99.29% | -99.29% |  | 0.58279
2038 | Done | V1 | 80 | 607 | overhead | overhead | Other Expenses |  |  | 7498.01 | 10000 | 10000 | -25.02% | -25.02% |  | 93.7251
2039 | Done | V1 |  | 607 | overhead | overhead | Other Expenses |  |  | 5
2040 | Done | V1 | 55 | 607 | overhead | overhead | Other Expenses |  |  | 5632.2 | 7000 | 7000 | -19.54% | -19.54% |  | 102.4036
2041 | Done | V2.2 | 108 | 607 | overhead | overhead | Other Expenses |  |  | 76.97 | 8000 | 8000 | -99.04% | -99.04% |  | 0.71269
2042 | Done | V2.2 | 75 | 607 | overhead | overhead | Other Expenses |  |  | 10312.7 | 8500 | 8500 | 21.33% | 21.33% |  | 137.5027
2043 | Done | V2.2 | 89 | 607 | overhead | overhead | Other Expenses |  |  | 5130 | 7000 | 7000 | -26.71% | -26.71% |  | 57.6404
2044 | Done | V2.2 | 78 | 607 | overhead | overhead | Other Expenses |  |  | 8101.46 | 7000 | 7000 | 15.74% | 15.74% |  | 103.8649
2045 | Done | V2.2 | 158 | 607 | overhead | overhead | Other Expenses |  |  | 652.9 | 1000 | 1000 | -34.71% | -34.71% |  | 4.1323
2046 | Done | V2.2 | 110 | 607 | overhead | overhead | Other Expenses |  |  | 8344.56 | 11500 | 11500 | -27.44% | -27.44% |  | 75.8596
2047 | Done | V2.2 | 70 | 607 | overhead | overhead | Other Expenses |  |  | 39.23 | 4000 | 4000 | -99.02% | -99.02% |  | 0.56043
2049 | Done | V2.2 | 296 | 607 | overhead | overhead | Other Expenses |  |  | 2750 | 10000 | 10000 | -72.5% | -72.5% |  | 9.2905
2050 | Done | V2.2 | 50 | 607 | overhead | overhead | Other Expenses |  |  | 5722.51 | 9000 | 9000 | -36.42% | -36.42% |  | 114.4502
2052 | Done | V2.2 | 107 | 607 | overhead | overhead | Other Expenses |  |  | 6517.37 | 12000 | 12000 | -45.69% | -45.69% |  | 60.91
2053 | Done | V2.2 | 136 | 607 | overhead | overhead | Other Expenses |  |  | 13008.75 | 11000 | 11000 | 18.26% | 18.26% |  | 95.6526
2054 | Done | V2.2 | 68 | 607 | overhead | overhead | Other Expenses |  |  | 2909.83 | 7000 | 7000 | -58.43% | -58.43% |  | 42.7916
2055 | Done | V2.2 | 98 | 607 | overhead | overhead | Other Expenses |  |  | 6301 | 7000 | 7000 | -9.986% | -9.986% |  | 64.2959
2056 | Done | V2.2 | 321 | 607 | overhead | overhead | Other Expenses |  |  | 20674.89 | 12000 | 12000 | 72.29% | 72.29% |  | 64.4078
2058 | Done | V2.2 | 77 | 607 | overhead | overhead | Other Expenses |  |  | 9064.4 | 7000 | 7000 | 29.49% | 29.49% |  | 117.7195
2059 | Done | V2.2 | 365 | 607 | overhead | overhead | Other Expenses |  |  | 226 | [5 empty] | 0.61918
2060 | Done | V2.2 | 270 | 607 | overhead | overhead | Other Expenses |  |  | 30712.97 | 30000 | 30000 | 2.377% | 2.377% |  | 113.7517
2098 | LIVE | V2.2 | 170 | 607 | overhead | overhead | Other Expenses |  |  | 77812.75 | 83451 | 83451 | -6.756% | -6.756% |  | 457.7221
2104 | LIVE | V2.2 | 24 | 607 | overhead | overhead | Other Expenses |  |  | 10462.27 | 10000 | 10000 | 4.623% | 4.623% |  | 435.9279
2107 | LIVE | V2.2 | 244 | 607 | overhead | overhead | Other Expenses |  |  | 58582.8 | 15000 | 59817 | 290.6% | -2.063% |  | 240.0934
2001 | Done | SUPABASE | 234 | 995 | burden | burden | Payroll Burden |  |  | 183056.2 | 170039.6 | 170039.6 | 7.655% | 7.655% |  | 782.2915
2008 | Done | SUPABASE | 258 | 995 | burden | burden | Payroll Burden |  |  | 270898.22 | 228724 | 254698.59 | 18.44% | 6.36% |  | 1049.9931
2009 | Done | SUPABASE | 56 | 995 | burden | burden | Payroll Burden |  |  | 34412.05 | 28928 | 32694.58 | 18.96% | 5.253% |  | 614.5009
2010 | Done | SUPABASE | 149 | 995 | burden | burden | Payroll Burden |  |  | 87883.44 | 145220.27 | 137421.67 | -39.48% | -36.05% |  | 589.8217
2011 | Done | SUPABASE | 117 | 995 | burden | burden | Payroll Burden |  |  | 61834.11 | 73133.62 | 75712.95 | -15.45% | -18.33% |  | 528.4967
2012 | Done | SUPABASE | 162 | 995 | burden | burden | Payroll Burden |  |  | 126300.46 | 125049.58 | 125049.58 | 1% | 1% |  | 779.6325
2015 | Done | SUPABASE | 197 | 995 | burden | burden | Payroll Burden |  |  | 249836.89 | 183990.41 | 206430.98 | 35.79% | 21.03% |  | 1268.2076
2017 | Done | SUPABASE | 119 | 995 | burden | burden | Payroll Burden |  |  | 131106.33 | 116366.6 | 118687.33 | 12.67% | 10.46% |  | 1101.7339
2018 | Done | SUPABASE | 211 | 995 | burden | burden | Payroll Burden |  |  | 195501.68 | 205165 | 207315.16 | -4.71% | -5.698% |  | 926.5482
2019 | Done | SUPABASE | 211 | 995 | burden | burden | Payroll Burden |  |  | 209946.79 | 262831.05 | 247825.38 | -20.12% | -15.28% |  | 995.0085
2020 | Done | SUPABASE | 256 | 995 | burden | burden | Payroll Burden |  |  | 338661.76 | 309922.16 | 265927.39 | 9.273% | 27.35% |  | 1322.8975
2021 | Done | SUPABASE | 136 | 995 | burden | burden | Payroll Burden |  |  | 178143.53 | 167567.61 | 160896.89 | 6.311% | 10.72% |  | 1309.8789
2022 | Done | SUPABASE | 18 | 995 | burden | burden | Payroll Burden |  |  | 25033.08 | 22607.03 | 23072.71 | 10.73% | 8.496% |  | 1390.7267
2023 | Done | V1 | 209 | 995 | burden | burden | Payroll Burden |  |  | 312024.89 | 219294.65 | 266088.03 | 42.29% | 17.26% |  | 1492.9421
2024 | Done | V1 | 117 | 995 | burden | burden | Payroll Burden |  |  | 167598.54 | 173096.55 | 180294 | -3.176% | -7.042% |  | 1432.4662
2025 | Done | V1 | 75 | 995 | burden | burden | Payroll Burden |  |  | 127300.38 | 116594.16 | 119607.14 | 9.182% | 6.432% |  | 1697.3384
2026 | Done | V1 | 49 | 995 | burden | burden | Payroll Burden |  |  | 93383.48 | 83136.63 | 83200.08 | 12.33% | 12.24% |  | 1905.7853
2027 | Done | V1 | 170 | 995 | burden | burden | Payroll Burden |  |  | 188248.16 | 208385 | 209087.09 | -9.663% | -9.967% |  | 1107.3421
2028 | Done | V1 | 296 | 995 | burden | burden | Payroll Burden |  |  | 252329.63 | 352418.16 | 306897.99 | -28.4% | -17.78% |  | 852.465
2029 | Done | V1 | 83 | 995 | burden | burden | Payroll Burden |  |  | 83396.48 | 117128.35 | 118491.17 | -28.8% | -29.62% |  | 1004.7769
2030 | Done | V1 | 144 | 995 | burden | burden | Payroll Burden |  |  | 223564.72 | 245563.45 | 260718.15 | -8.958% | -14.25% |  | 1552.5328
2031 | Done | V1 | 398 | 995 | burden | burden | Payroll Burden
2032 | Done | V1 | 71 | 995 | burden | burden | Payroll Burden |  |  | 59716.99 | 78153.57 | 80584.7 | -23.59% | -25.9% |  | 841.0844
2033 | Done | V1 | 139 | 995 | burden | burden | Payroll Burden |  |  | 209595.74 | 234571.61 | 218627.35 | -10.65% | -4.131% |  | 1507.883
2034 | Done | V1 | 128 | 995 | burden | burden | Payroll Burden |  |  | 216478.44 | 172076.45 | 183177.15 | 25.8% | 18.18% |  | 1691.2378
2035 | Done | V1 | 92 | 995 | burden | burden | Payroll Burden |  |  | 59186.15 | 81302.42 | 81925.22 | -27.2% | -27.76% |  | 643.3277
2036 | Done | V1 | 31 | 995 | burden | burden | Payroll Burden |  |  | 49931.78 | 48719.51 | 51014.51 | 2.488% | -2.122% |  | 1610.7026
2037 | Done | V1 | 122 | 995 | burden | burden | Payroll Burden |  |  | 196679.65 | 228804.89 | 240448.43 | -14.04% | -18.2% |  | 1612.1283
2038 | Done | V1 | 80 | 995 | burden | burden | Payroll Burden |  |  | 130913.02 | 112245.88 | 118365.88 | 16.63% | 10.6% |  | 1636.4127
2039 | Done | V1 |  | 995 | burden | burden | Payroll Burden |  |  | 3703.52 | 4524.12 | 4524.12 | -18.14% | -18.14%
2040 | Done | V1 | 55 | 995 | burden | burden | Payroll Burden |  |  | 65061.2 | 70036.27 | 71174.77 | -7.104% | -8.59% |  | 1182.9309
2041 | Done | V2.2 | 108 | 995 | burden | burden | Payroll Burden |  |  | 211657.53 | 195957.35 | 203353.75 | 8.012% | 4.083% |  | 1959.7919
2042 | Done | V2.2 | 75 | 995 | burden | burden | Payroll Burden |  |  | 86190.15 | 94526.7 | 95452.9 | -8.819% | -9.704% |  | 1149.202
2043 | Done | V2.2 | 89 | 995 | burden | burden | Payroll Burden |  |  | 144149.08 | 159145.54 | 163244.14 | -9.423% | -11.7% |  | 1619.6526
2044 | Done | V2.2 | 78 | 995 | burden | burden | Payroll Burden |  |  | 97584.65 | 90717 | 91810.5 | 7.57% | 6.289% |  | 1251.0853
2045 | Done | V2.2 | 158 | 995 | burden | burden | Payroll Burden |  |  | 179641.55 | 242030.68 | 269409.24 | -25.78% | -33.32% |  | 1136.9718
2046 | Done | V2.2 | 110 | 995 | burden | burden | Payroll Burden |  |  | 155266.79 | 189319.06 | 194737.66 | -17.99% | -20.27% |  | 1411.5163
2047 | Done | V2.2 | 70 | 995 | burden | burden | Payroll Burden |  |  | 66831.47 | 57937.8 | 65669.48 | 15.35% | 1.769% |  | 954.7353
2048 | Done | V2.2 | 72 | 995 | burden | burden | Payroll Burden |  |  | 52049.65 | 62565.31 | 66233.59 | -16.81% | -21.42% |  | 722.9118
2049 | Done | V2.2 | 296 | 995 | burden | burden | Payroll Burden |  |  | 253391.18 | 370110.42 | 387565.92 | -31.54% | -34.62% |  | 856.0513
2050 | Done | V2.2 | 50 | 995 | burden | burden | Payroll Burden |  |  | 72671.19 | 91167.11 | 94044.86 | -20.29% | -22.73% |  | 1453.4238
2051 | Done | V2.2 | 163 | 995 | burden | burden | Payroll Burden |  |  | 230366.76 | 334376.89 | 298673.44 | -31.11% | -22.87% |  | 1413.293
2052 | Done | V2.2 | 107 | 995 | burden | burden | Payroll Burden |  |  | 196578.34 | 223194.56 | 236116.28 | -11.93% | -16.75% |  | 1837.1807
2053 | Done | V2.2 | 136 | 995 | burden | burden | Payroll Burden |  |  | 224915.87 | 206809.13 | 210032.29 | 8.755% | 7.086% |  | 1653.7932
2054 | Done | V2.2 | 68 | 995 | burden | burden | Payroll Burden |  |  | 120818.93 | 89552.25 | 91307.25 | 34.91% | 32.32% |  | 1776.749
2055 | Done | V2.2 | 98 | 995 | burden | burden | Payroll Burden |  |  | 139298.13 | 108867.78 | 130355.28 | 27.95% | 6.86% |  | 1421.4095
2056 | Done | V2.2 | 321 | 995 | burden | burden | Payroll Burden |  |  | 510170.4 | 566393.59 | 575498.01 | -9.927% | -11.35% |  | 1589.3159
2057 | Done | V2.2 | 111 | 995 | burden | burden | Payroll Burden |  |  | 98191.39 | 113649.3 | 118231.65 | -13.6% | -16.95% |  | 884.6071
2058 | Done | V2.2 | 77 | 995 | burden | burden | Payroll Burden |  |  | 117712.31 | 98551.8 | 103591.8 | 19.44% | 13.63% |  | 1528.7313
2059 | Done | V2.2 | 365 | 995 | burden | burden | Payroll Burden |  |  | 527700.4 | 462438.71 | 483842.07 | 14.11% | 9.065% |  | 1445.7545
2060 | Done | V2.2 | 270 | 995 | burden | burden | Payroll Burden |  |  | 385611.57 | 499229.44 | 590721.42 | -22.76% | -34.72% |  | 1428.191
2098 | LIVE | V2.2 | 170 | 995 | burden | burden | Payroll Burden |  |  | 662213.84 | 733502.32 | 749404.3 | -9.719% | -11.63% |  | 3895.3755
2103 | LIVE | V2.2 | 234 | 995 | burden | burden | Payroll Burden |  |  | 809708.06 | 613551.26 | 686429.56 | 31.97% | 17.96% |  | 3460.2909
2104 | LIVE | V2.2 | 24 | 995 | burden | burden | Payroll Burden |  |  | 93452.29 | 76820.47 | 80714.75 | 21.65% | 15.78% |  | 3893.8454
2105 | LIVE | V2.2 | 219 | 995 | burden | burden | Payroll Burden |  |  | 1665.94 | [5 empty] | 7.607
2106 | LIVE | V2.2 | 146 | 995 | burden | burden | Payroll Burden |  |  | 4780.75 | [5 empty] | 32.7449
2107 | LIVE | V2.2 | 244 | 995 | burden | burden | Payroll Burden |  |  | 532803.32 | 487836.01 | 514607.79 | 9.218% | 3.536% |  | 2183.6202
2111 | LIVE | V_TX | 186 | 995 | burden | burden | Payroll Burden |  |  | 166948.96 | 459591.02 | 469357.02 | -63.67% | -64.43% |  | 897.5751
2112 | LIVE | V_TX | 20 | 995 | burden | burden | Payroll Burden |  |  | 49964.42 | 57228.41 | 60539.59 | -12.69% | -17.47% |  | 2498.221
2114 | LIVE | V2.2 | 239 | 995 | burden | burden | Payroll Burden |  |  | 3419.25 | [5 empty] | 14.3065
2115 | LIVE | V2.2 | 201 | 995 | burden | burden | Payroll Burden |  |  | 789.15 | [5 empty] | 3.9261
2116 | LIVE | V2.2 | 166 | 995 | burden | burden | Payroll Burden |  |  | 3106.5 | 364765.86 | 364765.86 | -99.15% | -99.15% |  | 18.7139
2117 | LIVE | V2.2 | 104 | 995 | burden | burden | Payroll Burden |  |  | 93.93 | [5 empty] | 0.90317
2001 | Done | SUPABASE | 234 | 998 | tax | tax | Payroll Taxes |  |  | 35009.63 | 31773.74 | 31773.74 | 10.18% | 10.18% |  | 149.6138
2008 | Done | SUPABASE | 258 | 998 | tax | tax | Payroll Taxes |  |  | 47960.74 | 43743.47 | 44946.82 | 9.641% | 6.706% |  | 185.8943
2009 | Done | SUPABASE | 56 | 998 | tax | tax | Payroll Taxes |  |  | 6479.41 | 5532.48 | 5769.64 | 17.12% | 12.3% |  | 115.7037
2010 | Done | SUPABASE | 149 | 998 | tax | tax | Payroll Taxes |  |  | 15530.57 | 26232.23 | 24250.88 | -40.8% | -35.96% |  | 104.232
2011 | Done | SUPABASE | 117 | 998 | tax | tax | Payroll Taxes |  |  | 10930.61 | 12905.93 | 13338.16 | -15.31% | -18.05% |  | 93.424
2012 | Done | SUPABASE | 162 | 998 | tax | tax | Payroll Taxes |  |  | 22289.38 | 22067.57 | 22067.57 | 1.005% | 1.005% |  | 137.5888
2015 | Done | SUPABASE | 197 | 998 | tax | tax | Payroll Taxes |  |  | 44881.34 | 32468.9 | 36371.93 | 38.23% | 23.4% |  | 227.8241
2017 | Done | SUPABASE | 119 | 998 | tax | tax | Payroll Taxes |  |  | 23153.01 | 20702.43 | 21109.42 | 11.84% | 9.681% |  | 194.5631
2018 | Done | SUPABASE | 211 | 998 | tax | tax | Payroll Taxes |  |  | 34525.13 | 36206 | 36585.44 | -4.643% | -5.632% |  | 163.6262
2019 | Done | SUPABASE | 211 | 998 | tax | tax | Payroll Taxes |  |  | 42749.09 | 46381.95 | 49285.97 | -7.832% | -13.26% |  | 202.6023
2020 | Done | SUPABASE | 256 | 998 | tax | tax | Payroll Taxes |  |  | 59950.63 | 54692.15 | 46511.34 | 9.615% | 28.89% |  | 234.1821
2021 | Done | SUPABASE | 136 | 998 | tax | tax | Payroll Taxes |  |  | 34939.52 | 28904 | 31252.44 | 20.88% | 11.8% |  | 256.9082
2022 | Done | SUPABASE | 18 | 998 | tax | tax | Payroll Taxes |  |  | 4430.68 | 3989.48 | 4069.81 | 11.06% | 8.867% |  | 246.1489
2023 | Done | V1 | 209 | 998 | tax | tax | Payroll Taxes |  |  | 54627.81 | 38699.06 | 46110.4 | 41.16% | 18.47% |  | 261.3771
2024 | Done | V1 | 117 | 998 | tax | tax | Payroll Taxes |  |  | 29136.68 | 30546.45 | 31729 | -4.615% | -8.17% |  | 249.0315
2025 | Done | V1 | 75 | 998 | tax | tax | Payroll Taxes |  |  | 21978.6 | 20575.44 | 21087.65 | 6.82% | 4.225% |  | 293.048
2026 | Done | V1 | 49 | 998 | tax | tax | Payroll Taxes |  |  | 16119.9 | 14671.17 | 14681.96 | 9.875% | 9.794% |  | 328.9776
2027 | Done | V1 | 170 | 998 | tax | tax | Payroll Taxes |  |  | 37580.97 | 42681.26 | 42817.2 | -11.95% | -12.23% |  | 221.0645
2028 | Done | V1 | 296 | 998 | tax | tax | Payroll Taxes |  |  | 43634.33 | 62191.44 | 54147.36 | -29.84% | -19.42% |  | 147.4133
2029 | Done | V1 | 83 | 998 | tax | tax | Payroll Taxes |  |  | 14385.7 | 20203.65 | 20435.34 | -28.8% | -29.6% |  | 173.3217
2030 | Done | V1 | 144 | 998 | tax | tax | Payroll Taxes |  |  | 38563.39 | 41423.6 | 44035.78 | -6.905% | -12.43% |  | 267.8013
2031 | Done | V1 | 398 | 998 | tax | tax | Payroll Taxes
2032 | Done | V1 | 71 | 998 | tax | tax | Payroll Taxes |  |  | 10300.89 | 13480.83 | 13894.12 | -23.59% | -25.86% |  | 145.083
2033 | Done | V1 | 139 | 998 | tax | tax | Payroll Taxes |  |  | 40260.5 | 46791.99 | 43548.16 | -13.96% | -7.549% |  | 289.6439
2034 | Done | V1 | 128 | 998 | tax | tax | Payroll Taxes |  |  | 41269.5 | 34325.55 | 36504.12 | 20.23% | 13.05% |  | 322.418
2035 | Done | V1 | 92 | 998 | tax | tax | Payroll Taxes |  |  | 10209.45 | 14023.98 | 14129.86 | -27.2% | -27.75% |  | 110.9723
2036 | Done | V1 | 31 | 998 | tax | tax | Payroll Taxes |  |  | 8613.1 | 8218.4 | 8608.55 | 4.803% | 0.05285% |  | 277.8419
2037 | Done | V1 | 122 | 998 | tax | tax | Payroll Taxes |  |  | 33926.12 | 38601.52 | 40602.38 | -12.11% | -16.44% |  | 278.083
2038 | Done | V1 | 80 | 998 | tax | tax | Payroll Taxes |  |  | 24849.39 | 21821.63 | 22992.11 | 13.88% | 8.078% |  | 310.6174
2039 | Done | V1 |  | 998 | tax | tax | Payroll Taxes |  |  | 638.8 | 763.16 | 763.16 | -16.3% | -16.3%
2040 | Done | V1 | 55 | 998 | tax | tax | Payroll Taxes |  |  | 11222.94 | 11814.28 | 12007.83 | -5.005% | -6.536% |  | 204.0535
2041 | Done | V2.2 | 108 | 998 | tax | tax | Payroll Taxes |  |  | 36509.63 | 33055.65 | 34341.65 | 10.45% | 6.313% |  | 338.0521
2042 | Done | V2.2 | 75 | 998 | tax | tax | Payroll Taxes |  |  | 14867.27 | 16305.06 | 16466.1 | -8.818% | -9.71% |  | 198.2303
2043 | Done | V2.2 | 89 | 998 | tax | tax | Payroll Taxes |  |  | 24864.98 | 27451.26 | 28163.89 | -9.421% | -11.71% |  | 279.3818
2044 | Done | V2.2 | 78 | 998 | tax | tax | Payroll Taxes |  |  | 16832.74 | 15772.39 | 15958.29 | 6.723% | 5.48% |  | 215.8044
2045 | Done | V2.2 | 158 | 998 | tax | tax | Payroll Taxes |  |  | 30987.05 | 40827.67 | 45587.82 | -24.1% | -32.03% |  | 196.1206
2046 | Done | V2.2 | 110 | 998 | tax | tax | Payroll Taxes |  |  | 26782.71 | 32655.94 | 33598.05 | -17.99% | -20.28% |  | 243.4792
2047 | Done | V2.2 | 70 | 998 | tax | tax | Payroll Taxes |  |  | 11528.09 | 9773.41 | 11117.69 | 17.95% | 3.691% |  | 164.687
2048 | Done | V2.2 | 72 | 998 | tax | tax | Payroll Taxes |  |  | 8978.19 | 10554.02 | 11191.8 | -14.93% | -19.78% |  | 124.6971
2049 | Done | V2.2 | 296 | 998 | tax | tax | Payroll Taxes |  |  | 43708.18 | 62433.18 | 65400.62 | -29.99% | -33.17% |  | 147.6628
2050 | Done | V2.2 | 50 | 998 | tax | tax | Payroll Taxes |  |  | 12535.41 | 15378.8 | 15868.03 | -18.49% | -21% |  | 250.7082
2051 | Done | V2.2 | 163 | 998 | tax | tax | Payroll Taxes |  |  | 41157.17 | 56405.36 | 50335.78 | -27.03% | -18.23% |  | 252.498
2052 | Done | V2.2 | 107 | 998 | tax | tax | Payroll Taxes |  |  | 33908.51 | 37650.24 | 39853.83 | -9.938% | -14.92% |  | 316.902
2053 | Done | V2.2 | 136 | 998 | tax | tax | Payroll Taxes |  |  | 42642.55 | 39552.25 | 40201.13 | 7.813% | 6.073% |  | 313.5482
2054 | Done | V2.2 | 68 | 998 | tax | tax | Payroll Taxes |  |  | 21641.82 | 15223.88 | 15522.24 | 42.16% | 39.42% |  | 318.2621
2055 | Done | V2.2 | 98 | 998 | tax | tax | Payroll Taxes |  |  | 25582.99 | 22298.22 | 25951.1 | 14.73% | -1.418% |  | 261.0509
2056 | Done | V2.2 | 321 | 998 | tax | tax | Payroll Taxes |  |  | 104250.16 | 113575.65 | 115408.52 | -8.211% | -9.669% |  | 324.7669
2057 | Done | V2.2 | 111 | 998 | tax | tax | Payroll Taxes |  |  | 16937.47 | 19320.38 | 20099.39 | -12.33% | -15.73% |  | 152.5898
2058 | Done | V2.2 | 77 | 998 | tax | tax | Payroll Taxes |  |  | 21237 | 16753.81 | 17610.62 | 26.76% | 20.59% |  | 275.8052
2059 | Done | V2.2 | 365 | 998 | tax | tax | Payroll Taxes |  |  | 95203.34 | 83533.79 | 87255.07 | 13.97% | 9.109% |  | 260.8311
2060 | Done | V2.2 | 270 | 998 | tax | tax | Payroll Taxes |  |  | 70655.82 | 102251.81 | 117805.26 | -30.9% | -40.02% |  | 261.6882
2098 | LIVE | V2.2 | 170 | 998 | tax | tax | Payroll Taxes |  |  | 118832.01 | 134724.92 | 137645.7 | -11.8% | -13.67% |  | 699.0118
2103 | LIVE | V2.2 | 234 | 998 | tax | tax | Payroll Taxes |  |  | 139063 | 121440.29 | 136111.89 | 14.51% | 2.168% |  | 594.2863
2104 | LIVE | V2.2 | 24 | 998 | tax | tax | Payroll Taxes |  |  | 15459.34 | 14386.21 | 15101.49 | 7.459% | 2.37% |  | 644.1392
2105 | LIVE | V2.2 | 219 | 998 | tax | tax | Payroll Taxes |  |  | 261.8 | [5 empty] | 1.1954
2106 | LIVE | V2.2 | 146 | 998 | tax | tax | Payroll Taxes |  |  | 763.76 | [5 empty] | 5.2312
2107 | LIVE | V2.2 | 244 | 998 | tax | tax | Payroll Taxes |  |  | 84211.38 | 91357.29 | 96280.07 | -7.822% | -12.53% |  | 345.1286
2111 | LIVE | V_TX | 186 | 998 | tax | tax | Payroll Taxes |  |  | 29028.34 | 90966.92 | 92932.97 | -68.09% | -68.76% |  | 156.0663
2112 | LIVE | V_TX | 20 | 998 | tax | tax | Payroll Taxes |  |  | 7919.25 | 10850 | 11458.18 | -27.01% | -30.89% |  | 395.9625
2114 | LIVE | V2.2 | 239 | 998 | tax | tax | Payroll Taxes |  |  | 564.08 | [5 empty] | 2.3602
2115 | LIVE | V2.2 | 201 | 998 | tax | tax | Payroll Taxes |  |  | 126.52 | [5 empty] | 0.62945
2116 | LIVE | V2.2 | 166 | 998 | tax | tax | Payroll Taxes |  |  | 496.52 | 68645.97 | 68645.97 | -99.28% | -99.28% |  | 2.9911
2117 | LIVE | V2.2 | 104 | 998 | tax | tax | Payroll Taxes |  |  | 15.07 | [5 empty] | 0.1449
2023 | Done | V1 | 209 | 999 | sales | sales | Sales |  |  | -2771369 | -2469500 | -2771369 | 12.22% | 0% |  | -13260.1388
2024 | Done | V1 | 117 | 999 | sales | sales | Sales |  |  | -1811843 | -1763480 | -1811843 | 2.742% | 0% |  | -15485.8376
2025 | Done | V1 | 75 | 999 | sales | sales | Sales |  |  | -1208338 | -1179300 | -1208338 | 2.462% | 0% |  | -16111.1733
2026 | Done | V1 | 49 | 999 | sales | sales | Sales |  |  | -830667 | -825370 | -830667 | 0.6418% | 0% |  | -16952.3878
2027 | Done | V1 | 170 | 999 | sales | sales | Sales |  |  | -2275444 | -2230810 | -2275444 | 2.001% | 0% |  | -13384.9647
2028 | Done | V1 | 296 | 999 | sales | sales | Sales |  |  | -2684887 | -2979880 | -2684887 | -9.899% | 0% |  | -9070.5642
2029 | Done | V1 | 83 | 999 | sales | sales | Sales |  |  | -1123747 | -1113220 | -1123747 | 0.9456% | 0% |  | -13539.1205
2030 | Done | V1 | 144 | 999 | sales | sales | Sales |  |  | -2322781 | -2135080 | -2322781 | 8.791% | 0% |  | -16130.4236
2031 | Done | V1 | 398 | 999 | sales | sales | Sales |  |  | -5187754 | -5051600 | -5187754 | 2.695% | 0% |  | -13034.5578
2032 | Done | V1 | 71 | 999 | sales | sales | Sales |  |  | -726403 | -685300 | -726403 | 5.998% | 0% |  | -10231.0282
2033 | Done | V1 | 139 | 999 | sales | sales | Sales |  |  | -2343188 | -2504600 | -2343188 | -6.445% | 0% |  | -16857.4676
2034 | Done | V1 | 128 | 999 | sales | sales | Sales |  |  | -1897650.9 | -1839000 | -1897650.9 | 3.189% | 0% |  | -14825.3977
2035 | Done | V1 | 92 | 999 | sales | sales | Sales |  |  | -722290 | -717400 | -722290 | 0.6816% | 0% |  | -7850.9783
2036 | Done | V1 | 31 | 999 | sales | sales | Sales |  |  | -418677 | -388515 | -418677 | 7.763% | 0% |  | -13505.7097
2037 | Done | V1 | 122 | 999 | sales | sales | Sales |  |  | -2076783 | -1920850 | -2076783 | 8.118% | 0% |  | -17022.8115
2038 | Done | V1 | 80 | 999 | sales | sales | Sales |  |  | -1229419 | -1210378 | -1229419 | 1.573% | 0% |  | -15367.7375
2039 | Done | V1 |  | 999 | sales | sales | Sales |  |  | -54900 | -54900 | -54900 | 0% | 0%
2040 | Done | V1 | 55 | 999 | sales | sales | Sales |  |  | -624171 | -604000 | -624171 | 3.34% | 0% |  | -11348.5636
2041 | Done | V2.2 | 108 | 999 | sales | sales | Sales |  |  | -1883761 | -1766205 | -1883761 | 6.656% | 0% |  | -17442.2315
2042 | Done | V2.2 | 75 | 999 | sales | sales | Sales |  |  | -922104 | -906587 | -922104 | 1.712% | 0% |  | -12294.72
2043 | Done | V2.2 | 89 | 999 | sales | sales | Sales |  |  | -1583445 | -1576200 | -1583445 | 0.4596% | 0% |  | -17791.5169
2044 | Done | V2.2 | 78 | 999 | sales | sales | Sales |  |  | -855264 | -832900 | -855264 | 2.685% | 0% |  | -10964.9231
2045 | Done | V2.2 | 158 | 999 | sales | sales | Sales |  |  | -2110205 | -1898200 | -2110205 | 11.17% | 0% |  | -13355.7278
2046 | Done | V2.2 | 110 | 999 | sales | sales | Sales |  |  | -1721867 | -1648500 | -1721867 | 4.451% | 0% |  | -15653.3364
2047 | Done | V2.2 | 70 | 999 | sales | sales | Sales |  |  | -553189 | -475800 | -553189 | 16.27% | 0% |  | -7902.7
2048 | Done | V2.2 | 72 | 999 | sales | sales | Sales |  |  | -517068 | -498700 | -517068 | 3.683% | 0% |  | -7181.5
2049 | Done | V2.2 | 296 | 999 | sales | sales | Sales |  |  | -2999780 | -2898965 | -2999780 | 3.478% | 0% |  | -10134.3919
2050 | Done | V2.2 | 50 | 999 | sales | sales | Sales |  |  | -918566 | -897800 | -918566 | 2.313% | 0% |  | -18371.32
2051 | Done | V2.2 | 163 | 999 | sales | sales | Sales |  |  | -2588279.5 | -2738000 | -2588279.5 | -5.468% | 0% |  | -15879.0153
2052 | Done | V2.2 | 107 | 999 | sales | sales | Sales |  |  | -2231035 | -2134000 | -2231035 | 4.547% | 0% |  | -20850.7944
2053 | Done | V2.2 | 136 | 999 | sales | sales | Sales |  |  | -2332680 | -2300309 | -2332680 | 1.407% | 0% |  | -17152.0588
2054 | Done | V2.2 | 68 | 999 | sales | sales | Sales |  |  | -843087 | -785600 | -843087 | 7.318% | 0% |  | -12398.3382
2055 | Done | V2.2 | 98 | 999 | sales | sales | Sales |  |  | -1315429 | -1142340 | -1315429 | 15.15% | 0% |  | -13422.7449
2056 | Done | V2.2 | 321 | 999 | sales | sales | Sales |  |  | -6034876 | -5877400 | -6034876 | 2.679% | 0% |  | -18800.2368
2057 | Done | V2.2 | 111 | 999 | sales | sales | Sales |  |  | -1133967 | -1098897 | -1133967 | 3.191% | 0% |  | -10215.9189
2058 | Done | V2.2 | 77 | 999 | sales | sales | Sales |  |  | -961556 | -928800 | -961556 | 3.527% | 0% |  | -12487.7403
2059 | Done | V2.2 | 365 | 999 | sales | sales | Sales |  |  | -4492453 | -4378750 | -4492453 | 2.597% | 0% |  | -12308.0904
2060 | Done | V2.2 | 270 | 999 | sales | sales | Sales |  |  | -6156577 | -5307510 | -6156577 | 16% | 0% |  | -22802.137
2098 | LIVE | V2.2 | 170 | 999 | sales | sales | Sales |  |  | -6917965.74 | -6885880 | -6917965.74 | 0.466% | 0% |  | -40693.9161
2103 | LIVE | V2.2 | 234 | 999 | sales | sales | Sales |  |  | -6608301.34 | -6030791 | -6625153.34 | 9.576% | -0.2544% |  | -28240.604
2104 | LIVE | V2.2 | 24 | 999 | sales | sales | Sales |  |  | -1193734 | -1143800 | -1196549 | 4.366% | -0.2353% |  | -49738.9167
2105 | LIVE | V2.2 | 219 | 999 | sales | sales | Sales |  |  | -193091.4 | [5 empty] | -881.6959
2106 | LIVE | V2.2 | 146 | 999 | sales | sales | Sales |  |  | -49275 | [5 empty] | -337.5
2107 | LIVE | V2.2 | 244 | 999 | sales | sales | Sales |  |  | -4422211 | -4671538 | -4889866 | -5.337% | -9.564% |  | -18123.8156
2111 | LIVE | V_TX | 186 | 999 | sales | sales | Sales |  |  | 2280568 | -4499870 | 4589762 | -150.7% | -50.31% |  | 12261.1183
2112 | LIVE | V_TX | 20 | 999 | sales | sales | Sales |  |  | 518063 | -664082 | 696427 | -178% | -25.61% |  | 25903.15
2114 | LIVE | V2.2 | 239 | 999 | sales | sales | Sales |  |  | -80000 | [5 empty] | -334.728
2031 | Done | V1 | 398 | 310 | other | other | Flats Underground Labor | 4229.5 |  | 101967.5 | 143266 | 138337 | -28.83% | -26.29% | 10.6269 | 256.1997
2032 | Done | V1 | 71 | 310 | other | other | Flats Underground Labor | 8 | [6 empty] | 0.11268
2031 | Done | V1 | 398 | 320 | other | other | Flats Roughin Labor | 21198.75 | 38.25 | 452849.38 | 423275 | 449230 | 6.987% | 0.8057% | 53.2632 | 1137.8125
2032 | Done | V1 | 71 | 320 | other | other | Flats Roughin Labor
2031 | Done | V1 | 398 | 330 | other | other | Flats Finish Labor | 4717 | 101.5 | 118040 | 117750 | 118330 | 0.2463% | -0.2451% | 11.8518 | 296.5829
2033 | Done | V1 | 139 | 330 | other | other | Flats Finish Labor
2038 | Done | V1 | 80 | 330 | other | other | Flats Finish Labor
2031 | Done | V1 | 398 | 410 | other | other | Flats Underground Mat |  |  | 50431.67 | 58800 | 37808 | -14.23% | 33.39% |  | 126.7127
2031 | Done | V1 | 398 | 420 | other | other | Flats Roughin Material |  |  | 200867.48 | 259245 | 274177 | -22.52% | -26.74% |  | 504.6922
2032 | Done | V1 | 71 | 420 | other | other | Flats Roughin Material
2030 | Done | V1 | 144 | 430 | other | other | Flats Finish Material
2031 | Done | V1 | 398 | 430 | other | other | Flats Finish Material |  |  | 373687.67 | 460418 | 470355 | -18.84% | -20.55% |  | 938.9137
2050 | Done | V2.2 | 50 | 800 | other | other | Office Time | 4 |  | 208 |  |  |  |  | 0.08 | 4.16
2050 | Done | V2.2 | 50 | 997 | other | other | Employee Benefits | 8 |  | 144 |  |  |  |  | 0.16 | 2.88
2055 | Done | V2.2 | 98 | 997 | other | other | Employee Benefits
2059 | Done | V2.2 | 365 | 997 | other | other | Employee Benefits | 8 |  | 184 |  |  |  |  | 0.021918 | 0.50411