## Schedule of V. Backup
Schedule of values
PROJECT: | The Cora Apartments |  |  |  | PAY APPLICATION #: |  | 16
LOCATION: | SEATTLE |  |  |  | APPLICATION DATE: |  | 2017-08-20
DESCRIPTION: APPLICATION FOR PAYMENT |  |  |  |  | PERIOD TO: |  | 2017-08-31
A | B |  | C | D | E | F | G |  | H | I
Area, level | DESCRIPTION | Name of Subcontractor/ | SCHEDULED | WORK COMPLETED |  |  | COMPLETED | PERCENT | BALANCE | RETAINAGE
and/or |  | Supplier | Value | FROM | THIS |  | AND STORED | COMPLETE | TO FINISH | 5%
phase |  |  |  | PREVIOUS | PERIOD |  | TO DATE
Plumbing | description of work |  | 1179300 | 1179300 | 0 |  | 1179300 | 100% | 0 | 58965
| plumbing design and engineering |  | 31000 | 31000 | 0 |  | 31000 | 100% | 0 | 1550
| plumbing permits | EXXEL | 7900 | 7900 | 0 |  | 7900 | 100% | 0 | 395
P1 underground | underground drain & foundation piping and structures | EXXEL | 56000 | 56000 | 0 |  | 56000 | 100% | 0 | 2800
P1 sump pumps | stock and install sump pump for foundation/storm drain | EXXEL | 8100 | 8100 | 0 |  | 8100 | 100% | 0 | 405
P1 sump pumps | stock and install sump pump for garage floor drainage |  | 8100 | 8100 | 0 |  | 8100 | 100% | 0 | 405
P1 parking | waste, vent and drain piping |  | 23800 | 23800 | 0 |  | 23800 | 100% | 0 | 1190
P1 boiler room | stock water heaters and mechanical equipment | EXXEL | 30300 | 30300 | 0 |  | 30300 | 100% | 0 | 1515
P1 boiler room | install water heaters and mechanical equipment | EXXEL | 22900 | 22900 | 0 |  | 22900 | 100% | 0 | 1145
P1 mech water room | stock pressure pump and backflow devices | EXXEL | 27500 | 27500 | 0 |  | 27500 | 100% | 0 | 1375
P1 mech water room | install pressure pump and backflow devices |  | 14600 | 14600 | 0 |  | 14600 | 100% | 0 | 730
gas piping | gas piping house main |  | 16300 | 16300 | 0 |  | 16300 | 100% | 0 | 815
L1 PT deck | canout, sleeve, loop water piping | EXXEL | 6000 | 6000 | 0 |  | 6000 | 100% | 0 | 300
L1 parking | waste, vent and drain piping | EXXEL | 20200 | 20200 | 0 |  | 20200 | 100% | 0 | 1010
L1 units/amenity | waste, vent and drain piping | EXXEL | 49500 | 49500 | 0 |  | 49500 | 100% | 0 | 2475
L2 PT deck | canout, sleeve, loop water piping |  | 6000 | 6000 | 0 |  | 6000 | 100% | 0 | 300
L2parking | waste, vent and drain piping |  | 19000 | 19000 | 0 |  | 19000 | 100% | 0 | 950
L2 water mains | hot, cold and return main water lines | EXXEL | 43000 | 43000 | 0 |  | 43000 | 100% | 0 | 2150
L2 units/amenity | waste, vent and drain piping |  | 42400 | 42400 | 0 |  | 42400 | 100% | 0 | 2120
L2 | stock fiberglass tubs in units | EXXEL | 3000 | 3000 | 0 |  | 3000 | 100% | 0 | 150
L2 | install fiberglass tubs in units | EXXEL | 850 | 850 | 0 |  | 850 | 100% | 0 | 42.5
L3 PT deck | canout, sleeve, loop water piping | EXXEL | 12000 | 12000 | 0 |  | 12000 | 100% | 0 | 600
L3 | roughin plumbing | EXXEL | 119900 | 119900 | 0 |  | 119900 | 100% | 0 | 5995
L3 | stock fiberglass tubs | EXXEL | 10200 | 10200 | 0 |  | 10200 | 100% | 0 | 510
L3 | install fiberglass tubs | EXXEL | 2900 | 2900 | 0 |  | 2900 | 100% | 0 | 145
L4 | roughin plumbing | roughin plumbing in units at level 1 west | 119900 | 119900 | 0 |  | 119900 | 100% | 0 | 5995
L4 | stock fiberglass tubs |  | 10200 | 10200 | 0 |  | 10200 | 100% | 0 | 510
L4 | install fiberglass tubs |  | 2900 | 2900 | 0 |  | 2900 | 100% | 0 | 145
L5 | roughin plumbing |  | 119900 | 119900 | 0 |  | 119900 | 100% | 0 | 5995
L5 | stock fiberglass tubs |  | 10200 | 10200 | 0 |  | 10200 | 100% | 0 | 510
L5 | install fiberglass tubs |  | 2900 | 2900 | 0 |  | 2900 | 100% | 0 | 145
L6 | roughin plumbing |  | 119900 | 119900 | 0 |  | 119900 | 100% | 0 | 5995
L6 | stock fiberglass tubs |  | 10200 | 10200 | 0 |  | 10200 | 100% | 0 | 510
L6 | install fiberglass tubs |  | 2900 | 2900 | 0 |  | 2900 | 100% | 0 | 145
L7 | roughin plumbing |  | 91550 | 91550 | 0 |  | 91550 | 100% | 0 | 4577.5
L7 | stock fiberglass tubs |  | 10200 | 10200 | 0 |  | 10200 | 100% | 0 | 510
L7 | install fiberglass tubs |  | 2900 | 2900 | 0 |  | 2900 | 100% | 0 | 145
L1 trim | install toilets, lavs and sinks |  | 3100 | 3100 | 0 |  | 3100 | 100% | 0 | 155
L2 trim | install toilets, lavs and sinks |  | 5600 | 5600 | 0 |  | 5600 | 100% | 0 | 280
L3 trim | install toilets, lavs and sinks |  | 17100 | 17100 | 0 |  | 17100 | 100% | 0 | 855
L4 trim | install toilets, lavs and sinks |  | 17100 | 17100 | 0 |  | 17100 | 100% | 0 | 855
L5 trim | install toilets, lavs and sinks |  | 17100 | 17100 | 0 |  | 17100 | 100% | 0 | 855
L6 trim | install toilets, lavs and sinks |  | 17100 | 17100 | 0 |  | 17100 | 100% | 0 | 855
L7 trim | install toilets, lavs and sinks |  | 17100 | 17100 | 0 |  | 17100 | 100% | 0 | 855
|  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
L7 trim |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
L7 trim |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
L7 trim |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
L7 trim |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
L7 trim |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
L7 trim |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
L7 trim |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
L7 trim |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
L7 trim |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
L7 trim |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
SUBTOTAL |  |  | 1179300 | 1179300 | 0 | 0 | 1179300 | #DIV/0! | 0 | 57415
CHANGE ORDERS
CO#1 | unit AC upgrade |  | 700 | 700 | 0 |  | 700 | 100% | 0 | 35
CO#2 | added costs per COR 04,05,06 |  | 4390 | 4390 | 0 |  | 4390 | 100% | 0 | 219.5
CO#3 | added exterior trench drains on 1st ave |  | 7881 | 7881 | 0 |  | 7881 | 100% | 0 | 394.05
CO#4 | gas permit temp heat |  | 650 | 650 | 0 |  | 650 | 100% | 0 | 32.5
CO#4 | ASI 002 activity room revisions |  | 2140 | 2140 | 0 |  | 2140 | 100% | 0 | 107
CO#4 | RI for future cold water meters |  | 607 | 607 | 0 |  | 607 | 100% | 0 | 30.35
CO#4 | RFI 65.1 BBQ & firepit |  | 5620 | 5620 | 0 |  | 5620 | 100% | 0 | 281
CO#5 | credit for residential lav substitute Toto to Lenova |  | -1971 | -1971 | 0 |  | -1971 | 100% | 0 | -98.55
CO#6 | plumbing systems |  | 3316 |  | 3316 |  | 3316 | 100% | 0 | 165.8
CO#7 |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
CO#8 |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
CO#9 |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
CO#10 |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
23333 |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
CONTRACT TOTAL |  |  | 1202633 | 1199317 | 3316 | 0 | 1202633 | 100% | 0 | 58581.65
INPUT NEW
PERCENT
COMPLETES
GOTO PAYAPP FORM
GOTO DETAIL BREAKDOWN
GOTO PAYAPP
INPUT NEW
PERCENT
COMPLETES
GOTO PAYAPP FORM
GOTO DETAIL BREAKDOWN