## Schedule of V. Backup
Schedule of values
PROJECT: | The Cora Apartments |  |  |  | PAY APPLICATION #: |  | 9
LOCATION: | SEATTLE |  |  |  | APPLICATION DATE: |  | 2017-01-20
DESCRIPTION: APPLICATION FOR PAYMENT |  |  |  |  | PERIOD TO: |  | 2017-01-31
A | B |  | C | D | E | F | G |  | H | I
Area, level | DESCRIPTION | Name of Subcontractor/ | SCHEDULED | WORK COMPLETED |  |  | COMPLETED | PERCENT | BALANCE | RETAINAGE
and/or |  | Supplier | Value | FROM | THIS |  | AND STORED | COMPLETE | TO FINISH | 5%
phase |  |  |  | PREVIOUS | PERIOD |  | TO DATE
Plumbing | description of work |  | 1179300 | 635300 | 275875 |  | 911175 | 77.26% | 268125 | 45558.75
| plumbing design and engineering |  | 31000 | 31000 | 0 |  | 31000 | 100% | 0 | 1550
| plumbing permits | EXXEL | 7900 | 7900 | 0 |  | 7900 | 100% | 0 | 395
P1 underground | underground drain & foundation piping and structures | EXXEL | 56000 | 56000 | 0 |  | 56000 | 100% | 0 | 2800
P1 sump pumps | stock and install sump pump for foundation/storm drain | EXXEL | 8100 |  | 0 |  | 0 | 0% | 8100 | 0
P1 sump pumps | stock and install sump pump for garage floor drainage |  | 8100 |  | 0 |  | 0 | 0% | 8100 | 0
P1 parking | waste, vent and drain piping |  | 23800 | 23800 | 0 |  | 23800 | 100% | 0 | 1190
P1 boiler room | stock water heaters and mechanical equipment | EXXEL | 30300 |  | 0 |  | 0 | 0% | 30300 | 0
P1 boiler room | install water heaters and mechanical equipment | EXXEL | 22900 |  | 0 |  | 0 | 0% | 22900 | 0
P1 mech water room | stock pressure pump and backflow devices | EXXEL | 27500 | 12000 | 0 |  | 12000 | 43.64% | 15500 | 600
P1 mech water room | install pressure pump and backflow devices |  | 14600 |  | 0 |  | 0 | 0% | 14600 | 0
gas piping | gas piping house main |  | 16300 | 14000 | 1000 |  | 15000 | 92.02% | 1300 | 750
L1 PT deck | canout, sleeve, loop water piping | EXXEL | 6000 | 6000 | 0 |  | 6000 | 100% | 0 | 300
L1 parking | waste, vent and drain piping | EXXEL | 20200 | 20200 | 0 |  | 20200 | 100% | 0 | 1010
L1 units/amenity | waste, vent and drain piping | EXXEL | 49500 | 49500 | 0 |  | 49500 | 100% | 0 | 2475
L2 PT deck | canout, sleeve, loop water piping |  | 6000 | 6000 | 0 |  | 6000 | 100% | 0 | 300
L2parking | waste, vent and drain piping |  | 19000 | 19000 | 0 |  | 19000 | 100% | 0 | 950
L2 water mains | hot, cold and return main water lines | EXXEL | 43000 | 43000 | 0 |  | 43000 | 100% | 0 | 2150
L2 units/amenity | waste, vent and drain piping |  | 42400 | 42400 | 0 |  | 42400 | 100% | 0 | 2120
L2 | stock fiberglass tubs in units | EXXEL | 3000 | 3000 | 0 |  | 3000 | 100% | 0 | 150
L2 | install fiberglass tubs in units | EXXEL | 850 |  | 0 |  | 0 | 0% | 850 | 0
L3 PT deck | canout, sleeve, loop water piping | EXXEL | 12000 | 12000 | 0 |  | 12000 | 100% | 0 | 600
L3 | roughin plumbing | EXXEL | 119900 | 108000 | 11900 |  | 119900 | 100% | 0 | 5995
L3 | stock fiberglass tubs | EXXEL | 10200 | 10200 | 0 |  | 10200 | 100% | 0 | 510
L3 | install fiberglass tubs | EXXEL | 2900 |  | 0 |  | 0 | 0% | 2900 | 0
L4 | roughin plumbing | roughin plumbing in units at level 1 west | 119900 | 108000 | 11900 |  | 119900 | 100% | 0 | 5995
L4 | stock fiberglass tubs |  | 10200 | 10200 | 0 |  | 10200 | 100% | 0 | 510
L4 | install fiberglass tubs |  | 2900 |  | 0 |  | 0 | 0% | 2900 | 0
L5 | roughin plumbing |  | 119900 | 48000 | 71900 |  | 119900 | 100% | 0 | 5995
L5 | stock fiberglass tubs |  | 10200 | 5100 | 5100 |  | 10200 | 100% | 0 | 510
L5 | install fiberglass tubs |  | 2900 |  | 0 |  | 0 | 0% | 2900 | 0
L6 | roughin plumbing |  | 119900 |  | 107900 |  | 107900 | 89.99% | 12000 | 5395
L6 | stock fiberglass tubs |  | 10200 |  | 10200 |  | 10200 | 100% | 0 | 510
L6 | install fiberglass tubs |  | 2900 |  | 0 |  | 0 | 0% | 2900 | 0
L7 | roughin plumbing |  | 91550 |  | 45775 |  | 45775 | 50% | 45775 | 2288.75
L7 | stock fiberglass tubs |  | 10200 |  | 10200 |  | 10200 | 100% | 0 | 510
L7 | install fiberglass tubs |  | 2900 |  | 0 |  | 0 | 0% | 2900 | 0
L1 trim | install toilets, lavs and sinks |  | 3100 |  | 0 |  | 0 | 0% | 3100 | 0
L2 trim | install toilets, lavs and sinks |  | 5600 |  | 0 |  | 0 | 0% | 5600 | 0
L3 trim | install toilets, lavs and sinks |  | 17100 |  | 0 |  | 0 | 0% | 17100 | 0
L4 trim | install toilets, lavs and sinks |  | 17100 |  | 0 |  | 0 | 0% | 17100 | 0
L5 trim | install toilets, lavs and sinks |  | 17100 |  | 0 |  | 0 | 0% | 17100 | 0
L6 trim | install toilets, lavs and sinks |  | 17100 |  | 0 |  | 0 | 0% | 17100 | 0
L7 trim | install toilets, lavs and sinks |  | 17100 |  | 0 |  | 0 | 0% | 17100 | 0
|  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
L7 trim |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
L7 trim |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
L7 trim |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
L7 trim |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
L7 trim |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
L7 trim |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
L7 trim |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
L7 trim |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
L7 trim |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
L7 trim |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
SUBTOTAL |  |  | 1179300 | 635300 | 275875 | 0 | 911175 | #DIV/0! | 268125 | 44008.75
CHANGE ORDERS
CO#1 | unit AC upgrade |  | 700 |  | 0 |  | 0 | 0% | 700 | 0
CO#2 |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
CO#3 |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
CO#4 |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
CO#5 |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
CO#6 |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
CO#7 |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
CO#8 |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
CO#9 |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
CO#10 |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
CO#11 |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
CO#12 |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
CO#13 |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
CO#14 |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
CO#15 |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
CO#16 |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
CO#17 |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
700 |  |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | 0
CONTRACT TOTAL |  |  | 1180000 | 635300 | 275875 | 0 | 911175 | 77.22% | 268825 | 44008.75
INPUT NEW
PERCENT
COMPLETES
GOTO PAYAPP FORM
GOTO DETAIL BREAKDOWN
GOTO PAYAPP
INPUT NEW
PERCENT
COMPLETES
GOTO PAYAPP FORM
GOTO DETAIL BREAKDOWN