## CGC BP
[7 empty] | PROJECT: | 2015 Rooster
[7 empty] | DATE: | 2014-11-03
RFI/ASI:
DESCRIPTION OF CHANGE/WORK PERFORMED
|  | Labor |  |  |  | Material/Equipment |  |  |  | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
DRINKING FOUNTAIN/BOTTLE FILLER IN FITNESS ROOM
| COORDINATE WITH IMAGING/CORE DRILLER | 1 | HRS | 75 | 75
| LAYOUT WASTE/VENT/WATER PIPING | 1.5 | HRS | 75 | 112.5
| INSTALL NEW WASTE/VENT LINES | 2 | HRS | 75 | 150 | 25 | LF | 0.85 | 21.25
| INSTALL NEW WATER LINES | 2 | HRS | 75 | 150 | 25 | LF | 0.5 | 12.5
| FITTINGS/HANGERS/WALL SUPPORTS |  |  |  |  | 1 | LOT | 136 | 136
| IN-WALL BLOCKING AND MOUNTING FRAME | 3 | HRS | 75 | 225
| TRIM/STARTUP/TEST LABOR | 3 | HRS | 75 | 225
| PERMIT | 0.25 | HRS | 80 | 20 | 1 | LS | 15 | 15
| CLEANUP | 0.5 | HRS | 46 | 23
| SUPERVISION | 2 | HRS | 75 | 150
| AS-BUILTS | 1 | HRS | 75 | 75
| Subtotals |  |  |  | 1205.5 |  |  |  | 184.75 |  | 0
| OH & Profit |  |  | 15% | 180.825 |  |  | 15% | 27.7125 | 15% | 0
| Totals |  |  |  | 1386.325 |  |  |  | 212.4625 |  | 0
Total this item
1598.7875
[13 empty] | Chilled? | Other | Quan | UOM | Unit Cost | Subtotal | OH&P | TOTAL
[12 empty] | EZWS-SFGRN8K EZH2O® Bottle Filling Station with SwirlFlo® Green Single Refrigerated Fountain | Yes | 12" Wall cavity needed, frame needed | 1 | EA | 2931.24 | 2931.24 | 15% | 3370.926
[12 empty] | LZSTL8WSS3K Filtered EZH2O® Bottle Filling Station with Versatile Bi-Level ADA Cooler | Yes |  | 1 | EA | 1263.89 | 1263.89 | 15% | 1453.4735
[12 empty] | LZS8WSS2K Filtered EZH2O® Bottle Filling Station with Single ADA Cooler | Yes |  | 1 | EA | 888.33 | 888.33 | 15% | 1021.5795
[12 empty] | EZSTL8LC Versatile Wall Mount Bi-Level ADA Cooler | Yes |  | 1 | EA | 625 | 625 | 15% | 718.75
[13 empty] | Chilled? | Notes | Quan | UOM | Cost | Subtotal | OH&P | TOTAL
[12 empty] | LZWSM8K Filtered EZH2O® Bottle Filling Station In-Wall WITH CHILLER | Yes | 12" Wall cavity needed, frame needed | 1 | EA | 2427 | 2427 | 15% | 2791.05
[12 empty] | LZWSMDK Filtered EZH2O® Bottle Filling Station In-Wall WITHOUT CHILLER | No | Frame needed | 1 | EA | 2007 | 2007 | 15% | 2308.05
Add drinking fountain at fitness room.