## CGC BP
[7 empty] | PROJECT: | CORA
[7 empty] | DATE: | 2017-01-27
[7 empty] | RFI/ASI: | TRENCH DRAINS
DESCRIPTION OF CHANGE/WORK PERFORMED
|  | Labor |  |  |  | Material/Equipment |  |  | Material | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
| LAYOUT/COORDINATE WITH OTHER SUBS | 4 | HRS | 80 | 320
| SUBMITTALS/PRICING/ORDERING MATERIAL | 2 | HRS | 95 | 190
| CLIP EARS OFF SIDE OF TRENCH DRAIN | 1 | HRS | 64 | 64
| INSTALL TRENCH DRAIN BODY (2 GUYS, 6 HRS) | 12 | HRS | 64 | 768
| 3" PIPE |  |  |  |  | 12 | LF | 1.33 | 15.96
| PIPE/FITTINGS/COUPLINGS/GLUE/ETC |  |  |  |  | 1 | LS | 100 | 100
| NDS DS-091N DURA SLOPE 4' SECTIONS |  |  |  |  | 16 | EA | 75 | 1200
| NDS DS-1234 SCREW PACKS |  |  |  |  | 16 | EA | 4.94 | 79.04
| NDS DS-224 END CAPS |  |  |  |  | 16 | EA | 12.38 | 198.08
| NDS DS-2265 STAINLESS STEEL GRATE, 2' SECTIONS |  |  |  |  | 32 | EA | 73.66 | 2357.12
| NDS DS-227 UNIVERSAL END OUTLET |  |  |  |  | 4 | EA | 12.15 | 48.6
| HARDWARE, MISCELLANEOUS |  |  |  |  | 1 | LS | 200 | 200
| WRAP/PROTECT TRENCH DRAIN FOR POUR | 2 | HRS | 64 | 128
| POUR WATCH | 3 | HRS | 64 | 192
| REMOVE PROTECTION, CLEAN CONCRETE | 4 | HRS | 64 | 256
| INSTALL TRENCH DRAIN COVERS | 4 | HRS | 64 | 256
| SUPERVISION | 4 | HRS | 80 | 320
| AS-BUILTING | 2 | HRS | 80 | 160
| Subtotals |  |  |  | 2654 |  |  |  | 4198.8 | 0 | 0 | 6852.8
| OH & Profit |  |  | 15% | 398.1 |  |  | 15% | 629.82 | 15% | 0
| Totals |  |  |  | 3052.1 |  |  |  | 4828.62 |  | 0
Total this page
7880.72
COST TO INSTALL TRENCH DRAINS AT WEST ENTRIES