## COR
[7 empty] | PROJECT: | CORA
[7 empty] | DATE: | 2016-11-28
RFI/ASI:
DESCRIPTION OF CHANGE/WORK PERFORMED
|  | Labor |  |  |  | Material/Equipment |  |  |  | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
| IMAGING & CORE DRILLING COORDINATION | 2 | HRS | 80 | 160
| IMAGING & CORE DRILLING - 5EA CORE DRILLS WITH 5EA ADDITIONAL CORES TO GET THE DRAIN TO FIT DOWN IN THE CONCRETE | [8 empty] | LS | 1500
| WATTS FD33 DRAINS |  |  |  |  | 5 | EA | 85 | 425
| ADDITIONAL PIPING | 3 | HRS | 60.5 | 181.5 | 30 | LF | 1.85 | 55.5
| SUPERVISION | 2 | HRS | 80 | 160
| Subtotals |  |  |  | 501.5 |  |  |  | 480.5 |  | 1500
| OH & Profit |  |  | 15% | 75.225 |  |  | 15% | 72.075 | 15% | 225
| Totals |  |  |  | 576.725 |  |  |  | 552.575 |  | 1725
Total this item
2854.3
CHANGE TRENCH DRAINS TO AREA DRAINS AT GARAGE ENTRANCES