## CGC BP
[7 empty] | PROJECT: | CORA
[7 empty] | DATE: | 2017-02-09
RFI/ASI:
DESCRIPTION OF CHANGE/WORK PERFORMED
|  | Labor |  |  |  | Material/Equipment |  |  |  | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
| LABELS |  |  |  |  | 8 | EA | 8.5 | 68
| HEAT TRACE WIRE |  |  |  |  | 30 | LF | 7.9 | 237
| POWER KIT/END SEAL |  |  |  |  | 1 | EA | 95.8 | 95.8
| MOUNTING BRACKET |  |  |  |  | 1 | EA | 20.6 | 20.6
| THERMOSTAT |  |  |  |  | 1 | EA | 160 | 160
| GLASS TAPE |  |  |  |  | 1 | ROLL | 9.8 | 9.8
| INSULATION |  |  |  |  | 30 | LF | 3.5 | 105
| WRAP INSULATION |  |  |  |  | 2 | EA | 15 | 30
| INSTALL LABOR | 8 | HRS | 64 | 512
| SUPERVISION/COORDINATION | 2 | HRS | 85 | 170
| Subtotals |  |  |  | 682 |  |  |  | 726.2 |  | 0
| OH & Profit |  |  | 15% | 102.3 |  |  | 15% | 108.93 | 15% | 0
| Subtotal |  |  |  | 784.3 |  |  |  | 835.13 |  | 0
TOTAL
1619.43
DESCRIPTION OF CHANGE/WORK PERFORMED
|  | Labor |  |  |  | Material/Equipment |  |  |  | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
| BOXES |  |  |  |  | 3 | EA | 112.493 | 337.479
| LABOR | 12 | HRS | 64 | 768
| GAS PIPING & FITTINGS |  |  |  | 0 | 1 | LOT | 250 | 250
| TRIM LABOR | 4 | HRS | 64 | 256
| SUPERVISION/COORDINATION | 2 | HRS | 85 | 170
| Subtotals |  |  |  | 1194 |  |  |  | 587.479 |  | 0
| OH & Profit |  |  | 15% | 179.1 |  |  | 15% | 88.1219 | 15% | 0
| Subtotal |  |  |  | 1373.1 |  |  |  | 675.6009 |  | 0
TOTAL
2048.7009
INSTALL HEAT TRACE ROOFTOP SINK
INSTALL ADDED GAS BOXES ON ROOF PER RFI-065.1