## COR
Change Order Request
Exxel Pacific
4220 Aurora Avenue N.
Seattle, WA 98103
Attn:
Re: | The Cora - Change Order Request #01 - Dog Wash Area Faucet & Drain
|  | Labor |  |  |  | Material/Equipment |  |  |  | Sub Tier
Description |  | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
FD |  |  |  |  | 0 | 1 | ea | 150 | 150 |  | 0
Wall hung faucet |  |  | HRS | 60.5 | 0 | 1 | ea | 400 | 400 |  | 0
RI Mat |  |  |  |  | 0 | 1 | LS | 200 | 200 |  | 0
Underground RI Labor |  | 4 | HRS | 60 | 240 |  |  |  | 0 |  | 0
Topout Labor |  | 8 | HRS | 60 | 480 |  |  |  | 0 |  | 0
Labor Adder |  | 1 | ea | 370 | 370 |  |  |  | 0 |  | 0
Permit |  |  | HRS | 60.5 | 0 | 1 | ea | 10 | 10 |  | 0
|  |  | HRS | 80 | 0 |  |  |  | 0 |  | 0
| Subtotals |  |  |  | 1090 |  |  |  | 760 |  | 0
| OH & Profit |  |  | 15% | 163.5 |  |  | 15% | 114 | 0% | 0
| Subtotal |  |  |  | 1253.5 |  |  |  | 874 |  | 0
TOTAL
2127.5
Sincerely,
Richard Donelson
Project Manager / Estimator
richd@owpllc.net
425-591-4296 cell