## Sheet1
Subject | Amount | Date Sent | Notes | CO Received | CO # | Approval to proceed received | Applied to Job ticket? | Applied to plans? | Applied to PO's?
Cora Apartments - COR #12r1 Common Area Sink & Icemaker Pump | 1215 | 2017-04-25 | Revised per RFI-112.1 | 2017-08-08 | 6
Raise trench drains on 1st Ave | 209 | 2017-07-05 | This is cancelled and wil be included in COR-11r1 for Parsonage, due to budget problems at Cora.
Cora Apartments - COR #13 Trench Drain Reinstall | 2101 | 2017-06-08 | This is cancelled and wil be included in COR-11r1 for Parsonage, due to budget problems at Cora.
Gas Piping for Rootop Fireplace | 1268 | 2017-06-07 | Email. UPDATE: This is cancelled and will be included in CORr1 for Parsonage, due to budget problems on Cora.
Dog wash faucet & drain | 2127 | 2016-03-03 | Email from Mike. UPDATE: This is cancelled and will be included in CORr1 for Parsonage, due to budget problems on Cora.
clean out sump pits | deleted |  | deleted
RFI-065.1 Added Gas Outlet boxes | 2050 | 2017-02-09 | Email titled Cora Apartments - RFI #065.1 - BBQ & Fire Pit at Rooftop Deck - RESPONSE | 2017-03-08 | 4 | yes | Yes | Yes
Rooftop Sink | 1951 | 2017-01-24 | email titled Cora - Rooftop Sink | 2017-03-08 | 4 | yes | Yes | Yes
Heat Trace at Rooftop Sink | 1620 | 2017-01-24 | email titled Cora - Rooftop Sink | 2017-03-08 | 4 | yes | Yes | Yes
Cora Apartments - COR #03r1 – ASI-002 Activity Room Revisions | 2140 | 2016-11-16 |  | 2017-03-08 | 4 | yes | Yes | Yes
Bottle Filler in Fitness Room |  |  | See emails for options - CANCELLED
Cora Apartments - COR #07 Exterior Trench Drains on 1st Ave | 7881 | 2017-01-27 |  | 2017-01-31 | 3 | 2017-01-31 | 2017-01-31 | 2017-01-31
COR #04 RFI-055 Trench Drain at Garage Entrances | 1109 | 2016-12-03 |  | 2017-01-31 | 2 | Yes | 2017-01-31 | Yes
COR #05 RFI-049 Added Drain at Planter | 1924 | 2016-12-03 |  | 2017-01-31 | 2 | Yes | 2017-01-31 | Yes
Cora Apartments - COR #06 RFI-063 Wall Hung Lavs in Common Baths | 1357 | 2017-01-05 |  | 2017-01-31 | 2 | Yes | 2017-01-31 | 2017-01-31
We will need to install an adaptor on our wash machine boxes for condensate line connections | 700 | 2016-08-10 | Email from Mike | 2016-11-18 | 1 |  | Yes | Yes | Jeff
Add sink & faucet in amenity lounge | 1800 | 2016-10-31 | Email from RD - CANCELLED, SEE ASI-002 | CANCELLED | CANCELLED
Cora Apartments - COR #02 RFI-001 Added Foundation Drainage | 4700 | 2016-03-30 | Email from Mike - CANCELLED | CANCELLED | CANCELLED
CHANGE TRENCH DRAINS TO AREA DRAINS | 2854 | 2016-11-28 | EMAIL FROM RD - CANCELLED
Fire rated valve boxes | 8550 | 2017-10-26 | CANCELLED
Cora Apartments - COR #09 Install Meter Jumper on Cold Side | 607 | 2017-02-20 |  | 2017-03-08 | 4 | Yes | Yes | na | na
Cora Apartments - COR #10 Gas Permit for Temp Heat | 650 | 2017-02-20 |  | 2017-03-08 | 4 | Yes | NA | NA | NA
Cora Apartments - COR #11 Lav Sink Change | -1971 | 2017-03-22 |  | 2017-04-13 | 5 | Yes | Yes | Yes | Yes
NOTE TO SELF: WE WERE DOUBLE PAYED FOR cor #13. WE GOT PAID FOR IT THROUGH PARSONAGE AND CORA.

## Sheet2
Subject | Amount | Date Sent | Notes
Upgrade Fire Caulking | 1955 | 2015-01-07
RFI-314 Dog Turf Drains | 2873 | 2015-01-09
ASI-019 South Building | 11299 | 2015-01-16
Hose bibs for pet patches | 5106 | 2015-01-20
ASI-024.5 Gas Main Relocation | 1981 | 2015-02-23
ASI-024 Overtime - Joe Barnhart | 4232 | 2015-03-02
Credit for Sterling Tubs @ 206, 301, 305, 311, 317, 319, 320, 321 | -3795 | 2015-03-02
RFI-464 Wall Changes | 494 | 2015-03-06
Temp Gas Hookups | 1495 | 2015-03-16
Common Area Gas Range Credit | -363 | 2015-03-16
ASI-024 Overtime - Complete | 8920 | 2015-03-17
South Building Water Management | 1680 | 2015-03-17
Remove Pipe for Mason | 492 | 2015-03-18
North Building Shower Drains | 2022 | 2015-03-25
RFI-484 - Added Roof Drain S. Building | 1323 | 2015-03-30
J&S Masonry Backcharges | -624 | 2015-04-07
Change to Cast Iron Piping in LW4-6 | 3674 | 2015-05-04
RFI-482 - Raise Drains | 2130 | 2015-04-28
Gas Meter Vent Pipe - Proceed T&M per JC 4/18/15 | 276 | 2015-05-11
RFI-491 - Possibly need to lower water mains due to dropped soffits | 1060 | 2015-05-11
ASI-033 Demo & Remove Gas Piping | 474 | 2015-06-09
Move Icemakers at all South Building Refers | TBD |  | T&M - Waiting on notice to proceed from Exxel
Costs/Credits to delete RL01 & RL02 bathrooms | TBD |  | ROM pricing given. Waiting on decision from Exxel.