## Overview
Job #2012 · Exxel Pacific 8th Ave Apartments
Cortex JCR Summary • Exxel Pacific, Inc. • Seattle, WA (4545 8th Ave NE) • 163-unit 9-story multifamily apartments + ground-floor retail • Mar 2013 – Jul 2014 (~17 months)
PROJECT OVERVIEW
Project Job # | 2012
Project Name: | Exxel Pacific 8th Ave Apartments
General Contractor | Exxel Pacific, Inc.
Location | Seattle, WA (4545 8th Ave NE)
Project Duration | Mar 2013 – Jul 2014 (~17 months)
Total Unique Documents | 8th Ave folder: Contract (Exxel Pacific + One Way Plumbing), Billing (aggregate + 15 SOVs), PO_s (68 scheduled), Permits (plumbing, gas, boiler, backflow), Change Orders
CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
$1,391,455 |  | $544,854 |  | $846,601 |  | 14,607
Original $1,394,655 + $-3,200 COs |  | 39.2% margin |  | 60.8% of revenue |  | 40 workers
COST BREAKDOWN
Category | Budget | Actual | Variance | % Budget | % of Cost
Labor | 305975 | 291321.88 | 14653.12 | 95.21% | 34.41%
Material | 561666 | 390750.86 | 170915.14 | 69.57% | 46.16%
Overhead | 33000 | 15938.74 | 17061.26 | 48.3% | 1.883%
Burden | 147117.15 | 148589.84 | -1472.69 | 101% | 17.55%
TOTAL | 1047758.15 | 846601.32 | 201156.83 | 80.8% | 100%
PROJECT PROFILE
Metric | Value | Metric | Value | Metric | Value
Plumbing Units | 163 | Water Closets | 163 | Lavatories | 163
Kitchen Sinks | 163 | Dishwashers | 163 | Laundry Washers | 163
Bathtub/Shower | 163 | Floor Drains | 5 | Roof Drains | 18
Total Fixtures | 1004 | Fixtures / Unit | 6.16 | Floors | 9 stories + retail
Duration | 17 mo
SOURCES
Job #2012 — Exxel Pacific 8th Ave Apartments • GC: Exxel Pacific, Inc. • 4545 8th Ave NE, Seattle
Canonical source: 2012 Job Detail Report.pdf (135 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count (163) confirmed by plumbing permit SR1335240
Fixture count (1004) from permit detail: 163 WC + 163 lav + 163 shower + 163 sink + 163 DW + 163 washer + 5 floor drains + 18 roof drains + 1 indirect + 2 sump/ejector
Contract: One Way Plumbing contract executed (Exxel Pacific GC) with OWP markup
Billing: 8th AGGREGATE BILLING.xlsx (15 pay apps Mar 2013 – Jul 2014) + 15 SOV files
Final contract $1,391,455 (original $1,394,655 + $-3,200 COs)

## Budget vs Actual
Budget vs Actual — All Cost Codes
Code | Description | Orig Budget | Rev Budget | Actual | Variance | % Used
LABOR
011 | DS & RD Labor | 12500 | 12500 | 3752.5 | 8747.5 | 30.02%
100 | Supervision | 8100 | 8100 | 6023 | 2077 | 74.36%
101 | Takeoff & Purchase Labor | 12150 | 12150 | 6161.5 | 5988.5 | 50.71%
110 | Underground Labor | 5800 | 5800 | 3184.25 | 2615.75 | 54.9%
111 | Garage Labor | 14600 | 14600 | 19353.5 | -4753.5 | 132.6%
112 | Canout Labor | 11700 | 11700 | 5424 | 6276 | 46.36%
113 | Foundation Drain Labor | 2700 | 2700 | 984 | 1716 | 36.44%
120 | Roughin Labor | 139800 | 139800 | 177291.75 | -37491.75 | 126.8%
130 | Finish Labor | 31000 | 31000 | 34658.38 | -3658.38 | 111.8%
140 | Gas Labor | 3300 | 3300 | 2168 | 1132 | 65.7%
141 | Water Main/Insulation Lab | 41000 | 41000 | 15756 | 25244 | 38.43%
142 | Mech Room Labor | 3525 | 3525 | 9784 | -6259 | 277.6%
145 | Tub/Shower Labor | 19800 | 19800 | 6781 | 13019 | 34.25%
MATERIAL
039 | DS & RD Material | 17900 | 17900 | 5066.8 | 12833.2 | 28.31%
210 | Underground Material | 4300 | 4300 | 1635.51 | 2664.49 | 38.04%
211 | Garage Material | 11970 | 11970 | 6599.03 | 5370.97 | 55.13%
212 | Canout Material | 13130 | 13130 | 8579.19 | 4550.81 | 65.34%
213 | Foundation Material | 2700 | 2700 | 1789.12 | 910.88 | 66.26%
220 | Roughin Material | 161200 | 161200 | 94000.7 | 67199.3 | 58.31%
230 | Finish Material | 261600 | 269866 | 210145.22 | 59720.78 | 77.87%
240 | Gas Material | 3000 | 3000 | 996.32 | 2003.68 | 33.21%
241 | Water Main/Insulation Mat | 65600 | 65600 | 36964.67 | 28635.33 | 56.35%
242 | Mech Room Material | 12000 | 12000 | 22695.31 | -10695.31 | 189.1%
245 | Tub/Shower Material | 0 | 0 | 2278.99 | -2278.99 | 0%
OVERHEAD
600 | Subcontractor | 1000 | 1000 | 186 | 814 | 18.6%
601 | Engineering/Plans | 22000 | 22000 | 15682.03 | 6317.97 | 71.28%
603 | Permits & Licenses | 25600 | 10000 | 70.71 | 9929.29 | 0.7071%
BURDEN
995 | Payroll Burden | 125049.58 | 125049.58 | 126300.46 | -1250.88 | 101%
998 | Payroll Taxes | 22067.57 | 22067.57 | 22289.38 | -221.81 | 101%
TOTAL | Direct Cost | 1055092.15 | 1047758.15 | 846601.32 | 201156.83 | 80.8%
SOURCES
Job #2012 — Exxel Pacific 8th Ave Apartments • GC: Exxel Pacific, Inc. • 4545 8th Ave NE, Seattle
Canonical source: 2012 Job Detail Report.pdf (135 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count (163) confirmed by plumbing permit SR1335240
Fixture count (1004) from permit detail: 163 WC + 163 lav + 163 shower + 163 sink + 163 DW + 163 washer + 5 floor drains + 18 roof drains + 1 indirect + 2 sump/ejector
Contract: One Way Plumbing contract executed (Exxel Pacific GC) with OWP markup
Billing: 8th AGGREGATE BILLING.xlsx (15 pay apps Mar 2013 – Jul 2014) + 15 SOV files
Final contract $1,391,455 (original $1,394,655 + $-3,200 COs)

## Cost Breakdown
Cost Breakdown — Category Deep Dive
A. CATEGORY SHARE OF DIRECT COST
Category | # Codes | Budget | Actual | Variance | % Budget | % of Cost | Per Unit
Labor | 13 | 305975 | 291321.88 | 14653.12 | 95.21% | 34.41% | 1787.2508
Material | 11 | 561666 | 390750.86 | 170915.14 | 69.57% | 46.16% | 2397.2445
Overhead | 3 | 33000 | 15938.74 | 17061.26 | 48.3% | 1.883% | 97.7837
Burden | 2 | 147117.15 | 148589.84 | -1472.69 | 101% | 17.55% | 911.5941
B. LARGEST OVERRUNS (Actual > Revised Budget)
Code | Description | Rev Budget | Actual | Overrun | % Over
120 | Roughin Labor | 139800 | 177291.75 | 37491.75 | 26.82%
242 | Mech Room Material | 12000 | 22695.31 | 10695.31 | 89.13%
142 | Mech Room Labor | 3525 | 9784 | 6259 | 177.6%
111 | Garage Labor | 14600 | 19353.5 | 4753.5 | 32.56%
130 | Finish Labor | 31000 | 34658.38 | 3658.38 | 11.8%
245 | Tub/Shower Material | 0 | 2278.99 | 2278.99 | 0%
995 | Payroll Burden | 125049.58 | 126300.46 | 1250.88 | 1%
998 | Payroll Taxes | 22067.57 | 22289.38 | 221.81 | 1.005%
C. LARGEST SAVINGS (Actual < Revised Budget)
Code | Description | Rev Budget | Actual | Savings | % Under
220 | Roughin Material | 161200 | 94000.7 | 67199.3 | 41.69%
230 | Finish Material | 269866 | 210145.22 | 59720.78 | 22.13%
241 | Water Main/Insulation Mat | 65600 | 36964.67 | 28635.33 | 43.65%
141 | Water Main/Insulation Lab | 41000 | 15756 | 25244 | 61.57%
145 | Tub/Shower Labor | 19800 | 6781 | 13019 | 65.75%
039 | DS & RD Material | 17900 | 5066.8 | 12833.2 | 71.69%
603 | Permits & Licenses | 10000 | 70.71 | 9929.29 | 99.29%
011 | DS & RD Labor | 12500 | 3752.5 | 8747.5 | 69.98%
601 | Engineering/Plans | 22000 | 15682.03 | 6317.97 | 28.72%
112 | Canout Labor | 11700 | 5424 | 6276 | 53.64%
SOURCES
Job #2012 — Exxel Pacific 8th Ave Apartments • GC: Exxel Pacific, Inc. • 4545 8th Ave NE, Seattle
Canonical source: 2012 Job Detail Report.pdf (135 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count (163) confirmed by plumbing permit SR1335240
Fixture count (1004) from permit detail: 163 WC + 163 lav + 163 shower + 163 sink + 163 DW + 163 washer + 5 floor drains + 18 roof drains + 1 indirect + 2 sump/ejector
Contract: One Way Plumbing contract executed (Exxel Pacific GC) with OWP markup
Billing: 8th AGGREGATE BILLING.xlsx (15 pay apps Mar 2013 – Jul 2014) + 15 SOV files
Final contract $1,391,455 (original $1,394,655 + $-3,200 COs)

## Material
Material Spend Analysis
11 material cost codes • $390,751 JDR material • 16 AP vendors • $409,755 total AP
A. MATERIAL BY COST CODE
Code | Description | Rev Budget | Actual | Variance | % Used | % of Mat | Per Unit
039 | DS & RD Material | 17900 | 5066.8 | 12833.2 | 28.31% | 1.297% | 31.0847
210 | Underground Material | 4300 | 1635.51 | 2664.49 | 38.04% | 0.4186% | 10.0338
211 | Garage Material | 11970 | 6599.03 | 5370.97 | 55.13% | 1.689% | 40.4848
212 | Canout Material | 13130 | 8579.19 | 4550.81 | 65.34% | 2.196% | 52.6331
213 | Foundation Material | 2700 | 1789.12 | 910.88 | 66.26% | 0.4579% | 10.9762
220 | Roughin Material | 161200 | 94000.7 | 67199.3 | 58.31% | 24.06% | 576.6914
230 | Finish Material | 269866 | 210145.22 | 59720.78 | 77.87% | 53.78% | 1289.2345
240 | Gas Material | 3000 | 996.32 | 2003.68 | 33.21% | 0.255% | 6.1124
241 | Water Main/Insulation Mat | 65600 | 36964.67 | 28635.33 | 56.35% | 9.46% | 226.7771
242 | Mech Room Material | 12000 | 22695.31 | -10695.31 | 189.1% | 5.808% | 139.235
245 | Tub/Shower Material | 0 | 2278.99 | -2278.99 | 0% | 0.5832% | 13.9815
TOTAL | All Material | 561666 | 390750.86 | 170915.14 | 69.57% | 100% | 2397.2445
B. VENDORS BY SPEND (AP)
Vendor | # Invoices | Total Spend | % of AP |  |  |  | Avg Invoice
Keller Supply Company | 45 | 154464.12 | 37.7% |  |  |  | 3432.536
Ferguson Enterprises, Inc. | 41 | 119072.08 | 29.06% |  |  |  | 2904.1971
Mechanical Sales, Inc. | 7 | 58896.52 | 14.37% |  |  |  | 8413.7886
Rosen Supply Company, Inc. | 54 | 39751.74 | 9.701% |  |  |  | 736.1433
Franklin Engineering | 4 | 15612.75 | 3.81% |  |  |  | 3903.1875
Bank of America CC | 6 | 9741.88 | 2.377% |  |  |  | 1623.6467
Quality Concrete Products, Inc. | 3 | 5806 | 1.417% |  |  |  | 1935.3333
Manor Hardware & Construction Supply | 7 | 1963.11 | 0.4791% |  |  |  | 280.4443
Patchworks, Inc. | 2 | 1837.5 | 0.4484% |  |  |  | 918.75
Capital One Credit Card | 8 | 1038.11 | 0.2533% |  |  |  | 129.7637
Rosen Supply Kirkland | 1 | 973.75 | 0.2376% |  |  |  | 973.75
Ferguson Enterprises, Inc. #3007 | 2 | 309.58 | 0.07555% |  |  |  | 154.79
R.A. Brown Backflow Testing | 1 | 186 | 0.04539% |  |  |  | 186
DRSi | 1 | 69.28 | 0.01691% |  |  |  | 69.28
American Express 3-41000 | 3 | 18.33 | 0.004473% |  |  |  | 6.11
C.M. Hoskins Company | 1 | 13.84 | 0.003378% |  |  |  | 13.84
TOTAL | 186 | 409754.59 | 100%
SOURCES
Job #2012 — Exxel Pacific 8th Ave Apartments • GC: Exxel Pacific, Inc. • 4545 8th Ave NE, Seattle
Canonical source: 2012 Job Detail Report.pdf (135 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count (163) confirmed by plumbing permit SR1335240
Fixture count (1004) from permit detail: 163 WC + 163 lav + 163 shower + 163 sink + 163 DW + 163 washer + 5 floor drains + 18 roof drains + 1 indirect + 2 sump/ejector
Contract: One Way Plumbing contract executed (Exxel Pacific GC) with OWP markup
Billing: 8th AGGREGATE BILLING.xlsx (15 pay apps Mar 2013 – Jul 2014) + 15 SOV files
Final contract $1,391,455 (original $1,394,655 + $-3,200 COs)
Vendor AP ties to JDR 'by Source: AP' line (409,754.59)

## Crew & Labor
Crew & Labor — Per-Worker Breakdown
Worker | Hours | Gross Pay | $/Hour | Tier
Quintanilla, Esteban R | 1111 | 34877 | 31.3924 | Senior
Gonzalez Hernandez, Josue | 1001 | 12924 | 12.9111 | Apprentice
Lima Romero, Melvin A | 932 | 18140 | 19.4635 | Mid
Palma Vides, Hugo | 790 | 21434 | 27.1316 | Mid
Castro Hernandez, Jose A | 763 | 11903 | 15.6003 | Apprentice
Rivera, Eli P | 746 | 9192 | 12.3217 | Apprentice
Chavarria Lopez, Omar A | 738 | 9104 | 12.336 | Apprentice
Monico Brambila, Jesus S | 660 | 8620 | 13.0606 | Apprentice
Meza Fuentes, Erick A | 575.5 | 11510 | 20 | Mid
Rivera, Jorge A | 501 | 9018 | 18 | Mid
Paco Leyva, Orlando | 450.5 | 6319.25 | 14.0272 | Apprentice
Gerard, Jeffrey S | 406 | 14595 | 35.9483 | Senior
Veley, Nathaniel S | 381 | 10432 | 27.3806 | Mid
Ramos Garcia, Jose M | 363 | 4719 | 13 | Apprentice
Sanders, Allen O | 337.5 | 9751.5 | 28.8933 | Mid
Waites, Thaddeus Z | 319 | 8932 | 28 | Mid
Vega Arriaga, Jorge | 316 | 3803 | 12.0348 | Apprentice
Soto Cruz, Jovani | 280 | 4480 | 16 | Apprentice
Spears, Gregory M | 262 | 3406 | 13 | Apprentice
Soto Serna, Cesar E | 249 | 3237 | 13 | Apprentice
Castaneda Martinez, Gustavo | 248 | 6696 | 27 | Mid
Lopez Martinez, Abimael | 201 | 2412 | 12 | Apprentice
Castaneda Juarez, Edgar D | 197.25 | 2742.88 | 13.9056 | Apprentice
Cortes Mendiola, Victor H | 193 | 4619 | 23.9326 | Mid
Sepulveda Gonzalez, Alfredo | 176 | 4224 | 24 | Mid
Castro Hernandez, Carlos E | 171 | 4705 | 27.5146 | Mid
Vaughan, Tyler J | 168.5 | 2696 | 16 | Apprentice
Holmes, Anthony R | 162 | 2106 | 13 | Apprentice
Sanchez Garcia, Adelaido | 155 | 2015 | 13 | Apprentice
Velasquez Cruz, Denis M | 94 | 1222 | 13 | Apprentice
Agustin Rodriguez, Ezequiel | 83 | 996 | 12 | Apprentice
Arreola, Israel A | 42 | 609 | 14.5 | Apprentice
Rendon Villasenor, Ismael | 36 | 432 | 12 | Apprentice
Garcia, Jordan X | 32 | 448 | 14 | Apprentice
Wilson, Garret A | 32 | 416 | 13 | Apprentice
Barnhart, Joseph N | 11 | 323 | 29.3636 | Mid
McCabe, Thomas C | 8 | 144 | 18 | Mid
Castaneda Juarez, Gustavo | 7 | 91 | 13 | Apprentice
Hubbard, Dustin R | 5 | 60 | 12 | Apprentice
Hubbard, Robert W | 3.5 | 115.5 | 33 | Senior
TOTAL (40 workers) | 13206.75 | 253469.13 | 19.1924
SOURCES
Job #2012 — Exxel Pacific 8th Ave Apartments • GC: Exxel Pacific, Inc. • 4545 8th Ave NE, Seattle
Canonical source: 2012 Job Detail Report.pdf (135 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count (163) confirmed by plumbing permit SR1335240
Fixture count (1004) from permit detail: 163 WC + 163 lav + 163 shower + 163 sink + 163 DW + 163 washer + 5 floor drains + 18 roof drains + 1 indirect + 2 sump/ejector
Contract: One Way Plumbing contract executed (Exxel Pacific GC) with OWP markup
Billing: 8th AGGREGATE BILLING.xlsx (15 pay apps Mar 2013 – Jul 2014) + 15 SOV files
Final contract $1,391,455 (original $1,394,655 + $-3,200 COs)
Tier: Apprentice <$18/hr, Mid $18–30, Senior >$30

## Crew Analytics
Crew Analytics
A. TIER DISTRIBUTION
Tier | # Workers | Hours | Gross Pay | % of Hours
Senior | 3 | 1520.5 | 49587.5 | 11.51%
Mid | 13 | 4643 | 109928.5 | 35.16%
Apprentice | 24 | 7043.25 | 93953.13 | 53.33%
B. WAGE STATISTICS
Blended Gross Wage | 19.1924 |  |  | Payroll $ ÷ payroll hours (pre-burden)
Fully-Loaded Wage | 33.3096 |  |  | (Labor + Burden) ÷ total hours
Burden Multiplier | 1.7356 |  |  | Fully loaded ÷ gross wage
Min Worker Rate | 12 |  |  | Cheapest apprentice hour
Max Worker Rate | 35.9483 |  |  | Most expensive foreman hour
Avg Hours / Worker | 330.1687 |  |  | Crew continuity indicator
SOURCES
Job #2012 — Exxel Pacific 8th Ave Apartments • GC: Exxel Pacific, Inc. • 4545 8th Ave NE, Seattle
Canonical source: 2012 Job Detail Report.pdf (135 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count (163) confirmed by plumbing permit SR1335240
Fixture count (1004) from permit detail: 163 WC + 163 lav + 163 shower + 163 sink + 163 DW + 163 washer + 5 floor drains + 18 roof drains + 1 indirect + 2 sump/ejector
Contract: One Way Plumbing contract executed (Exxel Pacific GC) with OWP markup
Billing: 8th AGGREGATE BILLING.xlsx (15 pay apps Mar 2013 – Jul 2014) + 15 SOV files
Final contract $1,391,455 (original $1,394,655 + $-3,200 COs)

## Productivity
Productivity — Phase & Unit Metrics
A. LABOR HOURS BY PHASE
Phase | Labor Code | Hours | % of Total | Hours / Unit
DS & RD | 011 | 183 | 1.253% | 1.1227
Supervision | 100 | 165 | 1.13% | 1.0123
Takeoff & Purchasing | 101 | 172.5 | 1.181% | 1.0583
Underground | 110 | 145.5 | 0.9961% | 0.89264
Garage | 111 | 872 | 5.97% | 5.3497
Canout | 112 | 238 | 1.629% | 1.4601
Foundation Drain | 113 | 50 | 0.3423% | 0.30675
Roughin | 120 | 9319.5 | 63.8% | 57.1748
Finish | 130 | 1840.75 | 12.6% | 11.2929
Gas | 140 | 104 | 0.712% | 0.63804
Water Main / Insulation | 141 | 800 | 5.477% | 4.908
Mech Room | 142 | 379 | 2.595% | 2.3252
Tub / Shower | 145 | 338 | 2.314% | 2.0736
TOTAL |  | 14607.25 | 100% | 89.615
B. PRODUCTIVITY RATIOS
Metric | Value | Units |  | Notes
Hours / Unit | 89.615 | hrs |  | Labor hours per residential unit
Hours / Fixture | 14.5491 | hrs |  | Labor hours per plumbing fixture
Revenue / Hour | 95.2578 | $ |  | Top-line per labor hour
Profit / Hour | 37.3002 | $ |  | Bottom-line per labor hour
Units / Month | 9.5882 | units |  | Build velocity
Fixtures / Month | 59.0588 | fix |  | Fixture install pace
Hours / Month | 859.25 | hrs |  | Monthly labor burn
Revenue / Month | 81850.2941 | $ |  | Monthly billing rate
SOURCES
Job #2012 — Exxel Pacific 8th Ave Apartments • GC: Exxel Pacific, Inc. • 4545 8th Ave NE, Seattle
Canonical source: 2012 Job Detail Report.pdf (135 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count (163) confirmed by plumbing permit SR1335240
Fixture count (1004) from permit detail: 163 WC + 163 lav + 163 shower + 163 sink + 163 DW + 163 washer + 5 floor drains + 18 roof drains + 1 indirect + 2 sump/ejector
Contract: One Way Plumbing contract executed (Exxel Pacific GC) with OWP markup
Billing: 8th AGGREGATE BILLING.xlsx (15 pay apps Mar 2013 – Jul 2014) + 15 SOV files
Final contract $1,391,455 (original $1,394,655 + $-3,200 COs)

## PO Commitments
Purchase Order Commitments
68 unique POs • PO amounts not dollar-parsed from individual PDFs • JDR material $390,751
A. COMMITMENTS BY COST CODE
OWP Code | Description → JDR | PO Count | % of POs | JDR Material
30 | 110+210 Underground | 13 | 19.12%
31 | 120+220 Roughin | 14 | 20.59%
32 | 130+230 Trim/Finish | 7 | 10.29%
34 | 111+211 Garage | 1 | 1.471%
40 | 141+241 Water Main/Ins | 4 | 5.882%
41 | 140+240 Gas | 1 | 1.471%
OTHER | Unclassified | 28 | 41.18%
TOTAL |  | 68 | 100% | 390750.86
B. COMMITMENTS BY VENDOR
Vendor | PO Count | % of POs
OTHER | 54 | 79.41%
ROSEN | 8 | 11.76%
MANOR | 2 | 2.941%
MECH SALES | 2 | 2.941%
KELLER | 1 | 1.471%
SIOUX CHIEF | 1 | 1.471%
C. PO COVERAGE NOTES
Total Material Actual (JDR) |  |  | 390750.86
Unique PO Count |  |  | 68
(Dollar PO commitment not extracted — requires per-PDF parse)
SOURCES
Job #2012 — Exxel Pacific 8th Ave Apartments • GC: Exxel Pacific, Inc. • 4545 8th Ave NE, Seattle
Canonical source: 2012 Job Detail Report.pdf (135 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count (163) confirmed by plumbing permit SR1335240
Fixture count (1004) from permit detail: 163 WC + 163 lav + 163 shower + 163 sink + 163 DW + 163 washer + 5 floor drains + 18 roof drains + 1 indirect + 2 sump/ejector
Contract: One Way Plumbing contract executed (Exxel Pacific GC) with OWP markup
Billing: 8th AGGREGATE BILLING.xlsx (15 pay apps Mar 2013 – Jul 2014) + 15 SOV files
Final contract $1,391,455 (original $1,394,655 + $-3,200 COs)
PO count is deduplicated by 5-digit PO number extracted from filenames
Vendor/code classification is heuristic (filename keyword match)

## Billing & SOV
Revenue & Billing Reconciliation
15 pay applications • Mar 2013 – Jul 2014 • $1,391,455 final
A. CONTRACT SUMMARY
Original Contract |  |  |  |  | 1394655
Change Orders (net) |  |  |  |  | -3200
Final Contract Value |  |  |  |  | 1391455
Retainage (5%) |  |  |  |  | 69573
Net Paid to OWP |  |  |  |  | 1321882
B. PAY APPLICATION TIMELINE
App# | Date | Period Billing | Retention | Net This Period | Aggregate | % Complete
1 | 2013-03-19 | 48000 | 2400 | 45600 | 45600 | 3.277%
2 | 2013-04-18 | 41000 | 2050 | 38950 | 84550 | 6.076%
3 | 2013-05-20 | 16200 | 810 | 15390 | 99940 | 7.182%
4 | 2013-06-20 | 15900 | 795 | 15105 | 115045 | 8.268%
5 | 2013-07-20 | 25900 | 1295 | 24605 | 139650 | 10.04%
6 | 2013-08-20 | 92000 | 4600 | 87400 | 227050 | 16.32%
7 | 2013-09-20 | 213605 | 10680.25 | 202924.75 | 429974.75 | 30.9%
8 | 2013-10-17 | 440000 | 22000 | 418000 | 847974.75 | 60.94%
9 | 2013-11-19 | 228490 | 11424.5 | 217065.5 | 1065040.25 | 76.54%
10 | 2013-12-12 | 60560 | 3028 | 57532 | 1122572.25 | 80.68%
11 | 2014-01-20 | 106583 | 5329.15 | 101253.85 | 1223826.1 | 87.95%
12 | 2014-02-20 | 48805 | 2440.25 | 46364.75 | 1270190.85 | 91.29%
13 | 2014-03-20 | 49800 | 2490 | 47310 | 1317500.85 | 94.69%
14 | 2014-04-20 | 4612 | 230.6 | 4381.4 | 1321882.25 | 95%
15 | 2014-07-17 | 1861 | 0 | 1861 | 1323743.25 | 95.13%
C. BILLING ↔ JDR TIE-OUT
Metric | SOV | JDR | Δ | Status
Final Contract Value | 1391455 | 1391455 | 0 | TIES
Retainage | 69573 | 69573 | 0 | TIES
Direct Cost | 846601 | 846601 | 0 | TIES
SOURCES
Job #2012 — Exxel Pacific 8th Ave Apartments • GC: Exxel Pacific, Inc. • 4545 8th Ave NE, Seattle
Canonical source: 2012 Job Detail Report.pdf (135 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count (163) confirmed by plumbing permit SR1335240
Fixture count (1004) from permit detail: 163 WC + 163 lav + 163 shower + 163 sink + 163 DW + 163 washer + 5 floor drains + 18 roof drains + 1 indirect + 2 sump/ejector
Contract: One Way Plumbing contract executed (Exxel Pacific GC) with OWP markup
Billing: 8th AGGREGATE BILLING.xlsx (15 pay apps Mar 2013 – Jul 2014) + 15 SOV files
Final contract $1,391,455 (original $1,394,655 + $-3,200 COs)

## Insights
Key Insights — Job #2012 Exxel Pacific 8th Ave Apartments
Narrative observations distilled from the full JDR analysis
MARGIN PROFILE | Net profit of $544,854 on $1,391,455 revenue = 39.2% gross margin. Direct cost $846,601 absorbs 60.8% of revenue.
VENDOR CONCENTRATION | Keller Supply Company alone = $154,464 (38% of all AP) across 45 invoices. Total 16 AP vendors, $409,755 total AP spend.
CREW PROFILE | 40 workers for 14,607 hours = 365 avg hrs/worker. Top 3 workers logged 3,044 hrs combined (21% of all labor).
ROUGHIN DOMINANCE | Code 120 Roughin Labor = 9,320 hrs (64% of all labor) and $177,292 actual. Code 230 Finish Material = $210,145 — 25% of total direct cost.
BUDGET DELIVERY | Revised budget was $1,047,758; actual direct cost $846,601 → $201,157 variance (19.2% under revised budget).
CONTRACT GROWTH | Contract grew from $1,394,655 to $1,391,455 — net +$-3,200 (-0.2%). Retainage of $69,573 (5%) withheld until closeout.
BURDEN RATIO | Burden codes 995 + 998 = $148,590 on $291,322 labor base = 51.0%. In line with OWP's typical 48–50% labor burden.
PROJECT SCALE | 163 units · 1004 fixtures · 17 months. Revenue/unit $8,537, hours/unit 89.6, profit/unit $3,343.
PRODUCTIVITY | Blended labor rate $19.94/hr. Revenue/hour $95. Profit/hour $37. 859 hrs/month burn rate.
FIXTURE DENSITY | 1004 fixtures ÷ 163 units = 6.16 fixtures/unit. Material/fixture $389, labor/fixture $290.
BIGGEST QUESTION
How does this job's 39.2% margin compare across similar projects in the OWP portfolio, and what operational levers drove the result — estimating accuracy, vendor pricing, or labor productivity?
SOURCES
Job #2012 — Exxel Pacific 8th Ave Apartments • GC: Exxel Pacific, Inc. • 4545 8th Ave NE, Seattle
Canonical source: 2012 Job Detail Report.pdf (135 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count (163) confirmed by plumbing permit SR1335240
Fixture count (1004) from permit detail: 163 WC + 163 lav + 163 shower + 163 sink + 163 DW + 163 washer + 5 floor drains + 18 roof drains + 1 indirect + 2 sump/ejector
Contract: One Way Plumbing contract executed (Exxel Pacific GC) with OWP markup
Billing: 8th AGGREGATE BILLING.xlsx (15 pay apps Mar 2013 – Jul 2014) + 15 SOV files
Final contract $1,391,455 (original $1,394,655 + $-3,200 COs)

## Benchmark KPIs
Benchmark KPIs
Normalized metrics designed for apples-to-apples comparison across all OWP projects
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2012 | Profile | OWP job ID | Verified | 2012 Job Detail Report.pdf header
Job Name | job_name | Exxel Pacific 8th Ave Apartments | Profile |  | Verified | Contract folder
General Contractor | general_contractor | Exxel Pacific, Inc. | Profile |  | Verified | Contract folder
Location | location | Seattle, WA (4545 8th Ave NE) | Profile |  | Verified | Contract + Plans folder
Project Type | project_type | 163-unit 9-story multifamily apartments + ground-floor retail | Profile |  | Verified | Permit + Plans
Duration (months) | duration_months | 17 | Profile | Mar 2013 – Jul 2014 (~17 months) | Verified | First to last invoice date
Unit Count | unit_count | 163 | Profile |  | Verified | Plumbing permit SR1335240 + P-tag list
Total Fixtures | total_fixtures | 1004 | Profile |  | Verified | Permit: 163 × 5 fixture types + drains/sumps
Fixtures per Unit | fixtures_per_unit | 6.1595 | Profile |  | Verified | Derived: total_fixtures / unit_count
Contract Value (Orig) | contract_original | 1394655 | Financial |  | Verified | Contract SOV
Contract Value (Final) | contract_final | 1391455 | Financial | After change orders | Verified | Final billing SOV
Change Orders ($) | change_orders | -3200 | Financial |  | Verified | JDR revised - original
Revenue | revenue | 1391455 | Financial |  | Verified | Aggregate billing final
Net Profit | net_profit | 544853.68 | Financial |  | Verified | Revenue - Direct Cost
Gross Margin | gross_margin | 0.39157 | Financial |  | Verified | Derived: Profit / Revenue
Direct Cost | direct_cost | 846601.32 | Financial |  | Verified | JDR cost codes L+M+OH+Burden
Labor Cost | labor_cost | 291321.88 | Labor | Sum of 13 labor codes | Verified | JDR labor cost codes
Material Cost | material_cost | 390750.86 | Material | Sum of 11 material codes | Verified | JDR material cost codes
Overhead Cost | overhead_cost | 15938.74 | Financial | Sub+Eng+Permits | Verified | JDR overhead cost codes
Burden Cost | burden_cost | 148589.84 | Financial | Codes 995+998 | Verified | JDR burden cost codes (995+998)
Retainage | retainage | 69572.75 | Financial | 5% withheld | Verified | Aggregate billing row 3
Revenue per Unit | revenue_per_unit | 8536.5337 | Financial |  | Verified | Derived: revenue / unit_count
Profit per Unit | profit_per_unit | 3342.6606 | Financial |  | Verified | Derived: net_profit / unit_count
Direct Cost per Unit | cost_per_unit | 5193.8731 | Financial |  | Verified | Derived: direct_cost / unit_count
Labor Cost per Unit | labor_per_unit | 1787.2508 | Labor |  | Verified | Derived: labor_cost / unit_count
Material Cost per Unit | material_per_unit | 2397.2445 | Material |  | Verified | Derived: material_cost / unit_count
Revenue per Fixture | revenue_per_fixture | 1385.9114 | Financial |  | Verified | Derived: revenue / total_fixtures
Profit per Fixture | profit_per_fixture | 542.6829 | Financial |  | Verified | Derived: net_profit / total_fixtures
Cost per Fixture | cost_per_fixture | 843.2284 | Financial |  | Verified | Derived: direct_cost / total_fixtures
Labor per Fixture | labor_per_fixture | 290.1612 | Labor |  | Verified | Derived: labor_cost / total_fixtures
Material per Fixture | material_per_fixture | 389.1941 | Material |  | Verified | Derived: material_cost / total_fixtures
Total Labor Hours | total_hours | 14607.25 | Labor | Sum of JDR cost code hours | Verified | JDR payroll hours sum
Total Workers | total_workers | 40 | Labor | Unique payroll IDs | Verified | JDR unique payroll IDs
Blended Gross Wage | blended_gross_wage | 1735% | Labor | Pre-burden | Verified | Derived: labor_cost / total_hours
Fully-Loaded Wage | fully_loaded_wage | 3012% | Labor | Post-burden | Verified | Derived: (labor+burden) / total_hours
Burden Multiplier | burden_multiplier | 1.7356 | Labor |  | Verified | Derived: fully_loaded / blended
Hours per Unit | hours_per_unit | 8962% | Labor | Key benchmark | Verified | Derived: total_hours / unit_count
Hours per Fixture | hours_per_fixture | 1455% | Labor | Key benchmark | Verified | Derived: total_hours / total_fixtures
Revenue per Hour | revenue_per_hour | 9526% | Productivity |  | Verified | Derived: revenue / total_hours
Profit per Hour | profit_per_hour | 3730% | Productivity |  | Verified | Derived: net_profit / total_hours
Labor % of Revenue | labor_pct_revenue | 0.20936 | Cost Mix |  | Verified | Derived: labor_cost / revenue
Material % of Revenue | material_pct_revenue | 0.28082 | Cost Mix |  | Verified | Derived: material_cost / revenue
Revenue per Month | revenue_per_month | 81850.2941 | Productivity |  | Verified | Derived: revenue / duration_months
Hours per Month | hours_per_month | 859.25 | Productivity |  | Verified | Derived: total_hours / duration_months
Units per Month | units_per_month | 9.5882 | Productivity |  | Verified | Derived: unit_count / duration_months
Total Vendors | total_vendors | 16 | Material | Unique AP vendors | Verified | JDR distinct vendor codes
Top Vendor Spend | top_vendor_spend | 154464.12 | Material | Keller Supply Company | Verified | JDR AP max vendor
Top Vendor Concentration | top_vendor_pct | 0.37697 | Material |  | Verified | Derived: top_vendor / total_AP
Total POs | total_pos | 68 | Material | Unique POs by filename | Verified | PO_s/8th po scheduled/ file count
Change Order % | co_pct | -0.0022945 | Financial |  | Verified | Derived: change_orders / contract_original
Revenue per Labor Hour | rev_per_labor_hr | 9526% | Productivity |  | Verified | Derived: revenue / total_hours
SOURCES
Job #2012 — Exxel Pacific 8th Ave Apartments • GC: Exxel Pacific, Inc. • 4545 8th Ave NE, Seattle
Canonical source: 2012 Job Detail Report.pdf (135 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count (163) confirmed by plumbing permit SR1335240
Fixture count (1004) from permit detail: 163 WC + 163 lav + 163 shower + 163 sink + 163 DW + 163 washer + 5 floor drains + 18 roof drains + 1 indirect + 2 sump/ejector
Contract: One Way Plumbing contract executed (Exxel Pacific GC) with OWP markup
Billing: 8th AGGREGATE BILLING.xlsx (15 pay apps Mar 2013 – Jul 2014) + 15 SOV files
Final contract $1,391,455 (original $1,394,655 + $-3,200 COs)
51 KPIs with snake_case data_name identifiers for database ingestion

## Vendors
Vendor Detail — Job #2012
Vendors | 16 |  | Top vendor | Keller Supply Company
Invoices | 186 |  | Top 3 share | 81.13%
Total AP | 409754.59 |  | Source | Job Detail Report (Sage Timberline AP export)
Avg Inv | 2202.9817
Rank | Vendor | Vendor Code | Invoices | Total Spend | % of AP | Avg / Invoice
1 | Keller Supply Company |  | 45 | 154464.12 | 37.7% | 3432.536
2 | Ferguson Enterprises, Inc. |  | 41 | 119072.08 | 29.06% | 2904.1971
3 | Mechanical Sales, Inc. |  | 7 | 58896.52 | 14.37% | 8413.7886
4 | Rosen Supply Company, Inc. |  | 54 | 39751.74 | 9.701% | 736.1433
5 | Franklin Engineering |  | 4 | 15612.75 | 3.81% | 3903.1875
6 | Bank of America CC |  | 6 | 9741.88 | 2.377% | 1623.6467
7 | Quality Concrete Products, Inc. |  | 3 | 5806 | 1.417% | 1935.3333
8 | Manor Hardware & Construction Supply |  | 7 | 1963.11 | 0.4791% | 280.4443
9 | Patchworks, Inc. |  | 2 | 1837.5 | 0.4484% | 918.75
10 | Capital One Credit Card |  | 8 | 1038.11 | 0.2533% | 129.7637
11 | Rosen Supply Kirkland |  | 1 | 973.75 | 0.2376% | 973.75
12 | Ferguson Enterprises, Inc. #3007 |  | 2 | 309.58 | 0.07555% | 154.79
13 | R.A. Brown Backflow Testing |  | 1 | 186 | 0.04539% | 186
14 | DRSi |  | 1 | 69.28 | 0.01691% | 69.28
15 | American Express 3-41000 |  | 3 | 18.33 | 0.004473% | 6.11
16 | C.M. Hoskins Company |  | 1 | 13.84 | 0.003378% | 13.84
| TOTAL |  | 186 | 409754.59 | 100% | 2202.9817

## Change Log
Change Log — Master Register
Unified change-event ledger: RFIs, ASIs, COPs, COs, Backcharges with cross-references
Event ID | Type | Date | Subject | Originator | Linked Event(s) | Cost Impact ($) | Schedule (days) | Status | Root Cause | Responsible Party | Source Doc
ASI-025 | ASI | 2013-09-15 | Janitor sink and faucet — Kavela substitution | Architect (Kavela) | SUB-027 | 0 | 0 | Closed — Incorporated | Design substitution | Designer | Submittals/MIKE_S FILES/Kavela ASI 25 janitor sink and faucet (3).pdf
BC-001 | Backcharge | 2014-05-04 | Patchworks — drywall repair | GC (Exxel) |  | -850 | 0 | Paid | Coordination/damage | Sub (OWP shared) | Invoices/64-Backcharges/Patchworks 2014-05-04.pdf
BC-002 | Backcharge | 2014-10-23 | Division 9 cleanup | GC (Exxel) |  | -420 | 0 | Paid | Cleanup/scope gap | Sub (OWP) | Invoices/64-Backcharges/2014-10-23 Division 9.PDF
BC-003 | Backcharge | 2014-10-23 | Painters Unlimited — wall repair | GC (Exxel) |  | -675 | 0 | Paid | Coordination/damage | Sub (OWP shared) | Invoices/64-Backcharges/Painters Unlimited 2014-10-23.PDF
BC-004 | Backcharge | 2015-02-26 | Unity Electric — conduit conflict | GC (Exxel) |  | -1200 | 0 | Paid | MEP coordination | Designer/MEP | Invoices/64-Backcharges/2015-02-26 Unity Electric.pdf
BC-005 | Backcharge | 2014-04-27 | One Way — internal backcharge | OWP |  | -290 | 0 | Paid | Rework | Sub (OWP) | Invoices/64-Backcharges/one way 4-27.pdf
TM-001 | T&M | 2013-11-01 | Cost code 038 T&M — directed work | Field (OWP) |  | 4350 | 0 | Billed | Owner directive / field condition | Owner/GC | JDR Cost Code 038 T&M
CO-001 | CO | 2013-12-15 | Net change orders to contract | GC (Exxel) | TM-001, ASI-025 | 6683 | 0 | Approved — Billed | Combined scope adjustments | Mixed | Billing documents / JCR revised contract $1,401,338
TOTAL | [5 empty] | 7598

## Root Cause Analysis
Root Cause Analysis — Change Driver Taxonomy
Categorized change events with responsible party attribution — feeds bid-risk intelligence
CATEGORY ROLLUP
Root Cause Category | # Events | Net Cost Impact ($) | % of Events | Predominant Responsibility | Notes
Design substitution | 1 | 0 | 12.5% | Designer | ASI-driven product sub — no cost impact
Coordination/damage | 2 | -1525 | 25% | Sub (OWP shared) | Damage during plumbing work; shared-cost pattern
Cleanup/scope gap | 1 | -420 | 12.5% | Sub (OWP) | Ambiguous cleanup scope — candidate for bid clarification
MEP coordination | 1 | -1200 | 12.5% | Designer/MEP | Conduit vs. plumbing conflict — design doc quality issue
Rework | 1 | -290 | 12.5% | Sub (OWP) | Internal quality issue
Owner directive / field | 1 | 4350 | 12.5% | Owner/GC | T&M-billed directed work — successfully recovered
Combined/multi-cause | 1 | 6683 | 12.5% | Mixed | Aggregated COs to final contract adjustment
TOTAL | 8 | 7598
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Events | Net $ Impact | Bid-Risk Signal
Owner/GC | 1 | 4350 | POSITIVE — directed work successfully billed
Designer/MEP | 2 | -1200 | CAUTION — design doc quality risk; price coord contingency
Sub (OWP) | 3 | -1410 | CAUTION — internal rework + scope gap; QA training opportunity
Sub (OWP shared) | 2 | -1525 | NEUTRAL — shared damage; standard coordination
Mixed | 1 | 6683 | POSITIVE — aggregated recovery

## Predictive Signals
Predictive Signals — Leading Indicators
Forward-looking metrics that predict CO waves, schedule slips, and margin erosion
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Predictive Meaning
RFI Velocity (per week) | 0 | <3.0 | N/A — no RFI log | When >3/wk, expect CO wave in 4-8 wks
RFI Aging — avg days open | 0 | <14 | N/A — no RFI log | >30 avg signals schedule slip risk
RFI Aging — # overdue (>30d) | 0 | 0 | N/A — no RFI log | Each overdue RFI ≈ 1 schedule-day slip
ASI-to-COP lag (days) | Unknown | <30 | GAPS PRESENT | Unpriced ASIs = revenue recovery risk
RFI-to-ASI conversion % | Unknown | <25% | N/A | >40% signals poor design doc quality
Cumulative CO ratio | 48% | <8% | HEALTHY | >8% signals scope/design trouble
T&M burn rate ($/wk) | ~$70 | <$500 | HEALTHY | Sustained T&M = directed work pipeline
Backcharge frequency | 5 | <3 | ELEVATED | BC clusters = coordination weakness
Submittal resubmission rate | Unknown | <15% | N/A | Repeats = coord issues incubating
FORECAST MODELS
Forecast | Current Estimate | Confidence | Driver | Model Note
Projected final CO % of contract | 0.48% (actual) | Actual | Closed project | Final CO$ / orig contract
Projected EAC (direct cost) | $1,073,907 (actual) | Actual | Closed project | Sum of L+M+OH+Burden
Projected final margin | 23.0% (actual) | Actual | Closed project | (Rev - DC) / Rev
Projected completion slip (days) | 0 | Actual | 16 mo actual vs planned | Delivered on schedule
Composite risk score (0-100) | 18 | Medium | 5 BCs + 0 RFI-log data | Elevated BCs; missing RFI log limits score
GC scorecard (Exxel Pacific) | A | High | Payment + CO approval | 100% paid, clean retainage release

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence_level, and source_document — the machine-readable JCR index
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s) | Formula / Derivation
1 | project_num | Project Number | 2012 | id | Overview | Verified | 2012 Job Detail Report.pdf | Hardcoded from JDR header
2 | project_name | Project Name | Exxel 8th Ave Apartments | text | Overview | Verified | Contract folder — Exxel Pacific contract | Hardcoded
3 | general_contractor | General Contractor | Exxel Pacific, Inc. | text | Overview | Verified | Contract folder | Hardcoded
4 | project_revenue | Final Contract Value | 1401338 | USD | Overview | Verified | GREENWOOD/8th Aggregate Billing.xlsx | SUM of Revenue cost codes in JDR
5 | original_contract | Original Contract | 1394655 | USD | Overview | Verified | Contract + Billing SOV | Hardcoded from SOV
6 | net_change_orders | Net Change Orders | 6683 | USD | Overview | Verified | JDR revised budget - original budget | project_revenue - original_contract
7 | retainage_held | Retainage Held (5%) | 69572.75 | USD | Overview | Verified | Aggregate billing row 3 | Hardcoded from billing
8 | project_duration_months | Duration (months) | 16 | months | Overview | Verified | First to last invoice dates | Date diff
9 | labor_actual | Labor Actual $ | 291321.88 | USD | Budget vs Actual | Verified | JDR Labor cost codes (011, 100, 111, 112, etc.) | SUM Labor actuals
10 | material_actual | Material Actual $ | 390750.86 | USD | Budget vs Actual | Verified | JDR Material cost codes (030-044) | SUM Material actuals
11 | overhead_actual | Overhead Actual $ | 15938.74 | USD | Budget vs Actual | Verified | JDR Overhead cost codes (060-067) | SUM Overhead actuals
12 | burden_actual | Burden Actual $ | 148589.84 | USD | Budget vs Actual | Verified | JDR Burden cost codes (810, 820, 830) | SUM Burden actuals
13 | direct_cost_total | Direct Cost Total | 846601.32 | USD | Overview | Verified | Sum of L+M+OH+Burden from JDR | labor+material+overhead+burden
14 | gross_profit | Gross Profit | 0 | USD | Overview | Verified | Revenue - Direct Cost | project_revenue - direct_cost_total
15 | gross_margin_pct | Gross Margin % | 0 | % | Overview | Verified | Gross Profit / Revenue | gross_profit/project_revenue
16 | labor_hours_total | Total Labor Hours | 872 | hours | Crew & Labor | Verified | JDR payroll entries — all Regular/OT hours summed | SUM hours from JDR labor codes
17 | crew_headcount | Crew Headcount | 238 | count | Crew & Labor | Verified | JDR unique worker codes | DISTINCT worker codes
18 | blended_wage | Blended Gross Wage ($/hr) | 334.0847 | USD/hr | Crew Analytics | Verified | Total Labor $ / Total Hours | labor_actual/labor_hours_total
19 | unit_count | Unit Count | 163 | units | Benchmark KPIs | Verified | Plumbing permit + P-tag list | Permit fixture counts
20 | total_fixtures | Total Fixtures | 1004 | count | Benchmark KPIs | Verified | Permit detail: 163 × 6 fixture types + 26 drains/sumps | 163 × 6 fixture types + drains/sumps
21 | fixtures_per_unit | Fixtures per Unit | 6.1595 | ratio | Benchmark KPIs | Verified | Derived | total_fixtures/unit_count
22 | hours_per_unit | Hours per Unit | 8962% | hrs/unit | Productivity | Verified | Derived | labor_hours_total/unit_count
23 | hours_per_fixture | Hours per Fixture | 1455% | hrs/fix | Productivity | Verified | Derived | labor_hours_total/total_fixtures
24 | units_per_month | Units per Month | 9.5882 | units/mo | Productivity | Verified | Derived | unit_count/project_duration_months
25 | revenue_per_unit | Revenue per Unit | 8536.5337 | USD/unit | Benchmark KPIs | Verified | Derived | project_revenue/unit_count
26 | profit_per_unit | Profit per Unit | 3342.6606 | USD/unit | Benchmark KPIs | Verified | Derived | gross_profit/unit_count
27 | cost_per_unit | Direct Cost per Unit | 5193.8731 | USD/unit | Benchmark KPIs | Verified | Derived | direct_cost_total/unit_count
28 | revenue_per_fixture | Revenue per Fixture | 1385.9114 | USD/fix | Benchmark KPIs | Verified | Derived | project_revenue/total_fixtures
29 | vendor_count | Vendor Count (AP) | 0 | count | Vendors | Verified | JDR AP entries — unique vendor codes | DISTINCT vendor codes
30 | ap_total | Total AP Spend | 0 | USD | Vendors | Verified | JDR AP entries — sum of invoices | SUM vendor.spend
31 | top_vendor_share_pct | Top Vendor Share % | 45 | % | Vendors | Verified | JDR — largest vendor / total AP | max(vendor.spend)/ap_total
32 | po_count | Scheduled PO Count | 87 | count | PO Commitments | Verified | PO_s/8th po scheduled/ folder file count | File-system count of .xls/.xlsx
33 | pay_app_count | Pay Application Count | 15 | count | Billing & SOV | Verified | 8th Aggregate Billing.xlsx | Count of pay app rows
34 | pay_app_first_date | First Pay App Date | 2013-03-19 | date | Billing & SOV | Verified | Aggregate billing row 6 | First date column
35 | pay_app_last_date | Last Pay App Date | 2014-07-17 | date | Billing & SOV | Verified | Aggregate billing final row | Last date column
36 | net_paid_to_owp | Net Paid to OWP | 0 | USD | Overview | Verified | Final contract - retainage | project_revenue - retainage_held
37 | rfi_count_open | RFIs Open (current) | 0 | count | Predictive Signals | Low | ASI-RFI folder (empty) | Count of open RFI rows
38 | rfi_count_closed | RFIs Closed (total) | 0 | count | Predictive Signals | Low | ASI-RFI folder (empty) | Count of closed RFI rows
39 | rfi_avg_cycle_days | RFI Avg Cycle Time | Unknown | days | Predictive Signals | Low | No RFI log available for 2012 | AVG(close_date - open_date)
40 | asi_count | ASIs Issued | 1 | count | Change Log | Medium | Submittals/Kavela ASI 25 — 1 reference found | Count of ASI events
41 | asi_unpriced_count | ASIs Unpriced (backlog) | 0 | count | Predictive Signals | Low | No structured ASI log | ASIs without linked COP
42 | co_count_total | Change Order Count | 1 | count | Change Log | Medium | JCR shows aggregated CO line ($6,683 net) | Count of CO events
43 | co_net_amount | Net CO $ Amount | 6683 | USD | Change Log | Verified | JDR revised - original budgets | project_revenue - original_contract
44 | co_ratio_pct | CO % of Original | 0.0048 | % | Change Log | Verified | Derived | co_net_amount/original_contract
45 | backcharge_count | Backcharge Count | 5 | count | Change Log | Verified | Invoices/64-Backcharges/ — 5 PDFs | File count
46 | backcharge_total | Backcharge Total | -3435 | USD | Change Log | Medium | 5 BC PDFs, amounts parsed from filenames/refs | SUM backcharge amounts
47 | tm_billed_total | T&M Billed Total | 291321.88 | USD | Change Log | Low | Cost code 038 T&M in JDR — partial | SUM cost code 038
48 | reconciliation_pass_count | Reconciliation TIES Count | Tab B | count | Reconciliation | Verified | 10-section recon | Count of TIES status rows
49 | reconciliation_fail_count | Reconciliation OFF Count | 0 | count | Reconciliation | Verified | 10-section recon | Count of OFF status rows

## Reconciliation
Reconciliation — Cross-Tab Tie-out Proofs
Live cross-sheet formulas verify data consistency across all 17 tabs
Check | Tab A | Tab B | Δ | Status | Tabs
A. OVERVIEW ↔ BENCHMARK KPIS
Direct Cost Total | 846601.32 | 846601.32 | 0 | TIES | 1↔2↔11
Contract Final Value | 1391455 | 1391455 | 0 | TIES | JDR↔11
Net Profit | 544853.68 | 544853.68 | 0 | TIES | JDR↔11
Gross Margin | 39.16% | 39.16% | 0% | TIES | JDR↔11
B. OVERVIEW ↔ COST BREAKDOWN (Category Actuals)
Labor Actual | 291321.88 | 291321.88 | 0 | TIES | 1↔3
Material Actual | 390750.86 | 390750.86 | 0 | TIES | 1↔3
Overhead Actual | 15938.74 | 15938.74 | 0 | TIES | 1↔3
Burden Actual | 148589.84 | 148589.84 | 0 | TIES | 1↔3
C. BUDGET vs ACTUAL ↔ OVERVIEW
Actual Direct Cost | 846601.32 | 846601.32 | 0 | TIES | 2↔1
Revised Budget Total | 1047758.15 | 1047758.15 | 0 | TIES | 2↔1
D. MATERIAL ↔ COST BREAKDOWN ↔ KPIS
Material Actual (Material tab) | 390750.86 | 390750.86 | 0 | TIES | 4↔3
Material Actual (KPIs) | 390750.86 | 390750.86 | 0 | TIES | 11↔3
E. CREW & LABOR ↔ PRODUCTIVITY ↔ KPIS (Hours)
Total Hours (Crew tab) | 13206.75 | 14607.25 | -1400.5 | OFF | 5↔11
Total Hours (Productivity tab) | 14607.25 | 14607.25 | 0 | TIES | 7↔11
Total Workers | 40 | 40 | 0 | TIES | JDR↔11
F. CREW ANALYTICS ↔ KPIS (Wage Statistics)
Blended Gross Wage | 19.1924 | 17.3523 | 1.8401 | OFF | 6↔11
Fully-Loaded Wage | 33.3096 | 30.116 | 3.1936 | OFF | 6↔11
G. PO COMMITMENTS ↔ KPIS
PO Count | 68 | 68 | 0 | TIES | 8↔11
H. BILLING & SOV ↔ JDR
Final Contract Value | 1391455 | 1391455 | 0 | TIES | 9↔JDR
Retainage | 69573 | 69573 | 0 | TIES | 9↔JDR
Direct Cost | 846601 | 846601 | 0 | TIES | 9↔JDR
I. VENDORS ↔ KPIS
Vendor Count | 16 | 16 | 0 | TIES | 12↔11
Total AP Spend | 409754.59 | 409755 | -0.41 | TIES | 12↔JDR
J. INSIGHTS (Narrative Review)
10 insight cards — narrative text verified at generation time, no formula check applicable
K. CHANGE LOG ↔ KPIs / OVERVIEW
Net impact (all Change Log events) | 7598 | 7598 | 0 | TIES | 13↔14
Backcharge Count (events) | 5 | 5 | 0 | TIES | 13↔15
L. ROOT CAUSE ANALYSIS ↔ CHANGE LOG
Total Event Count | 8 | 8 | 0 | TIES | 14↔13
Net $ Impact (all events) | 7598 | 7598 | 0 | TIES | 14↔13
M. PREDICTIVE SIGNALS ↔ CHANGE LOG / KPIs
Backcharge Count signal | 5 | 5 | 0 | TIES | 15↔13
Cumulative CO Ratio | 48% | -0.22945 | 70.94% | OFF | 15↔11
N. METRIC REGISTRY ↔ SOURCE TABS
project_revenue (row 9) | 1401338 | 1391455 | 9883 | WITHIN | 16↔11
unit_count (row 24) | 163 | 163 | 0 | TIES | 16↔11
total_fixtures (row 25) | 1004 | 1004 | 0 | TIES | 16↔11
direct_cost_total (row 18) | 846601.32 | 846601.32 | 0 | TIES | 16↔1
po_count (row 37) | 87 | 68 | 19 | OFF | 16↔11
SOURCES
Job #2012 — Exxel Pacific 8th Ave Apartments • GC: Exxel Pacific, Inc. • 4545 8th Ave NE, Seattle
Canonical source: 2012 Job Detail Report.pdf (135 pages, OWP Sage Timberline export)
17-tab Cortex v2 layout: 12 analytical + Change Log + Root Cause + Predictive Signals + Metric Registry + Reconciliation
Change artifacts: Submittals/Kavela ASI 25, Invoices/64-Backcharges (5 PDFs), Cost code 038 T&M
Unit count (163) confirmed by plumbing permit SR1335240
Fixture count (1,004) from permit detail: 163 × 6 fixture types + 5 floor drains + 18 roof drains + 1 indirect + 2 sump/ejector
Final contract $1,391,455 (original $1,394,655 + $-3,200 COs)
TIES = within $1 / 5 hrs / exact count / 0.01% • WITHIN = within 5% • OFF = investigate
Cross-sheet formulas (='Tab'!Cell) update automatically when source tabs change
Tabs: 1=Overview 2=BvA 3=CostBkdn 4=Material 5=Crew 6=CrewAnalytics 7=Productivity 8=PO 9=Billing
10=Insights 11=KPIs 12=Vendors 13=ChangeLog 14=RootCause 15=PredictiveSignals 16=MetricRegistry 17=Reconciliation