## Schedule
Job # | Job Name | GC | Units | Project Start Date | RI Foreman | Trim Foreman | Address | 2014-10-01 | 2017-02-01 | 2014-11-01 | 2014-12-01 | 2017-05-01 | 2015-01-01 | 2017-02-01 | 2015-02-01 | 2015-03-01 | 2017-05-01 | 2015-04-01 | 2015-05-01 | 2015-06-01 | 2015-07-01 | 2015-08-01 | 2015-09-01 | 2015-10-01 | 2015-11-01 | 2015-12-01 | 2016-01-01 | 2016-02-01 | 2016-03-01 |  | 2016-04-01 | 2016-05-01 |  | 2016-06-01 | 2016-07-01 | 2016-07-01 | 2016-09-01 | 2016-08-01 | 2016-09-01 | 2016-12-01 | 2016-10-01 | 2017-02-01 | 2016-11-01 | 2016-12-01 | 2017-05-01 | 2017-01-01 | 2017-07-01 | 2017-02-01 |  | 2017-03-01 | 2017-10-01 | 2017-04-01 | 2017-12-01 | 2017-05-01 | 2017-06-01 | 2018-03-01 | 2017-07-01 | 2018-05-01 | 2017-08-01 | 2017-09-01 | 2018-08-01 | 2017-10-01 | 2018-10-01 | 2017-11-01 | 2017-12-01 | 2017-12-01 |  | 2018-01-01 | 2018-02-01 |  | 2018-03-01 | 2018-04-01 | 2018-05-01 |  | 2018-06-01 |  | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 |  | 2018-11-01 |  | 2018-12-01 | 2019-01-01 |  | 2019-02-01 | 2019-03-01 | 2019-04-01 |  | 2019-05-01 |  | 2019-06-01 |  | 2019-07-01 |  | 2019-08-01 | 2019-09-01 |  | 2019-10-01 |  | 2019-11-01 |  | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 |  | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 |  | 2020-10-01 |  | 2020-11-01 | 2020-12-01 | 2021-01-01 |  | 2021-02-01 |  | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 |  | 2022-04-01 |  | 2022-05-01 | 2022-06-01 |  | 2022-07-01 | 2022-08-01 |  | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 |  | 2023-08-01 | 2023-09-01 |  | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 |  | 2024-02-01 |  | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 |  | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01
2001 | 230 Broadway | SRM | 234
2002 | Wedgewood | Exxel Pacific | 91
2003 | Evanston Space | Exxel Pacific | 28
2005 | Indigo/Kavela | Chinn | 66
2006 | Bella Lago | ICC | 319
2008 | 101 Taylor | SRM | 258 |  | Bob | Al
2009 | Greenwood | Chinn | 56
2010 | Old Town | Chinn | 149
2011 | Barrett Park | Chinn | 117
2012 | 8th Ave | Exxel Pacific | 162
2013 | NE 63rd | Exxel Pacific | 112
2016 | Sedona | Natural & Built | 85
2018 | Astro | SRM | 211 |  | Bob | Al |  | TRIM |  | TRIM | TRIM |  | TRIM |  | TRIM | TRIM
2017 | 36 Stone | Exxel Pacific | 119 |  | Esteban | Al |  | RI |  | RI | TRIM |  | TRIM |  | TRIM | TRIM
2022 | Interlake | Exxel Pacific | 18 |  | Al | Al |  |  |  |  | GW |  | GW |  |  | RI |  | RI |  | TRIM
2015 | Rooster | Exxel Pacific | 197 |  | Al - Trim | Al |  | RI |  | RI | RI |  | RI |  | RI | RI |  | RI | RI | TRIM | TRIM | TRIM | TRIM
2014 | Pike Motorworks | Exxel Pacific | 258 |  | Joe | Joe | 714 E Pike Street, Seattle, WA 98122 | RI |  | RI | RI |  | RI |  | RI | RI |  | RI | RI | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM
2020 | Bellevue Main | SRM | 256 |  | Nate (Al trim) | Al | 15 Bellevue Way SE, Bellevue, WA 98004 | RI |  | RI | RI |  | RI |  | RI | RI |  | RI | RI | RI | RI | RI | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM
2019 | 8th Republic | Exxel Pacific | 211 |  | Thaddeus (Al trim) | Al/Rick | 430 8th Ave North, Seattle, WA 98109 | GW |  | GW | PT |  | PT |  | PT | PT |  | RI | RI | RI | RI | RI | RI | TRIM | TRIM | TRIM | TRIM | TRIM
2024 | Merrill Gardens | SRM | 117 |  | Gustavo | Al | 5601 24th Ave NW, Seattle, WA 98107 | [8 empty] | GW |  | GW | PT | PT | RI | RI | RI | RI | RI | RI | RI | RI | TRIM |  | TRIM | TRIM |  | TRIM
2021 | Admiral | Exxel Pacific | 136 |  | Esteban | Al | 3210 California Ave SW, Seattle, WA 98116 | [8 empty] | GW |  | GW | GW | GW | PT | PT | RI | RI | RI | RI | RI | RI | RI |  | TRIM | TRIM |  | TRIM
2023 | Hadley | Chinn | 209 |  | Joe | Al | 2601 76th Ave SE, Mercer Island, WA 98040 | [5 empty] | GW |  | GW | GW |  | PT | PT | PT | RI | RI | RI | RI | RI | RI | RI | RI | RI |  | TRIM | TRIM |  | TRIM |  | TRIM |  | TRIM | TRIM
2028 | Reserve @ Lynnwood | Exxel Pacific | 296 |  |  |  | 19815 Scriber Lake Road, Lynnwood, WA 98036 | [22 empty] | GW | PT | PT | RI | PT | RI | RI |  | RI | RI |  | RI |  | RI | RI |  | TUBS |  | BURN
2025 | The Cora | Exxel Pacific | 75 |  | Thaddeus |  | 19 W Harrison, Seattle, WA 98119 | [27 empty] | GW | GW |  | PT | PT |  | PT | RI | RI | RI |  | RI |  | RI |  | PICKUP |  | PICKUP |  | TRIM | TRIM
2026 | Boren | Synnergy | 49 |  | Gustavo |  | 525 Boren Ave N, Seattle, WA 98109 | [24 empty] | GW |  | GW |  | PT |  | PT | PT | RI | RI |  | RI | RI |  | RI |  | RI |  | PICKUP |  | PICKUP |  | TRIM | TRIM |  | TRIM
2029 | Parsonage | Exxel Pacific | 83 |  | Rick |  | 4132 Brooklyn Ave NE, Seattle, WA 98105 | [30 empty] | GW | GW |  | GW | PT | PT | PT | RI | RI |  | RI |  | RI |  | PICKUP |  | TRIM | TRIM |  | TRIM
2027 | 550 Broadway | Exxel Pacific | 170 |  | Joe |  | 550 Broadway, Seattle, WA 98122 | [23 empty] | GW | GW | PT | PT |  | PT |  | PT | PT |  | RI |  | RI | RI |  | RI |  | RI |  | PICKUP |  | PICKUP |  | TRIM | TRIM |  | TRIM |  | TRIM
2035 | 162 Ten | Natural & Built | 92 | 2016-08-16 | Reuben |  | 16210 NE 80th St, Redmond, WA 98052 | [33 empty] | GW |  | GW | PT |  | PT |  | PT |  | RI |  | RI |  | RI | RI |  | RI |  | RI | PICKUP |  | PICKUP |  | TRIM |  | TRIM |  | TRIM | TRIM
2034 | Park Lane | Compass | 128 | 2016-08-05 | Thaddeus |  | 207 Park Lane, Kirkland, WA 98033 | [36 empty] | GW |  | PT |  | PT |  | RI |  | RI |  | RI | RI |  | RI |  | RI | PICKUP |  | PICKUP |  | PICKUP |  | TRIM |  | TRIM | TRIM
2032 | Luna | Blueprint | 71 | 2016-11-01 | Rick |  | 6921 Roosevelt Way NE, Seattle, WA 98115 | [41 empty] | GW | GW |  | GW | RI | RI | RI |  | RI |  | RI | RI |  | RI |  | RI |  | TRIM |  | TRIM | TRIM |  | TRIM | TRIM | TRIM
2036 | Westridge | Exxel Pacific | 31 | 2016-10-01 | Gustavo |  | 512 121st Place NE, Bellevue, WA | [39 empty] | GW |  | GW |  | GW | GW |  | GW | GW |  | RI |  | RI | RI |  | RI |  | RI |  | PICKUP |  | PICKUP | TRIM |  | TRIM | TRIM | TRIM |  | TRIM |  | TRIM
2048 | Ballinger | GRE | 72 | 2017-10-17 | Esteban | [56 empty] | RI |  | RI |  | RI |  | RI | PICKUP |  | TRIM | TRIM | TRIM |  | TRIM
2047 | Greenlake | GRE | 70 | 2017-10-17 | Reuben | [56 empty] | RI |  | RI |  | RI |  | RI | PICKUP |  | PICKUP | TRIM | TRIM |  | TRIM
2033 | Vuecrest | Compass | 139 | 2016-09-01 | Victor |  | 1000 100th Ave NE, Bellevue, WA | [37 empty] | GW | GW |  | GW | PT | PT | RI | RI |  | RI | RI |  | RI |  | RI | RI |  | RI |  | RI |  | PICKUP |  | PICKUP | TRIM |  | TRIM | TRIM | TRIM |  | TRIM |  | TRIM
2030 | East Union | Exxel Pacific | 144 | 2016-11-01 | Joe |  | 2220 E. Union Street, Seattle WA | [42 empty] | GW |  | GW | PT | PT | PT |  | RI |  | RI | RI |  | RI |  | RI |  | RI |  | RI | PICKUP |  | PICKUP | TRIM | TRIM |  | TRIM |  | TRIM
2038 | 2nd & John | Compass | 80 | 2017-02-17 | Thaddeus / Joe |  | 200 2nd Ave West, Seattle, WA | [49 empty] | GW |  | GW | PT |  | PT |  | PT |  | PT | RI | RI | RI |  | RI | RI | RI |  | PICKUP |  | PICKUP | TRIM | TRIM | TRIM |  | TRIM |  | TRIM
2040 | Roosevelt 65th | Blueprint | 55 | 2017-03-01 | Garrett / Joe |  | 1222 NE 65th Street, Seattle, WA 98115 | [52 empty] | GW |  | PT |  | PT |  | PT | RI | RI | RI |  | RI | RI | RI |  | RI |  | RI | PICKUP | TRIM | TRIM |  | TRIM |  | TRIM
2037 | University Apartments | Marpac | 122 | 2017-01-09 | Rick / Joe |  | 3025 NE 130th Street, Seattle WA | [49 empty] | GW |  | GW | PT |  | PT |  | PT |  | PT |  | PT | PT |  | RI | RI | RI |  | RI |  | RI | PICKUP | PICKUP | TRIM |  | TRIM |  | TRIM
2042 | Metro Flats | Shelter Holdings | 75 | AUGUST, 17 | Reuben / Bob | [61 empty] | GW | PT | PT |  | RI | RI | RI |  | RI |  | RI | PICKUP | TRIM | TRIM |  | TRIM |  | TRIM | TRIM |  | TRIM | TRIM
2043 | Aegis Mercer Island | Compass | 89 | 2017-03-01 | Victor / Bob | [60 empty] | GW |  | GW | PT |  | RI | RI | RI |  | RI |  | RI | RI | PICKUP | PICKUP |  | TRIM |  | TRIM | TRIM |  | TRIM | TRIM
2031 | Issaquah Gateway | Exxel Pacific | 398 | 2016-08-16 | Esteban / Bob |  | 2290 Newport Way NW, Issaquah, WA 98027 | [34 empty] | GW |  | GW |  | GW |  | GW | RI | RI |  | RI |  | RI | RI |  | RI |  | RI | RI |  | RI |  | RI |  | RI |  | RI | RI |  | RI | RI | RI |  | RI |  | RI | RI | PICKUP | TRIM |  | TRIM |  | TRIM | TRIM |  | TRIM | TRIM | TRIM |  | TRIM
2046 | 4218 Roosevelt | Marpac | 110 | end of sept mob | Thaddeus / Joe | [64 empty] | GW | GW | PT | PT |  | PT |  | PT | RI | RI | RI |  | RI |  | RI | RI |  | PICKUP | TRIM | TRIM |  | TRIM |  | TRIM
2050 | 2100 E. Madison | Compass | 50 | Winter 18 | Garrett / Joe | [66 empty] | GW | GW |  | PT |  | PT | PT | RI | RI |  | RI |  | RI | RI |  | PICKUP | TRIM | TRIM |  | TRIM
2044 | Roosevelt 66th | Blueprint | 78 | 2017-07-01 | Anthony / Joe |  | 836 NE 66th Street, Seattle, WA 98115 | [62 empty] | GW | GW | GW | PT |  | PT | RI | RI | RI | RI | RI |  | RI |  | RI | RI |  | RI | PICKUP | TRIM |  | TRIM |  | TRIM
2037 | University Townhomes | Marpac | 5 |  | Bob |  | 3025 NE 130th Street, Seattle WA | [74 empty] | GW |  | PT | PT |  | PT | RI | RI |  | RI | TRIM | TRIM |  | TRIM
2049 | Reserve Lynnwood Rebuild | Exxel Pacific | 296 | Summer 17 | Orlando / Bob | [66 empty] | GW |  |  | GW |  | RI | RI | RI | RI |  | RI |  | RI | RI |  | RI | RI | TRIM |  | TRIM |  | TRIM |  | TRIM |  | TRIM
2045 | GRE Notch | GRE | 158 |  | Mitch / Bob | [70 empty] | GW | GW | GW | RI | RI |  | RI |  | RI | RI |  | RI | RI | RI |  | RI | TRIM | TRIM |  | TRIM |  | TRIM | TRIM |  | TRIM |  | TRIM
2057 | Plaza | Natural & Built | 111 |  | Reuben / Bob | [72 empty] | GW | PT | PT |  | PT |  | RI | RI |  | RI | RI | RI |  | RI |  | RI |  | RI | TRIM | TRIM | TRIM |  | TRIM |  | TRIM
2041 | Luna 2749 California Ave | Chinn | 108 | Summer 17 | Rick / Joe | [68 empty] | GW | GW |  | PT | PT | PT | PT |  | RI |  | RI | RI |  | RI | RI | RI |  | RI |  | RI |  | RI |  | TRIM | TRIM |  | TRIM |  | TRIM
2052 | 5th & Roy | Farrell | 107 |  | Thaddeus / Joe | [70 empty] | GW | GW | PT | PT | PT |  | RI |  | RI | RI |  | RI | RI | RI |  | RI |  | RI |  | RI | TRIM | TRIM | TRIM |  | TRIM |  | TRIM |  | TRIM
2053 | Bellevue Parkside | Compass | 136 | 2018-01-01 | Victor / Bob | [71 empty] | GW | GW | PT | PT |  | PT |  | PT | PT | RI | RI | RI | RI |  | RI |  | RI |  | RI |  | RI | TRIM |  | TRIM |  | TRIM |  | TRIM | TRIM | TRIM | TRIM
2054 | Blueprint 800 5th Ave | Blueprint | 68 | 2018-03-18 | Thaddeus / Joe | [75 empty] | GW | GW | PT | PT | PT |  | RI | RI | RI |  | RI |  | RI |  | RI |  | RI | RI |  | RI |  | RI |  | TRIM | TRIM | TRIM | TRIM
2051 | Vail Apartments | Compass | 163 | Winter 18 | Bob | [75 empty] | GW | GW |  | PT | PT |  | PT | RI | RI |  | RI |  | RI |  | RI |  | RI | RI |  | RI |  | RI |  | TRIM | TRIM | TRIM | TRIM |  | COVID | TRIM | TRIM
2058 | Howell | Blueprint | 77 |  | Reuben / Bob | [84 empty] | GW | PT |  | PT |  | PT | RI | RI | RI |  | RI |  | RI |  | RI | RI | RI | TRIM |  | COVID | TRIM | TRIM | TRIM | TRIM | TRIM |  | TRIM
2059 | Meeker | GRE | 365 |  | Rick, Anthony / Joe | [84 empty] | GW | PT |  | RI |  | RI |  | RI | RI |  | RI |  | RI |  | RI | RI | RI | RI |  | COVID | RI | RI | RI | RI | RI |  | TRIM |  | TRIM | TRIM | TRIM |  | TRIM |  | TRIM
2056 | Acme Farms | Exxel Pacific | 321 |  | Mitch, Thaddeus / Joe | [88 empty] | GW | GW |  | PT | PT | RI | RI |  | RI |  | RI | RI | RI | RI |  | COVID | RI | RI | RI | RI | RI |  | TRIM |  | TRIM | TRIM | TRIM |  | TRIM |  | TRIM | TRIM | TRIM | TRIM
2063 | Aria Flats | Compass | 102 |  | Orlando / Bob | [97 empty] | GW | GW | GW | PT | PT |  | COVID | RI | RI | RI | RI | RI |  | RI |  | RI | RI | RI |  | TRIM |  | TRIM | TRIM | TRIM | TRIM
2074 | Buddha Jewel Monastery | Marpac | n/a |  | Jordan | [108 empty] | GW |  | RI |  | RI | RI | RI |  | TRIM | [5 empty] | GW | RI | RI | TRIM | TRIM | TRIM
2061 | Columbia City | Exxel Pacific | 242 |  | Victor | [99 empty] | GW | GW | GW | PT | COVID | PT | PT | RI | RI | RI |  | RI |  | RI | RI | RI |  | RI |  | RI | RI | RI | RI | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM
2064 | Jabooda Melody | Jabooda | 186 |  | Reuben | [99 empty] | GW | GW | PT |  | COVID | PT | RI | RI | RI | RI |  | RI |  | RI | RI | RI |  | RI |  | RI | RI | RI | RI | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM
2066 | Fireside Flats | Compass | 102 |  | Orlando | [115 empty] | GW | GW |  | GW | PT | RI | RI | RI | RI | RI | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM
2055 | Dockside | Blueprint | 98 |  | Orlando | [113 empty] | GW | GW |  | PT |  | PT | PT | RI | RI | RI | RI | RI | RI | TRIM | TRIM | TRIM | TRIM | TRIM |  | TRIM
2060 | Marina Square | Compass | 270 |  | Anthony | [91 empty] | GW | GW |  | GW | PT | PT |  | PT | PT | PT | PT | RI | COVID | HOLD | HOLD | HOLD | HOLD | HOLD |  | HOLD |  | HOLD | HOLD | HOLD |  | RI |  | RI | RI | RI | RI | RI | RI | RI | RI | RI | RI | TRIM | TRIM | TRIM |  | TRIM |  | TRIM | TRIM |  | TRIM
2076 | Yesler Terrace Bldg B | Compass | 215 |  | Mitch | [113 empty] | GW | GW |  | PT |  | PT | PT | RI | RI | RI | RI | RI | RI | RI | RI | RI | RI | RI | TRIM | TRIM |  | TRIM | TRIM |  | TRIM
2075 | Everett Rockefeller | Braseth | 165 |  | Reuben | [117 empty] | GW | GW | GW | PT | PT | PT | RI | RI | RI | RI | RI | RI | RI | RI |  | TRIM |  | TRIM | TRIM |  | TRIM | TRIM
2069 | Theory U-District | Exxel Pacific | 171 |  | Rick | [118 empty] | GW | GW | PT | PT | PT | RI | RI | RI | RI | RI | RI | RI | RI |  | TRIM |  | TRIM | TRIM |  | TRIM | TRIM
2079 | Crown Hill Mixed Use | BMDC | 54 |  | Tommy | [119 empty] | GW | PT | RI | HOLD | RI | RI | RI | RI | RI | RI | RI | RI | TRIM | TRIM |  | TRIM | TRIM |  | TRIM | TRIM |  | TRIM | TRIM | TRIM | TRIM | TRIM
2067 | Edmond 99 | GRE | 192 |  | Jordan | [117 empty] | GW | GW | GW | PT | PT | PT | RI | RI | RI | RI | RI | RI | RI | RI |  | RI |  | RI | TRIM |  | TRIM | TRIM |  | TRIM
2081 | 400 Queen Anne | Compass | 143 |  | Thaddeus | [122 empty] | GW | GW | PT | PT | RI | RI | RI | RI | RI |  | RI |  | RI | RI |  | TRIM | TRIM |  | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM
2096 | SunDowner | Chinn | 27 |  | Thaddeus/Steven | [140 empty] | RI | RI | RI | TRIM | TRIM | TRIM | TRIM | TRIM
2078 | 112 Lake Street | Compass | 141 |  | Victor | [121 empty] | GW | GW | PT | PT | PT | RI | RI | RI | RI | RI |  | RI |  | RI | RI |  | RI | RI |  | RI | RI | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM
2071 | 1405 Dexter | Chinn | 160 |  | Reuben | [128 empty] | ON HOLD | ON HOLD | ON HOLD |  | GW |  | GW | PT |  | PT | PT | RI | RI | RI | RI | RI | RI | RI | RI | RI | TRIM | TRIM | TRIM |  | TRIM
2085 | Basalt | Blueprint | 77 |  | Anthony | [128 empty] | ON HOLD | ON HOLD | ON HOLD |  | GW |  | GW | PT |  | PT | PT | RI | RI | RI | RI | RI | RI | RI | RI | RI | RI | TRIM | TRIM |  | TRIM | TRIM |  | TRIM | TRIM
2080 | Redmond Grand - Bldg B | Compass | 311 |  | Orlando | [128 empty] | ON HOLD | ON HOLD | ON HOLD |  | GW |  | GW | PT |  | PT | PT | RI | RI | RI | RI | RI | RI | RI | RI | RI | RI | RI | TRIM |  | TRIM | TRIM |  | TRIM | TRIM | TRIM | TRIM |  | TRIM
2088 | Gridline (Knights of Columbus) | SRM | 178 |  | Steven/Rick | [136 empty] | GW | GW | GW | PT | PT | RI | RI | RI | RI | RI | RI | RI | RI | RI | RI |  | TRIM | TRIM |  | TRIM | TRIM | TRIM | TRIM |  | TRIM
2086 | LIZA | Compass | 207 |  | Mitch | [128 empty] | ON HOLD | ON HOLD | ON HOLD |  | GW |  | GW | PT |  | PT | PT | RI | RI | RI | RI | RI | RI | RI | RI | RI | RI | RI | RI |  | TRIM | TRIM |  | TRIM | TRIM | TRIM | TRIM |  | TRIM |  | TRIM
2082 | Northgate | GRE | 235 |  | Tommy | [122 empty] | GW | GW | GW | PT | PT | RI | ON HOLD | ON HOLD | ON HOLD |  | PT |  | RI | RI |  | RI | RI |  | RI | RI | RI | RI | RI | RI | RI | RI | RI | TRIM | TRIM |  | TRIM | TRIM |  | TRIM | TRIM | TRIM | TRIM |  | TRIM |  | TRIM | TRIM
2090 | Chronicle | Blueprint | 78 |  | Julio/Tommy | [143 empty] | GW | GW | PT | PT | RI | RI | RI | RI |  | RI | RI |  | RI | RI | TRIM | TRIM |  | TRIM |  | TRIM | TRIM | TRIM | TRIM |  | TRIM
2084 | Willows | GRE | 195 |  | Jordan | [128 empty] | ON HOLD | ON HOLD | ON HOLD |  |  | GW | GW | GW |  | PT | PT |  | PT | PT | PT | RI | RI | RI | RI | RI | RI | RI | RI |  | RI | RI |  | RI | RI | TRIM | TRIM |  | TRIM |  | TRIM | TRIM | TRIM | TRIM |  | TRIM
2077 | Shoreline | Intracorp | 299 |  | Thaddeus/Garret/Reuben | [141 empty] | GW | GW |  | GW | GW | GW | RI | RI | RI | RI |  | RI | RI |  | RI | RI | RI | RI |  | RI |  | TRIM | TRIM | TRIM | TRIM
2093 | Symphony | Jabooda | 51 |  | Anthony | [143 empty] | GW | GW |  | HOLD | HOLD | HOLD | HOLD | RI |  | RI | RI |  | RI | RI | RI | RI |  | RI |  | RI | TRIM | TRIM | TRIM |  | TRIM | TRIM | TRIM | TRIM | TRIM
2094 | Carrick | Blueprint | 86 |  | Tommy | [145 empty] | GW | PT | PT | PT | HOLD | RI |  | RI | RI |  | RI | RI | RI | RI |  | RI |  | RI | TRIM | TRIM | TRIM |  | TRIM | TRIM | TRIM | TRIM | TRIM
2087 | Northgate (11201 Roosevelt) | Exxel Pacific | 295 |  | Victor/Mitch | [143 empty] | GW | GW | PT | PT | PT | GW | RI | RI |  | RI | RI |  | RI | RI | RI | RI |  | RI |  | RI | RI | RI | TRIM |  | TRIM | TRIM | TRIM | TRIM | TRIM
2089 | 24th & Market | Holland | 238 |  | Rick/Steven | [147 empty] | GW | GW | PT | PT |  | PT | PT | RI | RI | RI | RI | RI |  | RI |  | RI | RI | RI | TRIM |  | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM
2098 | Trailside 2 | Chinn | 170 |  | Orlando | [153 empty] | GW |  | GW | PT | PT | PT | RI | RI |  | RI | RI | RI | RI |  | RI | RI | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM
2092 | Reed Apartments | Blueprint | 125 |  | Reuben | [151 empty] | GW | GW | GW |  | GW | PT | PT | PT | RI | PT |  | RI | RI | RI | RI |  | RI | RI | RI | RI | RI | RI | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM
2097 | Marysville - Ph1 | Intracorp | 228 |  | Garrett/Mitch | [161 empty] | GW | GW | GW | RI | RI |  | RI | RI | RI | RI | RI | RI | RI | TRIM | TRIM | TRIM | TRIM | TRIM
2101 | Bella on Broadway Water Repipe | F&M | na |  | Anthony/Joe | [163 empty] | RI | RI
2105 | 3000 Western | Compass | 219 |  | CANCELLED
2099 | 300 W Republican | Kirtley Cole | 169 |  | Jordan/Rick | [166 empty] | GW | GW | PT | PT | RI | RI | RI | RI | RI | RI | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM
2104 | Big 1410 | BMDC | 24 |  | Tommy/Ben | [167 empty] | GW | GW | PT | RI | RI | RI | RI | RI | RI | RI | RI | RI | RI | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM
2103 | Northgate M2 | Compass | 234 |  | Victor/Orlando | [166 empty] | GW | GW | GW | PT | PT | RI | RI | RI | RI | RI | RI | RI | RI | RI | RI | RI | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM
2107 | 68th & Roosevelt | Chinn | 244 |  | Rick/Orlando | [175 empty] | GW | PT | PT | PT | RI | RI | RI | RI | RI | RI | RI | RI | RI | RI | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM
2109 | Marysville - Ph2 | Intracorp | 246 |  | Garrett/Mitch | [177 empty] | GW | GW | RI | RI | RI | RI | RI | RI | RI | RI | RI | RI | RI | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM
2112 | BIG3 | BMDC | 20 |  | Tommy | [179 empty] | GW | GW | RI | RI | RI | RI | RI | RI | RI | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM
2111 | Northgate M3 | Compass | 186 |  | Victor | [182 empty] | GW | GW | PT | PT | RI | RI | RI | RI | RI | RI | RI | RI | RI | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM
2116 | The V Apartments | SRM | 166 | [191 empty] | GW | GW | PT | PT | RI | RI | RI | RI | RI | RI | RI | RI | RI | RI | RI | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM
2114 | Ballard Blossom | Holland | 239 | [192 empty] | GW | GW | PT | PT | RI | RI | RI | RI | RI | RI | RI | RI | RI | RI | RI | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM
2110 | Roosevelt Manor | Sierra | 137 |  | Start Q2 2026 | [190 empty] | GW | GW | PT | PT | RI | RI | RI | RI | RI | RI | RI | RI | RI | RI | RI | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM
2117 | Lachlan Apartments | Ravenna Partners | 104 |  | Start Apr 2026 | [191 empty] | GW | GW | PT | PT | RI | RI | RI | RI | RI | RI | RI | RI | RI | RI | RI | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM
2106 | 6220 Roosevelt | Chinn | 146 |  | Start by July 2026 | [192 empty] | GW | GW | PT | PT | RI | RI | RI | RI | RI | RI | RI | RI | RI | RI | RI | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM
2115 | Elowen | Chinn | 201 |  | Start Q3 2026 | [193 empty] | GW | GW | PT | PT | RI | RI | RI | RI | RI | RI | RI | RI | RI | RI | RI | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM
2118 | Edmonds Behar | Exxel Pacific | 406 |  | Start Summer 26 | [193 empty] | GW | GW | PT | PT | RI | RI | RI | RI | RI | RI | RI | RI | RI | RI | RI | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM
| Frank (508 Fremont) | Exxel Pacific | 169 |  | Start Fall 26 | [194 empty] | GW | GW | PT | PT | RI | RI | RI | RI | RI | RI | RI | RI | RI | RI | RI | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM | TRIM
2108 | R&G Apartments | Braseth | 263 |  | ON HOLD- Summer 26?
Green = Construction contract issued.
Blue = Design contract issued.
2024 | Merrill Gardens | SRM | 117 |  | MANPOWER | [26 empty] | 3 |  | 2
2021 | Admiral | Exxel Pacific | 136 |  | MANPOWER | [26 empty] | 3 |  | 2
2023 | Hadley | Chinn | 209 |  | MANPOWER | [26 empty] | 4 |  | 5 |  | 4 |  | 3 | 2
2028 | Reserve @ Lynnwood | Exxel Pacific | 296 |  | MANPOWER | [26 empty] | 6 |  | 6 |  | 15 |  | 20 | 16 |  | 16 |  | 16 | 10 |  | 3 |  | BURN
2025 | The Cora | Exxel Pacific | 75 |  | MANPOWER | [28 empty] | 2 |  | 3 |  | 4 | 7 |  | 11 |  | 10 | 10 |  | 10 |  | 6 |  | 4 |  | 3 |  | 3 | 1
2026 | Boren | Synnergy | 49 |  | MANPOWER | [26 empty] | 3 |  | 2 |  | 1 |  | 4 | 6 |  | 8 |  | 5 | 5 |  | 4 |  | 4 |  | 2 |  | 2 |  | 2 | 1 |  | 1
2029 | Parsonage | Exxel Pacific | 83 |  | MANPOWER | [32 empty] | 3 | 3 |  | 3 |  | 3 | 5 |  | 10 |  | 10 |  | 8 |  | 6 |  | 4 | 1 |  | 1
2035 | 162 Ten | Natural & Built | 92 | 2016-08-16 | MANPOWER | [35 empty] | 2 |  | 2 | 3 |  | 6 |  | 4 |  | 6 |  | 10 |  | 6 | 6 |  | 4 |  | 2 | 3 |  | 1 |  | 1 |  | 1 |  | 1 | 1
2034 | Park Lane | Compass | 128 | 2016-08-05 | MANPOWER | [38 empty] | 2 |  | 3 |  | 6 |  | 10 |  | 11 |  | 11 | 10 |  | 10 |  | 8 | 6 |  | 4 |  | 3 |  | 2 |  | 3 | 2 |  | 1
2032 | Luna | Blueprint | 71 | 2016-11-01 | MANPOWER | [42 empty] | 3 |  | 3 |  | 6 |  | 8 | 5 |  | 8 |  | 6 | 6 |  | 4 |  | 2 |  | 2 |  | 1 | 1 |  | 1 | 1 | 0
2036 | Westridge | Exxel Pacific | 31 | 2016-10-01 | MANPOWER | [35 empty] | 2 | [8 empty] | 2 |  | 4 |  | 4 | 4 |  | 4 |  | 3 | 4 |  | 3 |  | 2 |  | 2 |  | 2 | 1 |  | 1 | 1 | 1 |  | 1 |  | 1
2048 | Ballinger | GRE | 72 | 2017-10-17 | MANPOWER | [56 empty] | 6 |  | 6 |  | 5 |  | 5 | 3 |  | 2 | 1 | 2 |  | 1
2047 | Greenlake | GRE | 70 | 2017-10-17 | MANPOWER | [56 empty] | 6 |  | 6 |  | 5 |  | 5 | 3 |  | 4 | 1 | 2 |  | 1
2033 | Vuecrest | Compass | 139 | 2016-09-01 | MANPOWER | [38 empty] | 2 |  | 3 |  | 5 |  | 6 |  | 8 |  | 11 | 11 |  | 10 |  | 9 | 8 |  | 8 |  | 3 |  | 3 |  | 5 | 2 |  | 1 | 1 | 3 |  | 2 |  | 1
2030 | East Union | Exxel Pacific | 144 | 2016-11-01 | MANPOWER | [44 empty] | 2 |  | 6 |  | 12 | 4 |  | 8 |  | 10 | 10 |  | 15 |  | 12 |  | 8 |  | 12 | 6 |  | 5 | 2 | 5 |  | 1 |  | 1
2038 | 2nd & John | Compass | 80 | 2017-02-17 | MANPOWER | [46 empty] | 2 |  | 2 | 3 |  | 4 |  | 1 | 2 |  | 2 |  | 2 |  | 7 |  | 8 | 10 |  | 12 | 10 | 9 |  | 4 |  | 2 | 2 | 1 | 1 |  | 1 |  | 1
2040 | Roosevelt 65th | Blueprint | 55 | 2017-03-01 | MANPOWER | [48 empty] | 2 |  |  | 3 |  |  | 2 |  | 2 |  | 2 |  | 6 |  | 5 | 5 |  | 2 | 6 | 4 |  | 4 |  | 2 | 3 | 1 | 1 |  | 1 |  | 1
2037 | University Apartments | Marpac | 122 | 2017-01-09 | MANPOWER | [48 empty] | 2 | 3 |  | 4 |  | 1 | 2 |  | 2 |  | 2 |  | 8 |  | 2 | 8 |  | 6 | 10 | 7 |  | 8 |  | 7 | 6 | 3 | 2 |  | 1 |  | 1
2042 | Metro Flats | Shelter Holdings | 75 | APR/JUN 17 | MANPOWER | [54 empty] | 2 | [5 empty] | 1 |  | 3 | 2 |  | 1 | 6 | 8 |  | 6 |  | 6 | 3 | 3 | 3 |  | 1 |  | 1 | 1 |  | 1 | 1
2043 | Aegis Mercer Island | Compass | 89 | 2017-03-01 | MANPOWER | [54 empty] | 2 | [5 empty] | 5 |  | 6 | 8 |  | 2 | 9 | 7 |  | 8 |  | 7 | 4 | 3 | 2 |  | 1 |  | 1 | 4 |  | 1 | 1
2031 | Issaquah Gateway | Exxel Pacific | 398 | 2016-08-16 | MANPOWER | [35 empty] | 3 |  |  | 5 |  | 10 |  | 7 |  | 12 |  | 12 |  | 12 | 12 |  | 12 |  | 12 | 12 |  | 8 |  | 12 |  | 12 |  | 10 | 16 |  | 23 | 20 | 15 |  | 15 |  | 8 | 10 | 8 | 3 |  | 1 |  | 1 | 2 |  | 2 | 2 | 2 |  | 1
2046 | 4218 Roosevelt | Marpac | 110 | August, 17 | MANPOWER | [62 empty] | 2 | 2 |  | 2 | 2 | 2 |  | 6 |  | 8 | 6 | 8 | 8 |  | 6 |  | 4 | 5 |  | 4 | 3 | 2 |  | 2 |  | 1
2050 | 2100 E. Madison | Compass | 50 | Winter 18 | MANPOWER | [66 empty] | 2 | 2 |  | 6 |  | 6 | 4 | 5 | 5 |  | 4 |  | 2 | 3 |  | 2 | 2 | 1 |  | 1
2044 | Roosevelt 66th | Blueprint | 78 | 2017-07-01 | MANPOWER | [63 empty] | 2 |  | 2 | 2 | 2 |  | 6 |  | 6 | 5 | 5 | 4 |  | 2 |  | 2 | 3 |  | 2 | 2 | 1 |  | 1 |  | 1
2037 | University Townhomes | Marpac | 5 |  | MANPOWER | [76 empty] | 1 |  | 0 | 0 |  | 1 | 3 | 3 |  | 3 |  | 2 |  | 1
2049 | Reserve Lynnwood Rebuild | Exxel Pacific | 296 | Summer 17 | MANPOWER | [51 empty] | 6 |  |  | 4 | [11 empty] | 3 | 1 |  | 3 |  | 10 | 10 | 10 | 10 |  | 6 |  | 5 | 8 |  | 9 | 8 | 6 |  | 3 |  | 3 |  | 2 |  | 1
2045 | GRE Notch | GRE | 158 | Summer 17 | MANPOWER | [48 empty] | 2 | [20 empty] | 2 |  | 3 | 5 | 8 | 10 |  | 10 |  | 8 | 8 |  | 9 | 7 | 5 |  | 3 |  | 2 |  | 3 |  | 3 | 3 |  | 1 |  | 1
2057 | Plaza | Natural & Built | 111 |  | MANPOWER | [72 empty] | 1 | 3 | 5 |  | 6 |  | 5 | 5 |  | 5 | 6 | 5 |  | 6 |  | 4 |  | 2 |  | 2 | 2 |  | 2 |  | 1
2041 | Luna 2749 California Ave | Chinn | 108 | Summer 17 | MANPOWER | [48 empty] | 2 | [18 empty] | 2 |  | 3 |  | 3 | 2 | 8 | 8 |  | 8 |  | 8 | 8 |  | 9 | 8 | 7 |  | 9 |  | 6 |  | 6 |  | 3 | 3 |  | 2 |  | 1
2052 | 5th & Roy | Farrell | 107 | Winter 18 | MANPOWER | [69 empty] | 2 |  | 3 | 2 | 8 | 10 |  | 10 |  | 10 | 8 |  | 8 | 8 | 7 |  | 9 |  | 6 |  | 5 |  | 3 | 3 |  | 2 |  | 1 |  | 1
2053 | Bellevue Parkside | Compass | 136 | 2018-01-01 | MANPOWER | [71 empty] | 2 | 2 | 3 | 8 |  | 10 |  | 10 | 2 |  | 8 | 9 | 10 |  | 13 |  | 13 |  | 12 |  | 8 | 7 |  | 4 |  | 4 |  | 4 | 1 | 1 | 1
2054 | Blueprint 800 5th Ave | Blueprint | 68 | 2018-03-18 | MANPOWER | [73 empty] | 1 | 2 |  | 5 |  | 5 | 1 |  | 3 | 4 | 4 |  | 5 |  | 6 |  | 5 |  | 6 | 4 |  | 5 |  | 5 |  | 3 | 2 | 2 | 1
2051 | Vail Apartments | Compass | 163 | Winter 18 | MANPOWER | [73 empty] | 1 | 5 |  | 8 |  | 10 | 2 |  | 3 | 6 | 10 |  | 7 |  | 12 |  | 14 |  | 14 | 12 |  | 6 |  | 8 |  | 4 | 3 | 3 | 1 |  | COVID | 1 | 1
2058 | Howell | Blueprint | 77 |  | MANPOWER | [78 empty] | 2 |  |  |  |  | 2 |  | 2 |  | 2 |  | 3 |  | 5 | 7 |  | 7 |  | 7 |  | 6 | 4 | 2 | 3 |  | COVID | 1 | 1 | 1 | 1 | 1 |  | 1
2059 | Meeker | GRE | 365 |  | MANPOWER | [83 empty] | 4 |  | 6 |  | 5 |  | 10 |  | 15 | 18 |  | 20 |  | 20 |  | 18 | 18 | 15 | 15 |  | COVID | 10 | 14 | 13 | 8 | 6 | 2 | 3 | 1 | 2 | 2 | 1 |  | 1 |  | 1
2056 | Acme Farms | Exxel Pacific | 321 |  | MANPOWER | [87 empty] | 1 |  | 5 |  | 5 | 5 |  | 12 |  | 13 |  | 25 | 25 | 25 | 25 |  | COVID | 12 | 16 | 15 | 11 | 5 |  | 3 |  | 5 | 2 | 1 |  | 3 |  | 1 | 1 | 1 | 1
2063 | Aria Flats | Compass | 102 |  | MANPOWER | [94 empty] | 2 |  | 3 |  | 3 | 3 | 5 | 6 |  | COVID | 6 | 7 | 8 | 9 | 11 |  | 8 |  | 7 | 5 | 3 |  | 3 |  | 2 | 2 | 1 | 1
2074 | Buddha Jewel Monastery | Marpac | n/a |  | MANPOWER | [108 empty] | 1 |  | 1 |  | 1 | 1 | 1 |  | 1 |  |  | 1 | 1 |  | 1 | 1 | 1 | 1 |  | 1
2061 | Columbia City | Exxel Pacific | 242 |  | MANPOWER | [99 empty] | 3 | 5 | 5 |  | COVID | 5 | 4 | 4 | 6 | 10 |  | 12 |  | 12 | 12 | 12 |  | 13 |  | 13 | 12 | 8 | 5 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1
2064 | Jabooda Melody | Jabooda | 186 |  | MANPOWER | [99 empty] | 2 | 5 | 5 |  | COVID | 6 | 3 | 4 | 6 | 8 |  | 11 |  | 11 | 10 | 10 |  | 10 |  | 5 | 10 | 6 | 4 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1
2066 | Fireside Flats | Compass | 102 |  | MANPOWER | [78 empty] | 2 | [35 empty] | 1 |  | 1 |  | 3 | 4 | 6 | 9 | 6 | 7 | 7 | 6 | 4 | 2 | 2 | 2 | 1
2055 | Dockside | Blueprint | 98 |  | MANPOWER | [78 empty] | 2 | [34 empty] | 1 | 2 |  | 4 |  | 5 | 2 | 7 | 7 | 6 | 5 | 5 | 4 | 3 | 2 | 1 | 2 | 1 |  | 1
2060 | Marina Square | Compass | 270 |  | MANPOWER | [89 empty] | 1 |  | 2 | 4 |  | 7 |  | 6 |  | 3 | 5 | 7 | 9 |  | COVID | HOLD | HOLD | [6 empty] | HOLD | HOLD | 3 |  | 6 |  | 6 | 5 | 6 | 8 | 11 | 8 | 9 | 8 | 6 | 8 | 5 | 4 | 4 |  | 2 |  | 1 | 1 |  | 1
2076 | Yesler Terrace Bldg B | Compass | 215 |  | MANPOWER | [113 empty] | 2 | 2 |  | 3 |  | 7 | 7 | 8 | 10 | 11 | 12 | 10 | 9 | 9 | 9 | 7 | 9 | 7 |  | 4 |  | 3 | 1 |  | 1
2075 | Everett Rockefeller | Braseth | 165 |  | MANPOWER | [118 empty] | 2 | 3 | 3 | 3 | 3 | 6 | 8 | 9 | 9 | 10 | 8 | 12 | 9 |  | 6 |  | 4 | 3 |  | 2 | 1
2069 | Theory U-District | Exxel Pacific | 171 |  | MANPOWER | [118 empty] | 2 | 5 | 6 | 8 | 5 | 10 | 15 | 15 | 15 | 14 | 10 | 11 | 9 |  | 7 |  | 6 | 5 |  | 4 | 2
2079 | Crown Hill Mixed Use | BMDC | 54 |  | MANPOWER | [119 empty] | 2 | 2 | 4 | 0 | 4 | 5 | 5 | 4 | 5 | 4 | 4 | 2 |  | 1 |  | 1 | 1 |  | 1 | 1 |  | 1
2067 | Edmonds 99 | GRE | 192 |  | MANPOWER | [118 empty] | 2 | 4 | 7 | 3 | 6 | 8 | 9 | 9 | 9 | 12 | 10 | 14 | 12 |  | 7 |  | 6 | 5 |  | 3 | 2 |  | 5
2081 | 400 Queen Anne | Compass | 143 |  | MANPOWER | [122 empty] | 2 | 2 | 2 | 4 | 8 | 6 | 9 | 14 | 14 |  | 14 |  | 10 | 7 |  | 5 | 4 |  | 4 | 3 | 1 | 1 | 1 | 1
2096 | SunDowner | Chinn | 27 |  | MANPOWER | [140 empty] | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1
2078 | 112 Lake Street | Compass | 141 |  | MANPOWER | [121 empty] | 1 | 1 | 2 | 2 | 4 | 5 | 6 | 9 | 4 | 8 |  | 12 |  | 12 | 10 |  | 8 | 7 |  | 13 | 5 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1
2071 | 1405 Dexter | Chinn | 160 |  | MANPOWER | [132 empty] | 1 |  | 2 | 3 |  | 4 | 6 |  | 7 | 9 | 9 | 10 | 10 | 12 | 8 | 5 | 3 | 2 | 1 |  | 1
2085 | Basalt | Blueprint | 77 |  | MANPOWER | [132 empty] | 2 |  | 2 | 5 |  | 5 | 5 |  | 2 | 5 | 5 | 5 | 5 | 7 | 5 | 4 | 2 | 2 | 1 |  | 2 | 1 |  | 2 | 1
2080 | Redmond Grand - Bldg B | Compass | 311 |  | MANPOWER | [132 empty] | 1 |  | 3 | 5 |  | 8 | 10 |  | 6 | 12 | 15 | 15 | 17 | 15 | 14 | 11 | 8 | 8 | 7 |  | 10 | 8 |  | 7 | 4 | 2 | 1 |  | 1
2088 | Gridline (Knights of Columbus) | SRM | 178 |  | MANPOWER | [135 empty] | 1 |  | 2 | 2 |  | 3 | 7 | 10 | 12 | 12 | 16 | 14 | 11 | 9 | 9 | 8 |  | 7 | 7 |  | 7 | 4 | 5 | 2 |  | 1
2086 | LIZA | Compass | 207 |  | MANPOWER | [132 empty] | 2 |  | 3 | 4 |  | 6 | 9 |  | 4 | 10 | 12 | 12 | 14 | 16 | 14 | 12 | 10 | 15 | 15 |  | 11 | 9 |  | 8 | 7 | 2 | 2 |  | 1 |  | 1
2082 | Northgate | GRE | 235 |  | MANPOWER | [121 empty] | 1 | 2 | 2 | 2 | 4 | 8 | 5 | 9 |  |  |  | 3 |  | 10 | 10 |  | 9 | 6 |  | 16 | 15 | 15 | 11 | 8 | 6 | 5 | 4 | 3 | 3 | 2 |  | 6 | 8 |  | 5 | 4 | 3 | 1 |  | 2 |  | 1 | 1
2090 | Chronicle | Blueprint | 78 |  | MANPOWER | [143 empty] | 1 | 2 | 2 | 4 | 4 | 4 | 4 | 6 |  | 7 | 4 |  | 4 | 5 | 3 | 3 |  | 2 |  | 2 | 2 | 1 | 1 |  | 1
2084 | Willows | GRE | 195 |  | MANPOWER | [132 empty] | 1 |  | 3 | 3 |  | 4 | 6 |  | 1 | 2 | 4 | 5 | 5 | 5 | 10 | 11 | 11 | 15 | 12 |  | 12 | 10 |  | 11 | 11 | 10 | 7 |  | 7 |  | 4 | 5 | 5 | 5 |  | 1
2077 | Shoreline | Intracorp | 299 |  | MANPOWER | [141 empty] | 2 | 2 | 1 | 2 | 2 | 4 | 7 | 8 | 8 | 13 |  | 25 | 28 |  | 27 | 21 | 22 | 19 |  | 15 |  | 8 | 5 | 4 | 6
2093 | Symphony | Jabooda | 51 |  | MANPOWER | [143 empty] | 1 | 2 |  | 1 |  | 3 | 2 | 5 |  | 6 | 2 |  | 4 | 4 | 5 | 5 |  | 7 |  | 5 | 2 | 2 | 2 |  | 2 | 1 | 1 | 1 | 1
2094 | Carrick | Blueprint | 86 |  | MANPOWER | [145 empty] | 2 | 2 | 4 | 5 | 6 | 6 |  | 6 | 3 |  | 4 | 4 | 6 | 6 |  | 6 |  | 4 | 4 | 3 | 3 |  | 3 | 2 | 1 | 1 | 1
2087 | Northgate (11201 Roosevelt) | Exxel Pacific | 295 |  | MANPOWER | [143 empty] | 2 | 2 | 2 | 3 | 5 | 7 | 4 | 8 |  | 8 | 11 |  | 11 | 18 | 23 | 23 |  | 18 |  | 18 | 15 | 12 | 8 |  | 6 | 5 | 2 | 2 | 1
2089 | 24th & Market | Holland | 238 |  | MANPOWER | [147 empty] | 2 | 2 | 4 | 5 |  | 3 | 8 |  | 12 | 15 | 21 | 22 |  | 25 |  | 24 | 16 | 15 | 12 |  | 8 | 6 | 6 | 5 | 1 | 2 | 2
2098 | Trailside 2 | Chinn | 170 |  | MANPOWER | [153 empty] | 2 |  | 3 | 5 | 3 | 10 |  | 12 |  | 22 | 24 | 31 | 28 |  | 10 | 12 | 12 | 8 | 7 | 6 | 5 | 5 | 4 | 2 | 1 | 1
2092 | Reed Apartments | Blueprint | 125 |  | MANPOWER | [146 empty] | 1 |  |  |  | 1 |  | 2 | 3 |  | 3 | 3 | 2 | 4 |  | 5 |  | 8 | 4 | 6 | 6 |  | 7 | 5 | 7 | 6 | 7 | 4 | 2 | 1 | 2 | 2 | 1 | 1
2097 | Marysville - Ph1 | Intracorp | 474 |  | MANPOWER | [160 empty] | 2 |  | 3 | 8 | 13 | 13 |  | 12 | 19 | 18 | 12 | 19 | 19 | 15 | 12 | 10 | 5 | 4 | 3
2101 | Bella on Broadway Water Repipe | F&M | na |  | MANPOWER | [163 empty] | 4 | 4
2105 | 3000 Western | Compass | 219 |  | CANCELLED
2099 | 300 W Republican | Kirtley Cole | 169 |  | MANPOWER | [165 empty] | 2 |  | 4 | 3 | 5 | 12 | 12 | 19 | 15 | 12 | 10 | 8 | 5 | 5 | 4 | 3 | 2
2104 | Big 1410 | BMDC | 24 |  | MANPOWER | [167 empty] | 2 | 2 | 2 | 3 | 4 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1
2103 | Northgate M2 | Compass | 234 |  | MANPOWER | [167 empty] | 2 | 4 | 5 | 8 | 12 | 6 | 11 | 16 | 22 | 30 | 32 | 25 | 25 | 12 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1
2107 | 68th & Roosevelt | Chinn | 244 |  | MANPOWER | [175 empty] | 3 | 4 | 3 | 8 | 8 | 15 | 18 | 18 | 18 | 16 | 16 | 14 | 12 | 10 | 8 | 6 | 5 | 4 | 3 | 2 | 1 | 1 | 1
2109 | Marysville - Ph2 | Intracorp | 246 |  | MANPOWER | [177 empty] | 3 | 6 | 13 | 18 | 18 | 18 | 18 | 23 | 20 | 18 | 15 | 10 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 2
2112 | BIG3 | BMDC | 20 |  | MANPOWER | [179 empty] | 2 | 3 | 3 | 4 | 4 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1
2111 | Northgate M3 | Compass | 186 |  | MANPOWER | [182 empty] | 2 | 3 | 6 | 10 | 12 | 18 | 25 | 25 | 22 | 15 | 13 | 12 | 11 | 10 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 1 | 1
2116 | The V Apartments | SRM | 166 |  | MANPOWER | [189 empty] | 3 | 5 | 8 | 10 | 12 | 15 | 15 | 15 | 15 | 15 | 13 | 12 | 10 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 1 | 1
2114 | Ballard Blossom | Holland | 239 |  | MANPOWER | [189 empty] | 2 | 3 | 5 | 8 | 10 | 12 | 15 | 18 | 18 | 15 | 15 | 13 | 12 | 10 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 1 | 1
2110 | Roosevelt Manor | Sierra | 137 |  | MANPOWER | [190 empty] | 2 | 3 | 5 | 8 | 10 | 12 | 15 | 15 | 15 | 15 | 15 | 13 | 12 | 10 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 1 | 1
2117 | Lachlan Apartments | Ravenna Partners | 104 |  | MANPOWER | [191 empty] | 2 | 3 | 5 | 8 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 10 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 1 | 1
2106 | 6220 Roosevelt | Chinn | 146 |  | MANPOWER | [192 empty] | 2 | 3 | 5 | 8 | 10 | 12 | 15 | 15 | 15 | 15 | 15 | 13 | 12 | 10 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 1 | 1
2115 | Elowen | Chinn | 201 |  | MANPOWER | [193 empty] | 2 | 3 | 5 | 8 | 10 | 12 | 15 | 18 | 18 | 15 | 15 | 13 | 12 | 10 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 1 | 1
2118 | Edmonds Behar | Exxel Pacific | 406 |  | MANPOWER | [193 empty] | 2 | 3 | 5 | 10 | 12 | 15 | 18 | 20 | 24 | 24 | 24 | 20 | 18 | 15 | 10 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 1
| Frank (508 Fremont) | Exxel Pacific | 169 |  | MANPOWER | [194 empty] | 2 | 3 | 5 | 8 | 10 | 12 | 15 | 18 | 18 | 15 | 15 | 13 | 12 | 10 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 1 | 1
2108 | R&G Apartments | Braseth | 263 |  | ON HOLD
| TOTAL MANPOWER | [30 empty] | #REF! |  | 19 |  | 23 |  | 34 | 34 |  | 42 |  | 36 | 37 |  | 39 |  | 45 |  | 55 |  | 70 |  | 79 | 61 |  | 69 |  | 52 | 59 |  | 61 |  | 53 |  | 67 |  | 70 | 72 |  | 65 | 77 | 72 |  | 79 |  | 76 | 65 | 79 | 87 |  | 82 |  | 77 | 60 |  | 67 | 70 | 69 |  | 71 |  | 64 |  | 69 |  | 67 | 68 |  | 70 |  | 70 |  | 67 | 66 | 70 | 71 |  | 0 | 41 | 46 | 45 | 41 | 44 |  | 40 |  | 38 | 35 | 36 |  | 45 |  | 49 | 58 | 62 | 65 | 60 | 69 | 78 | 80 | 82 | 82 | 76 | 79 | 68 |  | 64 |  | 66 | 64 |  | 63 | 61 |  | 64 | 73 | 77 | 79 | 82 | 88 | 87 | 82 | 76 | 83 | 90 |  | 106 | 104 |  | 108 | 106 | 107 | 105 |  | 104 |  | 100 | 90 | 96 | 86 |  | 58 | 59 | 59 | 58 | 65 | 61 | 55 | 51 | 56 | 56 | 52 | 52 | 55 | 53 | 52 | 52 | 51 | 55 | 55 | 52 | 51 | 50 | 48 | 46 | 45 | 51 | 62 | 75 | 86 | 102 | 110 | 115 | 120 | 124 | 125 | 114 | 103 | 91 | 80 | 67 | 53 | 43 | 35 | 28 | 22 | 16 | 11 | 7 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECTS BID
Type | Job Name | GC | Units | Project Start Date | Notes
BUDGET | 12th Place Apartments | Exxel/Compass | 274 |  | Intracorp considering buying job
BID | The Fir | Braseth | 204 |  | Per Mark Braseth on 12/3/25, this will likely be rebid summer 2026
BID | Sand Point Mixed Use | BMDC | 70 |  | Still on hold per Todd McHugh email on 11/18/25.
BID | SRM100 Apartments | SRM | 376
BID | 200 2nd Ave N | Exxel Pacific | 152 |  | Per John Hughes 6/13/25 email, we are looking good.
BID | 23rd & Holgate | BMDC | 40 |  | As of 6/11/25, on hold until interest rates come down
BID | Brizo Apartments | SRM | 220
BID | Paramount Ph2 | Corstone | 110
BUDGET | LUP Northgate | Sierra | 302 |  | Lake Union Partners
BUDGET | 12 Spruce | Exxel Pacific | 394
BID | Capitol Hill Apartments & Safeway | Compass | 290
BUDGET | 1200 116th Ave NE | Chinn | 215
BID | 30 Unit SEDU | Elite Builders | 30
BUDGET | Bothell Ridge Apartments | Compass | 126
BID | 3000 Western | Greystar | 219
BID | Filament | Holland | 294
BUDGET | Freestone | Braseth/HAL | 174
BID | 2601 Elliott | Carmel Partners | 258
BID | Jabooda Apollo Heights | Jabooda | 130
BID | Hidden Hills | Compass | 152
PROJECTS TO BID
Type | Job Name | GC | Units | Project Start Date | Notes
BID | LUP Northgate Vincent | Sierra | 302 |  | 2026-04-10
BID | Evergreen Pointe Apartments | Compass | 123 |  | 2026-04-10
BID | Anderson Apartments | Sierra | 172 |  | 2026-04-30
BID | 111th Ave NE Apartments | Gencap | 144 |  | Probably going to skip
FUTURE BIDS
Type | Job Name | GC | Units | Project Start Date | Notes
FUTURE | Continental Olive Way | Compass | ?
FUTURE | Vivo North | SRM | 168 |  | Rebid eventually?
FUTURE | Evergreen Point | Compass | 123 |  | See email - Tom Toomey
FUTURE | Bel-Red TOD | Compass | 184 |  | See email - Tom Toomey
FUTURE | Mt Baker TOD | Compass | 408 |  | See email - Tom Toomey
FUTURE | Sammamish Towncenter - Pillar Properties | Compass | 264 |  | See email - Nick Cunningham
FUTURE | Tacoma project | Chinn | ?
FUTURE | Overlake South Block 5 | Chinn/Exxel | 470
FUTURE | 3000 Western | Compass | 219
FUTURE | Shoreline 185 | Braseth | 197 |  | On 12/3/25, Mark Braseth said this would be coming back out to bid in first half of 2026

## Job Info
| Job Name | GC | Units | Original Contract |  | Contract w/ CO's |  | Franklin Costs to date | As-Bid Eng Budget | Frank Cost/unit | Insurance Type | GC PM | GC Sup | GC PE | Developer | Architect | Structural | Acoustical | ADA Consultant | Interior Design | Engineer | Levels Above | Levels Below | Concrete | Wood
|  |  |  | Total | Per unit | Total | Per Unit
2001 | 230 Broadway | SRM | 234 | 2026045.65 | 8658.3147 | 2121873.5 | 9067.8355 | 21979 | 30000 | 93.9274 | [5 empty] | Runberg
2002 | Wedgewood | Exxel Pacific | 91 | 879530 | 9665.1648 | 864597 | 9501.0659 | 10520 | 25000 | 115.6044
2003 | Evanston Space | Exxel Pacific | 5 |  | 0 |  | 0 | 8475 |  | 302.6786
2005 | Indigo/Kavela | Chinn | 66 | 501500 | 7598.4848 | 499368 | 7566.1818 | 13668 | 18000 | 207.0909 | [5 empty] | Johnson Architecture and Planning |  |  |  |  | Rushing
2006 | Bella Lago | ICC | 319 |  | 0 |  | 0 | 30611 |  | 95.9592
2008 | 101 Taylor | SRM | 258 |  | 0 |  | 0 | 56506 |  | 219.0155 |  |  |  | A.J. Haviland |  | Runberg |  |  |  |  | Rushing
2009 | Greenwood | Chinn | 56 | 384900 | 6873.2143 | 392855 | 7015.2679 | 4895 | 5000 | 87.4107 | [5 empty] | Studio Meng Strazzara
2010 | Old Town | Chinn | 149 | 1469800 | 9864.4295 | 1386419 | 9304.8255 | 10463 | 20000 | 70.2215 | [5 empty] | Weber Thompson | [5 empty] | 8
2011 | Barrett Park | Chinn | 117 | 813050 | 6949.1453 | 869823.5 | 7434.3889 | 12487 | 25000 | 106.7265 | [5 empty] | Studio Meng Strazzara |  |  |  |  | Rushing
2012 | 8th Ave | Exxel Pacific | 162 | 1394655 | 8608.9815 | 1393316 | 8600.716 | 15613 |  | 96.3765 | [5 empty] | NK |  |  |  |  | Pressler
2013 | NE 63rd | Exxel Pacific | 112 | 959780 | 8569.4643 | 966156 | 8626.3929 | 18532 | 25000 | 165.4643 |  |  |  |  | Intra-Corp | Runberg |  |  |  |  | Pressler | 6 | 1 | 2 | 5
2018 | Astro | SRM | 211 | 2499584.97 | 11846.3743 | 2524038.49 | 11962.2677 | 24000 |  | 113.7441 |  | Eric Petersen | John Schwab / James Wilkins | Andrew Withnell | SRM | Runberg | DCI Engineers | SSA Acoustics |  |  | Pressler | 6 | 2 | 3 | 5
2017 | 36 Stone | Exxel Pacific | 119 | 1373148 | 11539.0588 | 1365227 | 11472.4958 | 18000 |  | 151.2605 |  | Tyson Scheenstra / Tommy Booth | Brad Carpenter | Tommy Booth | Mack Urban | Baylis | CPL | SSA Acoustics | Karen Braitmayer | ObjectSpace | Rushing | 4 | 1 | 1 | 4
2022 | Interlake | Exxel Pacific | 18 | 232454 | 12914.1111 | 242637 | 13479.8333 | 4757 |  | 264.2778 |  | Tommy Booth | Brad Carpenter | Garret Olsen | Mack Urban | Nicholson Kovalchick | Michael Nouwens |  |  |  |  | 3 | 0 | 0 | 3
2015 | Rooster | Exxel Pacific | 197 | 1935285 | 9823.7817 | 2045883 | 10385.1929 | 48000 |  | 243.6548 | Not Wrap | John Hughes | Nick Amaya | Ben Prigmore / Mason Seto | Lake Union Partners | Weinstein AU | CPL | SSA Acoustics | Endelman & Associates |  | Rushing | 7 | 2 | 4 | 5
2014 | Pike Motorworks | Exxel Pacific | 241 | 2661895 | 11045.2075 |  | 0 | 65000 | 70000 | 251.938 | Wrap | Dave Biasini / Josh Purefoy | Jeff Christiansen / Bill Armstrong | Brett Johnston / Ben McCarty | The Wolff Company | Weber Thompson | CPL |  | theACCESSpartnership | Weber Thompson / Graham Baba | Ecotope | 7 | 3 | 5 | 5
2020 | Bellevue Main | SRM | 256 | 3415305 | 13341.0352 |  | 0 | NA |  | NA | Not Wrap | Todd Rankin / Erik Benzel | Bill Robinson / Jared Osborn | Renay Luzama | Pillar Properties / SRM | Benson & Bohl | DCI Engineers | SSA Acoustics |  |  | Pressler | 5 | 2 | 3 | 4
2019 | 8th Republic | Exxel Pacific | 211 | 2721210 | 12896.7299 |  | 0 | 70000 |  | 331.7536 | Wrap | Dave Biasini / Brian Christensen | Dan Phillips / Todd Tradal | Joel Palmer / Sam Bernoski | The Wolff Company | Runberg - Interior Miller Hull - Exterior | CPL | SSA Acoustics | theACCESSpartnership | Lair Design | Rushing | 8 | 2 | 10 | 0
2024 | Merrill Gardens | SRM | 104 | 1763480 | 16956.5385 |  | 0 | NA |  | #VALUE! | Not Wrap | Bill Robinson | James Wilkins | Ben Robles | Merrill Gardens / Pillar Properties | Urbal Architecture | DCI Engineers | SSA Acoustics |  | NAC Architecture | Abossein | 7 | 1 | 3 | 5
2021 | Admiral | Exxel Pacific | 136 | 1558650 | 11460.6618 |  | 0 | 53260 |  | 391.6176 | Wrap | Victor Vo / Justin Ripkin | Scott Weston / Nic Christoffer | Justin Ripkin | Intra-Corp | Nicholson Kovalchick | Panos (Yu & Troch..) | SSA Acoustics | Karen Braitmayer | ObjectSpace | Pressler | 5 | 1 | 2 | 4
2023 | Hadley | Chinn | 209 | 2469500 | 11815.7895 |  | 0 | 28144 |  | 134.6603 | Not Wrap | Charlie Poggemann | Mark Pesanti / Sim Mooers | Lauren Bjorndahl | Legacy Partners | VIA Architecture | Panos (Yu & Troch..) | JGL Acoustics | Karen Braitmayer | Robin Chell Design | Rushing | 6 | 1 | 3 | 4
2028 | Reserve @ Lynnwood | Exxel Pacific | 296 | 2979880 | 10067.1622 |  | 0 | 20233 |  | 68.3547 | Not Wrap | TJ Mellema / Coby Jones | Brad Holz |  | AVS Communities | Charles Morgan & Associates, LLC |  |  |  |  | N/A | 5 | 1 | 1 | 5
2027 | 550 Broadway | Exxel Pacific | 170 | 2230810 | 13122.4118 | 2275444 | 13384.9647 | 39854 |  | 234.4353 | Wrap | Justin Gotcher / Chris Austin | Brian Proctor | Chris Austin | Intra-Corp | Nicholson Kovalchick |  |  |  |  | Pressler
2026 | Boren (Fox & Finch) | Synnergy | 49 | 825370 | 16844.2857 |  | 0 | 17344 |  | 353.9592 | Not Wrap | Matt Stewart / Ron Auld / Jamie Creek | Aaron Steinke | Michele Lee
2025 | The Cora | Exxel Pacific | 75 | 1179300 | 15724 | 1202633 | 16035.1067 | 27970 |  | 372.9333 | Not Wrap | Victor Vo / Ben Prigmore | Tim Conner | Jola Bielecki | Barrientos, LLC
2029 | Parsonage | Exxel Pacific | 83 | 1113220 | 13412.2892 | 1129452 | 13607.8554 | 20121 |  | 242.4217 | Not Wrap | Victor Vo / Ben Prigmore | Bill Armstrong | Mason Seto
2030 | East Union | Exxel Pacific | 144 | 2135080 | 14826.9444 | 2322781 | 16130.4236 |  |  | 0 | Not Wrap | Coby Jones | Steve Booth | Matt Anderson | Lake Union Partners
2031 | Issaquah Gateway (Anthology) | Exxel Pacific | 398 | 5051600 | 12692.4623 | 5187754 | 13034.5578 |  |  |  | Not Wrap | Ben McCarty/Tim Spink | Dennis Schlosser | Connor Jungkuntz | Wolff | Weinstein AU
2032 | Luna | Blueprint | 71 | 685300 | 9652.1127 | 726903 | 10238.0704 |  |  |  | Not Wrap | Andrew Withnell | Scott McSpadden
2033 | Vuecrest (LUX) | Compass | 137 | 2447600 | 17865.6934 | 2286188 | 16687.5036 |  |  | 0 | Wrap | Ryan Ames/Vince Dennison | Todd Mortenson | Dan Peck | Continental
2034 | Park Lane (VODA) | Compass | 128 | 1784000 | 13937.5 | 1842651 | 14395.7109 |  |  | 0 | Wrap | Frank Weaver | Mike Horgan | Kait O'Neill | Continental | Johnson Braund | Yu & Trochalakis |  |  | Sechrist Design
2035 | 162 Ten | Natural & Built | 97 | 717400 | 7395.8763 | 722900 | 7452.5773 |  |  | 0 | Not Wrap | Tyson Cornett
2036 | Westridge | Exxel Pacific | 31 | 388515 | 12532.7419 | 418677 | 13505.7097 |  |  | 0 | Not Wrap | David Strid | Shon Geer | Jose Tapia
2037 | University Apartments (MYSA) | Marpac | 122 | 1920850 | 15744.6721 | 2076783 | 17022.8115 |  |  | 0 | Not Wrap | Evan Chan | Doyle Gustafson
2038 | 2nd & John | Compass | 80 | 1175378 | 14692.225 | 1195660 | 14945.75 |  |  |  | Wrap | Justin Anderson | Kurt Weagant | Karl Clocksin | Continental
2039 | Ravello Gas Piping | Shelter Holdings | na | 54900 | [6 empty] | Not Wrap | Renay Luzama | Bill Robinson
2040 | Brooklyn 65 | Blueprint | 55 | 604000 | 10981.8182 | 624171 | 11348.5636 |  |  |  | Not Wrap | Andrew Withnell | Mike Sanderson | Kyle Stenson
2041 | Luna | Chinn | 108 | 1766205 | 16353.75 | 1878824 | 17396.5185 |  |  |  | Not Wrap | Joe Hanley | James Casal | Amir Molavi
2042 | Metro Line Flats | Shelter Holdings | 72 | 906587 | 12591.4861 | 922362 | 12810.5833 |  |  |  | Not Wrap | Renay Luzama | Bill Robinson | Shonna Hiatt | Shelter Holdings
2043 | Aegis Mercer Island | Compass | 98 | 1576200 | 16083.6735 | 1583445 | 16157.602 |  |  |  | Not Wrap | Howard Jacobsen | Ryan O'Connell | Alina Lutenco | Aegis
2044 | Track 66 | Blueprint | 75 | 832900 | 11105.3333 | 855264 | 11403.52 |  |  |  | Not Wrap | Andrew Withnell | Scott McSpadden / Stefan Fjeldsted | Kyle Stenson | Blueprint
2045 | Notch Apartments | GRE | 158 | 1898200 | 12013.9241 | 2110205 | 13355.7278 |  |  |  | Not Wrap | Gavin Erickson / Christian Knorr / Jin Lee | Jason Hill | Michelle Deng
2046 | 4218 Roosevelt (Sundodger) | Marpac | 110 | 1648500 | 14986.3636 | 1721867 | 15653.3364 |  |  |  | Not Wrap | Pat Nakamura | Todd Weeks | Joey Mar
2047 | Greenlake (Crew) | GRE | 70 | 475800 | 6797.1429 | 553189 | 7902.7 |  |  |  | Not Wrap | Victor Vo | John Bolle | Astra Persue / Titus Uomoto
2048 | Ballinger (The 205) | GRE | 72 | 498700 | 6926.3889 | 517068 | 7181.5 |  |  |  | Not Wrap | Victor Vo | Dan Schaeffer | Astra Persue / Titus Uomoto
2049 | Lynnwood Reserve Rebuild | Exxel Pacific | 296 | 2588665 | 8745.4899 | 2689426 | 9085.8986 |  |  |  | Not Wrap | Coby Jones | Martin Solorio | ? | Reserve
2050 | 2100 Madison (Avant) | Compass | 50 | 897800 | 17956 | 918566 | 18371.32 |  |  |  | Not Wrap | Scott Miller | Pat McCabe | Steve Garka
2051 | Vail Apartments | Compass | 163 | 2672000 | 16392.638 | [5 empty] | Not Wrap | Justin Anderson | Will Fenton | Jeff Seeb | AAA Management
2052 | 5th & Roy | F&M | 107 | 2134000 | 19943.9252 | [5 empty] | Not Wrap | Sean McKenna | Scott Weston | Michael McKenna | Farrel McKenna
2053 | Bellevue Parkside | Compass | 135 | 2241309 | 16602.2889 | [5 empty] | Wrap | Dan Peck | Todd Mortenson | Jacob Jeske | Continental
2054 | 800 5th | Blueprint | 63 | 785600 | 12469.8413 | [5 empty] | Not Wrap | Andrew Withnell | Bill Shore | Stefan Fjeldsted | Blueprint
2055 | Dockside | Blueprint | 98 | 1293342 | 13197.3673 | [5 empty] | Not Wrap
2056 | Acme Farms | Exxel Pacific | 321 | 5877400 | 18309.6573 | [5 empty] | Wrap | Josh Purefoy / Steven Hall | Kyle Harmia | Kenji Norwood | Intra-Corp
2057 | Kirkland Plaza | Natural & Built | 111 | 1098897 | 9899.973 | [5 empty] | Not Wrap | Tyson Cornett | Don Cunningham | na | Natural & Built
2058 | Howell | Blueprint | 76 | 928800 | 12221.0526 | [5 empty] | Not Wrap | Andrew Withnell | Scott McSpadden / Stefan Fjeldsted | Kyle Stenson | Blueprint
2059 | Meeker | GRE | 365 | 4378750 | 11996.5753 | [5 empty] | Not Wrap | Victor Vo | Kirk Swenson / Dan Schaeffer / Brad Carpenter / Scott Messer | Titus Uomoto | GRE
2060 | Marina Square | Compass | 270 | 5307510 | 19657.4444 | [5 empty] | Not Wrap | Rich Swedstedt / Ryan Ames | Bill Christopherson / Richard Moore | Derya O'Rourke / Alina Lutenco | Sound West Group | Encore
2061 | Columbia City | Exxel Pacific | 242 | 4305550 | 17791.5289 | [5 empty] | Wrap | Brian Christensen / Zachary Vandiver | Tim Conner | Armando Espinosa
2062 | Origin 206 | Marpac | Cancelled | [7 empty] | Not Wrap
2063 | Aria Flats | Compass | 102 | 1535729 | 15056.1667 | [5 empty] | Wrap | Daniel Marks / Matt Johnson | Scott Donder | Qasim Gill
2064 | Jabooda Melody | Jabooda | 186 | 2952000 | 15870.9677 | [5 empty] | Not Wrap | Kaitlyn Huynh | Patrick Fischer
2065 | Flag Lot | Holland | Cancelled
2066 | Fireside Flats | Compass | 102 | 1565600 | 15349.0196 | [6 empty] | Jeff Seeb | Taylor Turay | Kait O'neal
2067 | Edmonds 99 | GRE | 192 | 2485780 | 12946.7708 | [6 empty] | Rob Kralis | Paul Mandish | Ben Lek
2068 | Alloy | Schuchart | Cancelled
2069 | Theory U-District | Exxel Pacific | 171 | 3872036 | 22643.4854 | [6 empty] | Brian Christensen/Matt Sims | Bill Armstrong | Bill Levison
2070 | Beacon Crossing | Chinn | Cancelled |  | #VALUE!
2071 | 1405 Dexter | Chinn | 160 | 2966700 | 18541.875 | [6 empty] | Danny Fletcher | Joe Vasey | Mike McClure
2072 | 56th Ballard | Exxel Pacific | Cancelled
2073 | 57th Ballard | Exxel Pacific | Cancelled
2074 | Buddha Jewel Monastery | Marpac | NA | 333600 | [7 empty] | Michelle Ip | Jeff Fogarty | Joey Mar / Maggie Cheng
2075 | Everett Rockefeller | Braseth | 165 | 2387900 | 14472.1212 | [6 empty] | Tyler Mitchell / Mark Braseth Jr. | Kawika Takasaki | Ken Tews / Kevin Mullen
2076 | Yesler Terrace Phase 2 | Compass | 215 | 3112600 | 14477.2093 | [6 empty] | Scott Miller / Justin Anderson / Brian Welsh | Will Fenton / Brandon Houghton | Chris Waters
2077 | Shoreline 147th | Intracorp | 299 | 5560950 | 18598.495 | [6 empty] | Tod Werner / | Jim Arnett / Lars Swenson / Chris Jones | Thomas Detrick / Kyle Skow
2078 | 112 Lake Street | Compass | 141 | 2711810 | 19232.695 | [6 empty] | Dan Peck / Howard Jacobsen | Todd Mortensen / Kenis Loven | Bridget Elliott / Kay Stertz
2079 | Crown Hill | BMDC | 54 | 992600 | 18381.4815 | [6 empty] | Wayd Munro / Tim Kairez | Ricky Pulley | Grace Peterson
2080 | Redmond Grand | Compass | 311 | 5848945 | 18806.8971 | [6 empty] | Nick Cunningham | Chris Auld / Nate Happenstall / David Ottolino | Derek Uchiumi / Logan Brooks / Oleg Chebotarev / Brittany Duhs
2081 | 400 Queen Anne | Compass | 143 | 2409160 | 16847.2727 | [6 empty] | Dan Peck / Frank Weaver | Csaba Orban | Daniel Burdick
2082 | Northgate Phase 2 | GRE | 235 | 3417420 | 14542.2128 | [6 empty] | Ken James / Gavin Erickson | Jeff Gerde / Jason Hill | Caitlin Supe
2083 | Bellevue Plaza | Compass | 312 |  | 0
2084 | Willows | GRE | 195 | 3398000 | 17425.641 | [6 empty] | Jin Lee | Richard Erickson | Jesse Dehnert
2085 | Basalt | Blueprint | 77 | 1288000 | 16727.2727
2086 | LIZA | Compass | 207 | 5369136 | 25937.8551 | [6 empty] | Gary Moss | Gino Cecsarini | Jordan Dye
2087 | Northgate (11201 Roosevelt) | Exxel Pacific | 295 | 5566100 | 18868.1356 | [6 empty] | Steven Hall | Nic Christoffer | Reed Servizi / Brett Johnston
2088 | Gridline | SRM | 178 | 4093785 | 22998.7921 | [6 empty] | Bill Robinson / Danielle Locklar | James Wilkins | Christian Dobbins / Jyoti Bhadrashetti
2089 | 24th & Market | Holland | 238 | 6052169 | 25429.2815 | [6 empty] | Drew Shemchuck / David Vo / Elizabeth Roberts | Seth Andersson / Charles "Casey" Dean | Tony Sippl / Ashley Roman
2090 | Chronicle | Blueprint | 78 | 1455000 | 18653.8462
2091 | GRE U-District Remodel | GRE | NA | 51144
2092 | Reed Apartments | Blueprint | 125 | 2456100 | 19648.8
2093 | 4221 37th Ave S | Jabooda | 51 | 1051120 | 20610.1961 | [6 empty] | Kaitlyn Huynh | Patrick Fischer
2094 | Carrick | Blueprint | 86 | 1689000 | 19639.5349
2095 | Josephine South | StoryBuilt | Cancelled
2096 | SunDowner | Chinn | 27 | 448000 | 16592.5926 | [7 empty] | Tim Brennan
2097 | Marysville | Intracorp | 228 | 5135097 | 22522.3553
2098 | Trailside 2 | Chinn | 170 | 6885880 | 40505.1765 | [6 empty] | Joe Hanley | Noel Baca | Bonnie Laremore Brennan / Mike McClure
2099 | KOZ on 3rd Ave West | Kirtley Cole | 169 | 2950000 | 17455.6213 | [6 empty] | Edgar Delgado / Corey Toepfer | Nick Mosteller
2100 | The Fir | Braseth | 204 |  | 0
2101 | Bella on Broadway Repipe | F&M | NA | 167100
2102 | 2621 Eastlake | Blueprint | 54 |  | 0
2103 | Northgate M2 | Compass | 234 | 6030791 | 25772.6111
2104 | Big 1410 | BMDC | 24
2105 | 3000 Western | Compass | 219
Note on J9: Richard Donelson: Increased to $6,000 somewhere during the project.
Note on J18: Richard Donelson: Possibly decreased to $60,000?

## Projects Bid
Job # | Job Name | OWP Bid Date | GC | Units | Base Bid | Price/unit | Owner | Architect | Engineer | Area | Start Date | General Schedule | Competitor | Competitor Bid? | Competitor | Competitor Bid? | Competitor | Competitor Bid? | Notes
BID | Block 11 | 2016-01-22 | Exxel Pacific | 386 | 6599000 | 17095.8549 | Vulcan | Runberg | Ecotope | South Lake Union | 2016-08-31 | 22 Months | Wolfe Plumbing |  | Ocean Park |  | PSF Mechanical
BID | 44th Ave SW Apartments | 2016-01-27 | Blueprint | 58 | 569000 | 9810.3448 | Blueprint | Cone | N/A | West Seattle | Spring 2016 | ~16 Months | DK Plumbing? | Think it was $412,000 |  |  |  |  | Mike Burdo sent Exh B on the following project that was put out to bid. On it there was the $412,000, which we think was for this project.
BID | East Union | 2016-01-22 | Exxel Pacific | 144 | 2063000 | 14326.3889 | Lake Union Partners | Weinstein A+U | Rushing | Madrona | Summer 2016 | 18 Months | Wolfe Plumbing | Approx $2,013,000 | Atlas Plumbing | Don't know
BID | Boylston Flats | 2016-02-19 | W.G. Clark | 107 | 1025000 | 9579.4393 | Johnson-Carr | S+H Works | N/A | Capitol Hill | 2016-05-01 | 15 Months
BID | Issaquah Gateway (SEE 2ND BID) | 2016-02-26 | Exxel Pacific | 398 | 4919200 | 12359.799 | Wolff Company | VIA | Glumac | Issaquah | Summer 2016 | 27 Months
BID | 66th & Roosevelt | 2016-03-15 | Exxel Pacific | 206 | 2996000 | 14543.6893 | HB Management | Weinstein A+U |  | Roosevelt
BID | 6505 15th Ave NE | 2016-03-15 | Exxel Pacific | 222 | 3343000 | 15058.5586 | Roosevelt Development Group | GGLO | PAE | Roosevelt
BID | 103rd Avenue Apartments | 2016-04-05 | Chinn | 162 | 2867000 | 17697.5309 | Shintex Global Holdings, LLC | GGLO | Rushing | Downtown Bellevue |  |  | SJS Mechanical | 2650000 | Transit | Even less than SJS, but Chinn went with SJS
BID | Ravelo Apartments | 2016-04-26 | Shelter Holdings | 102 | 1465800 | 14370.5882 | Shelter Holdings | SMR Architects | Sider+Byers | Redmond | 2016-07-01 | ~16 Months | Sunrise Plumbing? |  | Peltram | ~$160k lower
BID | Lake City Apartments | 2016-05-06 | Marpac | 122 | 1793000 | 14696.7213 |  | Studio19 Architects | N/A | Lake City | 2016-12-01
BID | Vuecrest Apartments | 2016-05-17 | Compass | 139 | 2419000 | 17402.8777 | Continental Properties | Encore Architects | Emerald City | Downtown Bellevue | 2016-07-16 | ~23 Months | Aloisio Plumbing | Don't know yet, but we are low so far. Update 5/17/16, Dan Peck told me Alosio was 5% low.
BID | 6921 Roosevelt Way NE | 2016-05-18 | Blueprint | 71 | 662800 | 9335.2113 | Blueprint | Cone | N/A | Roosevelt | 2016-11-01 |  | Tri-State | Mike said the bids were so close they were almost matching
BID | Capitol Hill Lofts | 2016-05-24 | Marpac | 55 | 891000 | 16200 | Vestus | NK Architects | N/A | Capitol Hill | Late 2016/early 17 |  | Wolfe Plumbing originally bid it but pulled their number, so no competition |  |  |  | Transit | Within $60k | Put bid in, he said we got it, then called back two weeks later and said that Transit got it. Classic case of us giving them a number and then they turn it over to Transit.
BID | Issaquah Gateway 2nd Time | 2016-06-02 | Exxel Pacific | 398 | 5049100 | 12686.1809 | Wolff Company | VIA | Glumac | Issaquah | Summer 2016 | 27 Months | Wolfe & Bigfoot possibly bid the mid-rise buildings, but sounds like no bidders on walk ups
BID | Park Lane Apartments | 2016-06-13 | Compass | 128 | 1839000 | 14367.1875 | Continental Properties | Johnson Braund | Emerald City | Kirkland | 2016-08-01 | 21 Months | SJS Mechanical | "Very close" | JD Plumbing
BID | Issaquah Senior Housing | 2016-06-13 | Exxel Pacific | 146 | 2249000 | 15404.1096 | Wolff Company | VIA | N/A | Issaquah | ? | ? | Bulldog | 2055000 |  |  |  |  | Bid to Halvorson, EP and Chinn
BID | 2nd & John | 2016-07-14 | Compass | 80 | 1179000 | 14737.5 | Continental Properties | Baylis | Emerald City | Capitol Hill | 2016-09-01 | ~16 Months
BID | 162 Ten | 2016-07-25 | Natural&Built | 96 | 698400 | 7275 | Natural & Built | Milbrandt Architects | Pressler | Redmond
BID | Cannery | 2016-08-25 | Exxel Pacific | 54 | 916400 | 16970.3704 | Barrientos | Hewitt | Rushing Narrative | Pioneer Square | Summer 2017
BID | Jefferson Park Apartments | 2016-10-19 | Marpac | 49 | 822000 | 16775.5102 |  | Encore Architects |  | International District | Not Sure | Not sure | Bulldog (got it) | 700000 | Tri-State (pulled) | 586000 | Transit | 930000
BID | Aegis Mercer Island | 2016-11-08 | Compass | 89 | 1481800 | 16649.4382 | Aegis | Ankrom Moisan | Coffman | Mercer Island
BID | NE 65th Street | 2016-11-16 | Blueprint | 55 | 604000 | 10981.8182 | Blueprint | Cone | N/A | Roosevelt | Summer 2017
BID | NE 66th Street | 2016-11-16 | Blueprint | 78 | 839500 | 10762.8205 | Blueprint | Cone | N/A | Roosevelt | Summer 2017 | [7 empty] | Per conversation with Andrew on 11/30, he is probably giving us this job, but the 65th will probably go to the same plumber that did the west seattle job
BID | Issaquah Senior Housing | 2016-11-30 | Exxel Pacific | 146 | 2369000 | 16226.0274 | Wolff Company | VIA | Glumac | Issaquah | 2016-12-01 | ? | Aloisio Plumbing | 2150000 | Transit | 2350000 | Wolff ended up getting this one |  | Glumac had drawings this time
BID | 403 Dexter | 2016-12-13 | Synnergy | 98 | 1542000 | 15734.6939 | Wilshire | VIA | Glumac | South Lake Union | ? | ?
BID | Issaquah Apartments | 2016-12-22 | Exxel Pacific | 110 | 1809400 | 16449.0909 | American Classic Homes | Group Architect | Ecotope | Issaquah | ?? | ?? | Edmonds Plumbing | 1388500 | United Plumbing | Not sure. Was told that Owner wants to work with United, and they have a relationship. They were cheaper too.
BID | Greenwood Apartments | 2017-01-19 | Rush Commerical | 85 | 1817800 | 21385.8824 | Greenwood Ave Investors | Encore Architects | Rushing | Greenwood | March, 2017 | 14 months | Dave Anderson provided a list of plumbing bidders, it was very long and very commercial
BID | Maple Leaf Flats Greenlake | 2017-02-03 | Charter | 42 | 724400 | 17247.619 | Flatiron Properties | Johnston Architects | Sider+Byers | Greenlake | July, 2017 | 13 months
FYI | Harbor Avenue | NA | Chinn | 15 | NA | NA |  |  |  | West Seattle |  |  | SJS Mechanical | 921000 |  |  |  |  | Charlie asked us to look at it but hadn't realized that it was already committed to SJS. Would have been a good job.
BID | 4218 Roosevelt | 2017-03-30 | Chinn | 110 | 1485200 | 13501.8182 | G&K Brothers, Inc. | Studio19 | Coffman? | University District | ??? | ???
BID | Bear Creek Apartments | 2017-04-07 | Fairfield | 360 | 5430700 | 15085.2778 | Fairfield Residential | ARK Architects | Interface Engineering | Redmond | Summer 17 | Long time | SJS Mechanical |  | LOST TO JET INDUSTRIES BY 5 OR 6% |  |  |  | I thought that Ocean Park and Allied Plumbing had submitted bids, but according to Justin with Fiarfield, they did not.
BID | 4218 Roosevelt | 2017-05-08 | Marpac | 110 | 1648500 | 14986.3636 | G&K Brothers, Inc. | Studio19 | Coffman? | University District | Late August 17 | ??? | SJS Mechanical | [5 empty] | Originally bid to Chinn. Owner re-bid it to Marpac. Chinn told us we were 20% low, so we raised our number to Marpac.
BID | Aegis Overlake | 2017-05-18 | Compass | 118 | 3210500 | 27207.6271 | Aegis | Ankrom Moisan | Coffman | Bellevue |  |  | Compass turned this project down. Exxel Pacific picked it up. Wolff got it for around $23k to $24k per unit.
BID | Metro Flats | 2017-05-30 | Shelter Holdings | 72 | 934800 | 12983.3333 | Shelter Holdings | Johnston Architects | N/A | First Hill | ? | ?
BID | Auburn Town Center Apartments | 2017-06-06 | Compass | 205 | 3209000 | 15653.6585 | Merrill Gardens | Urbal Architecture | N/A | Auburn | ? | ? | [6 empty] | BUDGET PRICING ONLY
BID | Bellevue Parkside | 2017-06-22 | Compass | 136 | 2592500 | 19062.5 | Continental Properties | Encore Architects | Emerald City | Bellevue | Q1 2018 | ? | Tri-State |  | SJS
BID | Bellevue Parkside Rebid | 2018-01-26 | Compass | 136 | 2302500 | 16930.1471 | Continental Properties | Encore Architects | Emerald City | Bellevue | Q1 2018 | ? | Tri-State |  | SJS
BID | Columbia City Apartments | 2017-06-26 | Exxel Pacific | 242 | 3974000 | 16421.4876 | Lake Union Partners | Weinstein A+U | Rushing | Columbia City | ? | ?
NO BID | 23rd & Jackson | na | Exxel Pacific | 532 |  |  | Vulcan |  | Ecotope |  |  |  | Hawk Mechanical got it, per Steve Sharrat
BID | 225 Roy | 2017-09-01 | Exxel Pacific | 269 | 5379300 | 19997.3978 | Barrientos | GGLO | Rushing | Queen Anne | Q2 2018 | 23 months | Wolff got it. |  | Trademark Plbg |  | JH Kelly |  | Wolff got it for about $800,000 less than our price.
BID | 98th Ave Apartments | 2017-09-15 | Compass | 79 | 1342000 | 16987.3418 | Harbour Homes | Group Architect | Emerald City | Bothell | 2018-02-01 | ? | SJS Mechanical
BID | 98th Ave Apartments Rebid | 2018-02-15 | Compass | 79 | 1477000 | 18696.2025 | Harbour Homes | Group Architect | Emerald City | Bothell | 2018-04-01 | ? | SJS Mechanical? | [5 empty] | Compass did not get this project, it went to High Country
BID | South Bayview | 2017-09-21 | Compass | 67 | 1189500 | 17753.7313 | Pacific Housing NW | Weinstein A+U | Ecotope | Beacon Hill | ? | ? | [6 empty] | As of 1/26/19, owner is still having permitting issues. Per conversation with Reid Bullock in October 2019, we were not low. Low bidder was at $15k/unit.
BID | Yoshikawa Mixed Use | 2017-10-16 | Marpac | 24 | 758900 | 31620.8333 | Yoshikawa Family | Roger H. Newell | N/A | Magnolia | ? | ? | Per Steve Sharratt, Kimco plumbing bid this back in July
BID | Interbay Apartments | 2017-11-03 | Graham | 93 | 1552600 | 16694.6237 | Pastakia Associates | Urbal Architecture | N/A | Interbay | 2018-04-01 | ? | [6 empty] | Rushing was on this, got kicked off
BID | Avalon North Creek | 2017-11-17 | Avalon | 316 | 4710000 | 14905.0633 | Avalon Residential | Rutledge Maul Architects | N/A | Mill Creek | 2018-01-01 | Long time | Andgar? | [5 empty] | Per email from John Jaeger 1/18/18, we were within 5% of the top 3 plumbers. We did not get it.
BUDGET | Vail Apartments | 2017-11-22 | Compass | 163 | 2738000 | 16797.546 | Zion Realty USA | JRA Architects | DC Engineering? | Shoreline | ? | ?
BUDGET | 2100 E. Madison | 2017-11-28 | Compass | 50 | 897800 | 17956 | JCMV LLC | Weinstein A+U | N/A | Capitol Hill | ? | ?
BID | 800 5th Ave | 2017-11-29 | Blueprint | 68 | 785600 | 11552.9412 | Blueprint | S+H Works | N/A | Queen Anne | ? | ?
BID | Totem Lake Apartments |  | Lennar |  | Decided not to bid |  | Lennar | [5 empty] | Peltram
BID | Legacy West Seattle | 2018-01-11 | Compass | 308 | 5469500 | 17758.1169 | Legacy Partners | Encore Architects | Rushing | West Seattle | ? | ?
BID | The Village | 2018-01-30 | Compass | 104 | 1598800 | 15373.0769 | Redmond Village Holdings | Veer Architecture | Abossein | Redmond |  |  | Atlas plumbing, per Steve Sharratt |  | Per conversation with Allan on 4/12/18, Tri-state got it, was $200k lower
BID | ACME Farms | 2018-01-31 | Exxel & Venture | 321 | 5759300 | 17941.7445 | Intracorp | Tiscarano Associates | N/A | International District | End of 2018 |  | Possibly SJS. Steve said the job was quoted on 8/25/17 to Keller and Consolidated.
BID | U-Place | 2018-02-06 | Marpac | 243 | 4045200 | 16646.9136 | University Place WA | DLR Group | DLR Group | U-Village | Spring 2018 | ?
BID | Merrill Gardens Renton | 2018-02-27 | SRM | 52 | 997500 | 19182.6923 | Merrill Gardens | Urbal Architecture | na | Renton | ?
BID | Plaza Kirkland | 2018-03-02 | Natural&Built | 107 | 1128800 | 10549.5327 | Natural & Built | Designs Northwest Architects | Pressler | Kirkland | ?
BID | Triton Court Apartments |  |  |  |  | #DIV/0! | [12 empty] | Dad talked to Reid on 6/29/18, Compass is still proposing to the Owner. He made it sound like they wouldn't know until labor day. The excavation isn't right either, so there's more work that needs to be done there.
BID | Marina Square | 2018-06-29 | Compass | 266 | 5278000 | 19842.1053 | [6 empty] | Herdman Plumbing | [5 empty] | Brent told dad he was $400k or $500k high to Herdman Plumbing
BID | North State Street Apartments | 2018-07-20 | Exxel Pacific | 161 | 3572000 | 22186.3354 | [6 empty] | Andgar |  | Lost to Wolff
BUDGET | Auburn Town Center Apartments | 2018-07-26 | Compass | 226 | 4746000 | 21000 | Teutsch / Pillar | Urbal Architecture | N/A | Auburn | ? | ? | I GAVE A BUDGET OF $20K TO $21K PER UNIT | [5 empty] | I was told by Nick Cunningham with Compass that they gave a verbal committmet to Tri-State for this job. I got a follow up email from Nick on 12/18/18 that said Tri-State was over $2,000,000 lower than us. So that would be somewhere around $10,000/unit.
BID | Shoreline Apartments | 2018-08-06 | Exxel Pacific | 122 | 2186000 | 17918.0328 | Evergreen Point Redmond | Caron | Sider Byers | Shoreline
BUDGET | 12th & Yesler | 2018-08-07 | Compass | 296 | 6216000 | 21000 | Centric Partners, LLC | Nicholson Kovalchick | N/A | Yesler | ? | ? | I GAVE A BUDGET OF $20K TO $21K PER UNIT | [5 empty] | Owner did not go through with purchase of this property.
BUDGET | Canyon Park Apartments | 2018-09-06 | Compass | 461 | 8528500 | 18500 | ? |  |  | Canyon Park | [8 empty] | Compass is still waiting to hear from the Owner as of 1/26/19
BUDGET | Othello Square Condos | 2018-09-07 | Marpac | 68 | 1632000 | 24000 | [12 empty] | Heat pump water heaters, very different system. Owner decided in May 2019 to switch the project to prevailing wage, so we backed out of it. Got a call from DM Kelly estimator asking questions about it.
BID | Alloy Apartments | 2019-10-04 | PSW | 155 | 3006200 | 19394.8387 | PSW | Johnston Architects | Sider Byers | Central District
BUDGET | BIG-1 Bell-Red Road | 2018-11-09 | Compass | 160 | 3120000 | 19500 | BIG 1 LLC | Encore Architects | na | Bellevue |  |  | I GAVE A BUDGET OF $18.5K TO $19.5K PER UNIT |  |  |  | Tri-State per Steve Sharrat |  | Per email from Ryan Ames on 5/9/19: "For Big 1, LLC we ended up awarding to Tristate, they provided a budget that was 35% lower than your number and their credit for ABS in lieu of Cast was 30% more. Tristate has successfully completed many projects for us, and the Sr. PM was confident that their number was complete. "
BID | 1200 NE 50th St Apartments | 2018-11-15 | Fairbank Construction | 49 | 887000 | 18102.0408 | BonaFide Ventures | Weinstein A+U | na | University District
BUDGET | Yesler Terrace | 2018-11-30 | Compass | 548 | 10686000 | 19500 | Seattle Tench, LLC | Ankrom Moisan | None Listed | Yesler |  |  | I GAVE A BUDGET OF $19.5K TO $20.5K PER UNIT | [5 empty] | Lost it, not sure who to.
BUDGET | CRUX 19022 Aurora |  | Compass |  |  |  |  | Clark Barnes | [10 empty] | This project went to someone else, not Compass
BID | Spuds Greenlake | 2018-12-28 | Blueprint | 61 | 795900 | 13047.541 | Blueprint | Cone Architecture | na | Greenlake
BID | Rhythm Apartments | 2019-01-02 | Chinn | 127 | 1943400 | 15302.3622 | Yuans H & H Properties | d/Arch LLC | Emerald City | University District | [8 empty] | Venture sent an invitation to bid on this project on 8/30/19.
BID | Pike & Pine Manor | 2019-01-11 | Chinn | 53 | 746500 | 14084.9057 | Xue Wei Investments | Caron | Sider Byers | Capitol Hill | Summer 2019 | [7 empty] | The Owner decided not to proceed with this project.
BID | 417 2nd Ave Apartments | 2019-01-21 | Schuchart | 95 | 2078400 | 21877.8947 | Hycroft Investment Inc | Johnston Architects | Sider Byers
BID | Alderwood South Apartments | 2019-01-24 | Compass | 240 | 3042000 | 12675 | Wolff | Katerra | Katerra | Lynnwood |  |  | Tri-State | [5 empty] | Compass told me that they were high to Synergy Construction and
BID | Crown Hill | 2019-01-31 | Braseth | 54 | 1135400 | 21025.9259 | Braseth | Johnston Architects | Sider Byers | Crown Hill | [8 empty] | On hold.
BID | Paradise Lake | 2019-02-21 | Compass | 360 | 4760000 | 13222.2222 | Wolff | Katerra | Katerra | Maltby | [8 empty] | Per conversation with Reid Bullock in October 2019, we were low on this job. The only other bid was $3.5mil higher.
BID | Columbia City Condos | 2019-02-22 | Schuchart | 155 | 3040800 | 19618.0645 | Storybuilt (PSW) | Johnston Architects | na | Columbia City
BID | Rivertrail Apartments | 2019-02-26 | Mill Creek | 233 | 3727200 | 15996.5665 | Mill Creek | GGLO | N/A | Redmond | [8 empty] | Mill Creek said they had several bidders, and that I was in the middle of the pack. The bids varied by several hundred 100k's.
BID | Legends of Everett | 2019-03-27 | Exxel Pacific | 320 | 4122000 | 12881.25 | Dominium | BCRA | ? | Everett | ? |  | Wolff got it. | 4107000 | Trademark Plbg | 3707000 |  |  | Craig tell me Wolff’s base bid was $4,107,000. OWP base bid was $4,122,000. Craig claims there was no other reason other than the low number for Wolff to get the project. Breaks down to high by $46.88 per unit. Trademark Plumbing was over $400,000 low on the project and after some questions from Craig, they withdrew their bid.
BID | Redmond Flats | 2019-04-01 | Compass | 102 | 1821000 | 17852.9412 | Tejal Pastakia | Encore Architects | Glumac | Redmond |  |  | JD got it, probably 100k beneath us |  | Atlas walked away |  | Priority, Compass wouldn't use |  | Compass gave us a second look at this but we still lost it.
BID | 206 Place Condos | 2019-04-17 | Marpac | 65 | 1293000 | 19892.3077 | Doug Mar | Hewitt | Tres West BOD | Pioneer Square |  |  | We were high to Bulldog Plumbing, but Will Ng walked us into the number
BID | Scout Apartments | 2019-04-18 | Compass | 59 | 1474000 | 24983.0508 | Kim Faust, George John | Dahlin Group | HV Engineering | Kirkland | [8 empty] | Owner decided not to proceed with this project.
BID | Redmond Flats - 2nd Bid | 2019-05-24 | Compass | 102 | 1753000 | 17186.2745 | Tejal Pastakia | Encore Architects | Glumac | Redmond |  |  | JD got it, probably 100k beneath us |  | Atlas walked away |  | Priority, Compass wouldn't use |  | Compass gave us a second look at this but we still lost it.
BID | 206 Place Condos - 2ND BID | 2019-06-04 | Marpac | 65 | 1185300 | 18235.3846 | Doug Mar | Hewitt | Tres West BOD | Pioneer Square | 43770
BID | 8105 Greenwood | 2019-06-17 | Blueprint | 66 | 863500 | 13083.3333 | Blueprint | [11 empty] | Project is being sold to another developer.
BUDGET | Overlake Place Parcel A (Seritage Place) | 2019-07-15 | Compass | 442 | 7381400 | 16700 | Mack Urban | GGLO | Rusing | Redmond (Old Sears lot) | [8 empty] | Per Dan Peck email 9/9/19, "Just got word that the developer went another direction"
BUDGET | Edmonds Senior Living | 2019-08-01 | Compass | 126 | 2470800 | 19609.5238 | CA Ventures | Ankrom Moisan | DC Engineers | Edmonds
BID | Edmonds 99 | 2019-08-30 | GRE | 192 | 2371900 | 12353.6458 | GRE | Studio Meng Strazzara | na | Edmonds
BUDGET | 12th & Yesler | 2019-09-20 | W.G. Clark | 269 | 4694000 | 17449.8141 | Centric Partners | Clark Barnes | na | Yesler | [8 empty] | Per email from Jason on 9/20/19, we were 16% high to one other bidder. Found out on 9/24/19 from Geoff Wood of Proctor Sales that Wolff was the other bidder.
BID | Mira Apartments | 2019-09-26 | Farrell McKenna | 112 | 1130700 | 10095.5357 | Redpoint Development Group | Ross Deckman & Associates | N/A | Burien | [8 empty] | Not proceeding because of federal funding.
BID | 1200 NE 50th St Apartments | 2019-10-09 | Marpac | 49 | 874800 | 17853.0612 | Bonafide Ventures | Weinstein A+U | na | University District
BID | Mira Apartments - 2nd Bid | 2019-10-31 | Farrell McKenna | 112 | 1151400 | 10280.3571 | Redpoint Development Group | Ross Deckman & Associates | N/A | Burien | [8 empty] | Not proceeding because of federal funding.
BUDGET | 112 Lake Street | 2019-10-29 | Compass | 142 | 2734000 | 19253.5211 | Continental Properties | Encore | na | Kirkland
BID | Reserve at Arlington | 2019-10-30 | Exxel Pacific | 150 | 1466000 | 9773.3333 | Reserve | Tiscarano Associates | Windsor | Arlington |  |  | West Coast | 1115000 | Andgar | 1115000 | Wolff | 1420000 | Coby gave us all the numbers from this bid, see to the left. West Coast plumbing has 18 L&I violations.
BUDGET | Hilltop | 2019-11-05 | Chinn | 68 | 1199500 | 17639.7059 | Hunters Capital | Studio Meng Strazzara | na | Capitol Hill | [8 empty] | Charlie says we came in second, but the bottom bidder was missing something. There were a total of 4 bids. The one higher than us was only half a percent above us.
BUDGET | Brooklyn Ave | 2020-11-13 | Chinn | 186 | 5529000 | 29725.8065 | Fields Holdings | Jackson Main | na | University District
BID | 2517 Eastlake | 2019-11-20 | Exxel Pacific | 183 | 3596000 | 19650.2732 | Washington Holdings | Hewitt | Rushing | Eastlake
BID | Fireside Flats | 2019-11-20 | Compass | 102 | 1734000 | 17000 | Tejal Pastakia | Encore | na | Roosevelt
BUDGET | Auburn Divine Court | 2019-11-22 | Chinn | 98 | 1599000 | 16316.3265 | MSRE Apartment | Benny Kim | Robison Engineering | Auburn
BID | Shelter Tacoma | 2019-12-05 | Chinn | 131 | 2118000 | 16167.9389 | Shelter Homes? | Christopher Jones |  | Tacoma | [8 empty] | Charlie says we came in third, but the bottom 2 bidders were missing things. One was missing design. He couldn't remember what the other was missing.
BUDGET | Block 56 North | 2019-12-05 | Compass | 144 | 2295000 | 15937.5 | Vulcan | Ankrom Moisan | na | South Lake Union
BID | Jabooda Melody | 2019-12-11 | Jabooda | 186 | 2952000 | 15870.9677 | Jabooda Homes | MAS Architecture | na | South Seattle | Now | [7 empty] | Best Bath had originally budgeted this, but couldn't fit it in.
BID | Dexter Flag Lot | 2019-12-17 | Holland | 85 | 1348500 | 15864.7059 | Holland | Weber Thompson | Rushing | South Lake Union
BUDGET | 1405 Dexter | 2019-12-23 | Schuchart | 169 | 2395000 | 14171.5976 | Intracorp | NK Architects | na | South Lake Union
BUDGET | Beacon Hill Mixed Use TOD | 2020-01-02 | Chinn | 106 | 1710000 | 16132.0755 | Scott McDonald, Adam Greisz? | Lemons Architecture | na | Beacon Hill
BUDGET | Redmond Square | 2020-01-10 | Chinn | 615 | 10885500 | 17700 | Legacy Partners | Katerra/Tiscareno | na | Redmond
BUDGET | Vail Two | 2020-01-22 | Compass | 215 | 3269500 | 15206.9767 | AAA Management | Carrier Johnson Cultur3 | na | Shoreline
BID | Edmonds 99 - 2nd bid | 2020-01-24 | GRE | 192 | 2418700 | 12597.3958 | GRE | Studio Meng Strazzara | na | Edmonds
BID | Ballard Yard | 2020-02-19 | Carmel Partners | 171 | 3084000 | 18035.0877 | Carmel Partners | VIA | Harris Group | Ballard |  |  | JD got it. Was 7.5% low to us.
BID | South Bayview | 2020-02-21 | Chinn | 67 | 1190000 | 17761.194 | Pacific Housing NW | Weinstein A+U | Ecotope? | Beacon Hill
BUDGET | Evergreen Pointe Student Housing | 2020-02-28 | Compass | 109 | 2119000 | 19440.367 | Sound West Group | Veer Architecture | na | Bremerton |  |  | Didn't get it. Was 12 to 15% high, according to Rich. They're using a plumber that's local to the peninsula.
BID | Northgate Phase 2 Apartments | 2020-03-11 | GRE | 235 | 3192400 | 13584.6809 | GRE | Group Architect | na | Northgate
BUDGET | Queen Anne Safeway Mixed Use | 2020-03-23 | Exxel Pacific | 323 | 6215000 | 19241.4861 | Barrientos | Runberg | Interface Engineering | Queen Anne | Didn't get it.
BID | Riverfront Building B | 2020-03-30 | Shelter Holdings | 172 | 3298000 | 19174.4186 | Shelter Holdings | SMR Architects | Glumac | Everett
BID | Fireside Flats | 2020-03-30 | Chinn | 102 | 1739000 | 17049.0196 | Tejal Pastakia | Encore | na | Roosevelt
BID | Vail Two | 2020-04-06 | GenCap | 215 | 3269500 | 15206.9767 | AAA Management | Carrier Johnson Cultur3 | Windsor Engineers | Shoreline | Didn't get it per email from Bo O-Shea. Was 3rd out of 4 bidders. Won't give any info.
BID | 100 Roy Street | 2020-04-10 | Compass | 167 | 2789000 | 16700.5988 | Continental Properties | Johnson Braund | Emerald City | Queen Anne
BUDGET | Interbay Apartments | 2020-05-13 | GenCap | 168 | 2753000 | 16386.9048 | AAA Management | Clark Barnes | N/A | Interbay
BUDGET | Northgate Redevelopment | 2020-05-15 | Compass | 414 | 8485000 | 20495.1691 | Simon Property Group | GGLO | Ecotope | Northgate
BUDGET | Knights of Columbus North Bldg | 2020-05-21 | SRM Development | 129 | 2059000 | 15961.2403 | SRM Development | Runberg | Emerald City | Capitol Hill
BID | Ballard Saratoga - 57th | 2020-06-01 | Exxel Pacific | 80 | 1352800 | 16910 | Saratoga Capital | GGLO | N/A | Ballard
BID | Ballard Saratoga - 56th | 2020-06-01 | Exxel Pacific | 51 | 912400 | 17890.1961 | Saratoga Capital | GGLO | N/A | Ballard
BID | Ethos Phase 2 | 2020-06-03 | FNW | 204 | 2659000 | 13034.3137 | FNW | Studio Meng Strazzara | Emerald City | Kent
BID | Block 56 North | 2020-07-10 | Exxel Pacific | 143 | 3269000 | 22860.1399 | Vulcan | Ankrom Moisan | Rushing | South Lake Union | [8 empty] | Per Chris Austin email on 9/2, we were 8% high. They went with another plumber.
BID | Yesler Terrace Bldg B | 2020-07-10 | Compass | 215 | 3359000 | 15623.2558 | Loews | Ankrom Moisan | SJS/Robison | Yesler | Tri-State is competition. SJS has job, we are trying to take it from them. See bid sheet and emails for more notes.
BUDGET | Roosevelt (Northgate) | 2020-07-24 | Kirtley Cole | 295 | 5174000 | 17538.9831 | Intracorp | Studio Meng Strazzara | N/A | Northgate
BID | 112 Lake Street | 2020-07-24 | Compass | 140 | 2659000 | 18992.8571 | Continental Properties | Encore | Emerald City | Kirkland
BID | Everett Rockefeller | 2020-07-30 | Braseth | 165 | 2459000 | 14903.0303 | Trent Development | Clark Barnes | Windsor Engineers | Everett
BID | Riverfront Building B - 2ND BID | 2020-08-26 | Shelter Holdings | 172 | 3338000 | 19406.9767 | Shelter Holdings | SMR Architects | Glumac | Everett
BUDGET | Harmony | 2020-09-16 | Natural&Built | 99 | 1415700 | 14300 | Natural & Built | Designs Northwest Architects | Pressler | Redmond
BUDGET | Alexan Alderwood | 2020-09-17 | Compass | 384 | 5081000 | 13231.7708 | Trammel Crow | Strouse Davis | Windsor | Lynnwood
BUDGET | Ballard Hub | 2020-09-23 | Compass | 210 | 3499000 | 16661.9048 | Wang Brothers | Bumgardner | Emerald City | Ballard
BID | 112 Lake Street | 2020-10-02 | Compass | 140 | 2968000 | 21200 | Continental Properties | Encore | Emerald City | Kirkland
BID | 400 Queen Anne | 2020-10-23 | Compass | 143 | 2469000 | 17265.7343 | Continental | Group Architect | Emerald City | Queen Anne
BID | Auburn Divine Court | 2020-10-28 | Chinn | 98 | 1747000 | 17826.5306 | MSRE Apartment | Benny Kim | Robinson | Auburn | Charlie said that SJS was competition on the last bid. He said my number was fine. It looks like a nasty job so my number went up.
BUDGET | Shoreline Place Block D | 2020-10-30 | Compass | 391 | 8206000 | 20987.2123 | Pillar Properties | Urbal Arch | NA | Shoreline
BUDGET | Redmond Square Bldg B | 2020-11-05 | Compass | 311 | 5441000 | 17495.1768 | Legacy Partners | Tiscareno | Emerald City | Redmond | Tri-State is competition
BID | Corner 63 | 2020-11-16 | Chinn | 139 | 2769000 | 19920.8633 | Trammel Crow | B+H | Emerald City | Roosevelt | I think SJS
BUDGET | Bellevue Station | 2020-11-18 | Compass | 292 | 5498000 | 18828.7671 | Legacy Partners | Encore | NA | Bellevue | Tri-State is competition
BUDGET | 1700 21st Ave | 2020-12-02 | Compass | 158 | 3137000 | 19854.4304 | Lake Union Partners | Public47 | Emerald City | South Seattle
BUDGET | Basalt (4401 42nd Ave SW) | 2020-12-08 | Blueprint | 77 | 1225000 | 15909.0909 | Blueprint | Cone | NA | West Seattle
BUDGET | Ballard Hub | 2020-12-11 | Chinn | 210 | 3677000 | 17509.5238 | Wang Brothers | Bumgardner | Emerald City | Ballard
BID | Roosevelt (Northgate) | 2021-02-12 | Kirtley Cole & Exxel Pacific | 295 | 5258000 | 17823.7288 | Intracorp | Studio Meng Strazzara | N/A | Northgate
BID | Seatac Multifamily | 2021-02-15 | Braseth | 108 | 1889000 | 17490.7407 | Trent Development | Clark Barnes | Windsor | Seatac | Per Ben Laws, this project was given to Rush Commercial
BID | 2nd & Bell | 2021-02-26 | Exxel Pacific | 175 | 3698000 | 21131.4286 | Paragon Real Estate | Ankrom Moisan | Rushing | Belltown | We were 10% higher than Wolfe, according to Tommy Booth. Trademark also bid it and was lower than us.
BID | Bellevue Station 2nd Bid | 2021-02-26 | Compass | 292 | 5696000 | 19506.8493 | Legacy Partners | Encore | Emerald City | Bellevue | Tri-State is competition
BID | Shoreline 147 | 2021-02-26 | Intracorp | 299 | 4825500 | 16138.796 | Intracorp | Milbrandt Architects | NA | Shoreline
BUDGET | Bellevue Plaza | 2021-03-17 | Compass | 312 | 6027000 | 19317.3077 | Pastakia Associates | Encore | NA | Bellevue
BUDGET | 1700 21st Ave | 2021-03-19 | Braseth | 158 | 3222000 | 20392.4051 | Lake Union Partners | Public47 | Emerald City | South Seattle
BID | Redmond Square Bldg B | 2021-04-01 | Compass | 311 | 5475000 | 17604.5016 | Legacy Partners | Tiscareno | Emerald City | Redmond | Tri-State & Atlas Plumbing is competition
BID | Knights of Columbus | 2021-06-08 | SRM Development | 178 | 3777000 | 21219.1011 | SRM Development | Runberg | Emerald City | Capitol Hill
BID | Harmony | 2021-08-10 | Natural&Built | 99 | 1435000 | 14494.9495 | Natural & Built | CDA + Pirscher Architects | Pressler | Redmond
BUDGET | Ballard 24th & Market | 2021-08-13 | Holland | 238 | 5450000 | 22899.1597 | Holland | Carrier Johnson Cultur3 | N/A | Ballard
BID | 1700 21st Ave | 2021-08-13 | Braseth | 158 | 3289000 | 20816.4557 | Lake Union Partners | Public47 | Emerald City | South Seattle
BUDGET | 2501 Market | 2021-08-31 | Chinn | 112 | 2912000 | 26000 | J Selig Real Estate | Mithun | na | Ballard
BUDGET | 149th Shoreline | 2021-09-03 | Compass | 252 | 5160000 | 20476.1905 | AAA Management | Urbal Architecture | Robison Engineering | Shoreline | AAA management decided to use Petra Construction.
BUDGET | HB Roosevelt 1A/1B | 2021-09-10 | Exxel Pacific | 275 | 6397000 | 23261.8182 | HB Management | Ankrom Moisan | Ecotope | Roosevelt | Per Tommy Booth, I was 9% high to Wolfe. He said that Wolfe may be too busy to take it on, so was going to keep in touch with me.
BUDGET | 1145 Market | 2021-09-17 | Chinn | 122 | 2929000 | 24008.1967 | J Selig Real Estate | Mithun | na | Ballard
BUDGET | Rainier & Genesee | 2021-09-29 | BMDC | 226 | 5150000 | 22787.6106 | Lake Union Partners | Skb Architects | Emerald City | South Seattle
BUDGET | Redmond Goodyear | 2021-10-07 | GRE | 134 | 2608000 | 19462.6866 | GRE | Group Architect | na | Redmond
BUDGET | 517 East Pike Street | 2021-10-12 | Exxel Pacific | 92 | 2170000 | 23586.9565 | Hunters Capital | Studio Meng Strazzara | Emerald City | Capitol Hill
BID | Knights of Columbus | 2021-10-12 | SRM Development | 178 | 3941000 | 22140.4494 | SRM Development | Runberg | Emerald City | Capitol Hill
BID | Shoreline 147 | 2021-10-15 | Intracorp | 299 | 5568600 | 18624.0803 | Intracorp | Milbrandt Architects | NA | Shoreline
FAKE | 21 Boston | 2021-10-20 | Compass | 325 | 8395000 | 25830.7692 | Barrientos | Runberg | HV Engineering | Queen Anne
BUDGET | Bellevue Plaza | 2021-12-08 | Compass | 312 | 6386400 | 20469.2308 | Pastakia Associates | Encore | na | Bellevue
BID | Intracorp Northgate | 2021-12-14 | Exxel Pacific | 295 | 5989000 | 20301.6949 | Intracorp | Studio Meng Strazzara | na | Northgate
BID | Beacon Crossing | 2021-12-16 | Chinn | 103 | 2174500 | 21111.6505 | Early Edge Services? | Tiscareno | na | Beacon Hill
BID | Chronicle | 2021-12-22 | Blueprint | 78 | 1455000 | 18653.8462 | Blueprint | Cone | na | Wallingford
BID | Seatac Apartments | 2022-01-10 | Chinn | 182 | 3345700 | 18382.967 | Lou Development | Studio19 | na | Seatac
BID | Origin 206 | 2022-01-17 | Edge Developers | 66 | 1457000 | 22075.7576 | Edge Developers | Hewitt | na | South Seattle | Per Steve Sharratt on 6/8/22, this project went to JJ Plumbing.
BID | Knights of Columbus | 2022-01-25 | SRM | 178 | 4049320 | 22748.9888 | SRM Development | Runberg | Emerald City | Capitol Hill
BID | Midvale Village | 2022-01-28 | ACG Builds | 210 | 3966400 | 18887.619 | Northlake Capital | Studio Meng Strazzara | Emerald City | Shoreline | Prokash plumbing was around $16,000 per unit and was still high
BUDGET | Juanita Kirkland | 2022-02-04 | Compass | 583 | 13600000 | 23327.6158 | Lowe | Encore | na | Juanita
BID | 100 Roy Street | 2022-02-16 | Compass | 167 | 4069000 | 24365.2695 | Continental Properties | Johnson Braund | Emerald City | Queen Anne | Lost this project to JJ plumbing.
BID | Vivo Queen Anne North | 2022-03-16 | SRM | 168 | 4763000 | 28351.1905 | SRM Development & Gary Merlino | Runberg | Emerald City | Queen Anne | 30% high to Best Plumbing
BID | AMLI Redmond | 2022-03-22 | Rafn | 376 | 9980000 | 26542.5532 | AMLI | Solomon Cordwell Buenz | Glumac | Redmond | JD and 1 other were competition. They were in $7m range, I was around $10m.
BID | 523 Hilltop | 2022-03-22 | Exxel Pacific | 68 | 1722000 | 25323.5294 | Hunters Capital | Studio Meng Strazzara | Emerald City | Capitol Hill
BID | Vivo Queen Anne South | 2022-04-08 | SRM | 113 | 3321000 | 29389.3805 | SRM | Runberg | Emerald City | Queen Anne | 30% high to Best Plumbing
BID | Eastlake Lago | 2022-04-12 | Compass | 93 | 2078000 | 22344.086 | Pastakia Associates | Urbal | HV Engineering | Eastlake
BID | Ballard 24th & Market | 2022-04-18 | Holland | 238 | 5852000 | 24588.2353 | Holland | Carrier Johnson Cultur3 | N/A | Ballard
BID | Eastlake Lago | 2022-04-19 | Chinn | 93 | 2078000 | 22344.086 | Pastakia Associates | Urbal | HV Engineering | Eastlake
BID | Reed Apartments | 2022-04-19 | Blueprint | 125 | 2483000 | 19864 | Blueprint | Cone | na | Wallingford
BID | Harmony | 2022-04-29 | Natural&Built | 99 | 1739000 | 17565.6566 | Natural & Built | CDA + Pirscher Architects | Pressler | Redmond
BID | 164th St Apartments | 2022-05-03 | Exxel Pacific | 326 | 7191400 | 22059.5092 | Grand Peaks Properties | Tiscareno | Windsor | Lynnwood
BID | Eastlake Lago | 2022-05-16 | Compass | 93 | 2078000 | 22344.086 | Pastakia Associates | Urbal | HV Engineering | Eastlake
BID | Candela (Mill Stream MLT Phase 1) | 2022-05-26 | Exxel Pacific | 424 | 9251000 | 21818.3962 | Skipstonesea | Runberg | Windsor | Mountlake Terrace
BID | Market | 2022-06-01 | Blueprint | 86 | 1689000 | 19639.5349 | Blueprint | Blueprint | na | Ballard
BID | 4221 37th Ave S | 2022-06-24 | Jabooda | 51 | 998500 | 19578.4314 | Jabooda Homes | MAS Architecture | na | South Seattle
BUDGET | Chambers | 2022-07-08 | Holland | 225 | 5849000 | 25995.5556 | Holland | MZA Architecture | na | Bellevue
BID | Park 5 Apartments | 2022-08-04 | High Country | 69 | 1687000 | 24449.2754 | Zarnoor Associates | Group Architect | Emerald City | Renton | Best Plumbing | 1360000 | Peltram | 1420000
BID | SunDowner | 2022-08-19 | Chinn | 27 | 448000 | 16592.5926 | Kevin Chinn | Johnson Oaklief | na | Wallingford
BID | Highland Park | 2022-09-01 | Exxel Pacific | 397 | 9728000 | 24503.7783 | Summerhill Communities | Runberg | Emerald City | Bellevue | Steve Sharratt says Wolfe is bidding it. Mike Moore said Ocean Park was looking at it. Per Matt Sims conversation on 12/16/22, we are within 5% of the low number. It's going to be rebid in February 2023, project will start in summer 2023.
BUDGET | Alta North City | 2022-10-14 | Wood Partners | 228 | 5588000 | 24508.7719 | Wood Partners | Urbal Architecture | Emerald City | Shoreline
BUDGET | 2621 Eastlake Ave E | 2022-10-17 | Blueprint | 54 | 1275000 | 23611.1111 | Blueprint | Blueprint | na | Eastlake
BUDGET | Alta Meridian Park | 2022-10-18 | Wood Partners | 357 | 8648000 | 24224.0896 | Wood Partners | Clark Barnes | Robison Engineering | Shoreline | Talked w/ Rick on 3/13, project is on hold, looking for investors. Travis said on 11/28/23 that it is on indefinite hold.
BID | Ori Roosevelt | 2022-10-20 | Schuchart | 81 | 2188000 | 27012.3457 | Onelin | Hewitt | na | Roosevelt | Per Schuchart email on 12/12/22, Schuchart did not get the job. Not sure who did.
BID | Ori Roosevelt | 2022-10-20 | Chinn | 81 | 2188000 | 27012.3457 | Onelin | Hewitt | na | Roosevelt
BID | 68th & Roosevelt | 2022-10-21 | Chinn | 244 | 5844000 | 23950.8197 | High Street (Trammell Crow) | Weinstein A+U | Emerald City | Roosevelt
BID | Candela (Mill Stream MLT Phase 1) | 2022-10-27 | Exxel Pacific | 425 | 9488000 | 22324.7059 | Mill Stream Properties | Runberg | Windsor | Mountlake Terrace | Did not get, per email from Will Wharton on 1/10/23. Was not low, but was competitive.
BUDGET | The M Apartments | 2022-10-28 | Compass | 210 | 4165000 | 19833.3333 | Caspian LLC | Ecco Design | na | Lake City | Compass did not get it. Owner was expecting the price to be 40% lower. See email from Reid Bullock 1/30/23
BUDGET | Parkshore Juanita Bay Senior Living | 2022-11-15 | SRM | 51 | 2548000 | 49960.7843 | Transforming Age | VIA | Rushing | Juanita | SRM did not get it. Rebid to Exxel Pacific.
BID | Trailside 2 | 2022-11-22 | Chinn | 170 | 6714000 | 39494.1176 | Phoenix Property Co | Weber Thompson | Rushing | U-Village
BUDGET | Euclid Union | 2022-11-30 | Compass | 139 | 3450000 | 24820.1439 | T.J. Lehman | Board & Vellum | Staengl Engineering | Capitol Hill
BID | Seatac Amelia | 2022-12-02 | Braseth | 108 | 2498000 | 23129.6296 | Trent Development | Clark Barnes | Robison Engineering | Seatac | Burk Mechanical | 1895000
BID | Marysville | 2022-12-16 | Intracorp | 474 | 10422514 | 21988.4262 | Intracorp | BCRA | na | Marysville
BID | Redmond 87 (Goodyear) | 2022-12-30 | GRE | 134 | 2778000 | 20731.3433 | GRE | Group Architect | na | Redmond | No competition, per Steve Sharratt
BUDGET | Cascade Yard | 2023-01-06 | Compass | 752 | 18700000 | 24867.0213 | Touchstone (URG) | Runberg | na | Bellevue
BID | 5th Ave Apartments | 2023-01-24 | Exxel Pacific | 295 | 7058000 | 23925.4237 | Grand Peaks Properties | Tiscareno | Windsor | Shoreline | No competition, per Steve Sharratt. Per Exxel, there were 2 other bidders. We were 9% high. They went with someone else.
BUDGET | Bellevue Main | 2023-01-27 | Holland | 360 | 9650000 | 26805.5556 | Holland | Weber Thompson | na | Bellevue | Per Nick Hoffman phone call on 6/19/23, they had to pull the plug on this job. Holland said it made sense to do the project, but their equity partner pulled out of it.
BID | Redmond 87 (Goodyear) | 2023-02-28 | GRE | 139 | 2826000 | 20330.9353 | GRE | Group Architect | na | Redmond
BID | Jabooda 2101 S Salon | 2023-03-03 | Jabooda | na | 405000 | na | Jabooda Homes | Catch Design Studio | Linda Burman | South Seattle | none? Maybe Tran's plumbing?
BID | Parkshore Juanita Bay Senior Living | 2023-03-13 | Exxel Pacific | 51 | 2228000 | 43686.2745 | Transforming Age | VIA | Rushing | Kirkland | Wolfe & Atlas. See bid sheet. Tommy is probably going to use Atlas plumbing.
BID | Eastlake Lago | 2023-03-22 | Compass | 93 | 2040000 | 21935.4839 | Pastakia Associates | Urbal | HV Engineering | Eastlake | Per Brian with Compass, they are still $2mil over budget on the project. May have to pass on the project.
BID | Alta North City | 2023-03-27 | Wood Partners | 230 | 5518000 | 23991.3043 | Wood Partners | Urbal Architecture | Emerald City | Shoreline | Wolfe & Artemis Plumbing. Brian said Artimus is very concerning low - $1mil under our number. He said us and Wolfe were right next to each other.
BID | KOZ 300 West Republican | 2023-03-30 | Kirtley-Cole | 169 | 3328000 | 19692.3077 | KOZ Development | Koz Architecture | Emerald City | Queen Anne | Trademark per Steve
BUDGET | 68th & Roosevelt | 2023-04-06 | Chinn | 244 | 6038000 | 24745.9016 | High Street (Trammell Crow) | Weinstein A+U | Emerald City | Roosevelt | Don't think anyone is competition. Charlie said this is just a budget update. Joe Hanley provided an update on 11/28/23, owner is still trying to find financing.
BUDGET | The Wave at Rucker Ave | 2023-04-12 | Chinn/Compass | 104 | 2368000 | 22769.2308 | Pastakia Associates | Urbal Architecture | na | Everett
BID | KOZ 300 West Republican rebid | 2023-04-19 | Kirtley-Cole | 169 | 3198000 | 18923.0769 | KOZ Development | Koz Architecture | Emerald City | Queen Anne | Trademark per Steve. Kirtley Cole says there are 5 total bidders.
BUDGET | Covington Commons | 2023-05-04 | Holland | 256 | 7300000 | 28515.625 | Holland | Graves & Associates | Emerald City | Covington | Brett said that Holland said this project was dead. They mentioned it at the subcontractor meeting that Brett went to.
BUDGET | 508 Fremont | 2023-05-10 | Exxel Pacific | 169 | 4700000 | 27810.6509 | Prometheus Real Estate | MG2 Architecture | Emerald City | Fremont
BUDGET | Sola Apartments | 2023-05-12 | GenCap | 71 | 2090000 | 29436.6197 | GranCorp | Jensen Design | Rushing | Eastlake
BID | Highland Park | 2023-05-23 | Exxel Pacific | 397 | 9128000 | 22992.4433 | Summerhill Communities | Runberg | Emerald City | Bellevue
BID | Marysville Clubhouse | 2023-05-24 | Intracorp | na | na |  | Intracorp | BCRA | na | Marysville
BID | Fremont 65 | 2023-05-26 | Compass | 65 | 1688000 | 25969.2308 | Infinity Investment Group | MZA Architecture | Robison Engineering | Fremont
BID | Fremont 65 | 2023-05-26 | ACG Builds | 65 | 1708000 | 26276.9231 | Infinity Investment Group | MZA Architecture | Robison Engineering | Fremont
BID | The Fir | 2023-06-07 | Braseth | 204 | 4178000 | 20480.3922 | Kamiak | Public47 | Robison/Wolfe | South Seattle | Wolfe & SJS are competition. Ben said my number was the winning number when I turned it in.
BID | 2621 Eastlake Ave E | 2023-06-09 | Blueprint | 54 | 1224000 | 22666.6667 | Blueprint | Blueprint | na | Eastlake | Per Andrews email on 6/19/23, they are not proceeding with this project. Not sure why.
BID | Bellevue Plaza | 2023-06-15 | Compass | 312 | 6722300 | 21545.8333 | Pastakia Associates | Encore | na | Bellevue | No competition per Dan Peck. Steve Sharratt was also supposed to tell me if he heard of anyone bidding, and I never heard of anyone.
BUDGET | Tanager Apartments (formerly Euclid Union) | 2023-06-21 | Compass | 139 | 3537000 | 25446.0432 | T.J. Lehman | Board & Vellum | Staengl Engineering | Capitol Hill | JJ Plumbing got this. They were waaaay lower than us.
BID | Marysville | 2023-06-30 | Intracorp | 474 | 10609805 | 22383.5549 | Intracorp | BCRA | na | Marysville
BID | Northgate M2 | 2023-07-12 | Compass | 234 | 6038000 | 25803.4188 | Simon Property Group | GGLO | Ecotope | Northgate | Stealing job from SJS. See quote sheet for analysis.
BID | Northgate M3 | 2023-07-12 | Compass | 186 | 4667000 | 25091.3978 | Simon Property Group | GGLO | Ecotope | Northgate | Stealing job from SJS. See quote sheet for analysis.
BID | Harmony | 2023-07-19 | Blueprint/Pantley | 99 | 1758000 | 17757.5758 | Blueprint/Pantley | CDA + Pirscher Architects | Pressler | Redmond
BID | Modera International District | 2023-08-02 | Mill Creek | 397 | 8638000 | 21758.1864 | Mill Creek | Tiscareno | HV Engineering | China Town
BID | KOZ 300 West Republican rebid | 2023-08-08 | Kirtley-Cole | 169 | 3065000 | 18136.0947 | KOZ Development | Koz Architecture | Emerald City | Queen Anne | Trademark per Steve. Kirtley Cole says there are 5 total bidders. Edmonds plumbing was lowest, I had to bring my price down to beat them.
BID | Bellevue Plaza | 2023-08-09 | Compass | 312 | 6250000 | 20032.0513 | Pastakia Associates | Encore | na | Bellevue | Price had to come down 10% to make project go.
BID | Bella on Broadway Repipe | 2023-08-09 | Farrell McKenna | na | 167100 |  | Farrell McKenna | na | na | Tacoma | Water main repipe.
BUDGET | 3831 Stone Way (Yonder) | 2023-08-28 | Exxel Pacific | 231 | 5200000 | 22510.8225 | Prometheus Real Estate | MG2 Architecture | Emerald City | Fremont
BID | Broadway Urbaine | 2023-08-30 | Exxel Pacific | 96 | 2048000 | 21333.3333 | TAP Collaborative | Knit | Robison Engineering | Capitol Hill | Per Colin Rogers email on 10/12, I was 3rd place out of 4. $275k high
BID | NW Market St | 2023-09-06 | Compass | 165 | 3498000 | 21200 | FA Johnson | Public47 | Emerald City | Ballard
BUDGET | 12th Place Apartments | 2023-09-13 | Compass | 274 | 5988000 | 21854.0146 | Gables Residential | Runberg | Ecotope | Bellevue
BID | 228th St Apartments | 2023-09-22 | Compass | 536 | 10890000 | 20317.1642 | NorthPoint Development | Strouse Davis | Emerald City | Bothell | SJS, Tri-State, and probably Wolfe are competition.
BID | 228th St Apartments | 2023-09-22 | Exxel Pacific | 536 | 10890000 | 20317.1642 | NorthPoint Development | Strouse Davis | Emerald City | Bothell | SJS, Tri-State, and probably Wolfe are competition.
BID | KOZ on MLK | 2023-09-29 | Kirtley-Cole | 131 | 2418000 | 18458.0153 | KOZ Development | Koz Architecture | Abossein | South Seattle | Probably Edmonds Plumbing. Nick Nelson said on 11/22 that I was in 4th place. Low bids were 12% to 18% lower than us. I said I could go down 2%.
BUDGET | LPC Port of Everett (Millwright?) | 2023-10-04 | Compass | 313 | 8360000 | 26709.2652 | Lincoln Property Company | Carrier Johnson | Rushing | Everett | Gencap is also bidding on this. Decided to ignore their bid request. I don't see a benefit to bidding to them. Only the potential for them to shop my number.
BUDGET | LPC Port of Everett (Millwright?) | 2023-10-05 | WG Clark | 313 | 8360000 | 26709.2652 | Lincoln Property Company | Carrier Johnson | Rushing | Everett | Gencap is also bidding on this. Decided to ignore their bid request. I don't see a benefit to bidding to them. Only the potential for them to shop my number.
BID | Marysville | 2023-10-06 | Intracorp | 474 | 10503592 | 22159.4768 | Intracorp | BCRA | na | Marysville
BID | 4001 S Willow St | 2023-10-13 | Compass | 191 | 3518000 | 18418.8482 | Nitze Stagen | Neiman Taber | Ocean Park | South Seattle | Ocean Park & Tri-State are competition
BUDGET | 508 Fremont (Frank) | 2023-10-19 | Exxel Pacific | 169 | 3898000 | 23065.0888 | Prometheus Real Estate | MG2 Architecture | Emerald City | Fremont
BUDGET | LPC Port of Everett (Millwright?) | 2023-10-31 | Compass | 313 | 7488000 | 23923.3227 | Lincoln Property Company | Carrier Johnson | Rushing | Everett | Rebid due to conversation with Daniel Marks & Ryan Ames. Wolfe was apparently 10% lower.
BUDGET | 201 Queen Anne Conversion | 2023-10-31 | Compass | 59 | 1640000 | 27796.6102 | Stream | None yet | na | Queen Anne
BUDGET | Shoreline III | 2023-11-14 | Compass | 360 | 7198000 | 19994.4444 | Evergreen Point Group | Tiscareno | Windsor | Shoreline
BUDGET | Shoreline III | 2023-11-14 | Exxel Pacific | 360 | 7198000 | 19994.4444 | Evergreen Point Group | Tiscareno | Windsor | Shoreline
BID | Big 1410 | 2023-11-17 | BMDC | 24 | 1198000 | 49916.6667 | Brocade Investment Group | Public47 | Robison | Capitol Hill
BID | Fremont 65 | 2023-11-20 | Compass | 65 | 1658000 | 25507.6923 | Infinity Investment Group | MZA Architecture | Robison Engineering | Fremont | Reduced price due to Compass request to get job to go.
BUDGET | Chelsea Square 2 Ph1 | 2023-11-28 | Exxel Pacific | 383 | 8250000 | 21540.47 | Equity Residential | Runberg | Rushing | Redmond | I'm guessing Wolfe
BUDGET | Swift 4200 | 2023-12-01 | Compass | 203 | 3739000 | 18418.7192 | Nitze Stagen | Neiman Taber | na | South Seattle
BUDGET | Springbrooke Phase 2 Annex | 2023-12-01 | Compass | 76 | 1788000 | 23526.3158 | Momentum Partners | Urbal Architecture | na | Lakewood | Tom Toomey said after I turned a bid in that it is going prevailing wage
BID | 4001 S Willow St | 2023-12-07 | Compass | 191 | 3480000 | 18219.8953 | Nitze Stagen | Neiman Taber | Ocean Park | South Seattle | Ocean Park & Tri-State are competition, Scott said there were 5 total bidders. On 1/2/24, Scott said that Trademark got it, at 8% lower than us. He said the ship has sailed, so no room to move.
BID | K2 Lynnwood | 2023-12-12 | AHB/ACG | 318 | 6598000 | 20748.4277 | American Capital Group | American Capital Group | Robison | Lynnwood | Western Mechanical & Tri-State are competition
BUDGET | 3421 Woodland Park | 2023-12-15 | Blueprint | 132 | 2610000 | 19772.7273 | Blueprint | Hybrid | Emerald City | Wallingford
BID | 1305 E Jefferson | 2023-12-19 | Chinn | 50 | 1378000 | 27560 | BE Partners (Jon Bunnell) | MNMuM Studio | Burman Design | Capitol Hill
BID | 1305 E Jefferson | 2023-12-19 | R Miller | 50 | 1378000 | 27560 | BE Partners (Jon Bunnell) | MNMuM Studio | Burman Design | Capitol Hill | Per Ben Muyres 4/10/24 email, I was 20% high
BUDGET | The Foundry at Totem Lake | 2023-12-21 | AHB/ACG | 463 | 10178000 | 21982.7214 | American Capital Group | American Capital Group | Robison | Totem Lake | Western Mechanical & Tri-State are competition
BUDGET | 3831 Stone Way (Yonder) | 2023-12-22 | Exxel Pacific | 231 | 5300000 | 22943.7229 | Prometheus Real Estate | MG2 Architecture | Emerald City | Fremont | Wolfe per Brian Christensen
BID | Bellevue Plaza | 2024-01-03 | Compass | 312 | 6250000 | 20032.0513 | Pastakia Associates | Encore | na | Bellevue | SJS and Atlas are competition
BID | Bellevue Plaza | 2024-01-08 | Compass | 312 | 5650000 | 18108.9744 | Pastakia Associates | Encore | na | Bellevue | SJS and Atlas are competition
BID | Songbird Mixed-Use | 2024-01-10 | R Miller | 119 | 2999000 | 25201.6807 | Kamiak | Hybrid | HV Engineering | Capitol Hill | Sunrise Plumbing, probably others. Per Ben Muyres email on 2/2, I was 5% high, came in 2nd place.
BUDGET | 12th Place Apartments | 2024-01-24 | Compass | 274 | 5899000 | 21529.1971 | Gables Residential | Runberg | Ecotope | Bellevue | Tri-State
BUDGET | 3000 Western | 2024-01-26 | Compass | 219 | 6388000 | 29168.9498 | Washington Holdings | Encore | Glumac | Downtown Seattle | Tri-State per Steve. Probably Wolfe too. Per WG Clark, we were best bid out of 4. 1 was garbage. 1 was Tri-State, and they don't like Tri-State. It seemed like we were lower than tri-state anyways.
BUDGET | 3000 Western | 2024-01-26 | WG Clark | 219 | 6388000 | 29168.9498 | Washington Holdings | Encore | Glumac | Downtown Seattle | Tri-State per Steve. Probably Wolfe too. Per WG Clark, we were best bid out of 4. 1 was garbage. 1 was Tri-State, and they don't like Tri-State. It seemed like we were lower than tri-state anyways.
BID | Blakeney Residence | 2024-02-01 | Schaefer Construction | na | 235000 | na | Blakeney | Board & Vellum | Berona | Capitol Hill
BID | Green Hill Apts Ph2 | 2024-02-14 | Compass | 48 | 960000 | 20000 | Green Hill Three LLC | Wattenbarger Architecture | Abossein | Lynnwood
BID | Green Hill Apts Ph2 | 2024-02-14 | Exxel Pacific | 48 | 960000 | 20000 | Green Hill Three LLC | Wattenbarger Architecture | Abossein | Lynnwood
BID | Green Hill Apts Ph2 | 2024-02-14 | Kirtley-Cole | 48 | 960000 | 20000 | Green Hill Three LLC | Wattenbarger Architecture | Abossein | Lynnwood
BUDGET | 1145 Market | 2024-02-14 | Chinn | 122 | 2698000 | 22114.7541 | J Selig Real Estate | Mithun | na | Ballard | SJS is competition, per Charlie. See bid sheet for notes. Charlie said on 11/29/23 they are hoping for a late 2024 start depending on financing.
BID | 68th & Roosevelt | 2024-03-06 | Chinn | 244 | 5098000 | 20893.4426 | High Street (Trammell Crow) | Weinstein A+U | Emerald City | Roosevelt | 5 other bidders per Compass, including Atlas. Nick Cunningham said via text on 3/18/24 that Trademark is $1mil lower than us. Ben w/ Braseth said on 4/11 that he had plugged our number, and that he though Braseth would get it. Per conversation with Derya & Kevin Chinn on 4/30/24, Chinn got the project. Per Chinn on 6/5/24, Wolfe is probably getting this one. They had the best number and are doing a project for the same owner down the street.
BID | 68th & Roosevelt | 2024-03-06 | Braseth | 244 | 5098000 | 20893.4426 | High Street (Trammell Crow) | Weinstein A+U | Emerald City | Roosevelt | 5 other bidders per Compass, including Atlas. Nick Cunningham said via text on 3/18/24 that Trademark is $1mil lower than us. Ben w/ Braseth said on 4/11 that he had plugged our number, and that he though Braseth would get it. Per conversation with Derya & Kevin Chinn on 4/30/24, Chinn got the project. Per Chinn on 6/5/24, Wolfe is probably getting this one. They had the best number and are doing a project for the same owner down the street.
BID | 68th & Roosevelt | 2024-03-06 | Compass | 244 | 5098000 | 20893.4426 | High Street (Trammell Crow) | Weinstein A+U | Emerald City | Roosevelt | 5 other bidders per Compass, including Atlas. Nick Cunningham said via text on 3/18/24 that Trademark is $1mil lower than us. Ben w/ Braseth said on 4/11 that he had plugged our number, and that he though Braseth would get it. Per conversation with Derya & Kevin Chinn on 4/30/24, Chinn got the project. Per Chinn on 6/5/24, Wolfe is probably getting this one. They had the best number and are doing a project for the same owner down the street.
BID | 68th & Roosevelt | 2024-03-06 | Venture | 244 | 5148000 | 21098.3607 | High Street (Trammell Crow) | Weinstein A+U | Emerald City | Roosevelt | 5 other bidders per Compass, including Atlas. Nick Cunningham said via text on 3/18/24 that Trademark is $1mil lower than us. Ben w/ Braseth said on 4/11 that he had plugged our number, and that he though Braseth would get it. Per conversation with Derya & Kevin Chinn on 4/30/24, Chinn got the project. Per Chinn on 6/5/24, Wolfe is probably getting this one. They had the best number and are doing a project for the same owner down the street.
BID | K2 Lynnwood | 2024-03-08 | AHB/ACG | 316 | 6598000 | 20879.7468 | American Capital Group | American Capital Group | Robison | Lynnwood | Western Mechanical, Tri-State, SJS, Puget Sound Mechanical, Ocean Park. Per Peter Kirks 4/30/24 email, we didn't get the project.
BID | Songbird Mixed-Use | 2024-03-12 | Braseth | 119 | 2849000 | 23941.1765 | Kamiak | Hybrid | HV Engineering | Capitol Hill | Sunrise Plumbing, probably others. Per Ben Muyres email on 2/2, I was 5% high when I first bid to RMiller, came in 2nd place.
BID | Chambers | 2024-03-15 | Holland | 224 | 5488000 | 24500 | Holland | MZA Architecture | Ocean Park | Bellevue | Ocean Park. Steve said he didn't know of any other bidders.
BID | Chambers | 2024-03-27 | Holland | 224 | 5353000 | 23897.3214 | Holland | MZA Architecture | Ocean Park | Bellevue | Ocean Park. Steve said he didn't know of any other bidders. Nick w/ Holland said we weren't low, so had to lower my number
BID | Edmonds Behar | 2024-03-29 | Exxel Pacific | 406 | 8198000 | 20192.1182 | Behar Company | Clark Barnes | Rushing | Edmonds
BUDGET | 3000 Western | 2024-04-02 | Compass | 219 | 6328000 | 28894.9772 | Washington Holdings | Encore | Glumac | Downtown Seattle | Tri-State per Steve. Probably Wolfe too. Per WG Clark, we were best bid out of 4. 1 was garbage. 1 was Tri-State, and they don't like Tri-State. It seemed like we were lower than tri-state anyways.
BUDGET | Woodland Park | 2024-04-03 | Compass | ? | ? | 22800 | Washington Holdings / Pastakia | Ankrom Moisan | Glumac? Not sure | Wallingford | Nick said he is only reaching out to us for numbers for now. Pastakia may be buying from Washington Holdings, and she just needs budget numbers for now.
BID | S33 | 2024-04-04 | Bode | 126 | 2698000 | 21412.6984 | Bode | Knit | Robison | North Seattle | Probably Edmonds and Burk Mechanical. Per Liz Roberts on 5/8/24: I was $6k per unit high, which makes low bid around $1,942,000. I'd be losing money to do the job.
BID | 4035 Stone Way | 2024-04-15 | Chinn | 56 | 1058000 | 18892.8571 | Kevin Chinn? | Clark Barnes | Abossein | Wallingford | Wolfe and SJS, per Charlie Poggeman. Kevin Chinn is not pursuing. Bank did not like pricing, so project will likely not go.
BUDGET | University Champion | 2024-04-23 | Compass | 202 | 3650000 | 18069.3069 | Champion Real Estate | Weinstein A+U | Sider Byers | U District | on 8/1/24 Tom Toomey told me the client has gone quiet.
BID | Seatac Apartments | 2024-04-24 | Chinn | 182 | 3128000 | 17186.8132 | 98188 Place LLC | Studio 19 Architects | SJS? | Seatac | Wolfe and SJS, per Charlie Poggeman. Charlie said that Wolfe and I are super close in pricing. More to come. As of 6/5/24, he still didn't have his pricing turned into the owner.
BID | Songbird Mixed-Use | 2024-04-25 | Braseth | 119 | 2788000 | 23428.5714 | Kamiak | Hybrid | HV Engineering | Capitol Hill | Sunrise Plumbing and Wolfe. Per Ben Laws and I conversation on 4/11/24, I was $50k higher than Wolfe, and Wolfe had a $50k alternate deduct to use Nyle. I updated my quote to be better than theirs.
BID | Riverfront Building C | 2024-04-30 | Shelter Holdings | 168 | 3298000 | 19630.9524 | Shelter Holdings | MG2 Architecture | Robison | Everett | Probably Wolfe, probably others
BID | Fremont 65 | 2024-05-02 | Compass | 65 | 1518000 | 23353.8462 | Infinity Investment Group | MZA Architecture | Robison Engineering | Fremont
BID | Fremont 65 | 2024-05-02 | Exxel Pacific | 65 | 1518000 | 23353.8462 | Infinity Investment Group | MZA Architecture | Robison Engineering | Fremont | Per Mark Gulin on 8/1/24: You placed 4th out of 5 bidders and were about 5-6% higher than our low “qualified” bidder.
BID | Fremont 65 | 2024-05-02 | R Miller | 65 | 1518000 | 23353.8462 | Infinity Investment Group | MZA Architecture | Robison Engineering | Fremont
BID | 739 Broadway | 2024-05-08 | Exxel Pacific | 61 | 1068000 | 17508.1967 | Scott McDonald, Matt Rankin? | Skidmore Janette | Berona | Capitol Hill | Per Mark Gulin on 8/1/24: You placed 3rd out of 4 bidders and were about 10-12% higher than our low “qualified” bidder.
BID | 739 Broadway | 2024-05-08 | R Miller | 61 | 1068000 | 17508.1967 | Scott McDonald, Matt Rankin? | Skidmore Janette | Berona | Capitol Hill
BID | 2404 Jackson | 2024-05-10 | BMDC | 37 | 1098000 | 29675.6757 | Sparkle Ventures? | Public47 | HV Engineering | South Seattle | Prokash plumbing - pretty sure they were at $1.1mil exactly per conversation w/ Drew. BMDC told me on 6/25/24 they were going with Prokash plumbing.
BUDGET | Greystar Capitol Hill | 2024-05-29 | Compass | 336 | 7870000 | 23422.619 | Greystar | Weber Thompson | Emerald City | Capitol Hill | Ocean Park & Tri-State
BID | Riverfront Building C | 2024-05-31 | Shelter Holdings | 168 | 3268000 | 19452.381 | Shelter Holdings | MG2 Architecture | Robison | Everett | Probably Wolfe, probably others
BUDGET | The MOORE | 2024-06-07 | Exxel Pacific | 172 | 3418000 | 19872.093 | Hunters Capital | Runberg | Ecotope | Capitol Hill | Per Mark Gulin email 9/24, I was 3rd out of 5 bidders, and 10% higher than the low number
BID | Lake Stevens Village Concepts Senior Living | 2024-06-12 | Rush Commerical | 140 | 2225000 | 15892.8571 | Rush Commercial | Wattenbarger Architecture | Abossein | Lake Stevens | Tri-State
BUDGET | Woodin Creek Village Ph 6 | 2024-06-19 | Exxel Pacific | 231 | 4798000 | 20770.5628 | Weidner Apartment Homes | Ankrom Moisan | Emerald City | Woodinville | Not Sure
BUDGET | Woodin Creek Village Ph 6 | 2024-06-19 | Compass | 231 | 4798000 | 20770.5628 | Weidner Apartment Homes | Ankrom Moisan | Emerald City | Woodinville | Not Sure
BUDGET | Woodin Creek Village Ph 6 | 2024-06-19 | Sierra Construction | 231 | 4798000 | 20770.5628 | Weidner Apartment Homes | Ankrom Moisan | Emerald City | Woodinville | Not Sure
BUDGET | Area 27 Apartments | 2024-06-24 | Compass | 396 | 8117000 | 20497.4747 | Corliss Resources | Milbrandt Architects | Robison | Puyallup | Not Sure
BUDGET | UW4 Blakely | 2024-07-02 | Exxel Pacific | 513 | 12775000 | 24902.5341 | Greystar | NAC Architecture | Glumac | U-Village | Ocean Park, probably Wolfe. Per John Hughes on 8/2/24, I was 2% high
BUDGET | UW4 Laurel | 2024-07-02 | Exxel Pacific | 340 | 8053000 | 23685.2941 | Greystar | Weber Thompson | Glumac | U-Village | Ocean Park, probably Wolfe. Per John Hughes on 8/2/24, I was 7% to 8% high
BID | Lake Stevens Village Concepts Senior Living | 2024-07-03 | Rush Commerical | 140 | 2108000 | 15057.1429 | Rush Commercial | Wattenbarger Architecture | Abossein | Lake Stevens | Tri-State. Ben said on 7/24/24 that they went with Trademark
BID | 2007 S. State St | 2024-07-10 | Jabooda | 58 | 1074000 | 18517.2414 | Jabooda Homes | MAS Architecture | na | South Seattle
BID | The Foundry at Totem Lake | 2024-07-11 | AHB/ACG | 461 | 9380000 | 20347.0716 | American Capital Group | American Capital Group | Robison | Totem Lake | Western Mechanical, Ocean Park. Possibly SJS and Tri-State
BUDGET | 3020 NE 45th St | 2024-07-19 | Compass | 796 | 16860000 | 21180.9045 | Quarterra | Encore Architects | SJS/HVE | U-Village | SJS, probably more.
ROM | Stream Residence Inn | 2024-07-19 | Compass | 126 | 2850000 | 22619.0476 | Stream | Board & Vellum | na | Lower Queen Anne | None, just giving Dan a wild ass guess ROM. See email.
BID | 56th & 57th | 2024-07-24 | WG Clark | 124 | 2438000 | 19661.2903 | Saratoga Capital | GGLO | Rushing | Ballard | Per phone call from Randy on 8/14/24, I was $150k high, and there was 5 other bidders
BUDGET | Chelsea Square 2 Ph1 | 2024-07-24 | Exxel Pacific | 382 | 7640000 | 20000 | Equity Residential | Runberg | Rushing | Redmond | Per Tony Johnson email 10/10/24, I'm in 2nd place among 4 bidders, only 1% high. Will rebid one more time.
ROM | 4311 7th Ave | 2024-08-02 | Jabooda | 10 | 400000 | 40000 | Tripalink | Shugart Wasse Workshop | Berona | U-District
BUDGET | 6220 Roosevelt | 2024-08-08 | Exxel Pacific | 146 | 2800000 | 19178.0822 | Phoenix Property Co | Weber Thompson | Emerald City | Roosevelt
BUDGET | 6220 Roosevelt | 2024-08-08 | Compass | 146 | 2800000 | 19178.0822 | Phoenix Property Co | Weber Thompson | Emerald City | Roosevelt
BID | Acer House | 2024-08-08 | Rush Commerical | 121 | 1985000 | 16404.9587 | Great Expectations | Schemata Workshop | Alpine / Atlas DB | Central District | Atlas has the job right now. Trademark may have had the lowest number. Compass said that Rush was 12% lower than Compass. Aaron Gallington said numbers would be confirmed by end of year. See emails from 9/23/24. Per Ben Laws text on 9/13/24, Atlas is low at $1.6mil
BID | 4035 Stone Way | 2024-08-16 | S&J Capital Group | 56 | 998000 | 17821.4286 | S&J Capital Group | Clark Barnes | Abossein | Wallingford | Satnam told Jeff that he has one other number. Not sure who it was.
BID | Acer House | 2024-08-16 | Compass | 121 | 1985000 | 16404.9587 | Great Expectations | Schemata Workshop | Alpine / Atlas DB | Central District | Atlas has the job right now. Trademark may have had the lowest number. Compass said that Rush was 12% lower than Compass. Aaron Gallington said numbers would be confirmed by end of year. See emails from 9/23/24. Per Ben Laws text on 9/13/24, Atlas is low at $1.6mil
BUDGET | 6220 Roosevelt | 2024-08-16 | Chinn | 146 | 2800000 | 19178.0822 | Phoenix Property Co | Weber Thompson | Emerald City | Roosevelt
BID | Chambers | 2024-08-21 | Holland | 224 | 5053000 | 22558.0357 | Holland | MZA Architecture | Ocean Park | Bellevue | Lowered number in effort to get the job to go. Project is put on hold. See email from Jordan on 10/9/24
BID | 508 Fremont (Frank) | 2024-08-28 | Exxel Pacific | 169 | 3598000 | 21289.9408 | Prometheus Real Estate | MG2 Architecture | Emerald City | Fremont | Atlas, Trademaker, Wolfe are all competition
BID | Woodin Creek Village Ph 4 | 2024-08-29 | Compass | 61 | 1220000 | 20000 | Weidner Apartment Homes | MG2 Architecture | Coffman | Woodinville | Trademark, Tri-State. Per Alan Thesenvitz phone call on 7/30/25, project is probably not going to proceed due to too many city demands (traffic circles, utility extensions, etc)
BID | Shoreline 185 | 2024-09-05 | WG Clark | 197 | 3888000 | 19736.0406 | Trent Development | Clark Barnes | Windsor | Shoreline | JD, United, probably others
BID | Tacoma II | 2024-09-10 | Rush Commerical | 376 | 6698000 | 17813.8298 | Trent Development | Public47 | Windsor | Tacoma | Not sure, probably a lot
BID | 508 Fremont (Frank) | 2024-09-10 | Build Group | 169 | 3898000 | 23065.0888 | Prometheus Real Estate | MG2 Architecture | Emerald City | Fremont | Atlas, Trademaker, Wolfe are all competition
BID | 201 Queen Anne Conversion | 2024-09-16 | Compass | 74 | 1330000 | 17972.973 | Stream | Board & Vellum | Windsor | Queen Anne | Not sure
BUDGET | The Sarah Queen Option 3 | 2024-09-17 | Chinn | 126 | $2.5m to $2.7m | na | ? | Public 47 | ? | Capitol Hill | Not sure
BUDGET | Kennydale Gateway | 2024-09-24 | Exxel Pacific | 385 | 7670000 | 19922.0779 | Vulcan | HLR | Rushing | Renton | Per Tony Johnson email 10/10/24, I'm in 4th place among 6 bidders, lowest is 4-5% lower than me.
BUDGET | Kennydale Gateway | 2024-09-24 | WG Clark | 385 | 7670000 | 19922.0779 | Vulcan | HLR | Rushing | Renton | Per Tony Johnson email 10/10/24, I'm in 4th place among 6 bidders, lowest is 4-5% lower than me.
BID | KOZ on Wetmore | 2024-09-26 | Kirtley-Cole | 169 | 2230000 | 13195.2663 | KOZ Development | Koz Architecture | Abossein | Everett | Best, JD, probably more
BID | Filament East & West | 2024-10-02 | WG Clark | 302 | 7328000 | 24264.9007 | Vulcan | Encore Architects | Rushing | Bellevue | Atlas, Ocean Park, probably more
BID | Filament East & West | 2024-10-02 | Exxel Pacific | 302 | 7328000 | 24264.9007 | Vulcan | Encore Architects | Rushing | Bellevue | Atlas, Ocean Park, probably more
BID | Pinnacle Bellevue Condos | 2024-10-04 | Pinnacle International | 101 | 2650000 | 26237.6238 | Pinnacle International | LDG Architects (Linardic Design Group) | Paraclete Engineers | Bellevue | Not sure
BID | R&G Apartments | 2024-10-08 | Braseth | 263 | 4460000 | 16958.1749 | Lake Union Partners / Braseth | Skb Architects | Emerald City | South Seattle | Not sure, probably a lot
BID | Marysville Phase 2 | 2024-10-11 | Intracorp | 246 | 4574995 | 18597.5407 | Intracorp | Intracorp | BCRA | na | Marysville
BID | 3000 Western | 2024-10-17 | Compass | 219 | 6428528 | 29354.0091 | Washington Holdings | Encore | Glumac | Downtown Seattle | Did not go out to other plumbing bidders, per Compass
BUDGET | 3421 Woodland Park | 2024-10-17 | Blueprint | 106 | 2100000 | 19811.3208 | Blueprint | Cone | None | Wallingford
BID | The Foundry at Totem Lake | 2024-10-21 | AHB/ACG | 453 | 9590000 | 21169.9779 | American Capital Group | American Capital Group | Robison | Totem Lake | Western Mechanical, Ocean Park. Possibly SJS and Tri-State. Per Jae Oh email on 11/11/24, there were 10 bidders, and I came in 7th place
BID | 125 15th Ave | 2024-11-01 | MRJ Constructors | 20 | 610000 | 30500 | Big Management Inc | B9 Architects | Robison | Capitol Hill
BID | Shoreline 185 | 2024-11-11 | Braseth | 197 | 3888000 | 19736.0406 | Trent Development | Clark Barnes | Windsor | Shoreline | JD, United, probably others
BID | KOZ on Wetmore | 2024-11-14 | Kirtley-Cole | 169 | 2200000 | 13017.7515 | KOZ Development | Koz Architecture | Abossein | Everett | Best, JD, probably more. Went to Edmonds Plumbing (found this out by searching permit info online)
BUDGET | Fremont | 2024-11-26 | Holland | 189 | 4900000 | 25925.9259 | HOlland | Weber Thompson | NA | Fremont | Very high level ROM, w/ heat pumps. Also gave a gas option.
BUDGET | 6220 Roosevelt | 2024-12-11 | Chinn | 147 | 2988000 | 20326.5306 | Phoenix Property Co | Weber Thompson | Emerald City | Roosevelt
BID | Stream Overlake (Cultivate) | 2024-12-18 | Compass | 224 | 5298000 | 23651.7857 | Stream | Board & Vellum | SJS/HVE | Redmond Overlake | See bid sheet. Dan said there were 7 other bidders.
BID | Sand Point Mixed Use | 2024-12-20 | BMDC | 70 | 1578000 | 22542.8571 | Shilshole Development | Public 47 | Emerald City | Sand Point
BID | SRM100 (12 Bellevue Way) | 2024-12-27 | SRM | 376 | 8148000 | 21670.2128 | SRM Development | Runberg | Glumac | Bellevue
BID | Margaret Estates Apartments | 2024-12-27 | Kirtley-Cole/Sierra/Corstone | 58 | 1298000 | 22379.3103 | KANG WILLIAM AND MARGARET LIVING TRUST | Benny and Lydia Kim Design | Abossein | Marysville
BID | Marysville Phase 2 | 2025-01-07 | Intracorp | 246 | 3700937 | 15044.4593 | Intracorp | Intracorp | BCRA | na | Marysville
BID | Block 18 | 2025-01-08 | Braseth | 118 | 2598000 | 22016.9492 | Vulcan | Public47 | Robison | South Lake Union | Best Plumbing was original plumbing sub. Not sure who else was competition.
BID | Block 18 | 2025-01-08 | WG Clark | 118 | 2598000 | 22016.9492 | Vulcan | Public47 | Robison | South Lake Union | Best Plumbing was original plumbing sub. Not sure who else was competition.
BUDGET | 200 2nd Ave N | 2025-01-10 | Exxel Pacific | 152 | 3428000 | 22552.6316 | Grousemont | Mithun | Rushing (IMEG) | Queen Anne | Wolfe plumbing, probably more (per Geoff Wood email). Per John Hughes 6/13/25 email, we are looking good.
BID | 125 15th Ave | 2025-01-13 | BMDC | 20 | 610000 | 30500 | Big Management Inc | B9 Architects | Robison | Capitol Hill
BID | 4401 Fremont West | 2025-01-24 | Kirtley Cole | 109 | 1998000 | 18330.2752 | Cohen Properties | Atelier Drome | HV Engineering | Fremont | JD is competition, probably more
BID | Northgate M3 | 2025-01-28 | Compass | 186 | 4268000 | 22946.2366 | Simon Property Group | GGLO | Ecotope | Northgate | Tri-State, Ocean Park, Apollo are competition
BID | Roosevelt Manor | 2025-01-29 | Sierra Construction | 137 | 2598000 | 18963.5036 | Jenkins Properties | Public 47 | Rushing | Roosevelt | Tri-State has been doing design on it
BID | Edmonds Behar | 2025-02-07 | Exxel Pacific | 409 | 7390000 | 18068.4597 | Behar Company | Clark Barnes | Rushing | Edmonds | Atlas, Trademark, possibly more
BUDGET | 6220 Roosevelt | 2025-02-24 | Chinn | 147 | 2937000 | 19979.5918 | Phoenix Property Co | Weber Thompson | Emerald City | Roosevelt
BID | Riverfront Building C | 2025-02-25 | Shelter Holdings | 168 | 3133000 | 18648.8095 | Shelter Holdings | MG2 Architecture | Robison | Everett | Probably Wolfe, probably others
BID | R&G Apartments | 2025-02-27 | Braseth | 263 | 4619052 | 17562.9354 | Lake Union Partners / Braseth | Skb Architects | Emerald City | South Seattle
BID | The Foundry at Totem Lake | 2025-03-04 | AHB/ACG | 453 | 9498000 | 20966.8874 | American Capital Group | American Capital Group | Robison | Totem Lake | Western Mechanical, Ocean Park. Possibly SJS and Tri-State. Trademark. Per Jae Oh on 3/24/25, we did not get the job. Low plumber was 12% lower than us.
BID | 201 Queen Anne Conversion | 2025-03-04 | Compass | 74 | 1498000 | 20243.2432 | Stream | Board & Vellum | Windsor | Queen Anne | JJ Plumbing is getting this. Dan Peck said they were way lower than us.
BID | 23rd & Holgate | 2025-03-14 | BMDC | 40 | 788000 | 19700 | SOLOMON ALEMAYEHU | JULIAN WEBER ARCHITECTS | na | South Seattle
BID | 125 15th Ave | 2025-03-20 | BMDC | 20 | 630000 | 31500 | Big Management Inc | B9 Architects | Robison | Capitol Hill
BID | Edmonds Behar | 2025-03-24 | Exxel Pacific | 409 | 7158000 | 17501.2225 | Behar Company | Clark Barnes | Rushing | Edmonds | See spreadsheet for info from Tommy Booth
BID | Yonder | 2025-03-25 | Exxel Pacific | 231 | 4828000 | 20900.4329 | Prometheus Real Estate | MG2 Architecture | Emerald City | Fremont | Trademark, Atlas, SJS, Wolfe, JH Kelly
BID | Highland Park | 2025-03-25 | Exxel Pacific | 397 | 7498000 | 18886.6499 | Summerhill Communities | Runberg | Emerald City | Bellevue
BID | Highland Park | 2025-03-25 | Compass | 397 | 7498000 | 18886.6499 | Summerhill Communities | Runberg | Emerald City | Bellevue
BID | Highland Park | 2025-03-25 | WG Clark | 397 | 7498000 | 18886.6499 | Summerhill Communities | Runberg | Emerald City | Bellevue
BID | Woodin Creek Village Ph 6 | 2025-04-02 | Compass | 231 | 4778000 | 20683.9827 | Weidner Apartment Homes | Ankrom Moisan | Emerald City | Woodinville | Lots. See file. Went to Tri-State, they beat us by 2-3%.
BID | The Fir | 2025-04-04 | Braseth | 204 | 4162000 | 20401.9608 | Kamiak | Public47 | Robison/Wolfe | South Seattle | Wolfe & SJS are competition. Ben said my number was the winning number when I turned it in.
BID | Fremont | 2025-04-10 | Holland | 185 | 4900000 | 26486.4865 | Holland | Weber Thompson | PAE | Fremont | JH Kelly got it
BID | Chelsea Square 2 Ph1 | 2025-04-16 | Exxel Pacific | 382 | 7748000 | 20282.7225 | Equity Residential | Runberg | Rushing | Redmond | Per Brian Christensen email on 2/23/26, Exxel does not have the project. Trying to figure out who the GC is that picked it up.
BUDGET | 6220 Roosevelt | 2025-05-06 | Chinn | 147 | 2968000 | 20190.4762 | Phoenix Property Co | Weber Thompson | Emerald City | Roosevelt
BID | The Perle | 2025-05-07 | SRM | 230 | 5498000 | 23904.3478 | SRM Development | Studio Meng Strazzara | Robison | Bellevue | Per Jamie Love at AirReps: Trademark, Atlas, Western Mechanical & Wolfe Plumbing
BID | Brizo | 2025-05-08 | SRM | 220 | 5159000 | 23450 | SRM Development | Runberg | Rushin (IMEG) | Bellevue
BUDGET | Ballard Blossom | 2025-05-14 | Holland | 239 | 6320000 | 26443.5146 | Holland | Ankrom Moisan | PAE | Ballard
BID | SRM100 (12 Bellevue Way) | 2025-05-15 | SRM | 376 | 8395000 | 22327.1277 | SRM Development | Runberg | Glumac | Bellevue
BID | Roosevelt Manor | 2025-05-16 | Sierra Construction | 137 | 2691000 | 19642.3358 | Jenkins Properties | Public 47 | Rushing | Roosevelt | Tri-State has been doing design on it
BID | Ballard Blossom | 2026-06-02 | Holland | 239 | 5670000 | 23723.8494 | Holland | Ankrom Moisan | PAE | Ballard
BUDGET | The Springs at Issaquah Highlands - SD Estimate | 2025-06-06 | Exxel Pacific | 225 | 7198000 | 31991.1111 | The Springs Living | GBD Architects | Interface Engineering | Issaquah | Best Plumbing, Ocean Park is also bidding per Steve. Ocean Park got it per Exxel. See email on 9/17/25
BID | 3020 NE 45th St | 2025-07-09 | Compass | 796 | 16659000 | 20928.392 | Quarterra | Encore Architects | ECE | U-Village | Lots. See file.
BID | Paramount Ph2 | 2025-07-22 | Corstone | 110 | 2110000 | 19181.8182 | W2L Enterprizes | Pelletier + Schaar | Glumac | Shoreline
BID | Songbird Mixed-Use | 2025-08-12 | Braseth | 118 | 2638000 | 22355.9322 | Kamiak | Hybrid | HV Engineering | Capitol Hill | Per Mark Braseth on 12/3/25, Burk Mechanical was $300k lower than us and Wolfe. They are going with them.
BID | Central Peak | 2025-08-19 | Cordillera Group | 26 | 1798000 | 69153.8462 | Cordillera Group | Baylis | Robison | Kirkland
BID | Sand Point Mixed Use | 2025-08-22 | BMDC | 70 | 1550000 | 22142.8571 | Shilshole Development | Public 47 | Emerald City | Sand Point
BID | Central Peak | 2025-08-25 | Cordillera Group | 26 | 1620000 | 62307.6923 | Cordillera Group | Baylis | Robison | Kirkland
BUDGET | Shannon & Wilson | 2025-09-04 | Rush Commerical | 170 | 3348000 | 19694.1176 | Pollard & Legacy Group | Urbal Architecture | Glumac | Fremont | Rush said I was high by 21%, didn't get it.
BID | 2601 Elliott | 2025-09-04 | Exxel Pacific | 259 | 5068000 | 19567.5676 | Vanbarton Group | Gensler | Delta E | Downtown Seattle | Exxel said on 11/18/25 that they did not get the project. See email from Tony Johnson
BID | 12th Place Apartments | 2025-09-10 | Exxel Pacific | 274 | 5099000 | 18609.4891 | Gables Residential | Runberg | Ecotope | Bellevue | Probably Wolfe.
BID | The V Apartments (Polynesia) | 2025-09-13 | SRM | 166 | 3258000 | 19626.506 | SRM Development | Urbal Architecture | Emerald City | Bellevue
BUDGET | Vincent - Northgate LUP | 2025-09-17 | Sierra Construction | 302 | 5888000 | 19496.6887 | Lake Union Partners | Weinstein A+U | Emerald City | Northgate
BUDGET | Elowen | 2025-09-24 | Chinn | 201 | 3950000 | 19651.7413 | Pastakia Associates | Urbal Architecture | NA | Lake Stevens
BID | Capitol Hill Apartments & Safeway | 2025-10-16 | Compass | 290 | 6770000 | 23344.8276 | Greystar | Weber Thompson | Emerald City | Capitol Hill
BUDGET | 12 Spruce | 2025-10-16 | Exxel Pacific | 394 | 7600000 | 19289.3401 | T Property Investments (TEC Equipment) | MG2 Architecture | Robison | Yesler | Tony Johnson said on 11/18/25 that we were 1 of 4 bidders. We were next to 3 other bids. 1 bid was very low.
BUDGET | The Gallery Richmond Beach Senior Living | 2025-10-24 | Exxel Pacific, Chinn | 205 | 6798000 | 33160.9756 | Nexcore Group | Urbal Architecture | Windsor | Shoreline | Joe Hanley told me on 2/24/26 that Venture got the job. Never got a bid invite from them.
BID | Highland Park | 2025-10-28 | Exxel Pacific | 397 | 7168000 | 18055.4156 | Summerhill Communities | Runberg | Emerald City | Bellevue | Probably Wolfe & JD.
BID | 12th Place Apartments | 2025-11-14 | Compass | 274 | 5267600 | 19224.8175 | Gables Residential | Runberg | Ecotope | Bellevue | Probably Wolfe.
BID | 3421 Woodland Park | 2025-11-19 | Ravenna Partners | 104 | 1948000 | 18730.7692 | Ravenna Partners | Cone | NA | Fremont
BID | 6220 Roosevelt | 2025-12-04 | Chinn | 147 | 3042140 | 20694.8299 | Phoenix Property Co | Weber Thompson | Emerald City | Roosevelt | I've heard that Tri-State is bidding
BUDGET | Wedgwood Center | 2025-12-05 | Exxel Pacific | 316 | 6800000 | 21518.9873 | Security Properties | SCB | Sider Byers | Wedgwood | Article in PSBJ on 1/8/26 says job is dead
BUDGET | 1200 116th Ave NE | 2025-12-11 | Chinn | 215 | 4700000 | 21860.4651 | High Street (Trammell Crow) | Weber Thompson | NA | Bellevue
BID | 4723 18th Ave NE | 2025-12-16 | Elite Builders | 30 | 818000 | 27266.6667 | GEORGE COINER | B9 Architects | Robison | U-District
BUDGET | Bothell Ridge Apartments | 2026-01-05 | Compass | 126 | 2345000 | 18611.1111 | Essex Property Trust | Dahlin | Emerald City | Bothell
BID | Edmonds Behar | 2026-01-16 | Exxel Pacific | 409 | 7183400 | 17563.3252 | Behar Company | Clark Barnes | Rushing | Edmonds
BUDGET | Edgewood Town Center Apartments | 2026-01-20 | Intracorp | 336 | 5772100 | 17178.869 | Intracorp | BCRA | na | Edgewood
BID | Roosevelt Manor | 2026-01-20 | Sierra Construction | 137 | 2583277 | 18856.0365 | Jenkins Properties | Public 47 | Rushing | Roosevelt
BID | 508 Fremont (Frank) | 2026-01-27 | Exxel Pacific | 169 | 3528000 | 20875.7396 | Prometheus Real Estate | MG2 Architecture | Emerald City | Fremont | Atlas, Trademark, Wolfe, Ocean Park, R&H, Best are all competition
BID | 3000 Western | 2026-02-06 | Greystar | 219 | 4798000 | 21908.6758 | Greystar | Encore | Glumac | Downtown Seattle
BID | 4401 Fremont West | 2026-02-23 | Kirtley Cole | 109 | 1988000 | 18238.5321 | Cohen Properties | Atelier Drome | HV Engineering | Fremont | JD is competition, probably more. Nick Nelson said I was 18% high on 3/12/26
BID | Chelsea Square 2 Ph1 | 2026-02-26 | Mill Creek | 382 | 7498000 | 19628.2723 | Equity Residential | Runberg | Rushing | Redmond | Atlas, Trademark
BID | Filament East & West | 2026-03-06 | Holland | 294 | 8120000 | 27619.0476 | Holland | Encore | NA | Bellevue
BUDGET | Freestone | 2026-03-13 | Braseth | 174 | 3700000 | 21264.3678 | HAL | Public 47 | Emerald City | Wallingford
BID | 2601 Elliott | 2026-03-13 | Carmel Partners | 258 | 5438000 | 21077.5194 | Vanbarton Group | Gensler | Delta E | Downtown Seattle | Trademark is competition
BID | Jabooda Apollo Heights | 2026-03-20 | Jabooda | 130 | 2488000 | 19138.4615 | Jabooda Homes | Axis GFA | Windsor | Tacoma | Schulte Plumbing is competition, probably more
BID | Hidden Hills | 2026-03-27 | Compass | 152 | 2564000 | 16868.4211 | He Development LLC | Tom Herstad Building Design | NA | Port Orchard
BID | SRM100 (12 Bellevue Way) | 2026-04-06 | SRM | 376 | 8395000 | 22327.1277 | SRM Development | Runberg | Glumac | Bellevue
BID | Filament East & West | 2026-04-08 | Holland | 294 | 7820000 | 26598.6395 | Holland | Encore | NA | Bellevue

## BbQuantityLink (hidden)
<?xml version="1.0" encoding="utf-8"?> <QuantityLinks Version="3"> <Links /> <Filesets /> <Guids /> </QuantityLinks> | 1

## Projects NOT Bid
Job Name | Invite Date | GC | Units | Owner | Area | Reason Did Not Bid | Competitor | Competitor Bid? | Notes
Bothell Commons Phase II | 2022-11-11 | Avalon Bay | 400 | Avalon Bay | Bothell | Too busy to get around to
Market Square | 2022-09-27 | Pavilion | 176 | Heron Properties | Tacoma | Been hearing bad things about Pavilion, south end job so competition will be cheap
KOZ Lynnwood Apartments | 2022-11-22 | Kirtley-Cole | 200 | Koz | Lynnwood | Too busy to get around to, messy spec, and I imagine competition would be cheap. I found on mybuildingpermit.com that their plumbing budget is $4,220,000, which is $21,100 per unit
2501 Market Street | 2022-11-29 | Chinn | 110 | Jordan Selig Real Estate | Ballard | Typical Chinn asking for budgets. Job will rebid competitively in future.
SRM Bellevue Way | 2023-01-17 | SRM | 376 | SRM | Bellevue | Very early budgeting. Will be asked to bid again in future. See notes in email I sent to myself.
Apollo Apartments | 2023-01-10 | Exxel Pacific | 255 | Blackfish Capital | Edmonds | See email for explanation.
Seatac Hyatt Hotel | 2023-01-31 | Chinn | 198 |  | Seatac | See email for explanation.
3831 Stone Way | 2023-02-08 | Exxel Pacific | 230 | Prometheus Real Estate Group | Wallingford | Told Exxel Pacific that I would bid it if the senior PM called me. It's a schematic bid, and way too early, so this is probably just budget pricing. Exxel never called me. Jens said that Eric would call me, but he never did. Just going to wait until it's further along, i should get a bid invite later.
Spruce Project | 2023-05-25 | Marpac | 400 | T Property Investments | South seattle | See email for explanation.
St Lukes | 2023-06-08 | Venture | 206 | Security Properties | Ballard | See email for explanation.
Ardea at Totem Lake | 2023-06-23 | Venture | 170 | TWG Development | Totem Lake | Venture project, busy with other bidding, Abossein design
1013 E Republican St | 2023-07-14 | Petra | 75 | Mike Martin? | Capitol Hill | Messy spec, Petra, probably a bunch of shitty plumbers bidding on it, etc
Overlake Square | 2023-07-13 | Carmel Partners | 569 | Carmel Partners | Redmond (Overlake) | Too big. CP is big and there's a lot of risk here
iVista Apartments | 2023-07-26 | Rush/Venture/Petra | 256 | Cosmos Group | Lynnwood | Don't have enough time before 2nd baby is due. Rush Commerical is GC. Nasty looking spec. Just got an invite to bid on Intracorp Lacey, so would like to concentrate on that. Also was invited to bid on this again in Feb/March 2024
Modera Bridle Trails | 2023-08-01 | Mill Creek | 372 | Mill Creek | Kirkland | Atlas and JD bid it, so it's already going to be cheap. The Modera ID project was bid very cheaply, so they're going to have a very cheap expectation. Also, it's big and complicated, and I don't have time to deal with this bid. Have a baby coming in a week.
12th Place Apartments | 2023-07-28 | Compass | 274 | Gables Residential | Bellevue | Very messy fixture spec. Bid invite says there will be future rounds of bidding, so we will have another chance. I have a baby due in a week, and there are other projects to bid, so need to prioritize. Also, bid invite says the project won't go if it doesn't meet owners budget, so isn't very promising.
Lacey Apartments | 2023-07-27 | Intracorp | 216 | Intracorp | Lacey | See email for explanation.
AAA Management Renton | 2023-08-25 | Compass | 343 | AAA Management | Renton | AAA Management is shitty owner, requires a lot of time/effort. They wanted pricing on tear down, rebuild, and conversion from office to apartment. Too much time to think about. Too many other things to bid right now.
Village at 47th | 2023-09-18 | ACG | 272 | Vintage Housing | Tukwila | Cannot find any info about permits online. Cannot figure out who bid it. Was a low level PE that called me about it, with little info. ACG is GC, which is probably a waste of time. Not sure if we want to work for them. There is other better stuff to bid on right now.
Bothell Campus Phase II | 2023-10-12 | Avalon Bay | 399 | Avalon Bay | Bothell | Don't feel like this is a good use of time. They call it budget numbers anyways.
CHELSEA SQUARE II_PHASE I_WEST | 2023-10-16 | Exxel Pacific | 390 | Equity Residential | Redmond | Declined by email to Brian Merris on 10/19, and told him to invite me on the next round of pricing. Project doesn't start for 2 years. These are just budget numbers. Don't have time, don't feel like I owe it to Exxel, and I'll be invited to bid on it in the future.
Yesler Hotel (Prospera, Marriot Residence Inn) | 2023-11-13 | Exxel Pacific | 194 | Marriot Hotel | Yesler | Robison design, very involved spec, hotel, very detailed, Exxel will just give it to Wolfe, and there's a lot to bid at the moment.
AAA 149th St South | 2023-12-06 | TB Penick & Sons | 252 | AAA Management | Shoreline | AAA Management is shitty owner, requires a lot of time/effort.
AAA 5th Ave North | 2023-12-06 | TB Penick & Sons | 310 | AAA Management | Shoreline | AAA Management is shitty owner, requires a lot of time/effort.
Tanager Apartments | 2023-12-11 | Braseth | 139 | T.J. Lehman | Capitol Hill | Bid the job to Compass several times. JJ had the winning number, and it was insanely low. No way I can beat him. And it looks like he's already started design, so there's no point.
629 - MJR | 2023-12-11 | Exxel Pacific & Chinn | 50 | MJR Development | Lacey | Job is down south, and is small, so they're going to get a ton of super low numbers. No point in wasting my time on this.
Overlake South Block 5 | 2024-01-19 | Chinn | 486 | Link Logistics | Redmond | Charlie never responded to my questions on the project so I skipped it. Very early so it's a waste of time.
110 1st Ave West Project | 2024-03-04 | Build Group | 70 | Lexington Asset Management | Seattle | Do not know Build Group. WG Clark is shown on coversheet. Too many jobs to bid at this time.
2947 Eastlake | 2024-02-27 | WG Clark | 130 | Daly Partners | Seattle | Atlas Plumbing is currently doing design, who is very cheap. So my number would have to be cheaper than Atlas, with design. WG Clark gives 2 weeks to bid, which is not enough time. Heat pump water heating system is not specified, so don't have time to figure out what to use and get quotes. Just an uphill battle.
Polynesia | 2024-03-05 | SRM | 166 | SRM | Bellevue | SRM is asking for budget pricing only, and says that this round is just budgeting, no sub selections will be made. So a waste of my time.
Mercer Island Mixed Use | 2024-02-29 | Venture/Graham | 146 | Xing Hua Group Ltd. | Mercer Island | Shitty GC's, don't know owner. Have a lot to bid on at the moment. Note: Marc w/ R Miller called me on 4/18/24 and asked if I was bidding this. I said I was passing on it. He said Adept had been doing precon on it, and that they had to get lower numbers. I told him I probably can't beat Adept, and that I'm still passing on it.
Overlake Mixed Use | 2024-03-22 | WG Clark | 230 | Johnson Carr | Overlake Redmond | Too much to bid right now. Never been able to land a job for Johnson Carr or WG Clark.
2404 Jackson St | 2024-03-26 | BMDC | 36 | Sparkle Ventures? | South seattle | Too much to bid right now. Too small. Talked to Drew Prokash about this, he said his budget was $808,000, but that BMDC was getting numbers back around $8,000 per unit, which isn't worth it.
2501 Market Street | 2024-02-05 | Chinn | 110 | Jordan Selig Real Estate | Ballard | Talked to Charlie on 4/2/24, and he said don’t worry about submitting a bid for this one. Said that plans are not far enough along, and that it will come back out.
Ori Roosevelt | 2024-04-10 | R Miller/Marpac | 81 | Onelin Capital | Roosevelt | Too much to bid right now, and seems like a waste of time. This owner has had all of the following GC's look at this, just seems like a waste of time: Chinn, Rmiller, Marpac, Shuchart
739 Broadway East | 2024-04-03 | R Miller | 61 | Scott McDonald, Matt Rankin | Capitol Hill | Too much to bid right now, seems very early to be bidding this one. I'm guessing that it will be bid out again in the future.
Little Saigon Landmark C&S | 2024-04-19 | BN Builders | 71 | Not sure | Chinatown | Prevailing wages
LIHI New Hope - East & West | 2024-05-02 | WG Clark | 92 | LIHI | Not sure | Prevailing wages
Viridian Grove | 2024-04-19 | Vaughn Bay | 98 | ? | Tacoma | Not enough time to look into it. Too much to bid. Don't know Vaughn Bay. I'm guessing they're used to dirt cheap numbers, and project is down south so I imagine they can get Trademark to do it for very cheap.
Cedarside Apartments | 2024-04-12 | West Edge Development | 516 | West Edge Development | Stanwood | Not enough time to look into it. Too much to bid. Don't know West Edge. I imagine they'll be looking for dirt cheap numbers.
Modera Bel-Red | 2024-05-13 | Mill Creek | 426 | Mill Creek | Overlake Redmond | Just didn't have time to get around to it. Too much to bid.
Milano Issaquah | 2024-06-06 | Rush Commercial | 65 | Not sure | Issaquah | Too much to bid right now
425 NW 85th Greenwood | 2024-06-13 | Ryan | 218 | Shea? | Greenwood | Too much to bid right now. Ryan is big and not sure if we want to work with them. Project is only at schematic design at this point.
Rose Hill Mixed Use | 2024-06-24 | Chinn | 810 | Madison Development Group (Tom Lee) | Kirkland | Charlie called me and said the project needed to switch to the new building codes. Tom Lee is looking to sell the project. Too much to bid at the time. Seemed like a waste of time.
185th Transit Center Apartments | 2024-08-14 | Redhawk | 26 | ? | Shoreline | Thought about doing this one, but I searched the lien records for Redhawk and it came up with several pages. Don't think it's worth even throwing my number out there.
Sunrise 12 Apartments | 2024-08-19 | High Country | 12 |  | Shoreline | Only 12 units, and I have plenty of other bids to concentrate on right now
165 Washington | 2024-08-23 | WG Clark | 77 | Johnson Carr | Pioneer Square | Feel like a project of this size is going to get a lot of bidders, and I've never been able to get a WG Clark job, so it's kind of pointless, and there's a ton of other jobs to bid on. Someone is going to come in stupid low.
149th Shoreline | 2024-09-24 | Rush | 252 | AAA Management | Shoreline | Job has been around for years, waste of time since it's AAA management and Rush. Lots to bid on, not going to waste my time on this one.
Tacoma Holiday Inn Express |  | Petra/Rmiller | 127 |  | Tacoma | Too much to bid on right now, would require a lot of effort, and it's for GC's that I haven't worked for.
Overlake Mixed Use |  | WG Clark | 233 | Johnson Carr | Overlake Redmond | Too much to bid on right now, and didn't have time to get around to this one. Seems like Johnson Carr is struggling to get jobs going right now and I doubt this one is starting very soon.
Uptown Apartments | 2024-10-16 | Compass | 215 | Kamiak | Queen Anne | Budgeting only. Kamiak can't get any jobs to start right now. Waste of time. If compass wants me to bid it, they'll call me.
Bell 10 | 2024-10-16 | WG Clark | 102 | Guntower Capital | Bellevue | Alpine/Atlas has already done plumbing engineering, so they have a cheap price. Waste of time.
4742 Apartments | 2024-12-10 | WGClark, Rmiller, Chinn | 89 | Campus U Development | U District | Too much to bid right now, they have 3 GC's looking at it, seems like a waste of time.
Astor Townhomes | 2025-01-10 | Fullwiler Construction | 39 | Fullwiler Construction, Shelter Homes? | Roosevelt | Never worked for these guys, seems like a messy job, townhomes, etc.
Pixel Apartments | 2025-01-08 | Gencap | 179 | McCraken Properties | Overlake Redmond | Gencap is a waste of time, always gives their jobs to JD
12th & Olive | 2025-01-14 | Rush | 134 | Mack Real Estate (not the Mack that we've worked for before, this is a big one out of New York) | Capitol Hill | Wanted it back within a week. Seems unlikely to actually go because he's asking me for prices to add units, revise major parts of building. Rush uses super cheap numbers that I don't feel like working for.
Acer House | 2025-01-15 | Rush | 121 | Great Expectations | Central District | Atlas has job. Trademark is bidding too. I bid on it the first time around, but it's very apparent that it's a waste of my time and is going to go for a stupid low number.
2nd & Bell | 2025-01-17 | Rush | 175 | HB Management / Paragon Real Estate | Belltown | Wolfe did design on job. Rush is used to stupid low numbers, and Trademark will probably be bidding. No point in wasting my time on this. Note that I bid this to Exxel I February 2021
Tacoma Trax | 2025-01-22 | Gencap | 202 | Parkview Financial of Los Angeles (used to be a GIS International job) | Tacoma | Gencap is a waste of time. They are calling it "budgetary" pricing.
Proctor 4 | 2025-01-27 | Rush | 98 | Rush | Tacoma | Rush is a waste of time. Going to be competing with Trademark and Atlas prices. They make you do finanical pre-quals and list your OH&P, etc.
124 Tacoma | 2025-01-31 | Rush | 147 | Rush | Tacoma | Rush is a waste of time. Going to be competing with Trademark and Atlas prices. They make you do finanical pre-quals and list your OH&P, etc.
Milano Issaquah | 2025-03-26 | R Miller | 65 | Not sure | Issaquah | Too much to bid right now. Rush was looking at this a year ago. Doesn't seem like a good project.
Deal Ballard Multifamily (2401 NW Market | 2025-03-31 | Rush | 178 | Deal Family | Ballard | Rush is a waste of time.
11040 Main Street Apartments | 2025-04-16 | Sierra | 351 | High Street Residential / Trammel Crow | Bellevue | Way too early to bid. Don't work with Sierra very much so don't owe them anything. Note, this project was a prospective Holland job at one point.
4800 40th Ave | 2025-05-15 | Braseth | 86 | Braseth | West Seattle | Mark Braseth called and said this is a project for them. He said it doesn't pencil right now, so don't bother bidding it. He said he'd reach out if they ever decide to bid it out again.
Avalon Redmond Tech Station Project | 2025-06-10 | Avalon Bay | 349 | Avalon Bay | Redmond | Very early, they are just looking for budgets for now. It will come back around.
2601 Elliott | 2025-07-07 | Exxel Pacific | 259 | Vanbarton Group | Seattle | Very early, they are just looking for budgets for now. It will come back around. Exxel said they would reach out when it comes back out to bid again.
Carrick Court | 2025-07-30 | Exxel Pacific | 10 | Wescott Homes | Edmonds | Too little units to make it worth it.
TWG Georgetown | 2025-08-11 | Venture | 158 | TWG Development | Georgetown | Venture project, busy with other bidding.
HoM District Residential | 2025-08-27 | Venture | 309 | Hines | Bellevue | Venture project, busy with other bidding, Venture narrative says that it's open book, lots of erronious requirements
Uptown Apartments | 2025-08-07 | Compass | 215 | Kamiak | Queen Anne | Shown as a budget for now. Talked with Dan Peck at the time and he didn't seem hopeful that the job would go, so seemed like a waste of time for now. He seemed to think that it will get bid out again.
Avalon Redmond Tech Station - Phase A Project | 2025-11-04 | Avalon Bay | 367 | Avalon Bay | Redmond | Very early, they are just looking for budgets for now. It will come back around. Brett says he's never heard good things about AvalonBay. He's not against working for them, but cautioned me, and said we should do research first.
Ori Roosevelt | 2025-11-17 | R Miller | 81 | Onelin Capital | Roosevelt | This owner has had all of the following GC's look at this, just seems like a waste of time: Chinn, Rmiller, Marpac, Shuchart. Ben Muyres was with Rmiller and is now with JD, so he's going to know all the numbers and knows where to be with this one. I imagine there is a lot of plumbers looking at it. Seems like a very convoluted/complicated job, for a small number of units. Just doesn't seem worth it. Also, I'd be willing to bet that the project is being sold, and they are just looking for updated numbers for marketing.
425 Pontius | 2025-12-22 | Ryan | 199 | Ryan | South Lake Union | Way too early to bid on. Ryan has some nasty contract stuff, never worked for them, very big company. Complicated project as well.
Uptown Apartments | 2025-12-19 | Rush | 204 | Kamiak | Queen Anne | See notes above from Compass for the same job. Seems like a waste of time.
Bothell Urban | 2026-02-13 | Exxel | 201 | Bridge Housing | Bothell | They are only asking for schematic budget pricing right now, don't have time to get to it, too much to bid right now.
Milano Issaquah | 2026-02-23 | Marpac | 65 | Not sure | Issaquah | Too much to bid right now. Rush & RMiller was looking at this a year ago. Doesn't seem like a good project.
Burl Apartments | 2026-02-06 | Compass | 171 | Spectrum | Shoreline | Was not able to get around to this bid because of hawaii trip and too busy. It had a lot of bidders on it including LJM, Wolfe, Atlas, Artemis and Western Mech, Trademark.
1661 East Olive Way |  | Compass |  |  |  | Too busy. Budget only at this time. Will probably be invited again.
R22 Phase 1 and Phase 2 | 2026-03-17 | ACG | 731 | ACG | Redmond | Too busy. Budget only at this time. Will probably be invited again.
AMLI Spring District II | 2026-03-07 | Rafn | 297 | AMLI | Bellevue | Too busy, couldn't get around to it. Backlog is looking pretty good so starting to be selective.