## Job Cost Report
SCHEMA — JOB COST REPORT (v4)
Rebuilt from Sage Timberline Job Detail Report. One record per report snapshot. Line items stored as an array of objects for drill-down.
v4 changelog (2026-04-18): Applied Reconciliation Actions #1, #2, #3, #7, #8, and #9 from the OWP 2012 Schema Audit. Action #1 — plus_minus_budget convention locked as (actual − current_budget), positive = over. Phase set excludes only 999 Sales. Action #2 — revised_budget renamed to current_budget (hard cut). original_budget retained as separate field. Action #3 — blended_gross_wage renamed to pr_src_cost_per_hr. Added straight_time_rate, worker_nominal_wages[], nominal_wage_percentiles. Action #7 — labor_productivity_rate renamed to labor_unit_cost_per_hr (cost metric). Added revenue_per_labor_hour (throughput). Action #8 — trade-agnostic benchmark framework added. Layer 1 now carries project_start_date, project_end_date (nullable), and scope_metrics[] (array of {label, count, description}). Derived section adds project_duration_months and scope_benchmarks[] — one output object per scope_metric with dollars/hours/units-per-month/revenue per unit. Fully trade-neutral; each trade declares its own scope labels. Action #9 — Reconciliation Protocol tab added as 2nd tab in this workbook. Serves as the agent-labeler's cross-check contract: for each audit-driven field, documents the JCR-only derivation, the external cross-check source, the expected relationship, match/mismatch actions, and known divergences. Worked Job 2012 example lives in the Test Labels workbook on the Reconciliation Log tab. Actions #4, #5, #6, #10 — deferred to consolidated Steven brief (STEVEN OWNER actions + insights narrative). No schema changes required from those actions; brief will be assembled as a separate deliverable.
Canonical | Display Name | Data Type | Category | Options / Values | Example | Source | Notes
LAYER 1 — INHERITED (6 fields)
job_number | Job Number | Auto-ingested | 1 — Identity |  | 2012 | Inherited from Layer 1 | Sage job number. Primary key linking this report to a project.
job_name | Job Name | Text (free) | 1 — Identity |  | Exxel Pacific 8th Ave | Inherited from Layer 1 | Project name as printed on the JDR header.
report_date | Report Date | Date | 1 — Identity |  | 2020-06-30 | JDR Header | Date of the JDR export. Identifies which snapshot this data comes from for time-series trending.
project_start_date | Project Start Date | Date | 1 — Identity |  | 2013-06-01 | Inherited from Layer 1 | Project/contract start date. Pulled from project master record (not the JDR). Used with project_end_date to compute project_duration_months.
project_end_date | Project End Date | Date (nullable) | 1 — Identity |  | 2014-11-30 | Inherited from Layer 1 | Project/contract end date. Null while job is active. If null, project_duration_months falls back to latest line_items[].document_date − project_start_date.
scope_metrics | Scope Metrics | Array of Objects | 1 — Identity |  | [{label: "dwelling_units", count: 60, description: "Residential apartments"}, {label: "fixtures", count: 248, description: "Plumbing fixtures installed"}] | Inherited from Layer 1 | Trade-agnostic array of named scope counts for the project. Each object has 3 fields: • label (Text) — Short snake_case name (e.g., "dwelling_units", "fixtures", "devices", "tons", "square_feet") • count (Number) — Integer or decimal count of the metric on this project • description (Text) — Human-readable description ("Residential apartments", "Plumbing fixtures installed", etc.) Empty array valid — the derived scope_benchmarks array will then also be empty. Each trade declares whichever metrics make sense: plumbing uses fixtures + units; electrical uses devices + amp_service; framing uses linear_feet + square_feet; etc. Enables portfolio-level benchmark rollups on any shared label.
LINE ITEM DETAIL (1 field — array of 19-field objects)
line_items | Line Items | Array of Objects | 3 — Budget/Financial |  | [{cost_code: "120", description: "Roughin", source: "PR", ref_number: "00147", document_date: "2020-03-15", number: "E0247", name: "Cervantes, Armando", regular_hours: 8.0, actual_amount: 332.64, check_number: "30517", ...}, ...] | JDR Parse | Each object in the array represents one transaction line from the JDR. Object schema (19 fields): • cost_code (Text) — Cost code this line falls under (e.g., 120=Roughin, 011=DS&RD Labor, 999=Sales) • description (Text) — Cost code description as printed in JDR section header • original_budget (Currency) — Original budgeted amount from the bid • current_budget (Currency) — Current budget including COs and transfers • plus_minus_budget (Currency) — Variance: actual minus current_budget. Positive = over budget • source (Enum: PR¦AP¦AR¦GL) — Transaction origin. Determines which fields are populated on this row • ref_number (Text) — Sage reference number. Audit trail to source ledger • document_date (Date) — Date transaction occurred: work date (PR), invoice date (AP), billing date (AR), entry date (GL) • posted_date (Date) — Date posted to ledger. May lag document_date from batch posting • number (Text) — Context-dependent ID: PR=employee code, AP=doc/invoice number, AR=doc number, GL=entry number • name (Text) — Context-dependent name: PR=worker (Last, First), AP=vendor, AR=customer, GL=description • regular_hours (Number) — Regular-rate hours. PR only; blank for AP/AR/GL • overtime_hours (Number) — OT-rate hours. PR only; blank for AP/AR/GL • regular_amount (Currency) — Dollar amount at regular rate (PR) or primary amount (AP/AR/GL) • overtime_amount (Currency) — Dollar amount at OT rate. PR only; blank for AP/AR/GL • actual_amount (Currency) — Total line amount. PR=reg+OT. AP/AR/GL=full amount. Rolls up to cost code totals • check_number (Text) — Payroll check number. PR only; blank for AP/AR/GL • net_due (Currency) — Amount due after retainage. Most lines: equals actual_amount. AR: actual minus retainage • retainage (Currency) — Retainage withheld. Primarily on AR billing lines. Earned but not collected
COST CODE SUMMARIES (1 field — array of 11-field objects)
cost_code_summaries | Cost Code Summaries | Array of Objects | 3 — Budget/Financial |  | [{cost_code: "120", description: "Roughin", current_budget: 119000, plus_minus_budget: 18300, actual_amount: 137300, net_due: 137300, retainage: 0, regular_hours: 2436, overtime_hours: 312.5, doubletime_hours: 0}, ...] | JDR Parse | Each object is one cost code totals row from the JDR. Object schema (11 fields): • cost_code (Text) — Cost code identifier • description (Text) — Cost code description • original_budget (Currency) — Original bid budget • current_budget (Currency) — Current budget with COs/transfers • plus_minus_budget (Currency) — Variance: actual minus current_budget. Positive = over budget • actual_amount (Currency) — Total actual spend under this code • net_due (Currency) — Net due after retainage • retainage (Currency) — Retainage held (primarily AR codes) • regular_hours (Number) — Total regular hours charged • overtime_hours (Number) — Total OT hours. OT ratio = OT÷(Reg+OT+DT) • doubletime_hours (Number) — Total DT hours. Should be near zero on well-managed jobs
JOB TOTALS (6 fields)
job_totals_revenue | Job Totals — Revenue | Currency | 3 — Budget/Financial |  | 1,391,455.00 | JDR Parse | Total AR billings for the job. Top line from the JDR Job Totals section.
job_totals_expenses | Job Totals — Expenses | Currency | 3 — Budget/Financial |  | 858,180.70 | JDR Parse | Total expenses (PR+AP+GL). Direct cost baseline for margin calculation.
job_totals_net | Job Totals — Net | Currency | 3 — Budget/Financial |  | 533,274.30 | JDR Parse | Revenue minus expenses. Gross profit before overhead burden.
job_totals_net_due | Job Totals — Net Due | Currency | 3 — Budget/Financial |  | 533,274.30 | JDR Parse | Net due across the entire job after retainage adjustments.
job_totals_retainage | Job Totals — Retainage | Currency | 3 — Budget/Financial |  | 69,572.75 | JDR Parse | Total retainage held across all AR billings. Earned but not collected.
job_totals_by_source | Job Totals — By Source | Array of {source, amount} | 3 — Budget/Financial |  | [{PR, 439953.72}, {AP, 408537.07}, {GL, 9689.91}] | JDR Parse | Expense breakdown by transaction source. Shows labor vs. material vs. overhead cost mix.
DERIVED — CALCULATED, NOT LABELED (47 fields)
project_duration_months | Project Duration (Months) | Number | 1 — Identity |  | 17.8 | Derived | (COALESCE(project_end_date, MAX(line_items[].document_date)) − project_start_date) ÷ 30.4. Fractional months. If project_end_date is null (active job), uses the latest line-item document date as a proxy.
scope_benchmarks | Scope Benchmarks | Array of Objects | 7 — Crew/Productivity |  | [{label: "dwelling_units", dollars_per_unit: 14200, hours_per_unit: 243, units_per_month: 5.2, revenue_per_unit: 23190}, {label: "fixtures", dollars_per_unit: 3460, hours_per_unit: 59, units_per_month: 21.5, revenue_per_unit: 5615}] | Derived | GROUP BY scope_metrics[].label. One object per scope metric entry. Object schema (5 fields): • label (Text) — Mirrored from scope_metrics[].label • dollars_per_unit (Currency) — total_jtd_cost ÷ scope_metrics[i].count • hours_per_unit (Number) — total_labor_hours ÷ scope_metrics[i].count • units_per_month (Number) — scope_metrics[i].count ÷ project_duration_months • revenue_per_unit (Currency) — abs(job_totals_revenue) ÷ scope_metrics[i].count Empty array if scope_metrics is empty. Benchmark-comparable across any projects sharing a label (e.g., any two jobs with "dwelling_units" can compare dollars_per_dwelling_unit).
effective_hourly_rate | Effective Hourly Rate | Currency | 7 — Crew/Productivity |  | $41.58 | Derived | line_items[].actual_amount ÷ line_items[].regular_hours (WHERE source=PR). Per-worker pay rate for escalation tracking.
cc_pct_budget_consumed | Cost Code — % Budget Consumed | Percent | 3 — Budget/Financial |  | 115.4% | Derived | cost_code_summaries[].actual_amount ÷ cost_code_summaries[].current_budget × 100. Over 100% = overrun.
cc_ot_ratio | Cost Code — OT Ratio | Percent | 7 — Crew/Productivity |  | 11.4% | Derived | cost_code_summaries[].overtime_hours ÷ (regular + overtime + doubletime) × 100. Above 15% = scheduling pressure.
cc_blended_cost_per_hour | Cost Code — Blended $/Hour | Currency | 7 — Crew/Productivity |  | $43.22 | Derived | SUM(line_items[].actual_amount WHERE source=PR AND cost_code=X) ÷ SUM(regular_hours + overtime_hours). Includes OT premium.
job_gross_margin_pct | Job Gross Margin % | Percent | 3 — Budget/Financial |  | 38.3% | Derived | job_totals_net ÷ job_totals_revenue × 100. Bottom-line project health metric.
days_to_post | Days to Post | Number | 13 — Workflow/Admin |  | 16 | Derived | line_items[].posted_date − line_items[].document_date. Posting lag per line. Flag > 30 days.
ot_premium_cost | OT Premium Cost | Currency | 3 — Budget/Financial |  | $4,687.50 | Derived | line_items[].overtime_amount − (effective_hourly_rate × overtime_hours). Incremental cost of OT above regular rate.
cost_by_source_pr_amount | Payroll (PR) Total | Currency | 3 — Budget/Financial |  | $439,953.72 | Derived | SUM(line_items[].actual_amount WHERE source=PR). Total in-house labor cost. The single biggest expense driver on most mechanical jobs.
cost_by_source_ap_amount | Accounts Payable (AP) Total | Currency | 3 — Budget/Financial |  | $408,537.07 | Derived | SUM(line_items[].actual_amount WHERE source=AP). Total material + subcontractor cost.
cost_by_source_gl_amount | General Ledger (GL) Total | Currency | 3 — Budget/Financial |  | $9,689.91 | Derived | SUM(line_items[].actual_amount WHERE source=GL). Overhead allocations, warehouse, misc fees.
direct_cost | Direct Cost | Currency | 3 — Budget/Financial |  | $858,180.70 | Derived | cost_by_source_pr_amount + cost_by_source_ap_amount + cost_by_source_gl_amount. Total project spend before margin.
net_profit | Net Profit | Currency | 3 — Budget/Financial |  | $533,274.30 | Derived | job_totals_revenue − direct_cost. Gross profit before overhead burden allocation.
pr_pct_of_revenue | PR % of Revenue | Percent | 3 — Budget/Financial |  | 31.6% | Derived | cost_by_source_pr_amount ÷ job_totals_revenue × 100. Labor cost as share of contract value.
ap_pct_of_revenue | AP % of Revenue | Percent | 3 — Budget/Financial |  | 29.4% | Derived | cost_by_source_ap_amount ÷ job_totals_revenue × 100. Material/sub cost as share of contract value.
direct_cost_pct_of_revenue | Direct Cost % of Revenue | Percent | 3 — Budget/Financial |  | 61.7% | Derived | direct_cost ÷ job_totals_revenue × 100. Overall cost ratio — complement of gross margin.
total_labor_hours | Total Labor Hours | Number | 7 — Crew/Productivity |  | 13,097.25 | Derived | SUM(line_items[].regular_hours + line_items[].overtime_hours) WHERE source=PR. Total field labor hours across all cost codes.
pr_src_cost_per_hr | PR-Source Cost per Hour | Currency | 7 — Crew/Productivity |  | $30.03 | Derived | cost_by_source_pr_amount ÷ total_labor_hours. Full PR-source cost per hour including OT premium. The "what the job actually cost in labor" number. Formerly blended_gross_wage (renamed per Action #3).
straight_time_rate | Straight-Time Rate | Currency | 7 — Crew/Productivity |  | $30.39 | Derived | SUM(line_items[].regular_amount WHERE source=PR) ÷ SUM(line_items[].regular_hours WHERE source=PR). Weighted straight-time wage rate across all PR hours — excludes OT premium. Closest JCR-native proxy for "nominal hourly wage."
worker_nominal_wages | Worker Nominal Wages | Array of Objects | 7 — Crew/Productivity |  | [{name: "Rivera, Eli P", reg_hours: 746.0, ot_hours: 110.0, reg_amount: 14896, ot_amount: 1992, nominal_rate: 19.97}, ...] | Derived | GROUP BY line_items[].name WHERE source=PR. One object per worker. Object schema (6 fields): • name (Text) — Worker name as printed on PR lines (Last, First) • reg_hours (Number) — SUM of regular_hours across all the worker's PR lines • ot_hours (Number) — SUM of overtime_hours • reg_amount (Currency) — SUM of regular_amount • ot_amount (Currency) — SUM of overtime_amount • nominal_rate (Currency) — reg_amount ÷ reg_hours. The worker's declared hourly rate as derived from Sage PR bookings. Enables any downstream slice (production-only, leads-only, etc.) without a separate worker roster.
nominal_wage_percentiles | Nominal Wage Percentiles | Object (5 fields) | 7 — Crew/Productivity |  | {p10: $18.12, p25: $19.63, p50: $22.12, p75: $40.70, p90: $49.29} | Derived | Percentile snapshot across worker_nominal_wages[].nominal_rate. Shape of the wage distribution in 5 numbers. A wide spread between p25 and p75 flags a bimodal roster (e.g. apprentices + leads); a tight spread indicates a homogeneous crew.
fully_loaded_wage | Fully-Loaded Wage | Currency | 7 — Crew/Productivity |  | $47.23 | Derived | (cost_by_source_pr_amount + burden_total) ÷ total_labor_hours. pr_src_cost_per_hr plus burden and payroll taxes. True loaded cost per labor hour.
burden_multiplier | Burden Multiplier | Number | 7 — Crew/Productivity |  | 1.34x | Derived | fully_loaded_wage ÷ pr_src_cost_per_hr. How much burden adds to each dollar of PR-source cost. Industry typical: 1.25–1.45x.
total_workers | Total Workers | Number | 7 — Crew/Productivity |  | 12 | Derived | COUNT DISTINCT(line_items[].name WHERE source=PR). Unique payroll IDs across the job. Crew size indicator.
lead_to_helper_ratio | Lead-to-Helper Ratio | Text (free) | 7 — Crew/Productivity |  | 1:8 | Derived | Supervision hours ÷ production hours. Derived from cost_code_summaries WHERE cost_code IN (100) vs production codes. Low ratio = under-supervised.
burden_total | Total Burden + Taxes | Currency | 3 — Budget/Financial |  | $148,589.84 | Derived | SUM(cost_code_summaries[].actual_amount WHERE cost_code IN (995, 998)). Payroll burden + taxes allocated to this job.
material_spend_total | Total Material Spend | Currency | 3 — Budget/Financial |  | $385,684.06 | Derived | SUM(cost_code_summaries[].actual_amount WHERE cost_code LIKE 2xx OR cost_code=039). All material cost codes combined.
material_budget_total | Total Material Budget | Currency | 3 — Budget/Financial |  | $398,550.00 | Derived | SUM(cost_code_summaries[].current_budget WHERE cost_code LIKE 2xx OR cost_code=039). Material budget baseline for variance.
material_codes_tracked | Material Codes Tracked | Number | 3 — Budget/Financial |  | 11 | Derived | COUNT(cost_code_summaries WHERE cost_code LIKE 2xx OR cost_code=039). Distinct material cost codes with activity.
material_codes_over_budget | Material Codes Over Budget | Number | 3 — Budget/Financial |  | 2 | Derived | COUNT(cost_code_summaries WHERE material code AND plus_minus_budget > 0). Flags material categories needing attention.
material_codes_under_budget | Material Codes Under Budget | Number | 3 — Budget/Financial |  | 9 | Derived | COUNT(cost_code_summaries WHERE material code AND plus_minus_budget <= 0). Strong estimating discipline indicator.
largest_material_overrun | Largest Material Overrun | Text (free) | 3 — Budget/Financial |  | 242 Mech Room Material: $22,695 vs $12,000 budget | Derived | Material cost code with the largest positive plus_minus_budget (actual − current_budget). Biggest hot spot in material spend.
largest_material_savings | Largest Material Savings | Text (free) | 3 — Budget/Financial |  | 230 Finish Material: $210,145 vs $278,000 budget | Derived | Material cost code with the largest negative plus_minus_budget (actual − current_budget). Biggest dollar save in materials.
material_vendor_count | Material Vendor Count | Number | 3 — Budget/Financial |  | 14 | Derived | COUNT DISTINCT(line_items[].name WHERE source=AP). Unique vendors invoiced on this job.
top_vendor_spend | Top Vendor Spend | Text (free) | 3 — Budget/Financial |  | Rosen Supply: $67,432 (37% of AP) | Derived | Vendor with highest SUM(line_items[].actual_amount WHERE source=AP). Vendor concentration risk — single vendor > 30% flags dependency.
phases_over_budget | Phases Over Budget | Number | 3 — Budget/Financial |  | 5 | Derived | COUNT(cost_code_summaries WHERE plus_minus_budget > 0 AND cost_code != 999). Number of work phases running over. All expense codes included (burden 995 and taxes 998 count as phases).
phases_under_budget | Phases Under Budget | Number | 3 — Budget/Financial |  | 9 | Derived | COUNT(cost_code_summaries WHERE plus_minus_budget <= 0 AND cost_code != 999). Phases with margin remaining.
largest_overrun | Largest Phase Overrun | Text (free) | 3 — Budget/Financial |  | 120 Roughin: $177,292 vs $119,000 budget (-$58,292) | Derived | Work phase cost code with largest positive plus_minus_budget (actual − current_budget). Risk hot spot — drives root cause analysis.
largest_savings | Largest Phase Savings | Text (free) | 3 — Budget/Financial |  | 130 Finish: $34,658 vs $60,800 budget (+$26,142) | Derived | Work phase with largest negative plus_minus_budget (actual − current_budget). May indicate conservative bid or scope not yet complete.
total_jtd_cost | Total Job-to-Date Cost | Currency | 3 — Budget/Financial |  | $858,180.70 | Derived | SUM(cost_code_summaries[].actual_amount WHERE cost_code NOT IN sales/revenue). Total actual spend across all expense codes.
total_budget | Total Budget (All Codes) | Currency | 3 — Budget/Financial |  | $528,617.57 | Derived | SUM(cost_code_summaries[].current_budget) for all expense codes. Total current budget baseline.
overall_pct_budget_consumed | Overall % Budget Consumed | Percent | 3 — Budget/Financial |  | 162.3% | Derived | total_jtd_cost ÷ total_budget × 100. Job-level budget health. Over 100% = total overrun.
total_over_under_budget | Total Over/Under Budget | Currency | 3 — Budget/Financial |  | -$329,563.13 | Derived | total_budget − total_jtd_cost. Negative = job is over budget in aggregate.
variance_trend | Variance Trend (vs Prior Period) | Text (free) | 13 — Workflow/Admin |  | Worsening | Derived | Compares current total_over_under_budget to prior report period. Flags accelerating overruns before they blow the job.
labor_unit_cost_per_hr | Labor Unit Cost per Hour | Currency | 7 — Crew/Productivity |  | $33.59/hr | Derived | SUM(cost_code_summaries[].actual_amount WHERE labor codes) ÷ total_labor_hours. The unit cost of one labor hour on this job. NOT a productivity/throughput metric — for that, see revenue_per_labor_hour below.
revenue_per_labor_hour | Revenue per Labor Hour | Currency | 7 — Crew/Productivity |  | $94.97/hr | Derived | abs(job_totals_revenue) ÷ total_labor_hours. Labor throughput — revenue generated per labor hour on the job. Complement to labor_unit_cost_per_hr: unit_cost is cost/hr, this is revenue/hr. Ratio = job gross margin per labor hour.
material_price_variance | Material Price Variance | Currency | 3 — Budget/Financial |  | +$12,865.94 | Derived | material_budget_total − material_spend_total. Positive = under budget on materials overall.
co_absorption_rate | CO Absorption Rate | Percent | 13 — Workflow/Admin |  | 0% | Derived | total_change_orders ÷ job_totals_revenue × 100. What portion of revenue comes from change order scope.
forecast_to_complete | Forecast to Complete | Currency | 3 — Budget/Financial |  | $0.00 | Derived | Estimated remaining spend based on cost_to_complete and burn rate trend. Projects total cost at completion.
labor_to_material_ratio | Labor-to-Material Ratio | Number | 3 — Budget/Financial |  | 1.08x | Derived | cost_by_source_pr_amount ÷ material_spend_total. Shows the balance between labor and material spend. Values >1 = labor-heavy job; <1 = material-heavy. Useful for bid validation and crew sizing.

## Reconciliation Protocol
RECONCILIATION PROTOCOL — agent-labeler cross-check contract
For each field listed below, the labeler must (1) derive from JCR per primary_derivation, (2) cross-check against the named external source, (3) handle match/mismatch per the documented actions. Divergence is not always an error — the known_divergences column explains which gaps are expected and why.
field_name | primary_derivation (JCR-only) | cross_check_source | expected_relationship | on_match | on_mismatch | known_divergences
plus_minus_budget | actual − current_budget per cost code (positive = over, negative = under) | prior v3 schema output | sign-flipped (v3 convention was inverted) | N/A — v3 outputs should never match v4 convention | Trust v4. Flag any downstream tool or Notion doc still using v3 sign convention as invalid. | ALL pre-Action-#1 artifacts (v3 schema, early Notion drafts) will show opposite sign. Expected.
current_budget + original_budget | Carried distinctly from JCR Budget column (original) and Current Budget column (original + Changes) | Sage Job Cost Report header/summary block | equal | Pass; no further action. | Escalate — likely JCR export corruption or column mis-mapping. Do not silently repair. | None expected. A mismatch here is a real error.
pr_src_cost_per_hr | total labor cost ÷ total labor hours across all labor phases (incl. 995 burden, 998 taxes; excl. 999 sales) | Sage PR-source report total blended rate | within ±$0.50/hr (rounding across 40+ workers) | Pass. | Re-derive with phase-code filter made explicit. Verify 999 Sales excluded and 995/998 included. | Do NOT compare to Notion's $19.94 figure — that is a different population slice (see worker_nominal_wages row).
worker_nominal_wages[] + nominal_wage_percentiles | Per worker: reg_amount ÷ reg_hours (from PR-source line items). Then compute p10/p25/p50/p75/p90 across workers. | Notion reconciliation doc "average wage ≈ $19.94" | POPULATION-SLICE — Notion measures Apprentice/Helper tier only (~25 of 42 workers) | SUSPICIOUS — if Notion equals the full-population p50, one side is measuring the wrong population. Investigate. | Expected. Verify Notion figure falls within JCR-derived p10-p25 range (~$19.59-$19.93). If yes, mark explained. | This is the canonical explained-variance case. Both sources are correct; they measure different slices of the workforce.
labor_unit_cost_per_hr vs revenue_per_labor_hour | labor_unit_cost_per_hr = total labor cost ÷ billable hours. revenue_per_labor_hour = contract revenue ÷ billable hours. | prior single field labor_productivity_rate (deprecated in v4) | NOT equal by design. For Job 2012: cost ≈ $19.88/hr, revenue ≈ $94.97/hr. | N/A — equality would indicate the labeler confused numerators. | If they come out equal, re-derive. One is a cost metric, the other is a throughput metric. | The ratio (revenue/cost ≈ 4.78x) is the actual productivity ratio. Neither field alone represents productivity.
scope_metrics[] + scope_benchmarks | Labeler reads project-attribute input for trade-declared metrics. scope_benchmarks[i] = {dollars_per_unit, hours_per_unit} for each metric. | None — trade-declared, no external authority | N/A until scope_metrics is populated | Once populated, compare year-over-year across similar trade/scope projects (future work). | If scope_benchmarks is requested before scope_metrics is declared, raise a warning — do not silently emit nulls. | Pending project-attribute input for Job 2012. Expected to remain pending until Sam/trade lead declares plumbing scope metrics.
Future additions: when a new audit finding produces a schema change, append a new row here before closing the action. The labeler reads this tab as its cross-check contract — treat it as production config, not documentation.