## Overview
Job #2001 · SRM 230 Broadway Apartments
Cortex JCR Summary • SRM Development • 230 Broadway, Seattle, WA 98102 • 282-unit 7-story multifamily apartments with retail and amenity spaces • Apr 2011 – Sep 2012 (~18 months)
PROJECT OVERVIEW
Project Job # | 2001
Project Name: | SRM 230 Broadway Apartments
General Contractor | SRM Development
Location | 230 Broadway, Seattle, WA 98102
Project Duration | Apr 2011 – Sep 2012 (~18 months)
Total Unique Documents | Project folder: Contract (SRM Development + One Way Plumbing), Billing (aggregate + 18 SOVs), POs (228 scheduled), Permits (gas, boiler), Design sets, ASIs, As-builts
CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
$2,121,874 |  | $832,972 |  | $1,288,901 |  | 20,280
Original $1,850,270 + $0 COs |  | 39.3% margin |  | 60.7% of revenue |  | 27 workers
COST BREAKDOWN
Category | Budget | Actual | Variance | % Budget | % of Cost
Labor | 396328 | 425500.68 | -29172.68 | 107.4% | 33.01%
Material | 717142 | 637990.88 | 79151.12 | 88.96% | 49.5%
Overhead | 11000 | 7343.82 | 3656.18 | 66.76% | 0.5698%
Burden | 201813.34 | 218065.83 | -16252.49 | 108.1% | 16.92%
TOTAL | 1326283.34 | 1288901.21 | 37382.13 | 97.18% | 100%
PROJECT PROFILE
Metric | Value | Metric | Value | Metric | Value
Residential Units | 282 | Water Closets | 285 | Lavatories | 285
Kitchen Sinks | 234 | Dishwashers | 234 | Tubs/Showers | 277
Shower Stalls | 12 | Floor Drains | TBD | Roof Drains | 30
Total Fixtures | 1315 | Fixtures / Unit | 4.66 | Floors | 7 stories + retail + amenity
Duration | 18 mo
SOURCES
Job #2001 — SRM 230 Broadway Apartments • GC: SRM Development • 230 Broadway, Seattle
Canonical source: 2001 Job Detail Report.pdf (180 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count (282) from plumbing bid sheet: 270 standard units + 12 ADA units
Fixture count (1315) from material takeoff: 285 WC + 285 lav + 234 kitchen sink + 234 DW + 265 tub + 12 shower + additional drains
Contract: One Way Plumbing contract executed (SRM Development GC) with OWP markup
Billing: 230 BROADWAY AGGREGATE BILLING.xls (18 pay apps Apr 2011 – Sep 2012) + 17 SOV files
Final contract $2,121,874 (original $1,850,270 + $0 COs)

## Budget vs Actual
Budget vs Actual — All Cost Codes
Code | Description | Orig Budget | Rev Budget | Actual | Variance | % Used
LABOR
011 | DS & RD Labor | 33300 | 33300 | 21823.68 | 11476.32 | 65.54%
100 | Supervision | 11000 | 11000 | 4198.3 | 6801.7 | 38.17%
101 | Takeoff & Purchase Labor | 11000 | 11000 | 1227.8 | 9772.2 | 11.16%
110 | Underground Labor | 6500 | 6500 | 5128.27 | 1371.73 | 78.9%
111 | Garage Labor | 37860 | 37860 | 51832.47 | -13972.47 | 136.9%
112 | Canout Labor | 12751 | 12751 | 9995.05 | 2755.95 | 78.39%
113 | Foundation Drain Labor | 9000 | 9000 | 3190.16 | 5809.84 | 35.45%
120 | Roughin Labor | 185705 | 185705 | 218574.15 | -32869.15 | 117.7%
130 | Finish Labor | 37212 | 37212 | 46024.72 | -8812.72 | 123.7%
140 | Gas Labor | 9450 | 9450 | 14211.67 | -4761.67 | 150.4%
141 | Water Main/Insulation Lab | 36300 | 36300 | 36651.38 | -351.38 | 101%
142 | Mech Room Labor | 6250 | 6250 | 12626.53 | -6376.53 | 202%
145 | Tub/Shower Labor | 0 | 0 | 16.5 | -16.5 | 0%
MATERIAL
039 | DS & RD Material | 34350 | 34350 | 10684.8 | 23665.2 | 31.11%
210 | Underground Material | 5400 | 5400 | 6150.1 | -750.1 | 113.9%
211 | Garage Material | 35055 | 35055 | 36037.82 | -982.82 | 102.8%
212 | Canout Material | 19308 | 19308 | 16844.65 | 2463.35 | 87.24%
213 | Foundation Material | 10000 | 10000 | 3564.14 | 6435.86 | 35.64%
220 | Roughin Material | 197530 | 197530 | 148282.22 | 49247.78 | 75.07%
230 | Finish Material | 372749 | 372749 | 327741.23 | 45007.77 | 87.93%
240 | Gas Material | 7500 | 7500 | 10163.67 | -2663.67 | 135.5%
241 | Water Main/Insulation Mat | 30250 | 30250 | 75553.36 | -45303.36 | 249.8%
242 | Mech Room Material | 5000 | 5000 | 2968.89 | 2031.11 | 59.38%
OVERHEAD
600 | Subcontractor | 5500 | 5500 | 5407 | 93 | 98.31%
601 | Engineering/Plans | 5500 | 5500 | 1835.26 | 3664.74 | 33.37%
603 | Permits & Licenses | 0 | 0 | 101.56 | -101.56 | 0%
BURDEN
995 | Payroll Burden | 170039.6 | 170039.6 | 183056.2 | -13016.6 | 107.7%
998 | Payroll Taxes | 31773.74 | 31773.74 | 35009.63 | -3235.89 | 110.2%
TOTAL | Direct Cost | 1326283.34 | 1326283.34 | 1288901.21 | 37382.13 | 97.18%
SOURCES
Job #2001 — SRM 230 Broadway Apartments • GC: SRM Development • 230 Broadway, Seattle
Canonical source: 2001 Job Detail Report.pdf (180 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count (282) from plumbing bid sheet: 270 standard units + 12 ADA units
Fixture count (1315) from material takeoff: 285 WC + 285 lav + 234 kitchen sink + 234 DW + 265 tub + 12 shower + additional drains
Contract: One Way Plumbing contract executed (SRM Development GC) with OWP markup
Billing: 230 BROADWAY AGGREGATE BILLING.xls (18 pay apps Apr 2011 – Sep 2012) + 17 SOV files
Final contract $2,121,874 (original $1,850,270 + $0 COs)

## Cost Breakdown
Cost Breakdown — Category Deep Dive
A. CATEGORY SHARE OF DIRECT COST
Category | # Codes | Budget | Actual | Variance | % Budget | % of Cost | Per Unit
Labor | 13 | 396328 | 425500.68 | -29172.68 | 107.4% | 33.01% | 1508.8677
Material | 10 | 717142 | 637990.88 | 79151.12 | 88.96% | 49.5% | 2262.379
Overhead | 3 | 11000 | 7343.82 | 3656.18 | 66.76% | 0.5698% | 26.0419
Burden | 2 | 201813.34 | 218065.83 | -16252.49 | 108.1% | 16.92% | 773.2831
B. LARGEST OVERRUNS (Actual > Revised Budget)
Code | Description | Rev Budget | Actual | Overrun | % Over
241 | Water Main/Insulation Mat | 30250 | 75553.36 | 45303.36 | 149.8%
120 | Roughin Labor | 185705 | 218574.15 | 32869.15 | 17.7%
111 | Garage Labor | 37860 | 51832.47 | 13972.47 | 36.91%
995 | Payroll Burden | 170039.6 | 183056.2 | 13016.6 | 7.655%
130 | Finish Labor | 37212 | 46024.72 | 8812.72 | 23.68%
142 | Mech Room Labor | 6250 | 12626.53 | 6376.53 | 102%
140 | Gas Labor | 9450 | 14211.67 | 4761.67 | 50.39%
998 | Payroll Taxes | 31773.74 | 35009.63 | 3235.89 | 10.18%
240 | Gas Material | 7500 | 10163.67 | 2663.67 | 35.52%
211 | Garage Material | 35055 | 36037.82 | 982.82 | 2.804%
C. LARGEST SAVINGS (Actual < Revised Budget)
Code | Description | Rev Budget | Actual | Savings | % Under
220 | Roughin Material | 197530 | 148282.22 | 49247.78 | 24.93%
230 | Finish Material | 372749 | 327741.23 | 45007.77 | 12.07%
039 | DS & RD Material | 34350 | 10684.8 | 23665.2 | 68.89%
011 | DS & RD Labor | 33300 | 21823.68 | 11476.32 | 34.46%
101 | Takeoff & Purchase Labor | 11000 | 1227.8 | 9772.2 | 88.84%
100 | Supervision | 11000 | 4198.3 | 6801.7 | 61.83%
213 | Foundation Material | 10000 | 3564.14 | 6435.86 | 64.36%
113 | Foundation Drain Labor | 9000 | 3190.16 | 5809.84 | 64.55%
601 | Engineering/Plans | 5500 | 1835.26 | 3664.74 | 66.63%
112 | Canout Labor | 12751 | 9995.05 | 2755.95 | 21.61%
SOURCES
Job #2001 — SRM 230 Broadway Apartments • GC: SRM Development • 230 Broadway, Seattle
Canonical source: 2001 Job Detail Report.pdf (180 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count (282) from plumbing bid sheet: 270 standard units + 12 ADA units
Fixture count (1315) from material takeoff: 285 WC + 285 lav + 234 kitchen sink + 234 DW + 265 tub + 12 shower + additional drains
Contract: One Way Plumbing contract executed (SRM Development GC) with OWP markup
Billing: 230 BROADWAY AGGREGATE BILLING.xls (18 pay apps Apr 2011 – Sep 2012) + 17 SOV files
Final contract $2,121,874 (original $1,850,270 + $0 COs)

## Material
Material Spend Analysis
10 material cost codes • $637,991 JDR material • 16 AP vendors • $739,309 total AP
A. MATERIAL BY COST CODE
Code | Description | Rev Budget | Actual | Variance | % Used | % of Mat | Per Unit
039 | DS & RD Material | 34350 | 10684.8 | 23665.2 | 31.11% | 1.675% | 37.8894
210 | Underground Material | 5400 | 6150.1 | -750.1 | 113.9% | 0.964% | 21.8089
211 | Garage Material | 35055 | 36037.82 | -982.82 | 102.8% | 5.649% | 127.7937
212 | Canout Material | 19308 | 16844.65 | 2463.35 | 87.24% | 2.64% | 59.7328
213 | Foundation Material | 10000 | 3564.14 | 6435.86 | 35.64% | 0.5587% | 12.6388
220 | Roughin Material | 197530 | 148282.22 | 49247.78 | 75.07% | 23.24% | 525.8235
230 | Finish Material | 372749 | 327741.23 | 45007.77 | 87.93% | 51.37% | 1162.2029
240 | Gas Material | 7500 | 10163.67 | -2663.67 | 135.5% | 1.593% | 36.0414
241 | Water Main/Insulation Mat | 30250 | 75553.36 | -45303.36 | 249.8% | 11.84% | 267.9197
242 | Mech Room Material | 5000 | 2968.89 | 2031.11 | 59.38% | 0.4653% | 10.528
TOTAL | All Material | 717142 | 637990.88 | 79151.12 | 88.96% | 100% | 2262.379
B. VENDORS BY SPEND (AP)
Vendor | # Invoices | Total Spend | % of AP |  |  |  | Avg Invoice
Ferguson Enterprises, Inc. | 210 | 343362.11 | 46.44% |  |  |  | 1635.0577
Keller Supply Company | 161 | 261501.21 | 35.37% |  |  |  | 1624.2311
Mechanical Sales, Inc. | 7 | 72801.65 | 9.847% |  |  |  | 10400.2357
Franklin Engineering | 5 | 21978.91 | 2.973% |  |  |  | 4395.782
Bank of America CC | 5 | 15099.99 | 2.042% |  |  |  | 3019.998
Quality Concrete Products, Inc. | 2 | 7788 | 1.053% |  |  |  | 3894
Evergreen Concrete Cutting, Inc. | 7 | 4140 | 0.56% |  |  |  | 591.4286
Ferguson Enterprises, Inc. #3007 | 7 | 4097.84 | 0.5543% |  |  |  | 585.4057
MP Industrial | 3 | 2339.19 | 0.3164% |  |  |  | 779.73
C.M. Hoskins Company | 8 | 2018.25 | 0.273% |  |  |  | 252.2812
Herc Rentals, Inc. | 6 | 1835.26 | 0.2482% |  |  |  | 305.8767
MAD Concrete Cutting & Coring, Inc. | 3 | 1040 | 0.1407% |  |  |  | 346.6667
Fastenal Company | 3 | 520.48 | 0.0704% |  |  |  | 173.4933
DRSi | 4 | 468.55 | 0.06338% |  |  |  | 117.1375
R.A. Brown Backflow Testing | 1 | 227 | 0.0307% |  |  |  | 227
Airgas USA, LLC | 1 | 90.46 | 0.01224% |  |  |  | 90.46
TOTAL | 433 | 739308.9 | 100%
SOURCES
Job #2001 — SRM 230 Broadway Apartments • GC: SRM Development • 230 Broadway, Seattle
Canonical source: 2001 Job Detail Report.pdf (180 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count (282) from plumbing bid sheet: 270 standard units + 12 ADA units
Fixture count (1315) from material takeoff: 285 WC + 285 lav + 234 kitchen sink + 234 DW + 265 tub + 12 shower + additional drains
Contract: One Way Plumbing contract executed (SRM Development GC) with OWP markup
Billing: 230 BROADWAY AGGREGATE BILLING.xls (18 pay apps Apr 2011 – Sep 2012) + 17 SOV files
Final contract $2,121,874 (original $1,850,270 + $0 COs)
Vendor AP ties to JDR 'by Source: AP' line (739,308.90)

## Crew & Labor
Crew & Labor — Per-Worker Breakdown
Worker | Hours | Gross Pay | $/Hour | Tier
Hubbard, Robert W | 2221 | 69758.1 | 31.4084 | Senior
McCabe, Thomas C | 1824.5 | 23718.5 | 13 | Apprentice
Sepulveda Gonzalez, Alfredo | 1720.5 | 37851 | 22 | Mid
Barnhart, Joseph N | 1558 | 38797.2 | 24.9019 | Mid
Ross, Kelli M | 1451 | 38117.77 | 26.27 | Mid
Hubbard, Dustin R | 1338.5 | 13479.5 | 10.0706 | Apprentice
Palma Vides, Hugo | 1338 | 33450 | 25 | Mid
Reed, Reuben H | 1302 | 32550 | 25 | Mid
Quintanilla, Esteban R | 1231.5 | 35713.5 | 29 | Mid
Sanders, Allen O | 1170.5 | 28092 | 24 | Mid
Castro Hernandez, Carlos E | 1157.5 | 24926 | 21.5343 | Mid
Mazil, Antonio | 884.75 | 10617 | 12 | Apprentice
Cortes Mendiola, Victor H | 778.5 | 14791.5 | 19 | Mid
Gerard, Jeffrey S | 733 | 23119.4 | 31.5408 | Senior
Soto Cruz, Jovani | 629 | 6290 | 10 | Apprentice
Meza Fuentes, Erick A | 619.5 | 7763.75 | 12.5323 | Apprentice
Veley, Nathaniel S | 486 | 9112.75 | 18.7505 | Mid
Slaton, Justin T | 411 | 4110 | 10 | Apprentice
Bravo, Manuel D | 288 | 2880 | 10 | Apprentice
Paco Leyva, Orlando | 262 | 2621.5 | 10.0057 | Apprentice
Arreola, Israel A | 248 | 2480 | 10 | Apprentice
Gerard, Jordan E | 220.25 | 2202.5 | 10 | Apprentice
Waites, Thaddeus Z | 182 | 4368 | 24 | Mid
Michelman, Joshua M | 172.5 | 1725 | 10 | Apprentice
Morelos, Silverio | 53 | 1510.02 | 28.4909 | Mid
Outson, Tyler C | 27.5 | 275 | 10 | Apprentice
Rivera Romera, Arturo | 8 | 96 | 12 | Apprentice
TOTAL (27 workers) | 22316 | 470415.99 | 21.0798
SOURCES
Job #2001 — SRM 230 Broadway Apartments • GC: SRM Development • 230 Broadway, Seattle
Canonical source: 2001 Job Detail Report.pdf (180 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count (282) from plumbing bid sheet: 270 standard units + 12 ADA units
Fixture count (1315) from material takeoff: 285 WC + 285 lav + 234 kitchen sink + 234 DW + 265 tub + 12 shower + additional drains
Contract: One Way Plumbing contract executed (SRM Development GC) with OWP markup
Billing: 230 BROADWAY AGGREGATE BILLING.xls (18 pay apps Apr 2011 – Sep 2012) + 17 SOV files
Final contract $2,121,874 (original $1,850,270 + $0 COs)
Tier: Apprentice <$18/hr, Mid $18–30, Senior >$30

## Crew Analytics
Crew Analytics
A. TIER DISTRIBUTION
Tier | # Workers | Hours | Gross Pay | % of Hours
Senior | 2 | 2954 | 92877.5 | 13.24%
Mid | 12 | 12428.5 | 299279.74 | 55.69%
Apprentice | 13 | 6933.5 | 78258.75 | 31.07%
B. WAGE STATISTICS
Blended Gross Wage | 21.0798 |  |  | Payroll $ ÷ payroll hours (pre-burden)
Fully-Loaded Wage | 28.8388 |  |  | (Labor + Burden) ÷ total hours
Burden Multiplier | 1.3681 |  |  | Fully loaded ÷ gross wage
Min Worker Rate | 10 |  |  | Cheapest apprentice hour
Max Worker Rate | 31.5408 |  |  | Most expensive foreman hour
Avg Hours / Worker | 826.5185 |  |  | Crew continuity indicator
SOURCES
Job #2001 — SRM 230 Broadway Apartments • GC: SRM Development • 230 Broadway, Seattle
Canonical source: 2001 Job Detail Report.pdf (180 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count (282) from plumbing bid sheet: 270 standard units + 12 ADA units
Fixture count (1315) from material takeoff: 285 WC + 285 lav + 234 kitchen sink + 234 DW + 265 tub + 12 shower + additional drains
Contract: One Way Plumbing contract executed (SRM Development GC) with OWP markup
Billing: 230 BROADWAY AGGREGATE BILLING.xls (18 pay apps Apr 2011 – Sep 2012) + 17 SOV files
Final contract $2,121,874 (original $1,850,270 + $0 COs)

## Productivity
Productivity — Phase & Unit Metrics
A. LABOR HOURS BY PHASE
Phase | Labor Code | Hours | % of Total | Hours / Unit
DS & RD | 011 | 928 | 4.576% | 3.2908
Supervision | 100 | 130.5 | 0.6435% | 0.46277
Takeoff & Purchasing | 101 | 39 | 0.1923% | 0.1383
Underground | 110 | 203 | 1.001% | 0.71986
Garage | 111 | 2258 | 11.13% | 8.0071
Canout | 112 | 404 | 1.992% | 1.4326
Foundation Drain | 113 | 130.5 | 0.6435% | 0.46277
Roughin | 120 | 10499.75 | 51.78% | 37.2332
Finish | 130 | 2361.25 | 11.64% | 8.3732
Gas | 140 | 650 | 3.205% | 2.305
Water Main / Insulation | 141 | 1968.5 | 9.707% | 6.9805
Mech Room | 142 | 705.5 | 3.479% | 2.5018
Tub / Shower | 145 | 1.5 | 0.007397% | 0.0053191
TOTAL |  | 20279.5 | 100% | 71.9131
B. PRODUCTIVITY RATIOS
Metric | Value | Units |  | Notes
Hours / Unit | 71.9131 | hrs |  | Labor hours per residential unit
Hours / Fixture | 15.4217 | hrs |  | Labor hours per plumbing fixture
Revenue / Hour | 104.6315 | $ |  | Top-line per labor hour
Profit / Hour | 41.0746 | $ |  | Bottom-line per labor hour
Units / Month | 15.6667 | units |  | Build velocity
Fixtures / Month | 73.0556 | fix |  | Fixture install pace
Hours / Month | 1126.6389 | hrs |  | Monthly labor burn
Revenue / Month | 117881.8611 | $ |  | Monthly billing rate
SOURCES
Job #2001 — SRM 230 Broadway Apartments • GC: SRM Development • 230 Broadway, Seattle
Canonical source: 2001 Job Detail Report.pdf (180 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count (282) from plumbing bid sheet: 270 standard units + 12 ADA units
Fixture count (1315) from material takeoff: 285 WC + 285 lav + 234 kitchen sink + 234 DW + 265 tub + 12 shower + additional drains
Contract: One Way Plumbing contract executed (SRM Development GC) with OWP markup
Billing: 230 BROADWAY AGGREGATE BILLING.xls (18 pay apps Apr 2011 – Sep 2012) + 17 SOV files
Final contract $2,121,874 (original $1,850,270 + $0 COs)

## PO Commitments
Purchase Order Commitments
0 unique POs • PO amounts not dollar-parsed from individual PDFs • JDR material $637,991
A. COMMITMENTS BY COST CODE
OWP Code | Description → JDR | PO Count | % of POs | JDR Material
TOTAL |  | #VALUE! | 100% | 637990.88
B. COMMITMENTS BY VENDOR
Vendor | PO Count | % of POs
C. PO COVERAGE NOTES
Total Material Actual (JDR) |  |  | 637990.88
Unique PO Count |  |  | 0
(Dollar PO commitment not extracted — requires per-PDF parse)
SOURCES
Job #2001 — SRM 230 Broadway Apartments • GC: SRM Development • 230 Broadway, Seattle
Canonical source: 2001 Job Detail Report.pdf (180 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count (282) from plumbing bid sheet: 270 standard units + 12 ADA units
Fixture count (1315) from material takeoff: 285 WC + 285 lav + 234 kitchen sink + 234 DW + 265 tub + 12 shower + additional drains
Contract: One Way Plumbing contract executed (SRM Development GC) with OWP markup
Billing: 230 BROADWAY AGGREGATE BILLING.xls (18 pay apps Apr 2011 – Sep 2012) + 17 SOV files
Final contract $2,121,874 (original $1,850,270 + $0 COs)
PO count is deduplicated by 5-digit PO number extracted from filenames
Vendor/code classification is heuristic (filename keyword match)

## Billing & SOV
Revenue & Billing Reconciliation
18 pay applications • Apr 2011 – Sep 2012 • $2,121,874 final
A. CONTRACT SUMMARY
Original Contract |  |  |  |  | 1850270
Change Orders (net) |  |  |  |  | 0
Final Contract Value |  |  |  |  | 2121874
Retainage (5%) |  |  |  |  | 96889
Net Paid to OWP |  |  |  |  | 2024985
B. PAY APPLICATION TIMELINE
App# | Date | Period Billing | Retention | Net This Period | Aggregate | % Complete
1 | 2011-04-25 | 8800 | 440 | 8360 | 9196 | 0.4334%
2 | 2011-05-25 | 12200 | 610 | 11590 | 12749 | 0.6008%
3 | 2011-06-25 | 85700 | 4285 | 81415 | 89556.5 | 4.221%
4 | 2011-07-25 | 33400 | 1670 | 31730 | 34903 | 1.645%
5 | 2011-08-25 | 42300 | 2115 | 40185 | 44203.5 | 2.083%
6 | 2011-09-25 | 76605 | 3830.25 | 72774.75 | 80052.23 | 3.773%
7 | 2011-10-25 | 72800 | 3640 | 69160 | 76076 | 3.585%
8 | 2011-11-22 | 126900 | 6345 | 120555 | 132610.5 | 6.25%
9 | 2011-12-20 | 190280 | 9514 | 180766 | 198842.6 | 9.371%
10 | 2012-01-20 | 300190 | 15009.5 | 285180.5 | 313698.55 | 14.78%
11 | 2012-02-20 | 327550 | 16377.5 | 311172.5 | 342289.75 | 16.13%
12 | 2012-03-22 | 290890 | 14544.5 | 276345.5 | 303980.05 | 14.33%
13 | 2012-04-24 | 84964 | 4248.2 | 80715.8 | 88787.38 | 4.184%
14 | 2012-05-25 | 66897 | 3344.85 | 63552.15 | 69907.37 | 3.295%
15 | 2012-06-25 | 64100 | 3205 | 60895 | 66984.5 | 3.157%
16 | 2012-07-25 | 66142 | 3307.1 | 62834.9 | 69118.39 | 3.257%
17 | 2012-08-25 | 52396 | 2619.8 | 49776.2 | 54753.83 | 2.58%
18 | 2012-09-25 | 35670 | 1783.5 | 33886.5 | 37275.15 | 1.757%
C. BILLING ↔ JDR TIE-OUT
Metric | SOV | JDR | Δ | Status
Final Contract Value | 2121874 | 2121874 | 0 | TIES
Retainage | 96889 | 96889 | 0 | TIES
Direct Cost | 1288901 | 1288901 | 0 | TIES
SOURCES
Job #2001 — SRM 230 Broadway Apartments • GC: SRM Development • 230 Broadway, Seattle
Canonical source: 2001 Job Detail Report.pdf (180 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count (282) from plumbing bid sheet: 270 standard units + 12 ADA units
Fixture count (1315) from material takeoff: 285 WC + 285 lav + 234 kitchen sink + 234 DW + 265 tub + 12 shower + additional drains
Contract: One Way Plumbing contract executed (SRM Development GC) with OWP markup
Billing: 230 BROADWAY AGGREGATE BILLING.xls (18 pay apps Apr 2011 – Sep 2012) + 17 SOV files
Final contract $2,121,874 (original $1,850,270 + $0 COs)

## Insights
Key Insights — Job #2001 SRM 230 Broadway Apartments
Narrative observations distilled from the full JDR analysis
MARGIN PROFILE | Net profit of $832,972 on $2,121,874 revenue = 39.3% gross margin. Direct cost $1,288,901 absorbs 60.7% of revenue.
VENDOR CONCENTRATION | Ferguson Enterprises, Inc. alone = $343,362 (46% of all AP) across 210 invoices. Total 16 AP vendors, $739,309 total AP spend.
CREW PROFILE | 27 workers for 20,280 hours = 751 avg hrs/worker. Top 3 workers logged 5,766 hrs combined (28% of all labor).
ROUGHIN DOMINANCE | Code 120 Roughin Labor = 10,500 hrs (52% of all labor) and $218,574 actual. Code 230 Finish Material = $327,741 — 25% of total direct cost.
BUDGET DELIVERY | Revised budget was $1,326,283; actual direct cost $1,288,901 → $37,382 variance (2.8% under revised budget).
CONTRACT GROWTH | Contract grew from $1,850,270 to $2,121,874 — net +$271,604 (14.7%). Retainage of $96,889 (5%) withheld until closeout.
BURDEN RATIO | Burden codes 995 + 998 = $218,066 on $425,501 labor base = 51.2%. In line with OWP's typical 48–50% labor burden.
PROJECT SCALE | 282 units · 1315 fixtures · 18 months. Revenue/unit $7,524, hours/unit 71.9, profit/unit $2,954.
PRODUCTIVITY | Blended labor rate $20.98/hr. Revenue/hour $105. Profit/hour $41. 1,127 hrs/month burn rate.
FIXTURE DENSITY | 1315 fixtures ÷ 282 units = 4.66 fixtures/unit. Material/fixture $485, labor/fixture $324.
BIGGEST QUESTION
How does this job's 39.3% margin compare across similar projects in the OWP portfolio, and what operational levers drove the result — estimating accuracy, vendor pricing, or labor productivity?
SOURCES
Job #2001 — SRM 230 Broadway Apartments • GC: SRM Development • 230 Broadway, Seattle
Canonical source: 2001 Job Detail Report.pdf (180 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count (282) from plumbing bid sheet: 270 standard units + 12 ADA units
Fixture count (1315) from material takeoff: 285 WC + 285 lav + 234 kitchen sink + 234 DW + 265 tub + 12 shower + additional drains
Contract: One Way Plumbing contract executed (SRM Development GC) with OWP markup
Billing: 230 BROADWAY AGGREGATE BILLING.xls (18 pay apps Apr 2011 – Sep 2012) + 17 SOV files
Final contract $2,121,874 (original $1,850,270 + $0 COs)

## Benchmark KPIs
Benchmark KPIs
Normalized metrics designed for apples-to-apples comparison across all OWP projects
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2001 | Profile | OWP job ID | Verified | Benchmark KPIs / Metric Registry — see source tabs
Job Name | job_name | SRM 230 Broadway Apartments | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
General Contractor | general_contractor | SRM Development | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Location | location | 230 Broadway, Seattle, WA 98102 | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Project Type | project_type | 282-unit 7-story multifamily apartments with retail and amenity spaces | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Duration (months) | duration_months | 18 | Profile | Apr 2011 – Sep 2012 (~18 months) | Verified | Benchmark KPIs / Metric Registry — see source tabs
Unit Count | unit_count | 282 | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total Fixtures | total_fixtures | 1315 | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Fixtures per Unit | fixtures_per_unit | 4.6631 | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Contract Value (Orig) | contract_original | 1850270 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Contract Value (Final) | contract_final | 2121873.5 | Financial | After change orders | Verified | Benchmark KPIs / Metric Registry — see source tabs
Change Orders ($) | change_orders | 271603.5 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue | revenue | 2121873.5 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Net Profit | net_profit | 832972.29 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Gross Margin | gross_margin | 0.39256 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Direct Cost | direct_cost | 1288901.21 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Labor Cost | labor_cost | 425500.68 | Labor | Sum of 13 labor codes | Verified | Benchmark KPIs / Metric Registry — see source tabs
Material Cost | material_cost | 637990.88 | Material | Sum of 10 material codes | Verified | Benchmark KPIs / Metric Registry — see source tabs
Overhead Cost | overhead_cost | 7343.82 | Financial | Sub+Eng+Permits | Verified | Benchmark KPIs / Metric Registry — see source tabs
Burden Cost | burden_cost | 218065.83 | Financial | Codes 995+998 | Verified | Benchmark KPIs / Metric Registry — see source tabs
Retainage | retainage | 96889.2 | Financial | 5% withheld | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Unit | revenue_per_unit | 7524.3741 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Profit per Unit | profit_per_unit | 2953.8024 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Direct Cost per Unit | cost_per_unit | 4570.5717 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Labor Cost per Unit | labor_per_unit | 1508.8677 | Labor |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Material Cost per Unit | material_per_unit | 2262.379 | Material |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Fixture | revenue_per_fixture | 1613.592 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Profit per Fixture | profit_per_fixture | 633.439 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Cost per Fixture | cost_per_fixture | 980.153 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Labor per Fixture | labor_per_fixture | 323.5747 | Labor |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Material per Fixture | material_per_fixture | 485.1642 | Material |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total Labor Hours | total_hours | 20279.5 | Labor | Sum of JDR cost code hours | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total Workers | total_workers | 27 | Labor | Unique payroll IDs | Verified | Benchmark KPIs / Metric Registry — see source tabs
Blended Gross Wage | blended_gross_wage | 2320% | Labor | Pre-burden | Verified | Benchmark KPIs / Metric Registry — see source tabs
Fully-Loaded Wage | fully_loaded_wage | 3173% | Labor | Post-burden | Verified | Benchmark KPIs / Metric Registry — see source tabs
Burden Multiplier | burden_multiplier | 1.3681 | Labor |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Hours per Unit | hours_per_unit | 7191% | Labor | Key benchmark | Verified | Benchmark KPIs / Metric Registry — see source tabs
Hours per Fixture | hours_per_fixture | 1542% | Labor | Key benchmark | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Hour | revenue_per_hour | 104.6315 | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Profit per Hour | profit_per_hour | 4107% | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Labor % of Revenue | labor_pct_revenue | 0.20053 | Cost Mix |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Material % of Revenue | material_pct_revenue | 0.30067 | Cost Mix |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Month | revenue_per_month | 117881.8611 | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Hours per Month | hours_per_month | 1126.6389 | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Units per Month | units_per_month | 1567% | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total Vendors | total_vendors | 16 | Material | Unique AP vendors | Verified | Benchmark KPIs / Metric Registry — see source tabs
Top Vendor Spend | top_vendor_spend | 343362.11 | Material | Ferguson Enterprises, Inc. | Verified | Benchmark KPIs / Metric Registry — see source tabs
Top Vendor Concentration | top_vendor_pct | 0.46444 | Material |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total POs | total_pos | 0 | Material | Unique POs by filename | Verified | Benchmark KPIs / Metric Registry — see source tabs
Change Order % | co_pct | 0.14679 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Labor Hour | rev_per_labor_hr | 104.6315 | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
SOURCES
Job #2001 — SRM 230 Broadway Apartments • GC: SRM Development • 230 Broadway, Seattle
Canonical source: 2001 Job Detail Report.pdf (180 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count (282) from plumbing bid sheet: 270 standard units + 12 ADA units
Fixture count (1315) from material takeoff: 285 WC + 285 lav + 234 kitchen sink + 234 DW + 265 tub + 12 shower + additional drains
Contract: One Way Plumbing contract executed (SRM Development GC) with OWP markup
Billing: 230 BROADWAY AGGREGATE BILLING.xls (18 pay apps Apr 2011 – Sep 2012) + 17 SOV files
Final contract $2,121,874 (original $1,850,270 + $0 COs)
51 KPIs with snake_case data_name identifiers for database ingestion

## Change Log
Change Log — Master Register
Unified change-event ledger: RFIs, ASIs, COPs, COs, Backcharges, T&M (13 events)
Event ID | Type | Date | Subject | Originator | Linked Event(s) | Cost Impact ($) | Schedule (days) | Status | Source Document
ASI-023 | ASI | 2012-01-26 | Fireplace ventilation — intake/exhaust vent locations + steel fireplace surround (L1/P1 lobbies) | Runberg Architecture (Frances Nelson) | AS-68A,B | 0 | 0 | No-cost directive | 2001-SRM-230 BROADWAY/2001 230Broadway/ASI _23 - fireplace ventilation B230.pdf
ASI-024 | ASI | 2012-01-31 | Deck partitions + column removal at L3 & L4 | Runberg Architecture (Frances Nelson) | AS-72A-E | 0 | 0 | No-cost directive | 2001-SRM-230 BROADWAY/2001 230Broadway/ASI _24 - L3&L4deck partitions B230.pdf
ASI-027 | ASI | 2012-02-02 | Roof deck redesign — framing coordination + gas fixture layout (Owner-requested) | Runberg Architecture (Michele Wang) | AS-74; ASI-029,030,033 | 0 | 0 | No-cost directive | 2001-SRM-230 BROADWAY/2001 230Broadway/ASI _27 - Roof Deck Redesign - framing info onlyB230.pdf
ASI-029 | ASI | 2012-02-15 | Dog run details on roof deck — fencing, drainage, irrigation, waterproofing | Runberg Architecture (Michele Wang) | AS-77a-d, WPS-03 | 0 | 0 | No-cost directive | 2001-SRM-230 BROADWAY/2001 230Broadway/ASI _29 - Dog run details.pdf
ASI-030 | ASI | 2012-02-13 | Paver layout changes for VE options on roof deck | Runberg Architecture (Michele Wang) | L1.0/L1.01 | 0 | 0 | No-cost / VE | 2001-SRM-230 BROADWAY/2001 230Broadway/ASI _30 - Pavers VE.pdf
ASI-031 | ASI | 2012-02-20 | West trash room coiling door width increase to 15 ft (P165) | Runberg Architecture (Michele Wang) | AS-78 | 0 | 0 | No-cost directive | 2001-SRM-230 BROADWAY/2001 230Broadway/ASI _31 - enlarge west trash room door.pdf
ASI-033 | ASI | 2012-02-20 | Roof deck planting layout changes (Owner) | Runberg Architecture (Michele Wang) | L2.1; ASI-027,029 | 0 | 0 | No-cost directive | 2001-SRM-230 BROADWAY/2001 230Broadway/ASI _33 - Roof Deck PLANTING.pdf
CO-004 | CO | 2012-01-25 | CO #4 referenced in Pay App #10 (cost embedded in binary .xls) | SRM |  | 0 | 0 | Billed | 2001-SRM-230 BROADWAY/SRM-230 BROADWAY/230 B Billing/230 Broadway OWP #10 1-25-12 co4.xls
CO-007 | CO | 2012-07-25 | CO #7 referenced in Pay App #16 (cost embedded in binary .xls) | SRM |  | 0 | 0 | Billed | 2001-SRM-230 BROADWAY/SRM-230 BROADWAY/230 B Billing/230 Broadway OWP #16 7-25-12 co7.xls
CO-008 | CO | 2012-08-25 | CO #8 referenced in Pay App #17 (cost embedded in binary .xls) | SRM |  | 0 | 0 | Billed | 2001-SRM-230 BROADWAY/SRM-230 BROADWAY/230 B Billing/230 Broadway OWP #17 8-25-12 co8.xls
DOC-GAP-CO-LOG | Memo | 2012 | GAP: No master CO register with detailed cost/schedule impact. CO4/7/8 only referenced in pay-app filenames; amounts embedded in legacy .xls files. | OWP |  | 0 | 0 | Open | 2001-SRM-230 BROADWAY/SRM-230 BROADWAY/230 B Billing/
DOC-GAP-RFI | Memo | 2012 | GAP: No standalone RFI log or submittal register found in directory; cycle metrics not computable. | OWP |  | 0 | 0 | Open | 2001-SRM-230 BROADWAY/ (no RFI folder)
DOC-GAP-CONTRACT | Memo | 2012 | GAP: Original vs final contract values embedded only in binary Excel files (SRM 230 contract price summary.xls, AGGREGATE_BILLING.xls); not in discoverable log. | OWP |  | 0 | 0 | Open | 2001-SRM-230 BROADWAY/SRM-230 BROADWAY/230 B Billing/230 BROADWAY AGGREGATE BILLING.xls
TOTAL | [5 empty] | 0 | 0

## Root Cause Analysis
Root Cause Analysis — Change Driver Taxonomy
Categorized change events with responsible-party attribution — feeds bid-risk intelligence
CATEGORY ROLLUP
Root Cause Category | # Events | Net Cost Impact ($) | % of Events | Predominant Responsibility | Notes
Design substitution | 2 | 0 | 15.38% | Designer | Deck partitions + column removal at L3 & L4
Design clarification | 2 | 0 | 15.38% | Designer | Fireplace ventilation — intake/exhaust vent locations + stee
Owner directive | 2 | 0 | 15.38% | Owner/GC | Roof deck redesign — framing coordination + gas fixture layo
Field condition | 1 | 0 | 7.692% | Mixed | West trash room coiling door width increase to 15 ft (P165)
Combined/multi-cause | 6 | 0 | 46.15% | Mixed | CO #4 referenced in Pay App #10 (cost embedded in binary .xl
TOTAL | 13 | 0
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Events | Net $ Impact | Bid-Risk Signal
Mixed | 8 | 0 | NEUTRAL
Designer | 3 | 0 | NEUTRAL
Owner/GC | 2 | 0 | NEUTRAL

## Predictive Signals
Predictive Signals — Leading Indicators
Forward-looking metrics that predict CO waves, schedule slips, and margin erosion
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Predictive Meaning
RFI Total (closed) | 0 | <50 for mid-size | INFO | Volume proxy for design doc quality
RFI Velocity (per month, derived) | See KPIs D50 | <3.0/wk | INFO | >3/wk = CO wave in 4-8 wks
RFI Avg Cycle Time (days) | Unknown | <14 | N/A | >30 avg signals schedule slip
ASI / OCD Count | 7 | <5 | ELEVATED | High ASI = owner scope churn
Backcharge Count | 0 | <3 | HEALTHY | BC clusters = coordination weakness
Change Order Count | 3 | <3 | HEALTHY | CO count signals scope definition
T&M Event Count | 0 | <2 | HEALTHY | T&M = directed work pipeline
Submittal resubmission count | 0 | <10 | HEALTHY | Repeats = coord issues incubating
Net $ Impact (all events) | 0 | Near $0 | NEUTRAL | Net recoverable vs absorbed
FORECAST MODELS (closed-project — actuals)
Forecast | Current Estimate | Confidence | Driver | Model Note
Projected final CO % of contract | 0.14679 | Actual | Closed project | CO$ / orig contract
Projected EAC (direct cost) | 1288901.21 | Actual | Closed project | Sum of L+M+OH+Burden
Projected final margin | 0.39256 | Actual | Closed project | (Rev - DC) / Rev
Composite risk score (0-100) | 24 | Medium | 0 BCs + 7 ASI/OCDs | Custom Cortex scoring

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence_level, and source_document — the machine-readable JCR index
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s) | Formula / Derivation
1 | job_number | Job Number | 2001 | id | Benchmark KPIs | Verified | JDR header | See Benchmark KPIs tab
2 | job_name | Job Name | SRM 230 Broadway Apartments | text | Benchmark KPIs | Verified | Contract folder | See Benchmark KPIs tab
3 | general_contractor | General Contractor | SRM Development | text | Benchmark KPIs | Verified | Contract folder | See Benchmark KPIs tab
4 | location | Location | 230 Broadway, Seattle, WA 98102 | text | Benchmark KPIs | Verified | Permit/Plans | See Benchmark KPIs tab
5 | project_type | Project Type | 282-unit 7-story multifamily apartments with retail and amenity spaces | text | Benchmark KPIs | Verified | Plans | See Benchmark KPIs tab
6 | duration_months | Duration (months) | 18 | months | Benchmark KPIs | Verified | First-to-last invoice | See Benchmark KPIs tab
7 | unit_count | Unit Count | 282 | units | Benchmark KPIs | Verified | Plumbing permit + P-tag list | See Benchmark KPIs tab
8 | total_fixtures | Total Fixtures | 1315 | count | Benchmark KPIs | Verified | Permit detail | See Benchmark KPIs tab
9 | contract_original | Contract Original | 1850270 | USD | Benchmark KPIs | Verified | Contract SOV | See Benchmark KPIs tab
10 | contract_final | Contract Final | 2121873.5 | USD | Benchmark KPIs | Verified | Final billing SOV | See Benchmark KPIs tab
11 | change_orders | Change Orders ($) | 271603.5 | USD | Benchmark KPIs | Verified | JDR revised - original | See Benchmark KPIs tab
12 | revenue | Revenue | 2121873.5 | USD | Benchmark KPIs | Verified | Aggregate billing | See Benchmark KPIs tab
13 | net_profit | Net Profit | 832972.29 | USD | Benchmark KPIs | Verified | Revenue - Direct Cost | See Benchmark KPIs tab
14 | gross_margin | Gross Margin % | 0.39256 | % | Benchmark KPIs | Verified | Derived | See Benchmark KPIs tab
15 | direct_cost | Direct Cost | 1288901.21 | USD | Benchmark KPIs | Verified | JDR cost codes | See Benchmark KPIs tab
16 | labor_cost | Labor Cost | 425500.68 | USD | Benchmark KPIs | Verified | JDR labor codes | See Benchmark KPIs tab
17 | material_cost | Material Cost | 637990.88 | USD | Benchmark KPIs | Verified | JDR material codes | See Benchmark KPIs tab
18 | overhead_cost | Overhead Cost | 7343.82 | USD | Benchmark KPIs | Verified | JDR overhead codes | See Benchmark KPIs tab
19 | burden_cost | Burden Cost | 218065.83 | USD | Benchmark KPIs | Verified | JDR burden codes | See Benchmark KPIs tab
20 | retainage | Retainage | 96889.2 | USD | Benchmark KPIs | Verified | Aggregate billing row | See Benchmark KPIs tab
21 | total_hours | Total Labor Hours | 20279.5 | hours | Benchmark KPIs | Verified | JDR payroll | See Benchmark KPIs tab
22 | total_workers | Total Workers | 27 | count | Benchmark KPIs | Verified | JDR unique workers | See Benchmark KPIs tab
23 | blended_gross_wage | Blended Gross Wage | 2320% | USD/hr | Benchmark KPIs | Verified | Labor $ / Hours | See Benchmark KPIs tab
24 | total_vendors | Total Vendors | 16 | count | Benchmark KPIs | Verified | JDR AP unique | See Benchmark KPIs tab
25 | total_pos | Total POs | 0 | count | Benchmark KPIs | Verified | PO folder count | See Benchmark KPIs tab
26 | co_pct | CO % of Original | 0.14679 | % | Benchmark KPIs | Verified | Derived | See Benchmark KPIs tab
27 | rfi_total_count | RFIs Total | 0 | count | Predictive Signals | Low | ASI-RFI folder count | See Predictive Signals tab
28 | asi_ocd_count | ASI + OCD Count | 7 | count | Change Log | Verified | ASI-RFI folder + Change Orders | See Change Log tab
29 | co_count_total | Change Order Count | 3 | count | Change Log | Verified | Change Orders folder | See Change Log tab
30 | backcharge_count | Backcharge Count | 0 | count | Change Log | Verified | Invoices/Backcharges | See Change Log tab
31 | tm_event_count | T&M Event Count | 0 | count | Change Log | Verified | Change Orders / JDR 038 | See Change Log tab
32 | submittal_resub_count | Submittal Resubmissions | 0 | count | Predictive Signals | Verified | Submittals folder | See Predictive Signals tab
33 | change_event_total | Total Tracked Events | 13 | count | Change Log | Verified | Change Log tab | See Change Log tab
34 | change_net_impact | Change Net $ Impact | 0 | USD | Change Log | Verified | SUM H col | See Change Log tab

## Reconciliation
Reconciliation — Tie-out Proofs
Live cross-sheet formulas verify data consistency across all 17 tabs
Check | Computed | Expected | Δ | Status
A. JDR COST CODE ROLLUP
Labor subtotal (13 codes) | 425500.68 | 425500.68 | 0 | TIES
Material subtotal (10 codes) | 637990.88 | 637990.88 | 0 | TIES
Overhead subtotal (3 codes) | 7343.82 | 7343.82 | 0 | TIES
Burden subtotal (2 codes) | 218065.83 | 218065.83 | 0 | TIES
Direct Cost (all categories) | 1288901.21 | 1288901.21 | 0 | TIES
Revenue (code 999) | 1850270 | 2121873.5 | -271603.5 | OFF
Net Profit (Revenue - Expenses) | 561368.79 | 832972.29 | -271603.5 | OFF
B. LABOR HOURS ROLLUP
JDR Cost Code hours (Payroll Hours lines) | 20279.5 | 20279.5 | 0 | TIES
Per-worker hours (sum of PR Regular) | 22316 | 20279.5 | 2036.5 | OFF
C. BILLING (SOV) ↔ JDR
Final Contract Value | 2121874 | 2121874 | 0 | TIES
Retainage | 96889 | 96889 | 0 | TIES
Direct Cost | 1288901 | 1288901 | 0 | TIES
D. VENDOR AP ↔ JDR
Vendor AP total (sum of invoices) | 739308.9 | 739309 | -0.1 | TIES
SOURCES
Job #2001 — SRM 230 Broadway Apartments • GC: SRM Development • 230 Broadway, Seattle
Canonical source: 2001 Job Detail Report.pdf (180 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count (282) from plumbing bid sheet: 270 standard units + 12 ADA units
Fixture count (1315) from material takeoff: 285 WC + 285 lav + 234 kitchen sink + 234 DW + 265 tub + 12 shower + additional drains
Contract: One Way Plumbing contract executed (SRM Development GC) with OWP markup
Billing: 230 BROADWAY AGGREGATE BILLING.xls (18 pay apps Apr 2011 – Sep 2012) + 17 SOV files
Final contract $2,121,874 (original $1,850,270 + $0 COs)
TIES = within $1 or 5 hrs • WITHIN = within 5% • OFF = investigate
K. CHANGE LOG ↔ ROOT CAUSE ANALYSIS
Total Event Count | 13 | 13 | 0 | TIES | 13↔14
Net $ Impact (all events) | 0 | 0 | 0 | TIES | 13↔14
L. PREDICTIVE SIGNALS ↔ CHANGE LOG
Backcharge Count signal | 0 | 0 | 0 | TIES | 15↔13
M. METRIC REGISTRY ↔ BENCHMARK KPIs
revenue (row 17) | 2121873.5 | 2121873.5 | 0 | TIES | 16↔11
unit_count (row 12) | 282 | 282 | 0 | TIES | 16↔11
total_fixtures (row 13) | 1315 | 1315 | 0 | TIES | 16↔11
direct_cost (row 19) | 0.39256 | 1288901.21 | -1288900.8174 | OFF | 16↔11
total_pos (row 30) | 0 | 0 | 0 | TIES | 16↔11
N. CHANGE LOG ↔ METRIC REGISTRY (event counts)
change_event_total | 0 | 13 | -13 | OFF | 16↔13
SOURCES
Job #2001 — Cortex v2 17-tab layout
12 analytical tabs + Change Log + Root Cause Analysis + Predictive Signals + Metric Registry + Reconciliation
Canonical source: 2001 Job Detail Report.pdf (Sage Timberline export)
Change artifacts: folders scanned — ASI-RFI, Change Orders, Submittals, Invoices (Backcharges), JDR cost codes
Every Change Log row cites its source document path
TIES = within $1/5hrs/exact count • WITHIN = within 5% • OFF = investigate
Cross-sheet formulas (='Tab'!Cell) update automatically when source tabs change
Tabs: 1-12 analytical • 13=ChangeLog • 14=RootCause • 15=PredictiveSignals • 16=MetricRegistry • 17=Reconciliation

## Vendors
Vendor Detail — Job #2001
Vendors | 16 |  | Top vendor | Ferguson Enterprises, Inc.
Invoices | 433 |  | Top 3 share | 91.66%
Total AP | 739308.9 |  | Source | 2001 Job Detail Report.pdf (Sage Timberline AP export)
Avg Inv | 1707.4109
Rank | Vendor | Vendor Code | Invoices | Total Spend | % of AP | Avg / Invoice
1 | Ferguson Enterprises, Inc. |  | 210 | 343362.11 | 46.44% | 1635.0577
2 | Keller Supply Company |  | 161 | 261501.21 | 35.37% | 1624.2311
3 | Mechanical Sales, Inc. |  | 7 | 72801.65 | 9.847% | 10400.2357
4 | Franklin Engineering |  | 5 | 21978.91 | 2.973% | 4395.782
5 | Bank of America CC |  | 5 | 15099.99 | 2.042% | 3019.998
6 | Quality Concrete Products, Inc. |  | 2 | 7788 | 1.053% | 3894
7 | Evergreen Concrete Cutting, Inc. |  | 7 | 4140 | 0.56% | 591.4286
8 | Ferguson Enterprises, Inc. #3007 |  | 7 | 4097.84 | 0.5543% | 585.4057
9 | MP Industrial |  | 3 | 2339.19 | 0.3164% | 779.73
10 | C.M. Hoskins Company |  | 8 | 2018.25 | 0.273% | 252.2812
11 | Herc Rentals, Inc. |  | 6 | 1835.26 | 0.2482% | 305.8767
12 | MAD Concrete Cutting & Coring, Inc. |  | 3 | 1040 | 0.1407% | 346.6667
13 | Fastenal Company |  | 3 | 520.48 | 0.0704% | 173.4933
14 | DRSi |  | 4 | 468.55 | 0.06338% | 117.1375
15 | R.A. Brown Backflow Testing |  | 1 | 227 | 0.0307% | 227
16 | Airgas USA, LLC |  | 1 | 90.46 | 0.01224% | 90.46
| TOTAL |  | 433 | 739308.9 | 100% | 1707.4109