## Overview
Job #2010 · Chinn Old Town Mixed Use
Cortex JCR Summary • Chinn Construction, LLC • Seattle, WA • 165-unit mixed-use multifamily apartments + ground-floor retail • Sep 2012 – Sep 2014 (~24 months)
PROJECT OVERVIEW
Project Job # | 2010
Project Name: | Chinn Old Town Mixed Use
General Contractor | Chinn Construction, LLC
Location | Seattle, WA
Project Duration | Sep 2012 – Sep 2014 (~24 months)
Total Unique Documents | Old Town folder: Contract, Billing (aggregate + 19 SOVs), PO_s (73), Permits, Plans, Submittals
CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
$1,386,419 |  | $800,420 |  | $585,999 |  | 9,992
Original $1,469,800 + $-83,381 COs |  | 57.7% margin |  | 42.3% of revenue |  | 22 workers
COST BREAKDOWN
Category | Budget | Actual | Variance | % Budget | % of Cost
Labor | 303565 | 196271.13 | 107293.87 | 64.66% | 33.49%
Material | 504680 | 282662.77 | 222017.23 | 56.01% | 48.24%
Overhead | 8000 | 3650.67 | 4349.33 | 45.63% | 0.623%
Burden | 161672.55 | 103414.01 | 58258.54 | 63.97% | 17.65%
TOTAL | 977917.55 | 585998.58 | 391918.97 | 59.92% | 100%
PROJECT PROFILE
Metric | Value | Metric | Value | Metric | Value
Plumbing Units | 165 | Water Closets | 165 | Kitchen Sinks | 150
Total Fixtures | 803 | Lavatories | 175 | Showers | 15
Fixtures / Unit | 4.87 | Tubs | 149 | Auto Washers | 149
Stacks | 30 | Duration | 24 mo | Cost Codes | 28
SOURCES
Job #2010 — Chinn Old Town Mixed Use • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2010 Job Detail Report.pdf (123 pages, OWP Sage Timberline export)
Cost codes parsed: 28
Unit count (165) and fixture count (803) confirmed from existing project data
Mixed-use: 165 plumbing units, 175 lavatories (suggests 10 powder-room units) + 15 shower-only units
Billing: OLD TOWN AGGREGATE BILLING.xlsx (18 pay apps Sep 2012 – Sep 2014)
Final contract $1,386,419 (original $1,469,800 + $-83,381 COs)

## Budget vs Actual
Budget vs Actual — All Cost Codes
Code | Description | Orig Budget | Rev Budget | Actual | Variance | % Used
LABOR
011 | DS & RD Labor | 7590 | 7590 | 2137 | 5453 | 28.16%
100 | Supervision | 10430 | 10430 | 4944 | 5486 | 47.4%
101 | Takeoff & Purchase Labor | 7450 | 7450 | 4286 | 3164 | 57.53%
110 | Underground Labor | 3820 | 3820 | 959 | 2861 | 25.1%
111 | Garage Labor | 39100 | 39100 | 28821.5 | 10278.5 | 73.71%
112 | Canout Labor | 6650 | 6650 | 2982.25 | 3667.75 | 44.85%
120 | Roughin Labor | 204925 | 159525 | 114688.38 | 44836.62 | 71.89%
130 | Finish Labor | 31000 | 31500 | 29825 | 1675 | 94.68%
140 | Gas Labor | 3600 | 3600 | 1712 | 1888 | 47.56%
141 | Water Main/Insulation Lab | 14900 | 33900 | 3672 | 30228 | 10.83%
142 | Mech Room Labor | 0 | 0 | 1871 | -1871 | 0%
145 | Tub/Shower Labor | 0 | 0 | 373 | -373 | 0%
MATERIAL
039 | DS & RD Material | 11500 | 11500 | 1188.86 | 10311.14 | 10.34%
210 | Underground Material | 3000 | 3000 | 1514.24 | 1485.76 | 50.47%
211 | Garage Material | 63370 | 63370 | 11302.9 | 52067.1 | 17.84%
212 | Canout Material | 7980 | 7980 | 5720.08 | 2259.92 | 71.68%
220 | Roughin Material | 204925 | 130025 | 66457.52 | 63567.48 | 51.11%
230 | Finish Material | 261700 | 251305 | 173652.72 | 77652.28 | 69.1%
240 | Gas Material | 3600 | 3600 | 1080.05 | 2519.95 | 30%
241 | Water Main/Insulation Mat | 14900 | 33900 | 20000.49 | 13899.51 | 59%
242 | Mech Room Material | 0 | 0 | 1098.46 | -1098.46 | 0%
245 | Tub/Shower Material | 0 | 0 | 647.45 | -647.45 | 0%
OVERHEAD
600 | Subcontractor | 1000 | 1000 | 1212 | -212 | 121.2%
601 | Engineering/Plans | 4000 | 4000 | 2404.21 | 1595.79 | 60.11%
603 | Permits & Licenses | 3000 | 3000 | 34.46 | 2965.54 | 1.149%
BURDEN
995 | Payroll Burden | 145220.27 | 137421.67 | 87883.44 | 49538.23 | 63.95%
998 | Payroll Taxes | 26232.23 | 24250.88 | 15530.57 | 8720.31 | 64.04%
TOTAL | Direct Cost | 1079892.5 | 977917.55 | 585998.58 | 391918.97 | 59.92%
SOURCES
Job #2010 — Chinn Old Town Mixed Use • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2010 Job Detail Report.pdf (123 pages, OWP Sage Timberline export)
Cost codes parsed: 28
Unit count (165) and fixture count (803) confirmed from existing project data
Mixed-use: 165 plumbing units, 175 lavatories (suggests 10 powder-room units) + 15 shower-only units
Billing: OLD TOWN AGGREGATE BILLING.xlsx (18 pay apps Sep 2012 – Sep 2014)
Final contract $1,386,419 (original $1,469,800 + $-83,381 COs)

## Cost Breakdown
Cost Breakdown — Category Deep Dive
A. CATEGORY SHARE OF DIRECT COST
Category | # Codes | Budget | Actual | Variance | % Budget | % of Cost | Per Unit
Labor | 12 | 303565 | 196271.13 | 107293.87 | 64.66% | 33.49% | 1189.522
Material | 10 | 504680 | 282662.77 | 222017.23 | 56.01% | 48.24% | 1713.1077
Overhead | 3 | 8000 | 3650.67 | 4349.33 | 45.63% | 0.623% | 22.1253
Burden | 2 | 161672.55 | 103414.01 | 58258.54 | 63.97% | 17.65% | 626.7516
B. LARGEST OVERRUNS (Actual > Revised Budget)
Code | Description | Rev Budget | Actual | Overrun | % Over
142 | Mech Room Labor | 0 | 1871 | 1871 | 0%
242 | Mech Room Material | 0 | 1098.46 | 1098.46 | 0%
245 | Tub/Shower Material | 0 | 647.45 | 647.45 | 0%
145 | Tub/Shower Labor | 0 | 373 | 373 | 0%
600 | Subcontractor | 1000 | 1212 | 212 | 21.2%
C. LARGEST SAVINGS (Actual < Revised Budget)
Code | Description | Rev Budget | Actual | Savings | % Under
230 | Finish Material | 251305 | 173652.72 | 77652.28 | 30.9%
220 | Roughin Material | 130025 | 66457.52 | 63567.48 | 48.89%
211 | Garage Material | 63370 | 11302.9 | 52067.1 | 82.16%
995 | Payroll Burden | 137421.67 | 87883.44 | 49538.23 | 36.05%
120 | Roughin Labor | 159525 | 114688.38 | 44836.62 | 28.11%
141 | Water Main/Insulation Lab | 33900 | 3672 | 30228 | 89.17%
241 | Water Main/Insulation Mat | 33900 | 20000.49 | 13899.51 | 41%
039 | DS & RD Material | 11500 | 1188.86 | 10311.14 | 89.66%
111 | Garage Labor | 39100 | 28821.5 | 10278.5 | 26.29%
998 | Payroll Taxes | 24250.88 | 15530.57 | 8720.31 | 35.96%
SOURCES
Job #2010 — Chinn Old Town Mixed Use • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2010 Job Detail Report.pdf (123 pages, OWP Sage Timberline export)
Cost codes parsed: 28
Unit count (165) and fixture count (803) confirmed from existing project data
Mixed-use: 165 plumbing units, 175 lavatories (suggests 10 powder-room units) + 15 shower-only units
Billing: OLD TOWN AGGREGATE BILLING.xlsx (18 pay apps Sep 2012 – Sep 2014)
Final contract $1,386,419 (original $1,469,800 + $-83,381 COs)

## Material
Material Spend Analysis
10 material cost codes • $282,663 JDR material • 18 AP vendors • $362,722 total AP
A. MATERIAL BY COST CODE
Code | Description | Rev Budget | Actual | Variance | % Used | % of Mat | Per Unit
039 | DS & RD Material | 11500 | 1188.86 | 10311.14 | 10.34% | 0.4206% | 7.2052
210 | Underground Material | 3000 | 1514.24 | 1485.76 | 50.47% | 0.5357% | 9.1772
211 | Garage Material | 63370 | 11302.9 | 52067.1 | 17.84% | 3.999% | 68.5024
212 | Canout Material | 7980 | 5720.08 | 2259.92 | 71.68% | 2.024% | 34.6672
220 | Roughin Material | 130025 | 66457.52 | 63567.48 | 51.11% | 23.51% | 402.7728
230 | Finish Material | 251305 | 173652.72 | 77652.28 | 69.1% | 61.43% | 1052.4407
240 | Gas Material | 3600 | 1080.05 | 2519.95 | 30% | 0.3821% | 6.5458
241 | Water Main/Insulation Mat | 33900 | 20000.49 | 13899.51 | 59% | 7.076% | 121.2151
242 | Mech Room Material | 0 | 1098.46 | -1098.46 | 0% | 0.3886% | 6.6573
245 | Tub/Shower Material | 0 | 647.45 | -647.45 | 0% | 0.2291% | 3.9239
TOTAL | All Material | 504680 | 282662.77 | 222017.23 | 56.01% | 100% | 1713.1077
B. VENDORS BY SPEND (AP)
Vendor | # Invoices | Total Spend | % of AP |  |  |  | Avg Invoice
Rosen Supply Company, Inc. | 73 | 215859.94 | 59.51% |  |  |  | 2956.9855
Ferguson Enterprises, Inc. | 58 | 84342.57 | 23.25% |  |  |  | 1454.1822
Bank of America CC | 3 | 30892.62 | 8.517% |  |  |  | 10297.54
Franklin Engineering | 4 | 10463 | 2.885% |  |  |  | 2615.75
Keller Supply Company | 7 | 10106.67 | 2.786% |  |  |  | 1443.81
Quality Concrete Products, Inc. | 2 | 2414 | 0.6655% |  |  |  | 1207
United Rentals, Inc. | 6 | 2404.21 | 0.6628% |  |  |  | 400.7017
Ferguson Enterprises, Inc. #3007 | 7 | 2271.7 | 0.6263% |  |  |  | 324.5286
Rosen Supply Kirkland | 3 | 1831.58 | 0.505% |  |  |  | 610.5267
Duraseal, Inc. | 1 | 950 | 0.2619% |  |  |  | 950
DRSi | 2 | 265.36 | 0.07316% |  |  |  | 132.68
R.A. Brown Backflow Testing | 1 | 212 | 0.05845% |  |  |  | 212
Manor Hardware & Construction Supply | 1 | 197.5 | 0.05445% |  |  |  | 197.5
Consolidated Supply Co. | 1 | 168.54 | 0.04647% |  |  |  | 168.54
Pacific Plumbing Supply Co., LLC | 2 | 121.4 | 0.03347% |  |  |  | 60.7
Fastenal Company | 2 | 96.67 | 0.02665% |  |  |  | 48.335
Kele, Inc | 1 | 69.69 | 0.01921% |  |  |  | 69.69
C.M. Hoskins Company | 1 | 54.4 | 0.015% |  |  |  | 54.4
TOTAL | 175 | 362721.85 | 100%
SOURCES
Job #2010 — Chinn Old Town Mixed Use • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2010 Job Detail Report.pdf (123 pages, OWP Sage Timberline export)
Cost codes parsed: 28
Unit count (165) and fixture count (803) confirmed from existing project data
Mixed-use: 165 plumbing units, 175 lavatories (suggests 10 powder-room units) + 15 shower-only units
Billing: OLD TOWN AGGREGATE BILLING.xlsx (18 pay apps Sep 2012 – Sep 2014)
Final contract $1,386,419 (original $1,469,800 + $-83,381 COs)
Vendor AP ties to JDR 'by Source: AP' line (362,721.85)

## Crew & Labor
Crew & Labor — Per-Worker Breakdown
Worker | Hours | Gross Pay | $/Hour | Tier
Anderson, Richard P | 1681 | 42050 | 25.0149 | Mid
Barnhart, Joseph N | 1588 | 46498.5 | 29.2812 | Mid
Hayton, Evan R | 1465 | 19207 | 13.1106 | Apprentice
Garcia, Jordan X | 1192 | 15781 | 13.2391 | Apprentice
Wilson, Garret A | 833.5 | 11129.5 | 13.3527 | Apprentice
Kinssies, Jr, John E | 727.5 | 9796.5 | 13.466 | Apprentice
Waites, Thaddeus Z | 680 | 18200 | 26.7647 | Mid
Mayfield, Elijah S | 366 | 4758 | 13 | Apprentice
Soto Serna, Cesar E | 366 | 4114 | 11.2404 | Apprentice
Gerard, Jeffrey S | 314.5 | 10992.5 | 34.9523 | Senior
Holmes, Anthony R | 301 | 3660 | 12.1595 | Apprentice
Nabbefeld, Maxwell B | 112 | 1344 | 12 | Apprentice
Leone, Jared S | 91 | 1092 | 12 | Apprentice
Meza Fuentes, Erick A | 59.5 | 892.5 | 15 | Apprentice
Salazar, Hajdar L | 47 | 525 | 11.1702 | Apprentice
Pennington, Patrick S | 40 | 480 | 12 | Apprentice
McCabe, Thomas C | 24 | 414 | 17.25 | Apprentice
Hubbard, Robert W | 11 | 358 | 32.5455 | Senior
Lima Romero, Melvin A | 9 | 153 | 17 | Apprentice
Sanders, Allen O | 7 | 203 | 29 | Mid
Paco Leyva, Orlando | 6.5 | 87.75 | 13.5 | Apprentice
Arreola, Israel A | 2 | 24 | 12 | Apprentice
TOTAL (22 workers) | 9923.5 | 191760.25 | 19.3239
SOURCES
Job #2010 — Chinn Old Town Mixed Use • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2010 Job Detail Report.pdf (123 pages, OWP Sage Timberline export)
Cost codes parsed: 28
Unit count (165) and fixture count (803) confirmed from existing project data
Mixed-use: 165 plumbing units, 175 lavatories (suggests 10 powder-room units) + 15 shower-only units
Billing: OLD TOWN AGGREGATE BILLING.xlsx (18 pay apps Sep 2012 – Sep 2014)
Final contract $1,386,419 (original $1,469,800 + $-83,381 COs)
Tier: Apprentice <$18/hr, Mid $18–30, Senior >$30

## Crew Analytics
Crew Analytics
A. TIER DISTRIBUTION
Tier | # Workers | Hours | Gross Pay | % of Hours
Senior | 2 | 325.5 | 11350.5 | 3.28%
Mid | 4 | 3956 | 106951.5 | 39.86%
Apprentice | 16 | 5642 | 73458.25 | 56.85%
B. WAGE STATISTICS
Blended Gross Wage | 19.3239 |  |  | Payroll $ ÷ payroll hours (pre-burden)
Fully-Loaded Wage | 30.1995 |  |  | (Labor + Burden) ÷ total hours
Burden Multiplier | 1.5628 |  |  | Fully loaded ÷ gross wage
Min Worker Rate | 11.1702 |  |  | Cheapest apprentice hour
Max Worker Rate | 34.9523 |  |  | Most expensive foreman hour
Avg Hours / Worker | 451.0682 |  |  | Crew continuity indicator
SOURCES
Job #2010 — Chinn Old Town Mixed Use • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2010 Job Detail Report.pdf (123 pages, OWP Sage Timberline export)
Cost codes parsed: 28
Unit count (165) and fixture count (803) confirmed from existing project data
Mixed-use: 165 plumbing units, 175 lavatories (suggests 10 powder-room units) + 15 shower-only units
Billing: OLD TOWN AGGREGATE BILLING.xlsx (18 pay apps Sep 2012 – Sep 2014)
Final contract $1,386,419 (original $1,469,800 + $-83,381 COs)

## Productivity
Productivity — Phase & Unit Metrics
A. LABOR HOURS BY PHASE
Phase | Labor Code | Hours | % of Total | Hours / Unit
DS & RD | 011 | 90 | 0.9007% | 0.54545
Supervision | 100 | 138 | 1.381% | 0.83636
Takeoff & Purchasing | 101 | 124 | 1.241% | 0.75152
Underground | 110 | 30 | 0.3002% | 0.18182
Garage | 111 | 1345 | 13.46% | 8.1515
Canout | 112 | 122.5 | 1.226% | 0.74242
Roughin | 120 | 6202.25 | 62.07% | 37.5894
Finish | 130 | 1569 | 15.7% | 9.5091
Gas | 140 | 79 | 0.7906% | 0.47879
Water Main / Insulation | 141 | 189.5 | 1.896% | 1.1485
Mech Room | 142 | 89 | 0.8907% | 0.53939
Tub / Shower | 145 | 14 | 0.1401% | 0.084848
TOTAL |  | 9992.25 | 100% | 60.5591
B. PRODUCTIVITY RATIOS
Metric | Value | Units |  | Notes
Hours / Unit | 60.5591 | hrs |  | Labor hours per residential unit
Hours / Fixture | 12.4436 | hrs |  | Labor hours per plumbing fixture
Revenue / Hour | 138.7494 | $ |  | Top-line per labor hour
Profit / Hour | 80.1041 | $ |  | Bottom-line per labor hour
Units / Month | 6.875 | units |  | Build velocity
Fixtures / Month | 33.4583 | fix |  | Fixture install pace
Hours / Month | 416.3438 | hrs |  | Monthly labor burn
Revenue / Month | 57767.4583 | $ |  | Monthly billing rate
SOURCES
Job #2010 — Chinn Old Town Mixed Use • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2010 Job Detail Report.pdf (123 pages, OWP Sage Timberline export)
Cost codes parsed: 28
Unit count (165) and fixture count (803) confirmed from existing project data
Mixed-use: 165 plumbing units, 175 lavatories (suggests 10 powder-room units) + 15 shower-only units
Billing: OLD TOWN AGGREGATE BILLING.xlsx (18 pay apps Sep 2012 – Sep 2014)
Final contract $1,386,419 (original $1,469,800 + $-83,381 COs)

## PO Commitments
Purchase Order Commitments
73 unique POs • PO amounts not dollar-parsed from individual PDFs • JDR material $282,663
A. COMMITMENTS BY COST CODE
OWP Code | Description → JDR | PO Count | % of POs | JDR Material
30 | 110+210 Underground | 12 | 16.44%
31 | 120+220 Roughin | 17 | 23.29%
32 | 130+230 Trim/Finish | 13 | 17.81%
40 | 141+241 Water Main/Ins | 1 | 1.37%
41 | 140+240 Gas | 3 | 4.11%
OTHER | Unclassified | 27 | 36.99%
TOTAL |  | 73 | 100% | 282662.77
B. COMMITMENTS BY VENDOR
Vendor | PO Count | % of POs
OTHER | 60 | 82.19%
ROSEN | 8 | 10.96%
FEI | 3 | 4.11%
CONSOLIDATED | 1 | 1.37%
SIOUX CHIEF | 1 | 1.37%
C. PO COVERAGE NOTES
Total Material Actual (JDR) |  |  | 282662.77
Unique PO Count |  |  | 73
(Dollar PO commitment not extracted — requires per-PDF parse)
SOURCES
Job #2010 — Chinn Old Town Mixed Use • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2010 Job Detail Report.pdf (123 pages, OWP Sage Timberline export)
Cost codes parsed: 28
Unit count (165) and fixture count (803) confirmed from existing project data
Mixed-use: 165 plumbing units, 175 lavatories (suggests 10 powder-room units) + 15 shower-only units
Billing: OLD TOWN AGGREGATE BILLING.xlsx (18 pay apps Sep 2012 – Sep 2014)
Final contract $1,386,419 (original $1,469,800 + $-83,381 COs)
PO count is deduplicated by 5-digit PO number extracted from filenames
Vendor/code classification is heuristic (filename keyword match)

## Billing & SOV
Revenue & Billing Reconciliation
18 pay applications • Sep 2012 – Sep 2014 • $1,386,419 final
A. CONTRACT SUMMARY
Original Contract |  |  |  |  | 1469800
Change Orders (net) |  |  |  |  | -83381
Final Contract Value |  |  |  |  | 1386419
Retainage (5%) |  |  |  |  | 69321
Net Paid to OWP |  |  |  |  | 1317098
B. PAY APPLICATION TIMELINE
App# | Date | Period Billing | Retention | Net This Period | Aggregate | % Complete
1 | 2012-09-20 | 24000 | 1200 | 22800 | 22800 | 1.645%
2 | 2012-10-18 | 48000 | 2400 | 45600 | 68400 | 4.934%
3 | 2012-12-20 | 15400 | 770 | 14630 | 83030 | 5.989%
4 | 2013-02-19 | 10100 | 505 | 9595 | 92625 | 6.681%
5 | 2013-04-18 | 6300 | 315 | 5985 | 98610 | 7.113%
6 | 2013-05-19 | 20400 | 1020 | 19380 | 117990 | 8.51%
7 | 2013-06-20 | 70200 | 3510 | 66690 | 184680 | 13.32%
8 | 2013-07-20 | 160800 | 8040 | 152760 | 337440 | 24.34%
9 | 2013-08-20 | 143247 | 7162.35 | 136084.65 | 473524.65 | 34.15%
10 | 2013-09-20 | 292950 | 14647.5 | 278302.5 | 751827.15 | 54.23%
11 | 2013-10-17 | 204800 | 10240 | 194560 | 946387.15 | 68.26%
12 | 2013-11-12 | 40600 | 2030 | 38570 | 984957.15 | 71.04%
13 | 2013-12-17 | 60666 | 3033.3 | 57632.7 | 1042589.85 | 75.2%
14 | 2014-01-20 | 40000 | 2000 | 38000 | 1080589.85 | 77.94%
15 | 2014-03-20 | 45755 | 2287.75 | 43467.25 | 1124057.1 | 81.08%
16 | 2014-04-20 | 128977 | 6448.85 | 122528.15 | 1246585.25 | 89.91%
17 | 2014-05-20 | 72376 | 3618.8 | 68757.2 | 1315342.45 | 94.87%
18 | 2014-09-20 | 1848 | 92.4 | 1755.6 | 1317098.05 | 95%
C. BILLING ↔ JDR TIE-OUT
Metric | SOV | JDR | Δ | Status
Final Contract Value | 1386419 | 1386419 | 0 | TIES
Retainage | 69321 | 69321 | 0 | TIES
Direct Cost | 585999 | 585999 | 0 | TIES
SOURCES
Job #2010 — Chinn Old Town Mixed Use • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2010 Job Detail Report.pdf (123 pages, OWP Sage Timberline export)
Cost codes parsed: 28
Unit count (165) and fixture count (803) confirmed from existing project data
Mixed-use: 165 plumbing units, 175 lavatories (suggests 10 powder-room units) + 15 shower-only units
Billing: OLD TOWN AGGREGATE BILLING.xlsx (18 pay apps Sep 2012 – Sep 2014)
Final contract $1,386,419 (original $1,469,800 + $-83,381 COs)

## Insights
Key Insights — Job #2010 Chinn Old Town Mixed Use
Narrative observations distilled from the full JDR analysis
MARGIN PROFILE | Net profit of $800,420 on $1,386,419 revenue = 57.7% gross margin. Direct cost $585,999 absorbs 42.3% of revenue.
VENDOR CONCENTRATION | Rosen Supply Company, Inc. alone = $215,860 (60% of all AP) across 73 invoices. Total 18 AP vendors, $362,722 total AP spend.
CREW PROFILE | 22 workers for 9,992 hours = 454 avg hrs/worker. Top 3 workers logged 4,734 hrs combined (47% of all labor).
ROUGHIN DOMINANCE | Code 120 Roughin Labor = 6,202 hrs (62% of all labor) and $114,688 actual. Code 230 Finish Material = $173,653 — 30% of total direct cost.
BUDGET DELIVERY | Revised budget was $977,918; actual direct cost $585,999 → $391,919 variance (40.1% under revised budget).
CONTRACT GROWTH | Contract grew from $1,469,800 to $1,386,419 — net +$-83,381 (-5.7%). Retainage of $69,321 (5%) withheld until closeout.
BURDEN RATIO | Burden codes 995 + 998 = $103,414 on $196,271 labor base = 52.7%. In line with OWP's typical 48–50% labor burden.
PROJECT SCALE | 165 units · 803 fixtures · 24 months. Revenue/unit $8,403, hours/unit 60.6, profit/unit $4,851.
PRODUCTIVITY | Blended labor rate $19.64/hr. Revenue/hour $139. Profit/hour $80. 416 hrs/month burn rate.
FIXTURE DENSITY | 803 fixtures ÷ 165 units = 4.87 fixtures/unit. Material/fixture $352, labor/fixture $244.
BIGGEST QUESTION
How does this job's 57.7% margin compare across similar projects in the OWP portfolio, and what operational levers drove the result — estimating accuracy, vendor pricing, or labor productivity?
SOURCES
Job #2010 — Chinn Old Town Mixed Use • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2010 Job Detail Report.pdf (123 pages, OWP Sage Timberline export)
Cost codes parsed: 28
Unit count (165) and fixture count (803) confirmed from existing project data
Mixed-use: 165 plumbing units, 175 lavatories (suggests 10 powder-room units) + 15 shower-only units
Billing: OLD TOWN AGGREGATE BILLING.xlsx (18 pay apps Sep 2012 – Sep 2014)
Final contract $1,386,419 (original $1,469,800 + $-83,381 COs)

## Benchmark KPIs
Benchmark KPIs
Normalized metrics designed for apples-to-apples comparison across all OWP projects
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2010 | Profile | OWP job ID | Verified | Benchmark KPIs / Metric Registry — see source tabs
Job Name | job_name | Chinn Old Town Mixed Use | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
General Contractor | general_contractor | Chinn Construction, LLC | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Location | location | Seattle, WA | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Project Type | project_type | 165-unit mixed-use multifamily apartments + ground-floor retail | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Duration (months) | duration_months | 24 | Profile | Sep 2012 – Sep 2014 (~24 months) | Verified | Benchmark KPIs / Metric Registry — see source tabs
Unit Count | unit_count | 165 | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total Fixtures | total_fixtures | 803 | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Fixtures per Unit | fixtures_per_unit | 4.8667 | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Contract Value (Orig) | contract_original | 1469800 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Contract Value (Final) | contract_final | 1386419 | Financial | After change orders | Verified | Benchmark KPIs / Metric Registry — see source tabs
Change Orders ($) | change_orders | -83381 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue | revenue | 1386419 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Net Profit | net_profit | 800420.42 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Gross Margin | gross_margin | 0.57733 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Direct Cost | direct_cost | 585998.58 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Labor Cost | labor_cost | 196271.13 | Labor | Sum of 12 labor codes | Verified | Benchmark KPIs / Metric Registry — see source tabs
Material Cost | material_cost | 282662.77 | Material | Sum of 10 material codes | Verified | Benchmark KPIs / Metric Registry — see source tabs
Overhead Cost | overhead_cost | 3650.67 | Financial | Sub+Eng+Permits | Verified | Benchmark KPIs / Metric Registry — see source tabs
Burden Cost | burden_cost | 103414.01 | Financial | Codes 995+998 | Verified | Benchmark KPIs / Metric Registry — see source tabs
Retainage | retainage | 69320.95 | Financial | 5% withheld | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Unit | revenue_per_unit | 8402.5394 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Profit per Unit | profit_per_unit | 4851.0328 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Direct Cost per Unit | cost_per_unit | 3551.5065 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Labor Cost per Unit | labor_per_unit | 1189.522 | Labor |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Material Cost per Unit | material_per_unit | 1713.1077 | Material |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Fixture | revenue_per_fixture | 1726.5492 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Profit per Fixture | profit_per_fixture | 996.7876 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Cost per Fixture | cost_per_fixture | 729.7616 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Labor per Fixture | labor_per_fixture | 244.4223 | Labor |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Material per Fixture | material_per_fixture | 352.0084 | Material |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total Labor Hours | total_hours | 9992.25 | Labor | Sum of JDR cost code hours | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total Workers | total_workers | 22 | Labor | Unique payroll IDs | Verified | Benchmark KPIs / Metric Registry — see source tabs
Blended Gross Wage | blended_gross_wage | 1919% | Labor | Pre-burden | Verified | Benchmark KPIs / Metric Registry — see source tabs
Fully-Loaded Wage | fully_loaded_wage | 2999% | Labor | Post-burden | Verified | Benchmark KPIs / Metric Registry — see source tabs
Burden Multiplier | burden_multiplier | 1.5628 | Labor |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Hours per Unit | hours_per_unit | 6056% | Labor | Key benchmark | Verified | Benchmark KPIs / Metric Registry — see source tabs
Hours per Fixture | hours_per_fixture | 1244% | Labor | Key benchmark | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Hour | revenue_per_hour | 138.7494 | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Profit per Hour | profit_per_hour | 8010% | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Labor % of Revenue | labor_pct_revenue | 0.14157 | Cost Mix |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Material % of Revenue | material_pct_revenue | 0.20388 | Cost Mix |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Month | revenue_per_month | 57767.4583 | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Hours per Month | hours_per_month | 416.3438 | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Units per Month | units_per_month | 6.875 | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total Vendors | total_vendors | 18 | Material | Unique AP vendors | Verified | Benchmark KPIs / Metric Registry — see source tabs
Top Vendor Spend | top_vendor_spend | 215859.94 | Material | Rosen Supply Company, Inc. | Verified | Benchmark KPIs / Metric Registry — see source tabs
Top Vendor Concentration | top_vendor_pct | 0.59511 | Material |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total POs | total_pos | 73 | Material | Unique POs by filename | Verified | Benchmark KPIs / Metric Registry — see source tabs
Change Order % | co_pct | -0.056729 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Labor Hour | rev_per_labor_hr | 138.7494 | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
SOURCES
Job #2010 — Chinn Old Town Mixed Use • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2010 Job Detail Report.pdf (123 pages, OWP Sage Timberline export)
Cost codes parsed: 28
Unit count (165) and fixture count (803) confirmed from existing project data
Mixed-use: 165 plumbing units, 175 lavatories (suggests 10 powder-room units) + 15 shower-only units
Billing: OLD TOWN AGGREGATE BILLING.xlsx (18 pay apps Sep 2012 – Sep 2014)
Final contract $1,386,419 (original $1,469,800 + $-83,381 COs)
51 KPIs with snake_case data_name identifiers for database ingestion

## Vendors
Vendor Detail — Job #2010
Vendors | 18 |  | Top vendor | Rosen Supply Company, Inc.
Invoices | 175 |  | Top 3 share | 91.28%
Total AP | 362721.85 |  | Source | Job Detail Report (Sage Timberline AP export)
Avg Inv | 2072.6963
Rank | Vendor | Vendor Code | Invoices | Total Spend | % of AP | Avg / Invoice
1 | Rosen Supply Company, Inc. |  | 73 | 215859.94 | 59.51% | 2956.9855
2 | Ferguson Enterprises, Inc. |  | 58 | 84342.57 | 23.25% | 1454.1822
3 | Bank of America CC |  | 3 | 30892.62 | 8.517% | 10297.54
4 | Franklin Engineering |  | 4 | 10463 | 2.885% | 2615.75
5 | Keller Supply Company |  | 7 | 10106.67 | 2.786% | 1443.81
6 | Quality Concrete Products, Inc. |  | 2 | 2414 | 0.6655% | 1207
7 | United Rentals, Inc. |  | 6 | 2404.21 | 0.6628% | 400.7017
8 | Ferguson Enterprises, Inc. #3007 |  | 7 | 2271.7 | 0.6263% | 324.5286
9 | Rosen Supply Kirkland |  | 3 | 1831.58 | 0.505% | 610.5267
10 | Duraseal, Inc. |  | 1 | 950 | 0.2619% | 950
11 | DRSi |  | 2 | 265.36 | 0.07316% | 132.68
12 | R.A. Brown Backflow Testing |  | 1 | 212 | 0.05845% | 212
13 | Manor Hardware & Construction Supply |  | 1 | 197.5 | 0.05445% | 197.5
14 | Consolidated Supply Co. |  | 1 | 168.54 | 0.04647% | 168.54
15 | Pacific Plumbing Supply Co., LLC |  | 2 | 121.4 | 0.03347% | 60.7
16 | Fastenal Company |  | 2 | 96.67 | 0.02665% | 48.335
17 | Kele, Inc |  | 1 | 69.69 | 0.01921% | 69.69
18 | C.M. Hoskins Company |  | 1 | 54.4 | 0.015% | 54.4
| TOTAL |  | 175 | 362721.85 | 100% | 2072.6963

## Change Log
Change Log — Master Register
Unified change-event ledger: RFIs, ASIs, COPs, COs, Backcharges, T&M (23 events)
Event ID | Type | Date | Subject | Originator | Linked Event(s) | Cost Impact ($) | Schedule (days) | Status | Source Document
CO-003 | CO | 2013-12-12 | Change Order #3 — embedded in schedule of values | GC (WPM) |  | 0 | 0 | Active | 2010-Chinn, Old Town/Oldtown billing/Chinn Old Town schedule of values- 13 -12-12-13 co#3.xlsx
CO-004 | CO | 2014-05-20 | Change Order #4 — embedded in schedule of values | GC (WPM) |  | 0 | 0 | Active | 2010-Chinn, Old Town/Oldtown billing/Chinn Old Town schedule of values- 17 -5-20-14 co#4.xlsx
ASI-001 | ASI | 2012-05-31 | Landscape for construction drawings | Architect (Weber Thompson) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/ASI No 1 Narrative.pdf
ASI-002 | ASI | 2012-06-19 | Structural Drawings Revision 7 — transformer cable room, wall replacement 8→6, dimensions, column repositioning | Architect (Weber Thompson) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/ASI No 2 Narratives.pdf
ASI-006 | ASI | 2012-Q3 | Architectural revisions — Level L011 | Architect (Weber Thompson) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/old town RFI-ASI/ASI 6 Architectural Revisions Level L011.pdf
ASI-008 | ASI | 2012-Q4 | Courtyard & street level irrigation plan details | Landscape Architect |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/old town RFI-ASI/Old Town ASI#8.pdf
ASI-023.R1 | ASI | 2013 | ASI 23 Revision 1 — resubmission | Architect (Weber Thompson) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/ASI No 23R1 Complete.pdf
ASI-024 | ASI | 2013 | ASI 24 — design clarification | Architect (Weber Thompson) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/ASI No 24 Complete.pdf
ASI-NARR | ASI | 2013 | ID Revisions Narrative — design revisions summary | Architect (Weber Thompson) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/Narrative for ID Revisions.pdf
RFI-004 | RFI | 2012 | PSE Transformer Relocation | GC (OTMU) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/old town RFI-ASI/RFI 4 PSE Transformer Relocation_Response.pdf
RFI-016 | RFI | 2012 | Oil/water separator relocation | GC (OTMU) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/old town RFI-ASI/Response - OTMU RFI #016 - oil water location relocation_.pdf
RFI-026 | RFI | 2012 | Vault room wall and footing details | GC (OTMU) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/old town RFI-ASI/RFI 026 - Response - Vault room wall and footing details.pdf
RFI-063 | RFI | 2013 | Crane blockout pourback | GC (OTMU) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/old town RFI-ASI/OTMU RFI #63 - crane blockout pourback_Response.pdf
RFI-086 | RFI | 2013 | Dog wash sleeve locations (plumbing coordination) | GC (OTMU) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/old town RFI-ASI/RFI 086 Dog Wash Sleeve Locations_WT Response.pdf
RFI-091 | RFI | 2013 | New location for backflow protection assembly | GC (OTMU) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/old town RFI-ASI/OTMU RFI 091 - New location for backflow protection assembly_Response.pdf
RFI-092 | RFI | 2013 | Water/sewer sleeves in PT slab for tenant spaces | GC (OTMU) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/old town RFI-ASI/OTMU RESPONSE RFI 092 - Watersewer sleeves in PT slab for tenant spaces.pdf
RFI-093 | RFI | 2013 | Elevation & location of fixtures in stairwells | GC (OTMU) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/old town RFI-ASI/OTMU RFI 093 - Elevation and location of fixtures in stairwells_Response.pdf
RFI-095 | RFI | 2013 | Water vault pump change (equipment substitution) | GC (OTMU) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/old town RFI-ASI/OTMU RFI 095 - Water vault pump change_Response.pdf
RFI-096 | RFI | 2013-03-01 | ERRCS head end equipment location | GC (OTMU) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/old town RFI-ASI/OTMU RFI 096 - ERRCS head end equipment location-AWA WT Response-3-1-13.pdf
RFI-099 | RFI | 2013 | L01 PT pour east design changes | GC (OTMU) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/old town RFI-ASI/OTMU RESPONSE RFI 99 L01 PT pour east design changes.pdf
RFI-104 | RFI | 2013 | PT deck at grid A level LM | GC (OTMU) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/old town RFI-ASI/OTMU RFI 104 - PT deck at grid A level LM_Response1.pdf
RFI-107 | RFI | 2013 | Warning horn or light at garage exits | GC (OTMU) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/old town RFI-ASI/OTMU RFI 107 - Warning Horn or Light at Garage Exits_Response1.pdf
RFI-115 | RFI | 2013 | Water repeater | GC (OTMU) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/old town RFI-ASI/OTMU RFI 115 - Water repeater_Response.pdf
TOTAL | [5 empty] | 0 | 0

## Root Cause Analysis
Root Cause Analysis — Change Driver Taxonomy
Categorized change events with responsible-party attribution — feeds bid-risk intelligence
CATEGORY ROLLUP
Root Cause Category | # Events | Net Cost Impact ($) | % of Events | Predominant Responsibility | Notes
Design error | 3 | 0 | 13.04% | Designer | Structural Drawings Revision 7 — transformer cable room, wal
Design substitution | 1 | 0 | 4.348% | Owner/GC | Water vault pump change (equipment substitution)
Design clarification | 9 | 0 | 39.13% | Designer | Landscape for construction drawings
Field condition | 2 | 0 | 8.696% | Owner/GC | Oil/water separator relocation
Coordination conflict | 5 | 0 | 21.74% | Owner/GC | PSE Transformer Relocation
Scope gap | 1 | 0 | 4.348% | Owner/GC | Warning horn or light at garage exits
Combined/multi-cause | 2 | 0 | 8.696% | Mixed | Change Order #3 — embedded in schedule of values
TOTAL | 23 | 0
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Events | Net $ Impact | Bid-Risk Signal
Owner/GC | 11 | 0 | NEUTRAL
Designer | 9 | 0 | NEUTRAL
Mixed | 3 | 0 | NEUTRAL

## Predictive Signals
Predictive Signals — Leading Indicators
Forward-looking metrics that predict CO waves, schedule slips, and margin erosion
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Predictive Meaning
RFI Total (closed) | 14 | <50 for mid-size | INFO | Volume proxy for design doc quality
RFI Velocity (per month, derived) | See KPIs D50 | <3.0/wk | INFO | >3/wk = CO wave in 4-8 wks
RFI Avg Cycle Time (days) | Unknown | <14 | N/A | >30 avg signals schedule slip
ASI / OCD Count | 7 | <5 | ELEVATED | High ASI = owner scope churn
Backcharge Count | 0 | <3 | HEALTHY | BC clusters = coordination weakness
Change Order Count | 2 | <3 | HEALTHY | CO count signals scope definition
T&M Event Count | 0 | <2 | HEALTHY | T&M = directed work pipeline
Submittal resubmission count | 0 | <10 | HEALTHY | Repeats = coord issues incubating
Net $ Impact (all events) | 0 | Near $0 | NEUTRAL | Net recoverable vs absorbed
FORECAST MODELS (closed-project — actuals)
Forecast | Current Estimate | Confidence | Driver | Model Note
Projected final CO % of contract | -0.056729 | Actual | Closed project | CO$ / orig contract
Projected EAC (direct cost) | 585998.58 | Actual | Closed project | Sum of L+M+OH+Burden
Projected final margin | 0.57733 | Actual | Closed project | (Rev - DC) / Rev
Composite risk score (0-100) | 24 | Medium | 0 BCs + 7 ASI/OCDs | Custom Cortex scoring

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence_level, and source_document — the machine-readable JCR index
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s) | Formula / Derivation
1 | job_number | Job Number | 2010 | id | Benchmark KPIs | Verified | JDR header | See Benchmark KPIs tab
2 | job_name | Job Name | Chinn Old Town Mixed Use | text | Benchmark KPIs | Verified | Contract folder | See Benchmark KPIs tab
3 | general_contractor | General Contractor | Chinn Construction, LLC | text | Benchmark KPIs | Verified | Contract folder | See Benchmark KPIs tab
4 | location | Location | Seattle, WA | text | Benchmark KPIs | Verified | Permit/Plans | See Benchmark KPIs tab
5 | project_type | Project Type | 165-unit mixed-use multifamily apartments + ground-floor retail | text | Benchmark KPIs | Verified | Plans | See Benchmark KPIs tab
6 | duration_months | Duration (months) | 24 | months | Benchmark KPIs | Verified | First-to-last invoice | See Benchmark KPIs tab
7 | unit_count | Unit Count | 165 | units | Benchmark KPIs | Verified | Plumbing permit + P-tag list | See Benchmark KPIs tab
8 | total_fixtures | Total Fixtures | 803 | count | Benchmark KPIs | Verified | Permit detail | See Benchmark KPIs tab
9 | contract_original | Contract Original | 1469800 | USD | Benchmark KPIs | Verified | Contract SOV | See Benchmark KPIs tab
10 | contract_final | Contract Final | 1386419 | USD | Benchmark KPIs | Verified | Final billing SOV | See Benchmark KPIs tab
11 | change_orders | Change Orders ($) | -83381 | USD | Benchmark KPIs | Verified | JDR revised - original | See Benchmark KPIs tab
12 | revenue | Revenue | 1386419 | USD | Benchmark KPIs | Verified | Aggregate billing | See Benchmark KPIs tab
13 | net_profit | Net Profit | 800420.42 | USD | Benchmark KPIs | Verified | Revenue - Direct Cost | See Benchmark KPIs tab
14 | gross_margin | Gross Margin % | 0.57733 | % | Benchmark KPIs | Verified | Derived | See Benchmark KPIs tab
15 | direct_cost | Direct Cost | 585998.58 | USD | Benchmark KPIs | Verified | JDR cost codes | See Benchmark KPIs tab
16 | labor_cost | Labor Cost | 196271.13 | USD | Benchmark KPIs | Verified | JDR labor codes | See Benchmark KPIs tab
17 | material_cost | Material Cost | 282662.77 | USD | Benchmark KPIs | Verified | JDR material codes | See Benchmark KPIs tab
18 | overhead_cost | Overhead Cost | 3650.67 | USD | Benchmark KPIs | Verified | JDR overhead codes | See Benchmark KPIs tab
19 | burden_cost | Burden Cost | 103414.01 | USD | Benchmark KPIs | Verified | JDR burden codes | See Benchmark KPIs tab
20 | retainage | Retainage | 69320.95 | USD | Benchmark KPIs | Verified | Aggregate billing row | See Benchmark KPIs tab
21 | total_hours | Total Labor Hours | 9992.25 | hours | Benchmark KPIs | Verified | JDR payroll | See Benchmark KPIs tab
22 | total_workers | Total Workers | 22 | count | Benchmark KPIs | Verified | JDR unique workers | See Benchmark KPIs tab
23 | blended_gross_wage | Blended Gross Wage | 1919% | USD/hr | Benchmark KPIs | Verified | Labor $ / Hours | See Benchmark KPIs tab
24 | total_vendors | Total Vendors | 18 | count | Benchmark KPIs | Verified | JDR AP unique | See Benchmark KPIs tab
25 | total_pos | Total POs | 73 | count | Benchmark KPIs | Verified | PO folder count | See Benchmark KPIs tab
26 | co_pct | CO % of Original | -0.056729 | % | Benchmark KPIs | Verified | Derived | See Benchmark KPIs tab
27 | rfi_total_count | RFIs Total | 14 | count | Predictive Signals | Verified | ASI-RFI folder count | See Predictive Signals tab
28 | asi_ocd_count | ASI + OCD Count | 7 | count | Change Log | Verified | ASI-RFI folder + Change Orders | See Change Log tab
29 | co_count_total | Change Order Count | 2 | count | Change Log | Verified | Change Orders folder | See Change Log tab
30 | backcharge_count | Backcharge Count | 0 | count | Change Log | Verified | Invoices/Backcharges | See Change Log tab
31 | tm_event_count | T&M Event Count | 0 | count | Change Log | Verified | Change Orders / JDR 038 | See Change Log tab
32 | submittal_resub_count | Submittal Resubmissions | 0 | count | Predictive Signals | Verified | Submittals folder | See Predictive Signals tab
33 | change_event_total | Total Tracked Events | 23 | count | Change Log | Verified | Change Log tab | See Change Log tab
34 | change_net_impact | Change Net $ Impact | 0 | USD | Change Log | Verified | SUM H col | See Change Log tab

## Reconciliation
Reconciliation — Cross-Tab Tie-out Proofs
Live cross-sheet formulas verify data consistency across all 17 tabs
Check | Tab A | Tab B | Δ | Status | Tabs
A. OVERVIEW ↔ BENCHMARK KPIS
Direct Cost Total | 585998.58 | 585998.58 | 0 | TIES | 1↔2↔11
Contract Final Value | 1386419 | 1386419 | 0 | TIES | JDR↔11
Net Profit | 800420.42 | 800420.42 | 0 | TIES | JDR↔11
Gross Margin | 57.73% | 57.73% | 0% | TIES | JDR↔11
B. OVERVIEW ↔ COST BREAKDOWN (Category Actuals)
Labor Actual | 196271.13 | 196271.13 | 0 | TIES | 1↔3
Material Actual | 282662.77 | 282662.77 | 0 | TIES | 1↔3
Overhead Actual | 3650.67 | 3650.67 | 0 | TIES | 1↔3
Burden Actual | 103414.01 | 103414.01 | 0 | TIES | 1↔3
C. BUDGET vs ACTUAL ↔ OVERVIEW
Actual Direct Cost | 585998.58 | 585998.58 | 0 | TIES | 2↔1
Revised Budget Total | 977917.55 | 977917.55 | 0 | TIES | 2↔1
D. MATERIAL ↔ COST BREAKDOWN ↔ KPIS
Material Actual (Material tab) | 282662.77 | 282662.77 | 0 | TIES | 4↔3
Material Actual (KPIs) | 282662.77 | 282662.77 | 0 | TIES | 11↔3
E. CREW & LABOR ↔ PRODUCTIVITY ↔ KPIS (Hours)
Total Hours (Crew tab) | 9923.5 | 9992.25 | -68.75 | WITHIN | 5↔11
Total Hours (Productivity tab) | 9992.25 | 9992.25 | 0 | TIES | 7↔11
Total Workers | 22 | 22 | 0 | TIES | JDR↔11
F. CREW ANALYTICS ↔ KPIS (Wage Statistics)
Blended Gross Wage | 19.3239 | 19.1909 | 0.13295 | TIES | 6↔11
Fully-Loaded Wage | 30.1995 | 29.9918 | 0.20778 | TIES | 6↔11
G. PO COMMITMENTS ↔ KPIS
PO Count | 73 | 73 | 0 | TIES | 8↔11
H. BILLING & SOV ↔ JDR
Final Contract Value | 1386419 | 1386419 | 0 | TIES | 9↔JDR
Retainage | 69321 | 69321 | 0 | TIES | 9↔JDR
Direct Cost | 585999 | 585999 | 0 | TIES | 9↔JDR
I. VENDORS ↔ KPIS
Vendor Count | 18 | 18 | 0 | TIES | 12↔11
Total AP Spend | 362721.85 | 362722 | -0.15 | TIES | 12↔JDR
J. INSIGHTS (Narrative Review)
10 insight cards — narrative text verified at generation time, no formula check applicable
K. CHANGE LOG ↔ ROOT CAUSE ANALYSIS
Total Event Count | 23 | 23 | 0 | TIES | 13↔14
Net $ Impact (all events) | 0 | 0 | 0 | TIES | 13↔14
L. PREDICTIVE SIGNALS ↔ CHANGE LOG
Backcharge Count signal | 0 | 0 | 0 | TIES | 15↔13
M. METRIC REGISTRY ↔ BENCHMARK KPIs
revenue (row 17) | 1386419 | 1386419 | 0 | TIES | 16↔11
unit_count (row 12) | 165 | 165 | 0 | TIES | 16↔11
total_fixtures (row 13) | 803 | 803 | 0 | TIES | 16↔11
direct_cost (row 19) | 0.57733 | 585998.58 | -585998.0027 | OFF | 16↔11
total_pos (row 30) | 73 | 73 | 0 | TIES | 16↔11
N. CHANGE LOG ↔ METRIC REGISTRY (event counts)
change_event_total | 0 | 23 | -23 | OFF | 16↔13
SOURCES
Job #2010 — Cortex v2 17-tab layout
12 analytical tabs + Change Log + Root Cause Analysis + Predictive Signals + Metric Registry + Reconciliation
Canonical source: 2010 Job Detail Report.pdf (Sage Timberline export)
Change artifacts: folders scanned — ASI-RFI, Change Orders, Submittals, Invoices (Backcharges), JDR cost codes
Every Change Log row cites its source document path
TIES = within $1/5hrs/exact count • WITHIN = within 5% • OFF = investigate
Cross-sheet formulas (='Tab'!Cell) update automatically when source tabs change
Tabs: 1-12 analytical • 13=ChangeLog • 14=RootCause • 15=PredictiveSignals • 16=MetricRegistry • 17=Reconciliation