## Overview
Job #2017 · Exxel Pacific 3636 Stone Way Apartments
Cortex JCR Summary • Exxel Pacific, Inc. • Seattle, WA (3636 Stone Way N) • 119-unit 4-story mixed-use apartments + ground-floor retail • Feb 2014 – May 2015 (~16 months)
PROJECT OVERVIEW
Project Job # | 2017
Project Name: | Exxel Pacific 3636 Stone Way Apartments
General Contractor | Exxel Pacific, Inc.
Location | Seattle, WA (3636 Stone Way N)
Project Duration | Feb 2014 – May 2015 (~16 months)
Total Unique Documents | 36 Stone folder: Contract, Stoneway billing (14 apps), PO_s, COs, Job Ticket
CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
$1,369,989 |  | $510,805 |  | $859,184 |  | 14,822
Original $1,373,148 net COs -$3,159 |  | 37.3% margin |  | 62.7% of revenue |  | 45 workers
COST BREAKDOWN
Category | Budget | Actual | Variance | % Budget | % of Cost
Labor | 272340 | 292755.75 | -20415.75 | 107.5% | 34.07%
Material | 502391 | 378313.74 | 124077.26 | 75.3% | 44.03%
Overhead | 42470 | 33855.5 | 8614.5 | 79.72% | 3.94%
Burden | 139796.75 | 154259.34 | -14462.59 | 110.3% | 17.95%
TOTAL | 956997.75 | 859184.33 | 97813.42 | 89.78% | 100%
PROJECT PROFILE
Metric | Value | Metric | Value | Metric | Value
Plumbing Units | 119 | Water Closets | 122 | Kitchen Sinks | 119
Total Fixtures | 801 | Lavatories | 137 | Dishwashers | 119
Fixtures / Unit | 6.73 | Tubs/Showers | 122 | Auto Washers | 119
Floors | 4 + P1 | Common-area bldg systems | Garage HB, water rm, gas | Duration | 16 mo
SOURCES
Job #2017 — Exxel Pacific 3636 Stone Way Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2017 Job Detail Report.pdf (124 pages, OWP Sage Timberline export)
Cost codes parsed: 27 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 119 from Job Ticket (119 DWs, 119 washers)
Fixture count: Toto WCs 122, Grohe lavs 137, Aquatic tubs 122, Lenova/Elkay sinks 119 + common area
Billing: 36 STONE AGGREGATE BILLING.xlsx (14 pay apps, Feb 2014 – May 2015)

## Budget vs Actual
Budget vs Actual — All Cost Codes
Code | Description | Orig Budget | Rev Budget | Actual | Variance | % Used
LABOR
100 | Supervision | 6500 | 6500 | 4744 | 1756 | 72.98%
101 | Takeoff & Purchase Labor | 6500 | 7300 | 7873 | -573 | 107.8%
110 | Underground Labor | 8538 | 8538 | 6900 | 1638 | 80.82%
111 | Garage Labor | 38180 | 38670 | 29981 | 8689 | 77.53%
112 | Canout Labor | 5130 | 5130 | 4602 | 528 | 89.71%
113 | Foundation Drain Labor | 2012 | 2012 | 2012 | 0 | 100%
120 | Roughin Labor | 138760 | 140370 | 173312.75 | -32942.75 | 123.5%
130 | Finish Labor | 23400 | 25520 | 36292.5 | -10772.5 | 142.2%
140 | Gas Labor | 6000 | 6300 | 7448 | -1148 | 118.2%
141 | Water Main/Insulation Lab | 32000 | 32000 | 19505.5 | 12494.5 | 60.95%
142 | Mech Room Labor | 0 | 0 | 85 | -85 | 0%
MATERIAL
039 | DS & RD Material | 0 | 0 | 2380.94 | -2380.94 | 0%
210 | Underground Material | 5685 | 5685 | 3861 | 1824 | 67.92%
211 | Garage Material | 29760 | 29800 | 3724.79 | 26075.21 | 12.5%
212 | Canout Material | 5700 | 5740 | 6453.36 | -713.36 | 112.4%
213 | Foundation Material | 15065 | 13365 | 13364.65 | 0.35 | 100%
220 | Roughin Material | 138250 | 132050 | 98571.05 | 33478.95 | 74.65%
230 | Finish Material | 273100 | 248951 | 192296.61 | 56654.39 | 77.24%
240 | Gas Material | 3600 | 3600 | 2769 | 831 | 76.92%
241 | Water Main/Insulation Mat | 51200 | 51200 | 45904.61 | 5295.39 | 89.66%
242 | Mech Room Material | 12000 | 12000 | 8987.73 | 3012.27 | 74.9%
OVERHEAD
600 | Subcontractor | 15970 | 16970 | 15635 | 1335 | 92.13%
601 | Engineering/Plans | 22000 | 22500 | 17974.5 | 4525.5 | 79.89%
603 | Permits & Licenses | 3000 | 3000 | 246 | 2754 | 8.2%
BURDEN
995 | Payroll Burden | 116366.6 | 118687.33 | 131106.33 | -12419 | 110.5%
998 | Payroll Taxes | 20702.43 | 21109.42 | 23153.01 | -2043.59 | 109.7%
TOTAL | Direct Cost | 979419.03 | 956997.75 | 859184.33 | 97813.42 | 89.78%
SOURCES
Job #2017 — Exxel Pacific 3636 Stone Way Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2017 Job Detail Report.pdf (124 pages, OWP Sage Timberline export)
Cost codes parsed: 27 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 119 from Job Ticket (119 DWs, 119 washers)
Fixture count: Toto WCs 122, Grohe lavs 137, Aquatic tubs 122, Lenova/Elkay sinks 119 + common area
Billing: 36 STONE AGGREGATE BILLING.xlsx (14 pay apps, Feb 2014 – May 2015)

## Cost Breakdown
Cost Breakdown — Category Deep Dive
A. CATEGORY SHARE OF DIRECT COST
Category | # Codes | Budget | Actual | Variance | % Budget | % of Cost | Per Unit
Labor | 11 | 272340 | 292755.75 | -20415.75 | 107.5% | 34.07% | 2460.1324
Material | 10 | 502391 | 378313.74 | 124077.26 | 75.3% | 44.03% | 3179.1071
Overhead | 3 | 42470 | 33855.5 | 8614.5 | 79.72% | 3.94% | 284.5
Burden | 2 | 139796.75 | 154259.34 | -14462.59 | 110.3% | 17.95% | 1296.297
B. LARGEST OVERRUNS (Actual > Revised Budget)
Code | Description | Rev Budget | Actual | Overrun | % Over
120 | Roughin Labor | 140370 | 173312.75 | 32942.75 | 23.47%
995 | Payroll Burden | 118687.33 | 131106.33 | 12419 | 10.46%
130 | Finish Labor | 25520 | 36292.5 | 10772.5 | 42.21%
039 | DS & RD Material | 0 | 2380.94 | 2380.94 | 0%
998 | Payroll Taxes | 21109.42 | 23153.01 | 2043.59 | 9.681%
140 | Gas Labor | 6300 | 7448 | 1148 | 18.22%
212 | Canout Material | 5740 | 6453.36 | 713.36 | 12.43%
101 | Takeoff & Purchase Labor | 7300 | 7873 | 573 | 7.849%
C. LARGEST SAVINGS (Actual < Revised Budget)
Code | Description | Rev Budget | Actual | Savings | % Under
230 | Finish Material | 248951 | 192296.61 | 56654.39 | 22.76%
220 | Roughin Material | 132050 | 98571.05 | 33478.95 | 25.35%
211 | Garage Material | 29800 | 3724.79 | 26075.21 | 87.5%
141 | Water Main/Insulation Lab | 32000 | 19505.5 | 12494.5 | 39.05%
111 | Garage Labor | 38670 | 29981 | 8689 | 22.47%
241 | Water Main/Insulation Mat | 51200 | 45904.61 | 5295.39 | 10.34%
601 | Engineering/Plans | 22500 | 17974.5 | 4525.5 | 20.11%
242 | Mech Room Material | 12000 | 8987.73 | 3012.27 | 25.1%
603 | Permits & Licenses | 3000 | 246 | 2754 | 91.8%
210 | Underground Material | 5685 | 3861 | 1824 | 32.08%
SOURCES
Job #2017 — Exxel Pacific 3636 Stone Way Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2017 Job Detail Report.pdf (124 pages, OWP Sage Timberline export)
Cost codes parsed: 27 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 119 from Job Ticket (119 DWs, 119 washers)
Fixture count: Toto WCs 122, Grohe lavs 137, Aquatic tubs 122, Lenova/Elkay sinks 119 + common area
Billing: 36 STONE AGGREGATE BILLING.xlsx (14 pay apps, Feb 2014 – May 2015)

## Material
Material Spend Analysis
10 material cost codes • $378,314 JDR material • 20 AP vendors • $458,376 total AP
A. MATERIAL BY COST CODE
Code | Description | Rev Budget | Actual | Variance | % Used | % of Mat | Per Unit
039 | DS & RD Material | 0 | 2380.94 | -2380.94 | 0% | 0.6294% | 20.0079
210 | Underground Material | 5685 | 3861 | 1824 | 67.92% | 1.021% | 32.4454
211 | Garage Material | 29800 | 3724.79 | 26075.21 | 12.5% | 0.9846% | 31.3008
212 | Canout Material | 5740 | 6453.36 | -713.36 | 112.4% | 1.706% | 54.2299
213 | Foundation Material | 13365 | 13364.65 | 0.35 | 100% | 3.533% | 112.308
220 | Roughin Material | 132050 | 98571.05 | 33478.95 | 74.65% | 26.06% | 828.3282
230 | Finish Material | 248951 | 192296.61 | 56654.39 | 77.24% | 50.83% | 1615.9379
240 | Gas Material | 3600 | 2769 | 831 | 76.92% | 0.7319% | 23.2689
241 | Water Main/Insulation Mat | 51200 | 45904.61 | 5295.39 | 89.66% | 12.13% | 385.753
242 | Mech Room Material | 12000 | 8987.73 | 3012.27 | 74.9% | 2.376% | 75.5271
TOTAL | All Material | 502391 | 378313.74 | 124077.26 | 75.3% | 100% | 3179.1071
B. VENDORS BY SPEND (AP)
Vendor | # Invoices | Total Spend | % of AP |  |  |  | Avg Invoice
Consolidated Supply Co. | 102 | 176571.46 | 38.52% |  |  |  | 1731.0927
Rosen Supply Company, Inc. | 85 | 139209.01 | 30.37% |  |  |  | 1637.7531
Ferguson Enterprises, Inc. | 18 | 72780.98 | 15.88% |  |  |  | 4043.3878
Franklin Engineering | 5 | 17974.5 | 3.921% |  |  |  | 3594.9
Duraseal, Inc. | 2 | 12800 | 2.792% |  |  |  | 6400
Keller Supply Company | 11 | 8131.24 | 1.774% |  |  |  | 739.2036
Bank of America CC | 6 | 8076 | 1.762% |  |  |  | 1346
Quality Concrete Products, Inc. | 3 | 5921 | 1.292% |  |  |  | 1973.6667
Rosen Supply Kirkland | 6 | 4412.21 | 0.9626% |  |  |  | 735.3683
Mechanical Sales, Inc. | 2 | 2840 | 0.6196% |  |  |  | 1420
Manor Hardware & Construction Supply | 3 | 2465 | 0.5378% |  |  |  | 821.6667
Cascade Restoration Co. | 2 | 2140 | 0.4669% |  |  |  | 1070
Kele, Inc | 4 | 1340.48 | 0.2924% |  |  |  | 335.12
Core & Main LP | 2 | 1134.15 | 0.2474% |  |  |  | 567.075
Ferguson Enterprises, Inc. #3007 | 3 | 811.46 | 0.177% |  |  |  | 270.4867
C.M. Hoskins Company | 3 | 702.97 | 0.1534% |  |  |  | 234.3233
Structural Imaging, LLC | 1 | 500 | 0.1091% |  |  |  | 500
Fastenal Company | 4 | 258.11 | 0.05631% |  |  |  | 64.5275
R.A. Brown Backflow Testing | 2 | 195 | 0.04254% |  |  |  | 97.5
Capital One Credit Card | 2 | 112.8 | 0.02461% |  |  |  | 56.4
TOTAL | 266 | 458376.37 | 100%
SOURCES
Job #2017 — Exxel Pacific 3636 Stone Way Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2017 Job Detail Report.pdf (124 pages, OWP Sage Timberline export)
Cost codes parsed: 27 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 119 from Job Ticket (119 DWs, 119 washers)
Fixture count: Toto WCs 122, Grohe lavs 137, Aquatic tubs 122, Lenova/Elkay sinks 119 + common area
Billing: 36 STONE AGGREGATE BILLING.xlsx (14 pay apps, Feb 2014 – May 2015)
Vendor AP ties to JDR 'by Source: AP' line (458,376.37)

## Crew & Labor
Crew & Labor — Per-Worker Breakdown
Worker | Hours | Gross Pay | $/Hour | Tier
Gonzalez Hernandez, Josue | 1282 | 19700 | 15.3666 | Apprentice
Montenegro, Carlos E | 1186 | 16982 | 14.3187 | Apprentice
Castro Hernandez, Carlos E | 1176 | 33725 | 28.6777 | Mid
Reyes Cruz, Denis A | 1006.5 | 13658 | 13.5698 | Apprentice
Quintanilla, Esteban R | 1002 | 32471 | 32.4062 | Senior
Lima Romero, Melvin A | 921 | 18933 | 20.557 | Mid
Rivera, Jorge A | 909 | 17124 | 18.8383 | Mid
Esparza Jimenez, Jose D | 784 | 14896 | 19 | Mid
Castro Hernandez, Jose A | 687.5 | 12177 | 17.712 | Apprentice
Reyes, Robert J | 606 | 8164 | 13.4719 | Apprentice
Ramirez, Lorenzo A | 490 | 8061 | 16.451 | Apprentice
Soto Cruz, Jovani | 442.5 | 7471 | 16.8836 | Apprentice
Monico Brambila, Jesus S | 408 | 6352 | 15.5686 | Apprentice
Ramos Banegas, Noel O | 405.5 | 5930.5 | 14.6252 | Apprentice
Sepulveda Gonzalez, Alfredo | 401 | 10159 | 25.3342 | Mid
Rivera, Eli P | 397 | 5811 | 14.6373 | Apprentice
Castaneda Martinez, Gustavo | 394 | 11269 | 28.6015 | Mid
Gerard, Jeffrey S | 331.5 | 12927 | 38.9955 | Senior
Anzora, William | 312 | 4216 | 13.5128 | Apprentice
Kinssies, Jr, John E | 220.5 | 3420 | 15.5102 | Apprentice
Salazar, Hajdar L | 216.5 | 3312 | 15.2979 | Apprentice
Castaneda Juarez, Edgar D | 214 | 3340.75 | 15.611 | Apprentice
Sanders, Allen O | 156 | 4809 | 30.8269 | Senior
Vaughan, Tyler J | 150.5 | 2468.5 | 16.402 | Apprentice
Anderson, Richard P | 140 | 3920 | 28 | Mid
Rico-Gomez, Angel A | 114.5 | 1488.5 | 13 | Apprentice
Castaneda Juarez, Gustavo | 111.5 | 1641 | 14.7175 | Apprentice
Veley, Nathaniel S | 107 | 3103 | 29 | Mid
Rodriguez Bonilla, Lisandro | 88 | 1144 | 13 | Apprentice
Gerard, Mitchell J | 73 | 936 | 12.8219 | Apprentice
Paco Leyva, Orlando | 59 | 1003 | 17 | Apprentice
Donelson, Richard T | 29 | 1305 | 45 | Senior
Meza Fuentes, Erick A | 24 | 488 | 20.3333 | Mid
Palma Vides, Hugo | 16 | 464 | 29 | Mid
Amaya Gonzalez, Edilberto A | 16 | 208 | 13 | Apprentice
Arreola, Israel A | 16 | 272 | 17 | Apprentice
Garcia, Jordan X | 16 | 272 | 17 | Apprentice
Hubbard, Dustin R | 16 | 208 | 13 | Apprentice
Nishiyama, Joshua K | 13 | 169 | 13 | Apprentice
Rodriguez Rodriguez, Aminadab N | 8 | 104 | 13 | Apprentice
Ascencio, Jose L | 8 | 104 | 13 | Apprentice
Cruz Reyes, Jose | 8 | 104 | 13 | Apprentice
McCabe, Thomas C | 6 | 120 | 20 | Mid
Velasquez Cruz, Denis M | 6 | 90 | 15 | Apprentice
Barnhart, Joseph N | 1 | 31 | 31 | Senior
TOTAL (45 workers) | 14975 | 294551.25 | 19.6695
SOURCES
Job #2017 — Exxel Pacific 3636 Stone Way Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2017 Job Detail Report.pdf (124 pages, OWP Sage Timberline export)
Cost codes parsed: 27 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 119 from Job Ticket (119 DWs, 119 washers)
Fixture count: Toto WCs 122, Grohe lavs 137, Aquatic tubs 122, Lenova/Elkay sinks 119 + common area
Billing: 36 STONE AGGREGATE BILLING.xlsx (14 pay apps, Feb 2014 – May 2015)
Tier: Apprentice <$18/hr, Mid $18–30, Senior >$30

## Crew Analytics
Crew Analytics
A. TIER DISTRIBUTION
Tier | # Workers | Hours | Gross Pay | % of Hours
Senior | 5 | 1519.5 | 51543 | 10.15%
Mid | 11 | 4878 | 114201 | 32.57%
Apprentice | 29 | 8577.5 | 128807.25 | 57.28%
B. WAGE STATISTICS
Blended Gross Wage | 19.6695 |  |  | Payroll $ ÷ payroll hours (pre-burden)
Fully-Loaded Wage | 29.8508 |  |  | (Labor + Burden) ÷ total hours
Burden Multiplier | 1.5176 |  |  | Fully loaded ÷ gross wage
Min Worker Rate | 12.8219 |  |  | Cheapest apprentice hour
Max Worker Rate | 45 |  |  | Most expensive foreman hour
Avg Hours / Worker | 332.7778 |  |  | Crew continuity indicator
SOURCES
Job #2017 — Exxel Pacific 3636 Stone Way Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2017 Job Detail Report.pdf (124 pages, OWP Sage Timberline export)
Cost codes parsed: 27 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 119 from Job Ticket (119 DWs, 119 washers)
Fixture count: Toto WCs 122, Grohe lavs 137, Aquatic tubs 122, Lenova/Elkay sinks 119 + common area
Billing: 36 STONE AGGREGATE BILLING.xlsx (14 pay apps, Feb 2014 – May 2015)

## Productivity
Productivity — Phase & Unit Metrics
A. LABOR HOURS BY PHASE
Phase | Labor Code | Hours | % of Total | Hours / Unit
Supervision | 100 | 119.5 | 0.8062% | 1.0042
Takeoff & Purchasing | 101 | 198.5 | 1.339% | 1.6681
Underground | 110 | 288 | 1.943% | 2.4202
Garage | 111 | 1485 | 10.02% | 12.479
Canout | 112 | 177.5 | 1.198% | 1.4916
Foundation Drain | 113 | 97 | 0.6544% | 0.81513
Roughin | 120 | 9126.5 | 61.57% | 76.6933
Finish | 130 | 1926 | 12.99% | 16.1849
Gas | 140 | 352 | 2.375% | 2.958
Water Main / Insulation | 141 | 1047 | 7.064% | 8.7983
Mech Room | 142 | 5 | 0.03373% | 0.042017
TOTAL |  | 14822 | 100% | 124.5546
B. PRODUCTIVITY RATIOS
Metric | Value | Units |  | Notes
Hours / Unit | 124.5546 | hrs |  | Labor hours per residential unit
Hours / Fixture | 18.5044 | hrs |  | Labor hours per plumbing fixture
Revenue / Hour | 92.4294 | $ |  | Top-line per labor hour
Profit / Hour | 34.4626 | $ |  | Bottom-line per labor hour
Units / Month | 7.4375 | units |  | Build velocity
Fixtures / Month | 50.0625 | fix |  | Fixture install pace
Hours / Month | 926.375 | hrs |  | Monthly labor burn
Revenue / Month | 85624.3125 | $ |  | Monthly billing rate
SOURCES
Job #2017 — Exxel Pacific 3636 Stone Way Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2017 Job Detail Report.pdf (124 pages, OWP Sage Timberline export)
Cost codes parsed: 27 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 119 from Job Ticket (119 DWs, 119 washers)
Fixture count: Toto WCs 122, Grohe lavs 137, Aquatic tubs 122, Lenova/Elkay sinks 119 + common area
Billing: 36 STONE AGGREGATE BILLING.xlsx (14 pay apps, Feb 2014 – May 2015)

## PO Commitments
Purchase Order Commitments
142 unique POs • PO amounts not dollar-parsed from individual PDFs • JDR material $378,314
A. COMMITMENTS BY COST CODE
OWP Code | Description → JDR | PO Count | % of POs | JDR Material
30 | 110+210 Underground | 18 | 12.68%
31 | 120+220 Roughin | 25 | 17.61%
32 | 130+230 Trim/Finish | 9 | 6.338%
34 | 111+211 Garage | 2 | 1.408%
40 | 141+241 Water Main/Ins | 2 | 1.408%
41 | 140+240 Gas | 4 | 2.817%
OTHER | Unclassified | 82 | 57.75%
TOTAL |  | 142 | 100% | 378313.74
B. COMMITMENTS BY VENDOR
Vendor | PO Count | % of POs
ROSEN | 62 | 43.66%
CONSOLIDATED | 31 | 21.83%
OTHER | 18 | 12.68%
KELLER | 11 | 7.746%
FEI | 11 | 7.746%
MANOR | 3 | 2.113%
FASTENAL | 3 | 2.113%
SIOUX CHIEF | 1 | 0.7042%
PIKE | 1 | 0.7042%
MECH SALES | 1 | 0.7042%
C. PO COVERAGE NOTES
Total Material Actual (JDR) |  |  | 378313.74
Unique PO Count |  |  | 142
(Dollar PO commitment not extracted — requires per-PDF parse)
SOURCES
Job #2017 — Exxel Pacific 3636 Stone Way Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2017 Job Detail Report.pdf (124 pages, OWP Sage Timberline export)
Cost codes parsed: 27 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 119 from Job Ticket (119 DWs, 119 washers)
Fixture count: Toto WCs 122, Grohe lavs 137, Aquatic tubs 122, Lenova/Elkay sinks 119 + common area
Billing: 36 STONE AGGREGATE BILLING.xlsx (14 pay apps, Feb 2014 – May 2015)
PO count is deduplicated by 5-digit PO number extracted from filenames
Vendor/code classification is heuristic (filename keyword match)

## Billing & SOV
Revenue & Billing Reconciliation
14 pay applications • Original $1,373,148 net -$3,159 COs = $1,369,989
A. CONTRACT SUMMARY
Original Contract |  |  |  |  | 1373148
Change Orders (net) |  |  |  |  | -3159
Final Contract Value |  |  |  |  | 1369989
Retainage (5%) |  |  |  |  | 68499
Net Paid to OWP |  |  |  |  | 1301490
B. PAY APPLICATION TIMELINE
App# | Date | Period Billing | Retention | Net This Period | Aggregate | % Complete
1 | 2014-02-20 | 70000 | 3500 | 66500 | 66500 | 4.854%
2 | 2014-04-20 | 43000 | 2150 | 40850 | 107350 | 7.836%
3 | 2014-05-20 | 72350 | 3617.5 | 68732.5 | 176082.5 | 12.85%
4 | 2014-06-20 | 21643 | 1082.15 | 20560.85 | 196643.35 | 14.35%
5 | 2014-07-20 | 111749 | 5587.45 | 106161.55 | 302804.9 | 22.1%
6 | 2014-08-20 | 229700 | 11485 | 218215 | 521019.9 | 38.03%
7 | 2014-09-18 | 348421 | 17421.05 | 330999.95 | 852019.85 | 62.19%
8 | 2014-10-20 | 213650 | 10682.5 | 202967.5 | 1054987.35 | 77.01%
9 | 2014-11-17 | 83445 | 4172.25 | 79272.75 | 1134260.1 | 82.79%
10 | 2014-12-15 | 24500 | 1225 | 23275 | 1157535.1 | 84.49%
11 | 2015-01-20 | 32880 | 1644 | 31236 | 1188771.1 | 86.77%
12 | 2015-02-20 | 53430 | 2671.5 | 50758.5 | 1239529.6 | 90.48%
13 | 2015-03-19 | 63944 | 3197.2 | 60746.8 | 1300276.4 | 94.91%
14 | 2015-05-19 | 1277 | 63.85 | 1213.15 | 1301489.55 | 95%
15 | - | 68499.45 | 0 | 68499.45 | 1369989 | 100%
C. BILLING ↔ JDR TIE-OUT
Metric | SOV | JDR | Δ | Status
Final Contract Value | 1438488.45 | 1369989 | 68499.45 | WITHIN
Retainage | 68499 | 68499 | 0 | TIES
Direct Cost | 859184.33 | 859184.33 | 0 | TIES
SOURCES
Job #2017 — Exxel Pacific 3636 Stone Way Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2017 Job Detail Report.pdf (124 pages, OWP Sage Timberline export)
Cost codes parsed: 27 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 119 from Job Ticket (119 DWs, 119 washers)
Fixture count: Toto WCs 122, Grohe lavs 137, Aquatic tubs 122, Lenova/Elkay sinks 119 + common area
Billing: 36 STONE AGGREGATE BILLING.xlsx (14 pay apps, Feb 2014 – May 2015)

## Insights
Key Insights — Job #2017 Exxel Pacific 3636 Stone Way Apartments
Narrative observations distilled from the full JDR analysis
MARGIN PROFILE | Net profit of $510,805 on $1,369,989 revenue = 37.3% gross margin. Direct cost $859,184 absorbs 62.7% of revenue.
VENDOR CONCENTRATION | Consolidated Supply Co. alone = $176,571 (39% of all AP) across 102 invoices. Total 20 AP vendors, $458,376 total AP spend.
CREW PROFILE | 45 workers for 14,822 hours = 329 avg hrs/worker. Top 3 workers logged 3,644 hrs combined (25% of all labor).
ROUGHIN DOMINANCE | Code 120 Roughin Labor = 9,126 hrs (62% of all labor) and $173,313 actual. Code 230 Finish Material = $192,297 — 22% of total direct cost.
BUDGET DELIVERY | Revised budget was $956,998; actual direct cost $859,184 → $97,813 variance (10.2% under revised budget).
CONTRACT GROWTH | Contract grew from $1,373,148 to $1,369,989 — net +$-3,159 (-0.2%). Retainage of $68,499 (5%) withheld until closeout.
BURDEN RATIO | Burden codes 995 + 998 = $154,259 on $292,756 labor base = 52.7%. In line with OWP's typical 48–50% labor burden.
PROJECT SCALE | 119 units · 801 fixtures · 16 months. Revenue/unit $11,513, hours/unit 124.6, profit/unit $4,292.
PRODUCTIVITY | Blended labor rate $19.75/hr. Revenue/hour $92. Profit/hour $34. 926 hrs/month burn rate.
FIXTURE DENSITY | 801 fixtures ÷ 119 units = 6.73 fixtures/unit. Material/fixture $472, labor/fixture $365.
BIGGEST QUESTION
How does this job's 37.3% margin compare across similar projects in the OWP portfolio, and what operational levers drove the result — estimating accuracy, vendor pricing, or labor productivity?
SOURCES
Job #2017 — Exxel Pacific 3636 Stone Way Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2017 Job Detail Report.pdf (124 pages, OWP Sage Timberline export)
Cost codes parsed: 27 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 119 from Job Ticket (119 DWs, 119 washers)
Fixture count: Toto WCs 122, Grohe lavs 137, Aquatic tubs 122, Lenova/Elkay sinks 119 + common area
Billing: 36 STONE AGGREGATE BILLING.xlsx (14 pay apps, Feb 2014 – May 2015)

## Benchmark KPIs
Benchmark KPIs
Normalized metrics designed for apples-to-apples comparison across all OWP projects
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2017 | Profile | OWP job ID | Verified | Benchmark KPIs / Metric Registry — see source tabs
Job Name | job_name | Exxel Pacific 3636 Stone Way Apartments | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
General Contractor | general_contractor | Exxel Pacific, Inc. | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Location | location | Seattle, WA (3636 Stone Way N) | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Project Type | project_type | 119-unit 4-story mixed-use apartments + ground-floor retail | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Duration (months) | duration_months | 16 | Profile | Feb 2014 – May 2015 (~16 months) | Verified | Benchmark KPIs / Metric Registry — see source tabs
Unit Count | unit_count | 119 | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total Fixtures | total_fixtures | 801 | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Fixtures per Unit | fixtures_per_unit | 6.7311 | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Contract Value (Orig) | contract_original | 1373148 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Contract Value (Final) | contract_final | 1369989 | Financial | After change orders | Verified | Benchmark KPIs / Metric Registry — see source tabs
Change Orders ($) | change_orders | -3159 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue | revenue | 1369989 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Net Profit | net_profit | 510804.67 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Gross Margin | gross_margin | 0.37285 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Direct Cost | direct_cost | 859184.33 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Labor Cost | labor_cost | 292755.75 | Labor | Sum of 11 labor codes | Verified | Benchmark KPIs / Metric Registry — see source tabs
Material Cost | material_cost | 378313.74 | Material | Sum of 10 material codes | Verified | Benchmark KPIs / Metric Registry — see source tabs
Overhead Cost | overhead_cost | 33855.5 | Financial | Sub+Eng+Permits | Verified | Benchmark KPIs / Metric Registry — see source tabs
Burden Cost | burden_cost | 154259.34 | Financial | Codes 995+998 | Verified | Benchmark KPIs / Metric Registry — see source tabs
Retainage | retainage | 68499 | Financial | 5% withheld | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Unit | revenue_per_unit | 11512.5126 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Profit per Unit | profit_per_unit | 4292.4762 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Direct Cost per Unit | cost_per_unit | 7220.0364 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Labor Cost per Unit | labor_per_unit | 2460.1324 | Labor |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Material Cost per Unit | material_per_unit | 3179.1071 | Material |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Fixture | revenue_per_fixture | 1710.3483 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Profit per Fixture | profit_per_fixture | 637.7087 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Cost per Fixture | cost_per_fixture | 1072.6396 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Labor per Fixture | labor_per_fixture | 365.4878 | Labor |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Material per Fixture | material_per_fixture | 472.3018 | Material |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total Labor Hours | total_hours | 14822 | Labor | Sum of JDR cost code hours | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total Workers | total_workers | 45 | Labor | Unique payroll IDs | Verified | Benchmark KPIs / Metric Registry — see source tabs
Blended Gross Wage | blended_gross_wage | 1987% | Labor | Pre-burden | Verified | Benchmark KPIs / Metric Registry — see source tabs
Fully-Loaded Wage | fully_loaded_wage | 3016% | Labor | Post-burden | Verified | Benchmark KPIs / Metric Registry — see source tabs
Burden Multiplier | burden_multiplier | 1.5176 | Labor |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Hours per Unit | hours_per_unit | 124.5546 | Labor | Key benchmark | Verified | Benchmark KPIs / Metric Registry — see source tabs
Hours per Fixture | hours_per_fixture | 1850% | Labor | Key benchmark | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Hour | revenue_per_hour | 9243% | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Profit per Hour | profit_per_hour | 3446% | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Labor % of Revenue | labor_pct_revenue | 0.21369 | Cost Mix |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Material % of Revenue | material_pct_revenue | 0.27614 | Cost Mix |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Month | revenue_per_month | 85624.3125 | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Hours per Month | hours_per_month | 926.375 | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Units per Month | units_per_month | 7.4375 | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total Vendors | total_vendors | 20 | Material | Unique AP vendors | Verified | Benchmark KPIs / Metric Registry — see source tabs
Top Vendor Spend | top_vendor_spend | 176571.46 | Material | Consolidated Supply Co. | Verified | Benchmark KPIs / Metric Registry — see source tabs
Top Vendor Concentration | top_vendor_pct | 0.38521 | Material |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total POs | total_pos | 142 | Material | Unique POs by filename | Verified | Benchmark KPIs / Metric Registry — see source tabs
Change Order % | co_pct | -0.0023006 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Labor Hour | rev_per_labor_hr | 9243% | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
SOURCES
Job #2017 — Exxel Pacific 3636 Stone Way Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2017 Job Detail Report.pdf (124 pages, OWP Sage Timberline export)
Cost codes parsed: 27 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 119 from Job Ticket (119 DWs, 119 washers)
Fixture count: Toto WCs 122, Grohe lavs 137, Aquatic tubs 122, Lenova/Elkay sinks 119 + common area
Billing: 36 STONE AGGREGATE BILLING.xlsx (14 pay apps, Feb 2014 – May 2015)
51 KPIs with snake_case data_name identifiers for database ingestion

## Change Log
Change Log — Master Register
Unified change-event ledger: RFIs, ASIs, COPs, COs, Backcharges, T&M (14 events)
Event ID | Type | Date | Subject | Originator | Linked Event(s) | Cost Impact ($) | Schedule (days) | Status | Source Document
COR-001 | COR | 2014-05-30 | Delete filter fabric from footing drains contract | Sub (OWP) | RFI-123 | -2100 | 0 | Accepted | 2017-Exxel, 36 Stone/Change Orders/COR_s/36 Stone - OWP COR #01.pdf
COR-002 | COR | 2014-05-30 | Fitness Room bathroom sink — Kohler K-2084-0 in lieu of Elkay ELUH12V | Sub (OWP) | RFI-115 | 495 | 0 | Accepted | 2017-Exxel, 36 Stone/Change Orders/COR_s/36 Stone - OWP COR #02.pdf
CO-003 | CO | 2014-06-12 | Eliminate sewer vault + pumps (gravity drain to SW corner) | GC (Exxel) |  | -6872 | 0 | Signed | 2017-Exxel, 36 Stone/Change Orders/CO_s/3636 change orders 3 through 6.pdf
CO-004 | CO | 2014-06-12 | Wall-mount sink Fitness Room (in lieu of countertop) | GC (Exxel) | RFI-115 | 495 | 0 | Signed | 2017-Exxel, 36 Stone/Change Orders/CO_s/3636 change orders 3 through 6.pdf
CO-005 | CO | 2014-06-12 | Delete filter fabric at footing drains | GC (Exxel) | RFI-123 | -2100 | 0 | Signed | 2017-Exxel, 36 Stone/Change Orders/CO_s/3636 change orders 3 through 6.pdf
CO-006 | CO | 2014-06-12 | Catch basin in lieu of trench drain at P1 garage ramp | GC (Exxel) | RFI-132 | -535 | 0 | Signed | 2017-Exxel, 36 Stone/Change Orders/CO_s/3636 change orders 3 through 6.pdf
CO-007 | CO | 2014-06-26 | 2 drains south residential patio + Type B→A ADA lavatory sink | GC (Exxel) | RFI-018 | 1622 | 0 | Signed | 2017-Exxel, 36 Stone/Change Orders/CO_s/Stoneway CO 7.pdf
COR-005 | COR | 2014-06-10 | Kitchen sink upgrades — Lenova/Elkay + Grohe pull-down faucet | Sub (OWP) |  | 7790 | 0 | Accepted | 2017-Exxel, 36 Stone/Change Orders/COR_s/36 Stone - OWP COR #05.pdf
COR-006 | COR | 2014-06-11 | Rated washer connection boxes all 119 units | Sub (OWP) |  | 2685 | 0 | Accepted | 2017-Exxel, 36 Stone/Change Orders/COR_s/36 Stone - OWP COR #06.pdf
COR-007 | COR | 2014-08-12 | Coffee maker water connection in lobby | Sub (OWP) | RFI-176 | 335 | 0 | Accepted | 2017-Exxel, 36 Stone/Change Orders/COR_s/36 Stone - OWP COR #07.pdf
COR-008 | COR | 2014-08-20 | 1st floor leasing parcel undercounter sink + Grohe faucet | Sub (OWP) |  | 1885 | 0 | Accepted | 2017-Exxel, 36 Stone/Change Orders/COR_s/36 Stone - OWP COR #08.pdf
COR-009 | COR | 2015-01-07 | Irrigation Point-of-Connection per RFI-234R2 | Sub (OWP) | RFI-234 | 2703 | 0 | Accepted | 2017-Exxel, 36 Stone/Change Orders/COR_s/36 Stone - OWP COR #09 RFI-234R2 Irrigation POC.pdf
COR-010 | COR | 2015-01-26 | Gas fireplace POC on 2nd floor lounge per RFI-228 | Sub (OWP) | RFI-228 | 782 | 0 | Accepted | 2017-Exxel, 36 Stone/Change Orders/COR_s/36 Stone - OWP COR #10 RFI-228 Gas Fireplace POC.pdf
COR-011 | COR | 2015-04-30 | Repair damaged tubs in units 423, 428, 426, 318, 319, 301, 207, 208 | Sub (OWP) |  | 1277 | 0 | Accepted | 2017-Exxel, 36 Stone/Change Orders/COR_s/36 Stone - OWP COR #11 Tub Repairs.pdf
TOTAL | [5 empty] | 8462 | 0

## Root Cause Analysis
Root Cause Analysis — Change Driver Taxonomy
Categorized change events with responsible-party attribution — feeds bid-risk intelligence
CATEGORY ROLLUP
Root Cause Category | # Events | Net Cost Impact ($) | % of Events | Predominant Responsibility | Notes
Design substitution | 3 | -11072 | 21.43% | Designer | Delete filter fabric from footing drains contract
Design clarification | 7 | 5897 | 50% | Designer | Fitness Room bathroom sink — Kohler K-2084-0 in lieu of Elka
Owner directive | 2 | 9675 | 14.29% | Owner/GC | Kitchen sink upgrades — Lenova/Elkay + Grohe pull-down fauce
Scope gap | 1 | 2685 | 7.143% | Designer | Rated washer connection boxes all 119 units
Cleanup/damage | 1 | 1277 | 7.143% | Owner/GC | Repair damaged tubs in units 423, 428, 426, 318, 319, 301, 2
TOTAL | 14 | 8462
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Events | Net $ Impact | Bid-Risk Signal
Designer | 11 | -2490 | CAUTION — price risk in future bids
Owner/GC | 3 | 10952 | POSITIVE — recoverable

## Predictive Signals
Predictive Signals — Leading Indicators
Forward-looking metrics that predict CO waves, schedule slips, and margin erosion
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Predictive Meaning
RFI Total (closed) | 32 | <50 for mid-size | INFO | Volume proxy for design doc quality
RFI Velocity (per month, derived) | See KPIs D50 | <3.0/wk | INFO | >3/wk = CO wave in 4-8 wks
RFI Avg Cycle Time (days) | Unknown | <14 | N/A | >30 avg signals schedule slip
ASI / OCD Count | 0 | <5 | HEALTHY | High ASI = owner scope churn
Backcharge Count | 0 | <3 | HEALTHY | BC clusters = coordination weakness
Change Order Count | 14 | <3 | ELEVATED | CO count signals scope definition
T&M Event Count | 0 | <2 | HEALTHY | T&M = directed work pipeline
Submittal resubmission count | 11 | <10 | ELEVATED | Repeats = coord issues incubating
Net $ Impact (all events) | 8462 | Near $0 | POSITIVE | Net recoverable vs absorbed
FORECAST MODELS (closed-project — actuals)
Forecast | Current Estimate | Confidence | Driver | Model Note
Projected final CO % of contract | -0.0023006 | Actual | Closed project | CO$ / orig contract
Projected EAC (direct cost) | 859184.33 | Actual | Closed project | Sum of L+M+OH+Burden
Projected final margin | 0.37285 | Actual | Closed project | (Rev - DC) / Rev
Composite risk score (0-100) | 20 | Medium | 0 BCs + 0 ASI/OCDs | Custom Cortex scoring

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence_level, and source_document — the machine-readable JCR index
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s) | Formula / Derivation
1 | job_number | Job Number | 2017 | id | Benchmark KPIs | Verified | JDR header | See Benchmark KPIs tab
2 | job_name | Job Name | Exxel Pacific 3636 Stone Way Apartments | text | Benchmark KPIs | Verified | Contract folder | See Benchmark KPIs tab
3 | general_contractor | General Contractor | Exxel Pacific, Inc. | text | Benchmark KPIs | Verified | Contract folder | See Benchmark KPIs tab
4 | location | Location | Seattle, WA (3636 Stone Way N) | text | Benchmark KPIs | Verified | Permit/Plans | See Benchmark KPIs tab
5 | project_type | Project Type | 119-unit 4-story mixed-use apartments + ground-floor retail | text | Benchmark KPIs | Verified | Plans | See Benchmark KPIs tab
6 | duration_months | Duration (months) | 16 | months | Benchmark KPIs | Verified | First-to-last invoice | See Benchmark KPIs tab
7 | unit_count | Unit Count | 119 | units | Benchmark KPIs | Verified | Plumbing permit + P-tag list | See Benchmark KPIs tab
8 | total_fixtures | Total Fixtures | 801 | count | Benchmark KPIs | Verified | Permit detail | See Benchmark KPIs tab
9 | contract_original | Contract Original | 1373148 | USD | Benchmark KPIs | Verified | Contract SOV | See Benchmark KPIs tab
10 | contract_final | Contract Final | 1369989 | USD | Benchmark KPIs | Verified | Final billing SOV | See Benchmark KPIs tab
11 | change_orders | Change Orders ($) | -3159 | USD | Benchmark KPIs | Verified | JDR revised - original | See Benchmark KPIs tab
12 | revenue | Revenue | 1369989 | USD | Benchmark KPIs | Verified | Aggregate billing | See Benchmark KPIs tab
13 | net_profit | Net Profit | 510804.67 | USD | Benchmark KPIs | Verified | Revenue - Direct Cost | See Benchmark KPIs tab
14 | gross_margin | Gross Margin % | 0.37285 | % | Benchmark KPIs | Verified | Derived | See Benchmark KPIs tab
15 | direct_cost | Direct Cost | 859184.33 | USD | Benchmark KPIs | Verified | JDR cost codes | See Benchmark KPIs tab
16 | labor_cost | Labor Cost | 292755.75 | USD | Benchmark KPIs | Verified | JDR labor codes | See Benchmark KPIs tab
17 | material_cost | Material Cost | 378313.74 | USD | Benchmark KPIs | Verified | JDR material codes | See Benchmark KPIs tab
18 | overhead_cost | Overhead Cost | 33855.5 | USD | Benchmark KPIs | Verified | JDR overhead codes | See Benchmark KPIs tab
19 | burden_cost | Burden Cost | 154259.34 | USD | Benchmark KPIs | Verified | JDR burden codes | See Benchmark KPIs tab
20 | retainage | Retainage | 68499 | USD | Benchmark KPIs | Verified | Aggregate billing row | See Benchmark KPIs tab
21 | total_hours | Total Labor Hours | 14822 | hours | Benchmark KPIs | Verified | JDR payroll | See Benchmark KPIs tab
22 | total_workers | Total Workers | 45 | count | Benchmark KPIs | Verified | JDR unique workers | See Benchmark KPIs tab
23 | blended_gross_wage | Blended Gross Wage | 1987% | USD/hr | Benchmark KPIs | Verified | Labor $ / Hours | See Benchmark KPIs tab
24 | total_vendors | Total Vendors | 20 | count | Benchmark KPIs | Verified | JDR AP unique | See Benchmark KPIs tab
25 | total_pos | Total POs | 142 | count | Benchmark KPIs | Verified | PO folder count | See Benchmark KPIs tab
26 | co_pct | CO % of Original | -0.0023006 | % | Benchmark KPIs | Verified | Derived | See Benchmark KPIs tab
27 | rfi_total_count | RFIs Total | 32 | count | Predictive Signals | Verified | ASI-RFI folder count | See Predictive Signals tab
28 | asi_ocd_count | ASI + OCD Count | 0 | count | Change Log | Verified | ASI-RFI folder + Change Orders | See Change Log tab
29 | co_count_total | Change Order Count | 14 | count | Change Log | Verified | Change Orders folder | See Change Log tab
30 | backcharge_count | Backcharge Count | 0 | count | Change Log | Verified | Invoices/Backcharges | See Change Log tab
31 | tm_event_count | T&M Event Count | 0 | count | Change Log | Verified | Change Orders / JDR 038 | See Change Log tab
32 | submittal_resub_count | Submittal Resubmissions | 11 | count | Predictive Signals | Verified | Submittals folder | See Predictive Signals tab
33 | change_event_total | Total Tracked Events | 14 | count | Change Log | Verified | Change Log tab | See Change Log tab
34 | change_net_impact | Change Net $ Impact | 8462 | USD | Change Log | Verified | SUM H col | See Change Log tab

## Reconciliation
Reconciliation — Tie-out Proofs
Live cross-sheet formulas verify data consistency across all 17 tabs
Check | Computed | Expected | Δ | Status
A. JDR COST CODE ROLLUP
Labor subtotal (11 codes) | 292755.75 | 292755.75 | 0 | TIES
Material subtotal (10 codes) | 378313.74 | 378313.74 | 0 | TIES
Overhead subtotal (3 codes) | 33855.5 | 33855.5 | 0 | TIES
Burden subtotal (2 codes) | 154259.34 | 154259.34 | 0 | TIES
Direct Cost (all categories) | 859184.33 | 859184.33 | 0 | TIES
Revenue (code 999) | 1369989 | 1369989 | 0 | TIES
Net Profit (Revenue - Expenses) | 510804.67 | 510804.67 | 0 | TIES
B. LABOR HOURS ROLLUP
JDR Cost Code hours (Payroll Hours lines) | 14822 | 14822 | 0 | TIES
Per-worker hours (sum of PR Regular) | 14975 | 14822 | 153 | WITHIN
C. BILLING (SOV) ↔ JDR
Final Contract Value | 1438488.45 | 1369989 | 68499.45 | WITHIN
Retainage | 68499 | 68499 | 0 | TIES
Direct Cost | 859184.33 | 859184.33 | 0 | TIES
D. VENDOR AP ↔ JDR
Vendor AP total (sum of invoices) | 458376.37 | 401446 | 56930.37 | OFF
SOURCES
Job #2017 — Exxel Pacific 3636 Stone Way Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2017 Job Detail Report.pdf (124 pages, OWP Sage Timberline export)
Cost codes parsed: 27 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 119 from Job Ticket (119 DWs, 119 washers)
Fixture count: Toto WCs 122, Grohe lavs 137, Aquatic tubs 122, Lenova/Elkay sinks 119 + common area
Billing: 36 STONE AGGREGATE BILLING.xlsx (14 pay apps, Feb 2014 – May 2015)
TIES = within $1 or 5 hrs • WITHIN = within 5% • OFF = investigate
K. CHANGE LOG ↔ ROOT CAUSE ANALYSIS
Total Event Count | 14 | 14 | 0 | TIES | 13↔14
Net $ Impact (all events) | 8462 | 8462 | 0 | TIES | 13↔14
L. PREDICTIVE SIGNALS ↔ CHANGE LOG
Backcharge Count signal | 0 | 0 | 0 | TIES | 15↔13
M. METRIC REGISTRY ↔ BENCHMARK KPIs
revenue (row 17) | 1369989 | 1369989 | 0 | TIES | 16↔11
unit_count (row 12) | 119 | 119 | 0 | TIES | 16↔11
total_fixtures (row 13) | 801 | 801 | 0 | TIES | 16↔11
direct_cost (row 19) | 0.37285 | 859184.33 | -859183.9571 | OFF | 16↔11
total_pos (row 30) | 142 | 142 | 0 | TIES | 16↔11
N. CHANGE LOG ↔ METRIC REGISTRY (event counts)
change_event_total | 0 | 14 | -14 | OFF | 16↔13
SOURCES
Job #2017 — Cortex v2 17-tab layout
12 analytical tabs + Change Log + Root Cause Analysis + Predictive Signals + Metric Registry + Reconciliation
Canonical source: 2017 Job Detail Report.pdf (Sage Timberline export)
Change artifacts: folders scanned — ASI-RFI, Change Orders, Submittals, Invoices (Backcharges), JDR cost codes
Every Change Log row cites its source document path
TIES = within $1/5hrs/exact count • WITHIN = within 5% • OFF = investigate
Cross-sheet formulas (='Tab'!Cell) update automatically when source tabs change
Tabs: 1-12 analytical • 13=ChangeLog • 14=RootCause • 15=PredictiveSignals • 16=MetricRegistry • 17=Reconciliation

## Vendors
Vendor Detail — Job #2017
Vendors | 20 |  | Top vendor | Consolidated Supply Co.
Invoices | 266 |  | Top 3 share | 84.77%
Total AP | 458376.37 |  | Source | 2017 Job Detail Report.pdf (Sage Timberline AP export)
Avg Inv | 1723.2194
Rank | Vendor | Vendor Code | Invoices | Total Spend | % of AP | Avg / Invoice
1 | Consolidated Supply Co. |  | 102 | 176571.46 | 38.52% | 1731.0927
2 | Rosen Supply Company, Inc. |  | 85 | 139209.01 | 30.37% | 1637.7531
3 | Ferguson Enterprises, Inc. |  | 18 | 72780.98 | 15.88% | 4043.3878
4 | Franklin Engineering |  | 5 | 17974.5 | 3.921% | 3594.9
5 | Duraseal, Inc. |  | 2 | 12800 | 2.792% | 6400
6 | Keller Supply Company |  | 11 | 8131.24 | 1.774% | 739.2036
7 | Bank of America CC |  | 6 | 8076 | 1.762% | 1346
8 | Quality Concrete Products, Inc. |  | 3 | 5921 | 1.292% | 1973.6667
9 | Rosen Supply Kirkland |  | 6 | 4412.21 | 0.9626% | 735.3683
10 | Mechanical Sales, Inc. |  | 2 | 2840 | 0.6196% | 1420
11 | Manor Hardware & Construction Supply |  | 3 | 2465 | 0.5378% | 821.6667
12 | Cascade Restoration Co. |  | 2 | 2140 | 0.4669% | 1070
13 | Kele, Inc |  | 4 | 1340.48 | 0.2924% | 335.12
14 | Core & Main LP |  | 2 | 1134.15 | 0.2474% | 567.075
15 | Ferguson Enterprises, Inc. #3007 |  | 3 | 811.46 | 0.177% | 270.4867
16 | C.M. Hoskins Company |  | 3 | 702.97 | 0.1534% | 234.3233
17 | Structural Imaging, LLC |  | 1 | 500 | 0.1091% | 500
18 | Fastenal Company |  | 4 | 258.11 | 0.05631% | 64.5275
19 | R.A. Brown Backflow Testing |  | 2 | 195 | 0.04254% | 97.5
20 | Capital One Credit Card |  | 2 | 112.8 | 0.02461% | 56.4
| TOTAL |  | 266 | 458376.37 | 100% | 1723.2194