## Overview
Job #2020 · SRM Bellevue @ Main Apartments
Cortex JCR Summary • SRM Development / Exxel Pacific (Owner: Bellevue Way Ventures) • Bellevue, WA (15 Bellevue Way SE) • 6-story 288-unit luxury multifamily + retail (268 Type B + 20 Type A ADA) • May 2014 – Feb 2016 (~22 months)
PROJECT OVERVIEW
Project Job # | 2020
Project Name: | SRM Bellevue @ Main Apartments
General Contractor | SRM Development / Exxel Pacific (Owner: Bellevue Way Ventures)
Location | Bellevue, WA (15 Bellevue Way SE)
Project Duration | May 2014 – Feb 2016 (~22 months)
Total Unique Documents | Bellevue @ Main folder: Contract, Billing (10 archived SOVs thru #23), PO_s (30+ with master trim quote), COs (11), Permit 13-133992-BO, Invoices, Vendor Lien Waivers
CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
$2,858,341 |  | $923,838 |  | $1,934,503 |  | 38,749
Original $3,119,000 − $260,659 net COs (11) = $2,858,341 |  | 32.3% margin |  | 67.7% of revenue |  | 57 workers
COST BREAKDOWN
Category | Budget | Actual | Variance | % Budget | % of Cost
Labor | 593974 | 766929.01 | -172955.01 | 129.1% | 39.64%
Material | 997196 | 735694.62 | 261501.38 | 73.78% | 38.03%
Overhead | 16000 | 33267.19 | -17267.19 | 207.9% | 1.72%
Burden | 312438.73 | 398612.39 | -86173.66 | 127.6% | 20.61%
TOTAL | 1919608.73 | 1934503.21 | -14894.48 | 100.8% | 100%
PROJECT PROFILE
Metric | Value | Metric | Value | Metric | Value
Plumbing Units | 288 | Type B (standard) | 268 | Type A (ADA) | 20
Water Closets | 288+20 ADA | Kitchen Faucets | 257 (incl. amenity) | Bathtub Trim | 288
Lav Faucets | 288 + 4 amenity | Total Fixtures | ~1,564 | Fixtures / Unit | ~5.4
Floors | P2/P1 garage + L1 retail + Mezz + L2–L5 residential | Duration | 22 mo
SOURCES
Job #2020 — SRM Bellevue @ Main Apartments • GC: Exxel Pacific / Owner: Bellevue Way Ventures • Bellevue, WA
Canonical source: 2020 Job Detail Report.pdf (352 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count (288) confirmed by TWO source documents:
1) Bellevue Main – Pricing to go to 101 Taylor Fixtures.xlsx: Type B lavs qty=268, Type A lavs qty=20, Lav faucets qty=288, Bathtub trim qty=288
2) BELLEVUE TRIM QUOTE PRICING organized by category USE.xlsx: Mansfield toilets 268 + 20 ADA = 288
Kitchen fixtures: 257 kitchen faucets (Delta 4353-AR-DST) — 31 fewer than units (studios/amenity)
Contract: One Way Plumbing Executed Contract OCR_D.pdf — Exxel Pacific / SRM Development GC
Billing: 10 archived Schedule of Values files (pay apps #4, 9, 10, 12, 13, 15, 18, 19, 20, 23)
Final contract $2,858,341 after 11 COs (net -$260,659, primarily CO#1 cast iron credit -$389,000)
Permit: City of Bellevue #13-133992-BO (building/plumbing)

## Budget vs Actual
Budget vs Actual — All Cost Codes
Code | Description | Orig Budget | Rev Budget | Actual | Variance | % Used
LABOR
100 | Supervision | 12800 | 13700 | 13026.5 | 673.5 | 95.08%
101 | Takeoff & Purchase Labor | 15360 | 17310 | 18552.5 | -1242.5 | 107.2%
110 | Underground Labor | 16160 | 16760 | 16803.75 | -43.75 | 100.3%
111 | Garage Labor | 114350 | 118946 | 142441 | -23495 | 119.8%
112 | Canout Labor | 16000 | 16100 | 16515.5 | -415.5 | 102.6%
113 | Foundation Drain Labor | 2843 | 2843 | 2843 | 0 | 100%
120 | Roughin Labor | 376600 | 266055 | 348602.98 | -82547.98 | 131%
130 | Finish Labor | 51400 | 58664 | 64250.9 | -5586.9 | 109.5%
140 | Gas Labor | 9000 | 13862 | 32025.5 | -18163.5 | 231%
141 | Water Main/Insulation Lab | 55600 | 57029 | 85831.88 | -28802.88 | 150.5%
142 | Mech Room Labor | 9900 | 12705 | 26035.5 | -13330.5 | 204.9%
MATERIAL
210 | Underground Material | 23100 | 23300 | 24415.78 | -1115.78 | 104.8%
211 | Garage Material | 95600 | 92894 | 54034.99 | 38859.01 | 58.17%
212 | Canout Material | 26400 | 26700 | 24723.82 | 1976.18 | 92.6%
220 | Roughin Material | 363580 | 213718 | 87900.72 | 125817.28 | 41.13%
230 | Finish Material | 478500 | 526401 | 411991.97 | 114409.03 | 78.27%
240 | Gas Material | 12600 | 12800 | 8263.12 | 4536.88 | 64.56%
241 | Water Main/Insulation Mat | 92600 | 93431 | 122165.25 | -28734.25 | 130.8%
242 | Mech Room Material | 7000 | 7952 | 2198.97 | 5753.03 | 27.65%
OVERHEAD
600 | Subcontractor | 4000 | 5000 | 21589.36 | -16589.36 | 431.8%
603 | Permits & Licenses | 1000 | 11000 | 11677.83 | -677.83 | 106.2%
BURDEN
995 | Payroll Burden | 309922.16 | 265927.39 | 338661.76 | -72734.37 | 127.4%
998 | Payroll Taxes | 54692.15 | 46511.34 | 59950.63 | -13439.29 | 128.9%
TOTAL | Direct Cost | 2149007.31 | 1919608.73 | 1934503.21 | -14894.48 | 100.8%
SOURCES
Job #2020 — SRM Bellevue @ Main Apartments • GC: Exxel Pacific / Owner: Bellevue Way Ventures • Bellevue, WA
Canonical source: 2020 Job Detail Report.pdf (352 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count (288) confirmed by TWO source documents:
1) Bellevue Main – Pricing to go to 101 Taylor Fixtures.xlsx: Type B lavs qty=268, Type A lavs qty=20, Lav faucets qty=288, Bathtub trim qty=288
2) BELLEVUE TRIM QUOTE PRICING organized by category USE.xlsx: Mansfield toilets 268 + 20 ADA = 288
Kitchen fixtures: 257 kitchen faucets (Delta 4353-AR-DST) — 31 fewer than units (studios/amenity)
Contract: One Way Plumbing Executed Contract OCR_D.pdf — Exxel Pacific / SRM Development GC
Billing: 10 archived Schedule of Values files (pay apps #4, 9, 10, 12, 13, 15, 18, 19, 20, 23)
Final contract $2,858,341 after 11 COs (net -$260,659, primarily CO#1 cast iron credit -$389,000)
Permit: City of Bellevue #13-133992-BO (building/plumbing)

## Cost Breakdown
Cost Breakdown — Category Deep Dive
A. CATEGORY SHARE OF DIRECT COST
Category | # Codes | Budget | Actual | Variance | % Budget | % of Cost | Per Unit
Labor | 11 | 593974 | 766929.01 | -172955.01 | 129.1% | 39.64% | 2662.948
Material | 8 | 997196 | 735694.62 | 261501.38 | 73.78% | 38.03% | 2554.4952
Overhead | 2 | 16000 | 33267.19 | -17267.19 | 207.9% | 1.72% | 115.5111
Burden | 2 | 312438.73 | 398612.39 | -86173.66 | 127.6% | 20.61% | 1384.0708
B. LARGEST OVERRUNS (Actual > Revised Budget)
Code | Description | Rev Budget | Actual | Overrun | % Over
120 | Roughin Labor | 266055 | 348602.98 | 82547.98 | 31.03%
995 | Payroll Burden | 265927.39 | 338661.76 | 72734.37 | 27.35%
141 | Water Main/Insulation Lab | 57029 | 85831.88 | 28802.88 | 50.51%
241 | Water Main/Insulation Mat | 93431 | 122165.25 | 28734.25 | 30.75%
111 | Garage Labor | 118946 | 142441 | 23495 | 19.75%
140 | Gas Labor | 13862 | 32025.5 | 18163.5 | 131%
600 | Subcontractor | 5000 | 21589.36 | 16589.36 | 331.8%
998 | Payroll Taxes | 46511.34 | 59950.63 | 13439.29 | 28.89%
142 | Mech Room Labor | 12705 | 26035.5 | 13330.5 | 104.9%
130 | Finish Labor | 58664 | 64250.9 | 5586.9 | 9.524%
C. LARGEST SAVINGS (Actual < Revised Budget)
Code | Description | Rev Budget | Actual | Savings | % Under
220 | Roughin Material | 213718 | 87900.72 | 125817.28 | 58.87%
230 | Finish Material | 526401 | 411991.97 | 114409.03 | 21.73%
211 | Garage Material | 92894 | 54034.99 | 38859.01 | 41.83%
242 | Mech Room Material | 7952 | 2198.97 | 5753.03 | 72.35%
240 | Gas Material | 12800 | 8263.12 | 4536.88 | 35.44%
212 | Canout Material | 26700 | 24723.82 | 1976.18 | 7.401%
100 | Supervision | 13700 | 13026.5 | 673.5 | 4.916%
SOURCES
Job #2020 — SRM Bellevue @ Main Apartments • GC: Exxel Pacific / Owner: Bellevue Way Ventures • Bellevue, WA
Canonical source: 2020 Job Detail Report.pdf (352 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count (288) confirmed by TWO source documents:
1) Bellevue Main – Pricing to go to 101 Taylor Fixtures.xlsx: Type B lavs qty=268, Type A lavs qty=20, Lav faucets qty=288, Bathtub trim qty=288
2) BELLEVUE TRIM QUOTE PRICING organized by category USE.xlsx: Mansfield toilets 268 + 20 ADA = 288
Kitchen fixtures: 257 kitchen faucets (Delta 4353-AR-DST) — 31 fewer than units (studios/amenity)
Contract: One Way Plumbing Executed Contract OCR_D.pdf — Exxel Pacific / SRM Development GC
Billing: 10 archived Schedule of Values files (pay apps #4, 9, 10, 12, 13, 15, 18, 19, 20, 23)
Final contract $2,858,341 after 11 COs (net -$260,659, primarily CO#1 cast iron credit -$389,000)
Permit: City of Bellevue #13-133992-BO (building/plumbing)

## Material
Material Spend Analysis
8 material cost codes • $735,695 JDR material • 21 AP vendors • $792,735 total AP
A. MATERIAL BY COST CODE
Code | Description | Rev Budget | Actual | Variance | % Used | % of Mat | Per Unit
210 | Underground Material | 23300 | 24415.78 | -1115.78 | 104.8% | 3.319% | 84.777
211 | Garage Material | 92894 | 54034.99 | 38859.01 | 58.17% | 7.345% | 187.6215
212 | Canout Material | 26700 | 24723.82 | 1976.18 | 92.6% | 3.361% | 85.8466
220 | Roughin Material | 213718 | 87900.72 | 125817.28 | 41.13% | 11.95% | 305.2108
230 | Finish Material | 526401 | 411991.97 | 114409.03 | 78.27% | 56% | 1430.5277
240 | Gas Material | 12800 | 8263.12 | 4536.88 | 64.56% | 1.123% | 28.6914
241 | Water Main/Insulation Mat | 93431 | 122165.25 | -28734.25 | 130.8% | 16.61% | 424.1849
242 | Mech Room Material | 7952 | 2198.97 | 5753.03 | 27.65% | 0.2989% | 7.6353
TOTAL | All Material | 997196 | 735694.62 | 261501.38 | 73.78% | 100% | 2554.4952
B. VENDORS BY SPEND (AP)
Vendor | # Invoices | Total Spend | % of AP |  |  |  | Avg Invoice
Ferguson Enterprises, Inc. | 121 | 216177.2 | 27.27% |  |  |  | 1786.5884
Keller Supply Company | 101 | 204979.52 | 25.86% |  |  |  | 2029.5002
Rosen Supply Company | 172 | 188562.66 | 23.79% |  |  |  | 1096.2945
Mechanical Sales, Inc. | 4 | 67935.82 | 8.57% |  |  |  | 16983.955
Consolidated Supply Co. | 11 | 47819.57 | 6.032% |  |  |  | 4347.2336
United Rentals, Inc. | 40 | 23301.34 | 2.939% |  |  |  | 582.5335
Quality Concrete Products, Inc. | 5 | 15202 | 1.918% |  |  |  | 3040.4
Scan2Core, Inc. | 13 | 8585 | 1.083% |  |  |  | 660.3846
MAD Concrete Cutting & Coring, Inc. | 5 | 4605 | 0.5809% |  |  |  | 921
Kele, Inc | 6 | 3172.33 | 0.4002% |  |  |  | 528.7217
C.M. Hoskins Company | 5 | 2334.26 | 0.2945% |  |  |  | 466.852
Rosen Supply Kirkland | 8 | 2331.87 | 0.2942% |  |  |  | 291.4837
Capital One Credit Card | 16 | 2040.76 | 0.2574% |  |  |  | 127.5475
Shirley Dennison | 17 | 1700 | 0.2144% |  |  |  | 100
Seton Identification Products | 3 | 1302.22 | 0.1643% |  |  |  | 434.0733
American Express 3-41000 | 1 | 945 | 0.1192% |  |  |  | 945
NRP-Meydenbauer | 4 | 474 | 0.05979% |  |  |  | 118.5
Ferguson Enterprises, Inc. #3007 | 2 | 458.5 | 0.05784% |  |  |  | 229.25
Fastenal Company | 5 | 456.5 | 0.05759% |  |  |  | 91.3
A.R. Brown Backflow Testing | 3 | 304 | 0.03835% |  |  |  | 101.3333
Rosen Supply Company, Inc. | 3 | 47.32 | 0.005969% |  |  |  | 15.7733
TOTAL | 545 | 792734.87 | 100%
SOURCES
Job #2020 — SRM Bellevue @ Main Apartments • GC: Exxel Pacific / Owner: Bellevue Way Ventures • Bellevue, WA
Canonical source: 2020 Job Detail Report.pdf (352 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count (288) confirmed by TWO source documents:
1) Bellevue Main – Pricing to go to 101 Taylor Fixtures.xlsx: Type B lavs qty=268, Type A lavs qty=20, Lav faucets qty=288, Bathtub trim qty=288
2) BELLEVUE TRIM QUOTE PRICING organized by category USE.xlsx: Mansfield toilets 268 + 20 ADA = 288
Kitchen fixtures: 257 kitchen faucets (Delta 4353-AR-DST) — 31 fewer than units (studios/amenity)
Contract: One Way Plumbing Executed Contract OCR_D.pdf — Exxel Pacific / SRM Development GC
Billing: 10 archived Schedule of Values files (pay apps #4, 9, 10, 12, 13, 15, 18, 19, 20, 23)
Final contract $2,858,341 after 11 COs (net -$260,659, primarily CO#1 cast iron credit -$389,000)
Permit: City of Bellevue #13-133992-BO (building/plumbing)
Vendor AP ties to JDR 'by Source: AP' line (792,734.87)

## Crew & Labor
Crew & Labor — Per-Worker Breakdown
Worker | Hours | Gross Pay | $/Hour | Tier
Veley, Nathaniel S | 2965.5 | 93837.5 | 31.6431 | Senior
Paco Leyva, Orlando | 2928.5 | 58335.5 | 19.9199 | Mid
Gerard, Mitchell J | 2472 | 37490 | 15.1659 | Apprentice
Moran Fernandez, Jose | 2334.5 | 37020 | 15.8578 | Apprentice
Reed, Reuben H | 2246 | 67320 | 29.9733 | Mid
Rodriguez, Fernando V | 1869.5 | 28508 | 15.249 | Apprentice
Meza Fuentes, Erick A | 1472.5 | 32385.5 | 21.9935 | Mid
Monico Brambila, Jesus S | 1389 | 22908.5 | 16.4928 | Apprentice
Taylor, Evan R | 1342.5 | 18092.5 | 13.4767 | Apprentice
Ayers, Jordan L | 1335.5 | 20429.5 | 15.2973 | Apprentice
Holmes, Anthony R | 990.5 | 15385.5 | 15.5331 | Apprentice
Wennig, Johnathan M | 978 | 14097.5 | 14.4146 | Apprentice
Barbosa, Michael S | 973.5 | 12783.5 | 13.1315 | Apprentice
Salazar, Hajdar L | 857 | 13712 | 16 | Apprentice
Cruz Jimenez, Adalberto | 857 | 11998 | 14 | Apprentice
Gonzalez Guzman, Rigoberto A | 856.5 | 11286.5 | 13.1775 | Apprentice
Gerard, Jordan E | 824 | 11312 | 13.7282 | Apprentice
Waites, Thaddeus Z | 784 | 23440 | 29.898 | Mid
Walker, Craig M | 730.5 | 10406 | 14.245 | Apprentice
Sanders, Allen O | 712 | 23807.5 | 33.4375 | Senior
Kinssies, Jr, John E | 673 | 10985 | 16.3224 | Apprentice
Ramos, Jose G | 540 | 7020 | 13 | Apprentice
Donelson, Richard T | 477 | 21465 | 45 | Senior
Galdamez, Dagoberto A | 448 | 6368 | 14.2143 | Apprentice
Lopez Barrios, Luis F | 444.5 | 5778.5 | 13 | Apprentice
Vaughan, Tyler J | 412 | 7940.5 | 19.2731 | Mid
Castro Hernandez, Jose A | 411.5 | 8323 | 20.226 | Mid
Lopez Martinez, Abimael | 397 | 5955 | 15 | Apprentice
Alba Jimenez, Jovani | 366 | 5856 | 16 | Apprentice
Garcia, Jordan X | 365.5 | 6024.5 | 16.4829 | Apprentice
Alba Martinez, Santiago | 361 | 6498 | 18 | Mid
Hubbard, Robert W | 359.5 | 13363.5 | 37.1725 | Senior
Ross, Kelli M | 348 | 10788 | 31 | Senior
Ramos Banegas, Noel O | 341.5 | 5464 | 16 | Apprentice
Ramirez, Lorenzo A | 297 | 5049 | 17 | Apprentice
Santiago, William T | 286.5 | 3724.5 | 13 | Apprentice
Gerard, Jeffrey S | 279.5 | 11102.5 | 39.7227 | Senior
Soto Cruz, Jovani | 274 | 4384 | 16 | Apprentice
Reyes, Robert J | 199.5 | 2793 | 14 | Apprentice
Eliassen, Cory H | 192.5 | 2502.5 | 13 | Apprentice
Palma Vides, Jorge A | 176 | 2464 | 14 | Apprentice
Lima Romero, Melvin A | 176 | 4032 | 22.9091 | Mid
Cortes Mendiola, Victor H | 173 | 4844 | 28 | Mid
Cruz Reyes, Jose | 144 | 2016 | 14 | Apprentice
Palma Vides, Hugo | 144 | 4464 | 31 | Senior
Soto Serna, Cesar E | 140 | 1820 | 13 | Apprentice
Whitaker, Daniel J | 110 | 1430 | 13 | Apprentice
Trump, Norman W | 108 | 1836 | 17 | Apprentice
Hubbard, Dustin R | 95 | 1406 | 14.8 | Apprentice
Schaefer, Taylor E | 88 | 1232 | 14 | Apprentice
Cruz Guzman, Joel A | 80 | 1040 | 13 | Apprentice
Ruiz, Hugo | 56 | 784 | 14 | Apprentice
Gonzalez Hernandez, Josue | 46 | 736 | 16 | Apprentice
Cortes Sepulveda, Jose R | 40 | 520 | 13 | Apprentice
Sepulveda Gonzalez, Alfredo | 24 | 640 | 26.6667 | Mid
Ascencio, Jose L | 8 | 112 | 14 | Apprentice
Anderson, Richard P | 7.5 | 230 | 30.6667 | Senior
TOTAL (57 workers) | 38007.5 | 745546 | 19.6158
SOURCES
Job #2020 — SRM Bellevue @ Main Apartments • GC: Exxel Pacific / Owner: Bellevue Way Ventures • Bellevue, WA
Canonical source: 2020 Job Detail Report.pdf (352 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count (288) confirmed by TWO source documents:
1) Bellevue Main – Pricing to go to 101 Taylor Fixtures.xlsx: Type B lavs qty=268, Type A lavs qty=20, Lav faucets qty=288, Bathtub trim qty=288
2) BELLEVUE TRIM QUOTE PRICING organized by category USE.xlsx: Mansfield toilets 268 + 20 ADA = 288
Kitchen fixtures: 257 kitchen faucets (Delta 4353-AR-DST) — 31 fewer than units (studios/amenity)
Contract: One Way Plumbing Executed Contract OCR_D.pdf — Exxel Pacific / SRM Development GC
Billing: 10 archived Schedule of Values files (pay apps #4, 9, 10, 12, 13, 15, 18, 19, 20, 23)
Final contract $2,858,341 after 11 COs (net -$260,659, primarily CO#1 cast iron credit -$389,000)
Permit: City of Bellevue #13-133992-BO (building/plumbing)
Tier: Apprentice <$18/hr, Mid $18–30, Senior >$30

## Crew Analytics
Crew Analytics
A. TIER DISTRIBUTION
Tier | # Workers | Hours | Gross Pay | % of Hours
Senior | 8 | 5293 | 179058 | 13.93%
Mid | 10 | 8988.5 | 213758.5 | 23.65%
Apprentice | 39 | 23726 | 352729.5 | 62.42%
B. WAGE STATISTICS
Blended Gross Wage | 19.6158 |  |  | Payroll $ ÷ payroll hours (pre-burden)
Fully-Loaded Wage | 30.6661 |  |  | (Labor + Burden) ÷ total hours
Burden Multiplier | 1.5633 |  |  | Fully loaded ÷ gross wage
Min Worker Rate | 13 |  |  | Cheapest apprentice hour
Max Worker Rate | 45 |  |  | Most expensive foreman hour
Avg Hours / Worker | 666.7982 |  |  | Crew continuity indicator
SOURCES
Job #2020 — SRM Bellevue @ Main Apartments • GC: Exxel Pacific / Owner: Bellevue Way Ventures • Bellevue, WA
Canonical source: 2020 Job Detail Report.pdf (352 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count (288) confirmed by TWO source documents:
1) Bellevue Main – Pricing to go to 101 Taylor Fixtures.xlsx: Type B lavs qty=268, Type A lavs qty=20, Lav faucets qty=288, Bathtub trim qty=288
2) BELLEVUE TRIM QUOTE PRICING organized by category USE.xlsx: Mansfield toilets 268 + 20 ADA = 288
Kitchen fixtures: 257 kitchen faucets (Delta 4353-AR-DST) — 31 fewer than units (studios/amenity)
Contract: One Way Plumbing Executed Contract OCR_D.pdf — Exxel Pacific / SRM Development GC
Billing: 10 archived Schedule of Values files (pay apps #4, 9, 10, 12, 13, 15, 18, 19, 20, 23)
Final contract $2,858,341 after 11 COs (net -$260,659, primarily CO#1 cast iron credit -$389,000)
Permit: City of Bellevue #13-133992-BO (building/plumbing)

## Productivity
Productivity — Phase & Unit Metrics
A. LABOR HOURS BY PHASE
Phase | Labor Code | Hours | % of Total | Hours / Unit
Supervision | 100 | 301 | 0.7768% | 1.0451
Takeoff & Purchasing | 101 | 434 | 1.12% | 1.5069
Underground | 110 | 775 | 2% | 2.691
Garage | 111 | 6414 | 16.55% | 22.2708
Canout | 112 | 776.5 | 2.004% | 2.6962
Foundation Drain | 113 | 144 | 0.3716% | 0.5
Roughin | 120 | 18980.5 | 48.98% | 65.9045
Finish | 130 | 3322 | 8.573% | 11.5347
Gas | 140 | 1515.5 | 3.911% | 5.2622
Water Main / Insulation | 141 | 4519 | 11.66% | 15.691
Mech Room | 142 | 1567.5 | 4.045% | 5.4427
TOTAL |  | 38749 | 100% | 134.5451
B. PRODUCTIVITY RATIOS
Metric | Value | Units |  | Notes
Hours / Unit | 134.5451 | hrs |  | Labor hours per residential unit
Hours / Fixture | 24.7756 | hrs |  | Labor hours per plumbing fixture
Revenue / Hour | 73.7655 | $ |  | Top-line per labor hour
Profit / Hour | 23.8416 | $ |  | Bottom-line per labor hour
Units / Month | 13.0909 | units |  | Build velocity
Fixtures / Month | 71.0909 | fix |  | Fixture install pace
Hours / Month | 1761.3182 | hrs |  | Monthly labor burn
Revenue / Month | 129924.5909 | $ |  | Monthly billing rate
SOURCES
Job #2020 — SRM Bellevue @ Main Apartments • GC: Exxel Pacific / Owner: Bellevue Way Ventures • Bellevue, WA
Canonical source: 2020 Job Detail Report.pdf (352 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count (288) confirmed by TWO source documents:
1) Bellevue Main – Pricing to go to 101 Taylor Fixtures.xlsx: Type B lavs qty=268, Type A lavs qty=20, Lav faucets qty=288, Bathtub trim qty=288
2) BELLEVUE TRIM QUOTE PRICING organized by category USE.xlsx: Mansfield toilets 268 + 20 ADA = 288
Kitchen fixtures: 257 kitchen faucets (Delta 4353-AR-DST) — 31 fewer than units (studios/amenity)
Contract: One Way Plumbing Executed Contract OCR_D.pdf — Exxel Pacific / SRM Development GC
Billing: 10 archived Schedule of Values files (pay apps #4, 9, 10, 12, 13, 15, 18, 19, 20, 23)
Final contract $2,858,341 after 11 COs (net -$260,659, primarily CO#1 cast iron credit -$389,000)
Permit: City of Bellevue #13-133992-BO (building/plumbing)

## PO Commitments
Purchase Order Commitments
279 unique POs • PO amounts not dollar-parsed from individual PDFs • JDR material $735,695
A. COMMITMENTS BY COST CODE
OWP Code | Description → JDR | PO Count | % of POs | JDR Material
30 | 110+210 Underground | 58 | 20.79%
31 | 120+220 Roughin | 43 | 15.41%
32 | 130+230 Trim/Finish | 28 | 10.04%
34 | 111+211 Garage | 1 | 0.3584%
40 | 141+241 Water Main/Ins | 6 | 2.151%
41 | 140+240 Gas | 22 | 7.885%
OTHER | Unclassified | 121 | 43.37%
TOTAL |  | 279 | 100% | 735694.62
B. COMMITMENTS BY VENDOR
Vendor | PO Count | % of POs
ROSEN | 96 | 34.41%
FEI | 71 | 25.45%
KELLER | 60 | 21.51%
OTHER | 38 | 13.62%
FASTENAL | 6 | 2.151%
MECH SALES | 4 | 1.434%
CONSOLIDATED | 2 | 0.7168%
PIKE | 1 | 0.3584%
SIOUX CHIEF | 1 | 0.3584%
C. PO COVERAGE NOTES
Total Material Actual (JDR) |  |  | 735694.62
Unique PO Count |  |  | 279
(Dollar PO commitment not extracted — requires per-PDF parse)
SOURCES
Job #2020 — SRM Bellevue @ Main Apartments • GC: Exxel Pacific / Owner: Bellevue Way Ventures • Bellevue, WA
Canonical source: 2020 Job Detail Report.pdf (352 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count (288) confirmed by TWO source documents:
1) Bellevue Main – Pricing to go to 101 Taylor Fixtures.xlsx: Type B lavs qty=268, Type A lavs qty=20, Lav faucets qty=288, Bathtub trim qty=288
2) BELLEVUE TRIM QUOTE PRICING organized by category USE.xlsx: Mansfield toilets 268 + 20 ADA = 288
Kitchen fixtures: 257 kitchen faucets (Delta 4353-AR-DST) — 31 fewer than units (studios/amenity)
Contract: One Way Plumbing Executed Contract OCR_D.pdf — Exxel Pacific / SRM Development GC
Billing: 10 archived Schedule of Values files (pay apps #4, 9, 10, 12, 13, 15, 18, 19, 20, 23)
Final contract $2,858,341 after 11 COs (net -$260,659, primarily CO#1 cast iron credit -$389,000)
Permit: City of Bellevue #13-133992-BO (building/plumbing)
PO count is deduplicated by 5-digit PO number extracted from filenames
Vendor/code classification is heuristic (filename keyword match)

## Billing & SOV
Revenue & Billing Reconciliation
10 archived pay applications (of ~23) • Original $3,119,000 − $260,659 COs = $2,858,341
A. CONTRACT SUMMARY
Original Contract |  |  |  |  | 3119000
Change Orders (net) |  |  |  |  | -260659
Final Contract Value |  |  |  |  | 2858341
Retainage (5%) |  |  |  |  | 142517
Net Paid to OWP |  |  |  |  | 2715824
B. PAY APPLICATION TIMELINE
App# | Date | Period Billing | Retention | Net This Period | Aggregate | % Complete
4 | 2014-08-25 | 33600 | 0 | 33600 | 146751 | 5.134%
9 | 2014-12-15 | 159218 | 0 | 159218 | 827139 | 28.94%
10 | 2015-01-22 | 202569 | 0 | 202569 | 1029708 | 36.02%
12 | 2015-03-24 | 193214 | 0 | 193214 | 1604888 | 56.15%
13 | 2015-04-23 | 119208 | 0 | 119208 | 1731896 | 60.59%
15 | 2015-06-25 | 291977 | 0 | 291977 | 2234401 | 78.17%
18 | 2015-09-25 | 129074 | 0 | 129074 | 2662685 | 93.15%
19 | 2015-10-23 | 81921 | 0 | 81921 | 2744606 | 96.02%
20 | 2015-11-23 | 75825 | 0 | 75825 | 2820431 | 98.67%
23 | 2016-02-25 | 14578 | 142517.05 | -127939.05 | 2858341 | 100%
C. BILLING ↔ JDR TIE-OUT
Metric | SOV | JDR | Δ | Status
Final Contract Value | 2858341 | 2858341 | 0 | TIES
Retainage | 142517 | 142517 | 0 | TIES
Direct Cost | 1934503.21 | 1934503.21 | 0 | TIES
SOURCES
Job #2020 — SRM Bellevue @ Main Apartments • GC: Exxel Pacific / Owner: Bellevue Way Ventures • Bellevue, WA
Canonical source: 2020 Job Detail Report.pdf (352 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count (288) confirmed by TWO source documents:
1) Bellevue Main – Pricing to go to 101 Taylor Fixtures.xlsx: Type B lavs qty=268, Type A lavs qty=20, Lav faucets qty=288, Bathtub trim qty=288
2) BELLEVUE TRIM QUOTE PRICING organized by category USE.xlsx: Mansfield toilets 268 + 20 ADA = 288
Kitchen fixtures: 257 kitchen faucets (Delta 4353-AR-DST) — 31 fewer than units (studios/amenity)
Contract: One Way Plumbing Executed Contract OCR_D.pdf — Exxel Pacific / SRM Development GC
Billing: 10 archived Schedule of Values files (pay apps #4, 9, 10, 12, 13, 15, 18, 19, 20, 23)
Final contract $2,858,341 after 11 COs (net -$260,659, primarily CO#1 cast iron credit -$389,000)
Permit: City of Bellevue #13-133992-BO (building/plumbing)

## Insights
Key Insights — Job #2020 SRM Bellevue @ Main Apartments
Narrative observations distilled from the full JDR analysis
MARGIN PROFILE | Net profit of $923,838 on $2,858,341 revenue = 32.3% gross margin. Direct cost $1,934,503 absorbs 67.7% of revenue.
VENDOR CONCENTRATION | Ferguson Enterprises, Inc. alone = $216,177 (27% of all AP) across 121 invoices. Total 21 AP vendors, $792,735 total AP spend.
CREW PROFILE | 57 workers for 38,749 hours = 680 avg hrs/worker. Top 3 workers logged 8,366 hrs combined (22% of all labor).
ROUGHIN DOMINANCE | Code 120 Roughin Labor = 18,980 hrs (49% of all labor) and $348,603 actual. Code 230 Finish Material = $411,992 — 21% of total direct cost.
BUDGET DELIVERY | Revised budget was $1,919,609; actual direct cost $1,934,503 → $-14,894 variance (-0.8% under revised budget).
CONTRACT GROWTH | Contract grew from $3,119,000 to $2,858,341 — net +$-260,659 (-8.4%). Retainage of $142,517 (5%) withheld until closeout.
BURDEN RATIO | Burden codes 995 + 998 = $398,612 on $766,929 labor base = 52.0%. In line with OWP's typical 48–50% labor burden.
PROJECT SCALE | 288 units · 1564 fixtures · 22 months. Revenue/unit $9,925, hours/unit 134.5, profit/unit $3,208.
PRODUCTIVITY | Blended labor rate $19.79/hr. Revenue/hour $74. Profit/hour $24. 1,761 hrs/month burn rate.
FIXTURE DENSITY | 1564 fixtures ÷ 288 units = 5.43 fixtures/unit. Material/fixture $470, labor/fixture $490.
BIGGEST QUESTION
How does this job's 32.3% margin compare across similar projects in the OWP portfolio, and what operational levers drove the result — estimating accuracy, vendor pricing, or labor productivity?
SOURCES
Job #2020 — SRM Bellevue @ Main Apartments • GC: Exxel Pacific / Owner: Bellevue Way Ventures • Bellevue, WA
Canonical source: 2020 Job Detail Report.pdf (352 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count (288) confirmed by TWO source documents:
1) Bellevue Main – Pricing to go to 101 Taylor Fixtures.xlsx: Type B lavs qty=268, Type A lavs qty=20, Lav faucets qty=288, Bathtub trim qty=288
2) BELLEVUE TRIM QUOTE PRICING organized by category USE.xlsx: Mansfield toilets 268 + 20 ADA = 288
Kitchen fixtures: 257 kitchen faucets (Delta 4353-AR-DST) — 31 fewer than units (studios/amenity)
Contract: One Way Plumbing Executed Contract OCR_D.pdf — Exxel Pacific / SRM Development GC
Billing: 10 archived Schedule of Values files (pay apps #4, 9, 10, 12, 13, 15, 18, 19, 20, 23)
Final contract $2,858,341 after 11 COs (net -$260,659, primarily CO#1 cast iron credit -$389,000)
Permit: City of Bellevue #13-133992-BO (building/plumbing)

## Benchmark KPIs
Benchmark KPIs
Normalized metrics designed for apples-to-apples comparison across all OWP projects
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2020 | Profile | OWP job ID | Verified | Benchmark KPIs / Metric Registry — see source tabs
Job Name | job_name | SRM Bellevue @ Main Apartments | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
General Contractor | general_contractor | SRM Development / Exxel Pacific (Owner: Bellevue Way Ventures) | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Location | location | Bellevue, WA (15 Bellevue Way SE) | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Project Type | project_type | 6-story 288-unit luxury multifamily + retail (268 Type B + 20 Type A ADA) | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Duration (months) | duration_months | 22 | Profile | May 2014 – Feb 2016 (~22 months) | Verified | Benchmark KPIs / Metric Registry — see source tabs
Unit Count | unit_count | 288 | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total Fixtures | total_fixtures | 1564 | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Fixtures per Unit | fixtures_per_unit | 5.4306 | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Contract Value (Orig) | contract_original | 3119000 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Contract Value (Final) | contract_final | 2858341 | Financial | After change orders | Verified | Benchmark KPIs / Metric Registry — see source tabs
Change Orders ($) | change_orders | -260659 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue | revenue | 2858341 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Net Profit | net_profit | 923837.79 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Gross Margin | gross_margin | 0.32321 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Direct Cost | direct_cost | 1934503.21 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Labor Cost | labor_cost | 766929.01 | Labor | Sum of 11 labor codes | Verified | Benchmark KPIs / Metric Registry — see source tabs
Material Cost | material_cost | 735694.62 | Material | Sum of 8 material codes | Verified | Benchmark KPIs / Metric Registry — see source tabs
Overhead Cost | overhead_cost | 33267.19 | Financial | Sub+Eng+Permits | Verified | Benchmark KPIs / Metric Registry — see source tabs
Burden Cost | burden_cost | 398612.39 | Financial | Codes 995+998 | Verified | Benchmark KPIs / Metric Registry — see source tabs
Retainage | retainage | 142517 | Financial | 5% withheld | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Unit | revenue_per_unit | 9924.7951 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Profit per Unit | profit_per_unit | 3207.7701 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Direct Cost per Unit | cost_per_unit | 6717.025 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Labor Cost per Unit | labor_per_unit | 2662.948 | Labor |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Material Cost per Unit | material_per_unit | 2554.4952 | Material |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Fixture | revenue_per_fixture | 1827.5838 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Profit per Fixture | profit_per_fixture | 590.6891 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Cost per Fixture | cost_per_fixture | 1236.8946 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Labor per Fixture | labor_per_fixture | 490.3638 | Labor |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Material per Fixture | material_per_fixture | 470.393 | Material |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total Labor Hours | total_hours | 38749 | Labor | Sum of JDR cost code hours | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total Workers | total_workers | 57 | Labor | Unique payroll IDs | Verified | Benchmark KPIs / Metric Registry — see source tabs
Blended Gross Wage | blended_gross_wage | 1924% | Labor | Pre-burden | Verified | Benchmark KPIs / Metric Registry — see source tabs
Fully-Loaded Wage | fully_loaded_wage | 3008% | Labor | Post-burden | Verified | Benchmark KPIs / Metric Registry — see source tabs
Burden Multiplier | burden_multiplier | 1.5633 | Labor |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Hours per Unit | hours_per_unit | 134.5451 | Labor | Key benchmark | Verified | Benchmark KPIs / Metric Registry — see source tabs
Hours per Fixture | hours_per_fixture | 2478% | Labor | Key benchmark | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Hour | revenue_per_hour | 7377% | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Profit per Hour | profit_per_hour | 2384% | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Labor % of Revenue | labor_pct_revenue | 0.26831 | Cost Mix |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Material % of Revenue | material_pct_revenue | 0.25739 | Cost Mix |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Month | revenue_per_month | 129924.5909 | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Hours per Month | hours_per_month | 1761.3182 | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Units per Month | units_per_month | 1309% | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total Vendors | total_vendors | 21 | Material | Unique AP vendors | Verified | Benchmark KPIs / Metric Registry — see source tabs
Top Vendor Spend | top_vendor_spend | 216177.2 | Material | Ferguson Enterprises, Inc. | Verified | Benchmark KPIs / Metric Registry — see source tabs
Top Vendor Concentration | top_vendor_pct | 0.2727 | Material |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total POs | total_pos | 279 | Material | Unique POs by filename | Verified | Benchmark KPIs / Metric Registry — see source tabs
Change Order % | co_pct | -0.083571 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Labor Hour | rev_per_labor_hr | 7377% | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
SOURCES
Job #2020 — SRM Bellevue @ Main Apartments • GC: Exxel Pacific / Owner: Bellevue Way Ventures • Bellevue, WA
Canonical source: 2020 Job Detail Report.pdf (352 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count (288) confirmed by TWO source documents:
1) Bellevue Main – Pricing to go to 101 Taylor Fixtures.xlsx: Type B lavs qty=268, Type A lavs qty=20, Lav faucets qty=288, Bathtub trim qty=288
2) BELLEVUE TRIM QUOTE PRICING organized by category USE.xlsx: Mansfield toilets 268 + 20 ADA = 288
Kitchen fixtures: 257 kitchen faucets (Delta 4353-AR-DST) — 31 fewer than units (studios/amenity)
Contract: One Way Plumbing Executed Contract OCR_D.pdf — Exxel Pacific / SRM Development GC
Billing: 10 archived Schedule of Values files (pay apps #4, 9, 10, 12, 13, 15, 18, 19, 20, 23)
Final contract $2,858,341 after 11 COs (net -$260,659, primarily CO#1 cast iron credit -$389,000)
Permit: City of Bellevue #13-133992-BO (building/plumbing)
51 KPIs with snake_case data_name identifiers for database ingestion

## Change Log
Change Log — Master Register
Unified change-event ledger: RFIs, ASIs, COPs, COs, Backcharges, T&M (13 events)
Event ID | Type | Date | Subject | Originator | Linked Event(s) | Cost Impact ($) | Schedule (days) | Status | Source Document
CO-003-UNEXEC | COR | 2014-10-07 | CR #1092 Upgrade plumbing fixture package to match 101 Taylor (UNEXECUTED) | Owner (SRM) | CR-1092 | 37931 | 0 | Unexecuted | 2020-SRM, Bellevue @ Main/Change Orders/CO_s/ONEWAY UNEXECUTED CO 3.pdf
CO-004 | CO | 2014-11-14 | CR #1102 Undercounter vanity sinks — Kohler K2214 Ladena Type A/B | Owner (SRM) | CR-1102 | 31418 | 0 | Executed | 2020-SRM, Bellevue @ Main/Change Orders/CO_s/One Way signed change order 4.pdf
CO-005-UNEXEC | COR | 2014-12-02 | CR #1106 Water cooler upgrades (Elkay LZSTL8WSS3K, LZS8WSS2K) — UNEXECUTED | Owner (SRM) | CR-1106 | 5085 | 0 | Unexecuted | 2020-SRM, Bellevue @ Main/Change Orders/CO_s/UNEXECUTED OWP CO 5.pdf
CO-006 | CO | 2015-01-19 | CR #1121 Misc plumbing revisions — 9 planter drains, sports lounge, mop sinks, drains, grease interceptor, RPBA, hose bibb, FD deletes | Owner (SRM) | CR-1121 | 4756 | 0 | Executed | 2020-SRM, Bellevue @ Main/Change Orders/CO_s/One Way signed change order 6.pdf
CO-007 | CO | 2015-09-23 | CR #1235 Eyewash station w/ mixing valve @ Maintenance Shop | Owner (SRM) | CR-1235 | 2852 | 0 | Executed | 2020-SRM, Bellevue @ Main/Change Orders/CO_s/One Way signed change order 7.pdf
CO-008 | CO | 2015-10-26 | CR #1253 Hose bibbs (courtyard + decks) + 3 BBQ sinks + 1-1/4" gas to Whisk retail | Owner (SRM) | CR-1253 | 22671 | 0 | Executed | 2020-SRM, Bellevue @ Main/Change Orders/CO_s/One Way signed change order 8.pdf
CO-009 | CO | 2015-11-23 | CR #1277 Theater sink + relocate ice maker boxes L4-5 + courtyard water feature piping + CBV consolidation | Owner (SRM) | CR-1277 | 9131 | 0 | Executed | 2020-SRM, Bellevue @ Main/Change Orders/CO_s/One Way signed change order 9.pdf
CO-010 | CO | 2016-01-18 | CR #1305 Attic stock + ADA toilet flange relocations units 327/331/231/450/461 | Owner (SRM) / Todd Rankin | CR-1305 | 4210 | 0 | Executed | 2020-SRM, Bellevue @ Main/Change Orders/CO_s/One Way signed change order 10.pdf
CO-011 | CO | 2016-02-25 | CR #1361 Barber waste extension + vanity sink replacements (trade damage) + condensate drains + retail/gas deduct meters + two-stage drains | Owner (SRM) | CR-1361 | 15963 | 0 | Executed | 2020-SRM, Bellevue @ Main/Change Orders/CO_s/One Way signed change order 11.pdf
CO-012 | Backcharge | 2016-03-11 | CR #1396 Water damage repair — OWP uncapped pipe (CREDIT) | GC | CR-1396 | -6655 | 0 | Executed | 2020-SRM, Bellevue @ Main/Change Orders/CO_s/One Way signed change order 12.pdf
DOC-GAP-CO-1-2 | Memo | 2014 | GAP: CO #1 and CO #2 not found in any extracted folder; may exist in archived OLD DROPBOX FILES subdirectories. | OWP |  | 0 | 0 | Open | 2020-SRM, Bellevue @ Main/Change Orders/CO_s/ (CO1+CO2 missing)
DOC-GAP-RESUB | Memo | 2014-2016 | GAP: 206+ submittal documents but no formal resubmission log; tracked only by ORIGINAL/RESPONSE folder structure. | OWP |  | 0 | 0 | Open | 2020-SRM, Bellevue @ Main/Submittals/
RFI-SUMMARY | Memo | 2014-2016 | 56 RFIs in primary folder (duplicates across 4 extracted instances totaling 282 occurrences). RFI range #027-#258. Focus: structural, concrete, shearwall, countertop, column conflicts, drainage, flashing. | GC |  | 0 | 0 | Informational | 2020-SRM, Bellevue @ Main/ASI-RFI/
TOTAL | [5 empty] | 127362 | 0

## Root Cause Analysis
Root Cause Analysis — Change Driver Taxonomy
Categorized change events with responsible-party attribution — feeds bid-risk intelligence
CATEGORY ROLLUP
Root Cause Category | # Events | Net Cost Impact ($) | % of Events | Predominant Responsibility | Notes
Design substitution | 2 | 69349 | 15.38% | Designer | CR #1092 Upgrade plumbing fixture package to match 101 Taylo
Design clarification | 5 | 20949 | 38.46% | Designer | CR #1121 Misc plumbing revisions — 9 planter drains, sports
Owner directive | 2 | 27756 | 15.38% | Owner/GC | CR #1106 Water cooler upgrades (Elkay LZSTL8WSS3K, LZS8WSS2K
Cleanup/damage | 1 | -6655 | 7.692% | Sub (OWP) | CR #1396 Water damage repair — OWP uncapped pipe (CREDIT)
Combined/multi-cause | 3 | 15963 | 23.08% | Mixed | CR #1361 Barber waste extension + vanity sink replacements (
TOTAL | 13 | 127362
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Events | Net $ Impact | Bid-Risk Signal
Designer | 7 | 90298 | POSITIVE — recoverable
Mixed | 3 | 15963 | POSITIVE — recoverable
Owner/GC | 2 | 27756 | POSITIVE — recoverable
Sub (OWP) | 1 | -6655 | CAUTION — price risk in future bids

## Predictive Signals
Predictive Signals — Leading Indicators
Forward-looking metrics that predict CO waves, schedule slips, and margin erosion
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Predictive Meaning
RFI Total (closed) | 56 | <50 for mid-size | INFO | Volume proxy for design doc quality
RFI Velocity (per month, derived) | See KPIs D50 | <3.0/wk | INFO | >3/wk = CO wave in 4-8 wks
RFI Avg Cycle Time (days) | Unknown | <14 | N/A | >30 avg signals schedule slip
ASI / OCD Count | 0 | <5 | HEALTHY | High ASI = owner scope churn
Backcharge Count | 1 | <3 | HEALTHY | BC clusters = coordination weakness
Change Order Count | 9 | <3 | ELEVATED | CO count signals scope definition
T&M Event Count | 0 | <2 | HEALTHY | T&M = directed work pipeline
Submittal resubmission count | 12 | <10 | ELEVATED | Repeats = coord issues incubating
Net $ Impact (all events) | 127362 | Near $0 | POSITIVE | Net recoverable vs absorbed
FORECAST MODELS (closed-project — actuals)
Forecast | Current Estimate | Confidence | Driver | Model Note
Projected final CO % of contract | -0.083571 | Actual | Closed project | CO$ / orig contract
Projected EAC (direct cost) | 1934503.21 | Actual | Closed project | Sum of L+M+OH+Burden
Projected final margin | 0.32321 | Actual | Closed project | (Rev - DC) / Rev
Composite risk score (0-100) | 25 | Medium | 1 BCs + 0 ASI/OCDs | Custom Cortex scoring

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence_level, and source_document — the machine-readable JCR index
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s) | Formula / Derivation
1 | job_number | Job Number | 2020 | id | Benchmark KPIs | Verified | JDR header | See Benchmark KPIs tab
2 | job_name | Job Name | SRM Bellevue @ Main Apartments | text | Benchmark KPIs | Verified | Contract folder | See Benchmark KPIs tab
3 | general_contractor | General Contractor | SRM Development / Exxel Pacific (Owner: Bellevue Way Ventures) | text | Benchmark KPIs | Verified | Contract folder | See Benchmark KPIs tab
4 | location | Location | Bellevue, WA (15 Bellevue Way SE) | text | Benchmark KPIs | Verified | Permit/Plans | See Benchmark KPIs tab
5 | project_type | Project Type | 6-story 288-unit luxury multifamily + retail (268 Type B + 20 Type A ADA) | text | Benchmark KPIs | Verified | Plans | See Benchmark KPIs tab
6 | duration_months | Duration (months) | 22 | months | Benchmark KPIs | Verified | First-to-last invoice | See Benchmark KPIs tab
7 | unit_count | Unit Count | 288 | units | Benchmark KPIs | Verified | Plumbing permit + P-tag list | See Benchmark KPIs tab
8 | total_fixtures | Total Fixtures | 1564 | count | Benchmark KPIs | Verified | Permit detail | See Benchmark KPIs tab
9 | contract_original | Contract Original | 3119000 | USD | Benchmark KPIs | Verified | Contract SOV | See Benchmark KPIs tab
10 | contract_final | Contract Final | 2858341 | USD | Benchmark KPIs | Verified | Final billing SOV | See Benchmark KPIs tab
11 | change_orders | Change Orders ($) | -260659 | USD | Benchmark KPIs | Verified | JDR revised - original | See Benchmark KPIs tab
12 | revenue | Revenue | 2858341 | USD | Benchmark KPIs | Verified | Aggregate billing | See Benchmark KPIs tab
13 | net_profit | Net Profit | 923837.79 | USD | Benchmark KPIs | Verified | Revenue - Direct Cost | See Benchmark KPIs tab
14 | gross_margin | Gross Margin % | 0.32321 | % | Benchmark KPIs | Verified | Derived | See Benchmark KPIs tab
15 | direct_cost | Direct Cost | 1934503.21 | USD | Benchmark KPIs | Verified | JDR cost codes | See Benchmark KPIs tab
16 | labor_cost | Labor Cost | 766929.01 | USD | Benchmark KPIs | Verified | JDR labor codes | See Benchmark KPIs tab
17 | material_cost | Material Cost | 735694.62 | USD | Benchmark KPIs | Verified | JDR material codes | See Benchmark KPIs tab
18 | overhead_cost | Overhead Cost | 33267.19 | USD | Benchmark KPIs | Verified | JDR overhead codes | See Benchmark KPIs tab
19 | burden_cost | Burden Cost | 398612.39 | USD | Benchmark KPIs | Verified | JDR burden codes | See Benchmark KPIs tab
20 | retainage | Retainage | 142517 | USD | Benchmark KPIs | Verified | Aggregate billing row | See Benchmark KPIs tab
21 | total_hours | Total Labor Hours | 38749 | hours | Benchmark KPIs | Verified | JDR payroll | See Benchmark KPIs tab
22 | total_workers | Total Workers | 57 | count | Benchmark KPIs | Verified | JDR unique workers | See Benchmark KPIs tab
23 | blended_gross_wage | Blended Gross Wage | 1924% | USD/hr | Benchmark KPIs | Verified | Labor $ / Hours | See Benchmark KPIs tab
24 | total_vendors | Total Vendors | 21 | count | Benchmark KPIs | Verified | JDR AP unique | See Benchmark KPIs tab
25 | total_pos | Total POs | 279 | count | Benchmark KPIs | Verified | PO folder count | See Benchmark KPIs tab
26 | co_pct | CO % of Original | -0.083571 | % | Benchmark KPIs | Verified | Derived | See Benchmark KPIs tab
27 | rfi_total_count | RFIs Total | 56 | count | Predictive Signals | Verified | ASI-RFI folder count | See Predictive Signals tab
28 | asi_ocd_count | ASI + OCD Count | 0 | count | Change Log | Verified | ASI-RFI folder + Change Orders | See Change Log tab
29 | co_count_total | Change Order Count | 9 | count | Change Log | Verified | Change Orders folder | See Change Log tab
30 | backcharge_count | Backcharge Count | 1 | count | Change Log | Verified | Invoices/Backcharges | See Change Log tab
31 | tm_event_count | T&M Event Count | 0 | count | Change Log | Verified | Change Orders / JDR 038 | See Change Log tab
32 | submittal_resub_count | Submittal Resubmissions | 12 | count | Predictive Signals | Verified | Submittals folder | See Predictive Signals tab
33 | change_event_total | Total Tracked Events | 13 | count | Change Log | Verified | Change Log tab | See Change Log tab
34 | change_net_impact | Change Net $ Impact | 127362 | USD | Change Log | Verified | SUM H col | See Change Log tab

## Reconciliation
Reconciliation — Tie-out Proofs
Live cross-sheet formulas verify data consistency across all 17 tabs
Check | Computed | Expected | Δ | Status
A. JDR COST CODE ROLLUP
Labor subtotal (11 codes) | 766929.01 | 766929.01 | 0 | TIES
Material subtotal (8 codes) | 735694.62 | 735694.62 | 0 | TIES
Overhead subtotal (2 codes) | 33267.19 | 33267.19 | 0 | TIES
Burden subtotal (2 codes) | 398612.39 | 398612.39 | 0 | TIES
Direct Cost (all categories) | 1934503.21 | 1934503.21 | 0 | TIES
Revenue (code 999) | 2852262.93 | 2858341 | -6078.07 | WITHIN
Net Profit (Revenue - Expenses) | 917759.72 | 923837.79 | -6078.07 | WITHIN
B. LABOR HOURS ROLLUP
JDR Cost Code hours (Payroll Hours lines) | 38749 | 38749 | 0 | TIES
Per-worker hours (sum of PR Regular) | 38007.5 | 38749 | -741.5 | WITHIN
C. BILLING (SOV) ↔ JDR
Final Contract Value | 2858341 | 2858341 | 0 | TIES
Retainage | 142517 | 142517 | 0 | TIES
Direct Cost | 1934503.21 | 1934503.21 | 0 | TIES
D. VENDOR AP ↔ JDR
Vendor AP total (sum of invoices) | 792734.87 | 792735 | -0.13 | TIES
SOURCES
Job #2020 — SRM Bellevue @ Main Apartments • GC: Exxel Pacific / Owner: Bellevue Way Ventures • Bellevue, WA
Canonical source: 2020 Job Detail Report.pdf (352 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count (288) confirmed by TWO source documents:
1) Bellevue Main – Pricing to go to 101 Taylor Fixtures.xlsx: Type B lavs qty=268, Type A lavs qty=20, Lav faucets qty=288, Bathtub trim qty=288
2) BELLEVUE TRIM QUOTE PRICING organized by category USE.xlsx: Mansfield toilets 268 + 20 ADA = 288
Kitchen fixtures: 257 kitchen faucets (Delta 4353-AR-DST) — 31 fewer than units (studios/amenity)
Contract: One Way Plumbing Executed Contract OCR_D.pdf — Exxel Pacific / SRM Development GC
Billing: 10 archived Schedule of Values files (pay apps #4, 9, 10, 12, 13, 15, 18, 19, 20, 23)
Final contract $2,858,341 after 11 COs (net -$260,659, primarily CO#1 cast iron credit -$389,000)
Permit: City of Bellevue #13-133992-BO (building/plumbing)
TIES = within $1 or 5 hrs • WITHIN = within 5% • OFF = investigate
K. CHANGE LOG ↔ ROOT CAUSE ANALYSIS
Total Event Count | 13 | 13 | 0 | TIES | 13↔14
Net $ Impact (all events) | 127362 | 127362 | 0 | TIES | 13↔14
L. PREDICTIVE SIGNALS ↔ CHANGE LOG
Backcharge Count signal | 1 | 1 | 0 | TIES | 15↔13
M. METRIC REGISTRY ↔ BENCHMARK KPIs
revenue (row 17) | 2858341 | 2858341 | 0 | TIES | 16↔11
unit_count (row 12) | 288 | 288 | 0 | TIES | 16↔11
total_fixtures (row 13) | 1564 | 1564 | 0 | TIES | 16↔11
direct_cost (row 19) | 0.32321 | 1934503.21 | -1934502.8868 | OFF | 16↔11
total_pos (row 30) | 279 | 279 | 0 | TIES | 16↔11
N. CHANGE LOG ↔ METRIC REGISTRY (event counts)
change_event_total | 0 | 13 | -13 | OFF | 16↔13
SOURCES
Job #2020 — Cortex v2 17-tab layout
12 analytical tabs + Change Log + Root Cause Analysis + Predictive Signals + Metric Registry + Reconciliation
Canonical source: 2020 Job Detail Report.pdf (Sage Timberline export)
Change artifacts: folders scanned — ASI-RFI, Change Orders, Submittals, Invoices (Backcharges), JDR cost codes
Every Change Log row cites its source document path
TIES = within $1/5hrs/exact count • WITHIN = within 5% • OFF = investigate
Cross-sheet formulas (='Tab'!Cell) update automatically when source tabs change
Tabs: 1-12 analytical • 13=ChangeLog • 14=RootCause • 15=PredictiveSignals • 16=MetricRegistry • 17=Reconciliation

## Vendors
Vendor Detail — Job #2020
Vendors | 21 |  | Top vendor | Ferguson Enterprises, Inc.
Invoices | 545 |  | Top 3 share | 76.91%
Total AP | 792734.87 |  | Source | 2020 Job Detail Report.pdf (Sage Timberline AP export)
Avg Inv | 1454.5594
Rank | Vendor | Vendor Code | Invoices | Total Spend | % of AP | Avg / Invoice
1 | Ferguson Enterprises, Inc. |  | 121 | 216177.2 | 27.27% | 1786.5884
2 | Keller Supply Company |  | 101 | 204979.52 | 25.86% | 2029.5002
3 | Rosen Supply Company |  | 172 | 188562.66 | 23.79% | 1096.2945
4 | Mechanical Sales, Inc. |  | 4 | 67935.82 | 8.57% | 16983.955
5 | Consolidated Supply Co. |  | 11 | 47819.57 | 6.032% | 4347.2336
6 | United Rentals, Inc. |  | 40 | 23301.34 | 2.939% | 582.5335
7 | Quality Concrete Products, Inc. |  | 5 | 15202 | 1.918% | 3040.4
8 | Scan2Core, Inc. |  | 13 | 8585 | 1.083% | 660.3846
9 | MAD Concrete Cutting & Coring, Inc. |  | 5 | 4605 | 0.5809% | 921
10 | Kele, Inc |  | 6 | 3172.33 | 0.4002% | 528.7217
11 | C.M. Hoskins Company |  | 5 | 2334.26 | 0.2945% | 466.852
12 | Rosen Supply Kirkland |  | 8 | 2331.87 | 0.2942% | 291.4837
13 | Capital One Credit Card |  | 16 | 2040.76 | 0.2574% | 127.5475
14 | Shirley Dennison |  | 17 | 1700 | 0.2144% | 100
15 | Seton Identification Products |  | 3 | 1302.22 | 0.1643% | 434.0733
16 | American Express 3-41000 |  | 1 | 945 | 0.1192% | 945
17 | NRP-Meydenbauer |  | 4 | 474 | 0.05979% | 118.5
18 | Ferguson Enterprises, Inc. #3007 |  | 2 | 458.5 | 0.05784% | 229.25
19 | Fastenal Company |  | 5 | 456.5 | 0.05759% | 91.3
20 | A.R. Brown Backflow Testing |  | 3 | 304 | 0.03835% | 101.3333
21 | Rosen Supply Company, Inc. |  | 3 | 47.32 | 0.005969% | 15.7733
| TOTAL |  | 545 | 792734.87 | 100% | 1454.5594