## Overview
Job #2021 · Exxel Pacific Admiral East Apartments
Cortex JCR Summary • Exxel Pacific, Inc. • Seattle, WA (2600 SW Admiral Way, West Seattle) • 5-story 182-unit multifamily apartments + retail/garage • Feb 2015 – Aug 2016 (~19 months)
PROJECT OVERVIEW
Project Job # | 2021
Project Name: | Exxel Pacific Admiral East Apartments
General Contractor | Exxel Pacific, Inc.
Location | Seattle, WA (2600 SW Admiral Way, West Seattle)
Project Duration | Feb 2015 – Aug 2016 (~19 months)
Total Unique Documents | Admiral folder: Contract (OCR), Billing (aggregate + 17 SOVs), PO_s (trim consolidated + level-specific), Change Orders, Invoices, Vendor Quotes
CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
$1,581,818 |  | $448,741 |  | $1,133,077 |  | 19,800
Original $1,558,650 + $23,168 COs |  | 28.4% margin |  | 71.6% of revenue |  | 40 workers
COST BREAKDOWN
Category | Budget | Actual | Variance | % Budget | % of Cost
Labor | 387079 | 429422.78 | -42343.78 | 110.9% | 37.9%
Material | 494749 | 423924.46 | 70824.54 | 85.68% | 37.41%
Overhead | 71320 | 66646.5 | 4673.5 | 93.45% | 5.882%
Burden | 192149.33 | 213083.05 | -20933.72 | 110.9% | 18.81%
TOTAL | 1145297.33 | 1133076.79 | 12220.54 | 98.93% | 100%
PROJECT PROFILE
Metric | Value | Metric | Value | Metric | Value
Plumbing Units | 182 | Standard Units | 171 | ADA Units | 11
Water Closets | 182 | Lav Faucets | 182 | Kitchen Faucets | 138
Tub/Shower Valves | 159 | Shower Only | 21 | Total Fixtures | 891
Fixtures / Unit | 4.90 | Floors | L1 garage/retail + L2–L5 residential | Duration | 19 mo
SOURCES
Job #2021 — Exxel Pacific Admiral East Apartments • GC: Exxel Pacific, Inc. • 2600 SW Admiral Way, West Seattle
Canonical source: 2021 Job Detail Report.pdf (189 pages, OWP Sage Timberline export)
Cost codes parsed: 25
Unit count (182) confirmed by ADMIRAL TRIM - KELLER.xlsx SUMMATION:
• 171 Gerber 21-962 standard elongated toilets
• 11 Gerber 21-928 ADA elongated toilets
• 182 Delta 559LF-PP lav faucets (one per unit)
• 159 tub/shower + 21 shower-only = 180 bathing fixtures
• 138 kitchen faucets (44 fewer than units — studio/SRO variants)
Contract: Admiral Contract executed - OCR_d.pdf (Exxel Pacific GC)
Billing: ADMIRAL AGGREGATE BILLING.xlsx (17 pay apps Feb 2015 – Aug 2016) + 17 SOV files
Final contract $1,581,818 (original $1,558,650 + $23,168 COs)

## Budget vs Actual
Budget vs Actual — All Cost Codes
Code | Description | Orig Budget | Rev Budget | Actual | Variance | % Used
LABOR
100 | Supervision | 12920 | 13414 | 8726 | 4688 | 65.05%
101 | Takeoff & Purchase Labor | 12920 | 13887 | 19430.5 | -5543.5 | 139.9%
110 | Underground Labor | 12625 | 18310 | 21121.15 | -2811.15 | 115.4%
111 | Garage Labor | 46180 | 48780 | 40673.76 | 8106.24 | 83.38%
112 | Canout Labor | 8500 | 8500 | 9421.18 | -921.18 | 110.8%
120 | Roughin Labor | 205015 | 208728 | 232285.5 | -23557.5 | 111.3%
130 | Finish Labor | 32520 | 32580 | 30179 | 2401 | 92.63%
140 | Gas Labor | 5500 | 7990 | 10305.46 | -2315.46 | 129%
141 | Water Main/Insulation Lab | 34750 | 34890 | 56135.73 | -21245.73 | 160.9%
142 | Mech Room Labor | 0 | 0 | 1144.5 | -1144.5 | 0%
MATERIAL
210 | Underground Material | 13250 | 13550 | 21743.86 | -8193.86 | 160.5%
211 | Garage Material | 36150 | 37700 | 39526.02 | -1826.02 | 104.8%
212 | Canout Material | 9520 | 9520 | 6538.72 | 2981.28 | 68.68%
220 | Roughin Material | 145590 | 120660 | 99695.01 | 20964.99 | 82.62%
230 | Finish Material | 256900 | 260675 | 202739.69 | 57935.31 | 77.77%
240 | Gas Material | 5500 | 7369 | 3604.09 | 3764.91 | 48.91%
241 | Water Main/Insulation Mat | 45175 | 45275 | 49938.59 | -4663.59 | 110.3%
242 | Mech Room Material | 0 | 0 | 5.44 | -5.44 | 0%
244 | Fire Caulking Material | 0 | 0 | 133.04 | -133.04 | 0%
OVERHEAD
600 | Subcontractor | 21050 | 21550 | 4501 | 17049 | 20.89%
601 | Engineering/Plans | 38000 | 39000 | 53259.5 | -14259.5 | 136.6%
603 | Permits & Licenses | 10770 | 10770 | 8886 | 1884 | 82.51%
BURDEN
995 | Payroll Burden | 167567.61 | 160896.89 | 178143.53 | -17246.64 | 110.7%
998 | Payroll Taxes | 28904 | 31252.44 | 34939.52 | -3687.08 | 111.8%
TOTAL | Direct Cost | 1149306.61 | 1145297.33 | 1133076.79 | 12220.54 | 98.93%
SOURCES
Job #2021 — Exxel Pacific Admiral East Apartments • GC: Exxel Pacific, Inc. • 2600 SW Admiral Way, West Seattle
Canonical source: 2021 Job Detail Report.pdf (189 pages, OWP Sage Timberline export)
Cost codes parsed: 25
Unit count (182) confirmed by ADMIRAL TRIM - KELLER.xlsx SUMMATION:
• 171 Gerber 21-962 standard elongated toilets
• 11 Gerber 21-928 ADA elongated toilets
• 182 Delta 559LF-PP lav faucets (one per unit)
• 159 tub/shower + 21 shower-only = 180 bathing fixtures
• 138 kitchen faucets (44 fewer than units — studio/SRO variants)
Contract: Admiral Contract executed - OCR_d.pdf (Exxel Pacific GC)
Billing: ADMIRAL AGGREGATE BILLING.xlsx (17 pay apps Feb 2015 – Aug 2016) + 17 SOV files
Final contract $1,581,818 (original $1,558,650 + $23,168 COs)

## Cost Breakdown
Cost Breakdown — Category Deep Dive
A. CATEGORY SHARE OF DIRECT COST
Category | # Codes | Budget | Actual | Variance | % Budget | % of Cost | Per Unit
Labor | 10 | 387079 | 429422.78 | -42343.78 | 110.9% | 37.9% | 2359.4658
Material | 9 | 494749 | 423924.46 | 70824.54 | 85.68% | 37.41% | 2329.2553
Overhead | 3 | 71320 | 66646.5 | 4673.5 | 93.45% | 5.882% | 366.1896
Burden | 2 | 192149.33 | 213083.05 | -20933.72 | 110.9% | 18.81% | 1170.786
B. LARGEST OVERRUNS (Actual > Revised Budget)
Code | Description | Rev Budget | Actual | Overrun | % Over
120 | Roughin Labor | 208728 | 232285.5 | 23557.5 | 11.29%
141 | Water Main/Insulation Lab | 34890 | 56135.73 | 21245.73 | 60.89%
995 | Payroll Burden | 160896.89 | 178143.53 | 17246.64 | 10.72%
601 | Engineering/Plans | 39000 | 53259.5 | 14259.5 | 36.56%
210 | Underground Material | 13550 | 21743.86 | 8193.86 | 60.47%
101 | Takeoff & Purchase Labor | 13887 | 19430.5 | 5543.5 | 39.92%
241 | Water Main/Insulation Mat | 45275 | 49938.59 | 4663.59 | 10.3%
998 | Payroll Taxes | 31252.44 | 34939.52 | 3687.08 | 11.8%
110 | Underground Labor | 18310 | 21121.15 | 2811.15 | 15.35%
140 | Gas Labor | 7990 | 10305.46 | 2315.46 | 28.98%
C. LARGEST SAVINGS (Actual < Revised Budget)
Code | Description | Rev Budget | Actual | Savings | % Under
230 | Finish Material | 260675 | 202739.69 | 57935.31 | 22.23%
220 | Roughin Material | 120660 | 99695.01 | 20964.99 | 17.38%
600 | Subcontractor | 21550 | 4501 | 17049 | 79.11%
111 | Garage Labor | 48780 | 40673.76 | 8106.24 | 16.62%
100 | Supervision | 13414 | 8726 | 4688 | 34.95%
240 | Gas Material | 7369 | 3604.09 | 3764.91 | 51.09%
212 | Canout Material | 9520 | 6538.72 | 2981.28 | 31.32%
130 | Finish Labor | 32580 | 30179 | 2401 | 7.37%
603 | Permits & Licenses | 10770 | 8886 | 1884 | 17.49%
SOURCES
Job #2021 — Exxel Pacific Admiral East Apartments • GC: Exxel Pacific, Inc. • 2600 SW Admiral Way, West Seattle
Canonical source: 2021 Job Detail Report.pdf (189 pages, OWP Sage Timberline export)
Cost codes parsed: 25
Unit count (182) confirmed by ADMIRAL TRIM - KELLER.xlsx SUMMATION:
• 171 Gerber 21-962 standard elongated toilets
• 11 Gerber 21-928 ADA elongated toilets
• 182 Delta 559LF-PP lav faucets (one per unit)
• 159 tub/shower + 21 shower-only = 180 bathing fixtures
• 138 kitchen faucets (44 fewer than units — studio/SRO variants)
Contract: Admiral Contract executed - OCR_d.pdf (Exxel Pacific GC)
Billing: ADMIRAL AGGREGATE BILLING.xlsx (17 pay apps Feb 2015 – Aug 2016) + 17 SOV files
Final contract $1,581,818 (original $1,558,650 + $23,168 COs)

## Material
Material Spend Analysis
9 material cost codes • $423,924 JDR material • 21 AP vendors • $436,423 total AP
A. MATERIAL BY COST CODE
Code | Description | Rev Budget | Actual | Variance | % Used | % of Mat | Per Unit
210 | Underground Material | 13550 | 21743.86 | -8193.86 | 160.5% | 5.129% | 119.4718
211 | Garage Material | 37700 | 39526.02 | -1826.02 | 104.8% | 9.324% | 217.1759
212 | Canout Material | 9520 | 6538.72 | 2981.28 | 68.68% | 1.542% | 35.927
220 | Roughin Material | 120660 | 99695.01 | 20964.99 | 82.62% | 23.52% | 547.7748
230 | Finish Material | 260675 | 202739.69 | 57935.31 | 77.77% | 47.82% | 1113.9543
240 | Gas Material | 7369 | 3604.09 | 3764.91 | 48.91% | 0.8502% | 19.8027
241 | Water Main/Insulation Mat | 45275 | 49938.59 | -4663.59 | 110.3% | 11.78% | 274.3879
242 | Mech Room Material | 0 | 5.44 | -5.44 | 0% | 0.001283% | 0.02989
244 | Fire Caulking Material | 0 | 133.04 | -133.04 | 0% | 0.03138% | 0.73099
TOTAL | All Material | 494749 | 423924.46 | 70824.54 | 85.68% | 100% | 2329.2553
B. VENDORS BY SPEND (AP)
Vendor | # Invoices | Total Spend | % of AP |  |  |  | Avg Invoice
Ferguson Enterprises, Inc. | 82 | 121504.28 | 27.84% |  |  |  | 1481.7595
Rosen Supply Company | 77 | 98623.69 | 22.6% |  |  |  | 1280.8271
Keller Supply Company | 52 | 76284.33 | 17.48% |  |  |  | 1467.0063
Franklin Engineering | 8 | 53259.5 | 12.2% |  |  |  | 6657.4375
Mechanical Sales, Inc. | 3 | 34858.54 | 7.987% |  |  |  | 11619.5133
Specification Sales, Inc. | 2 | 21294 | 4.879% |  |  |  | 10647
Bank of America CC | 5 | 8886 | 2.036% |  |  |  | 1777.2
Core & Main LP | 6 | 4652.03 | 1.066% |  |  |  | 775.3383
Scan2Core, Inc. | 5 | 4401 | 1.008% |  |  |  | 880.2
Quality Concrete Products, Inc. | 4 | 3386 | 0.7759% |  |  |  | 846.5
Manor Hardware & Construction Supply | 4 | 1442.8 | 0.3306% |  |  |  | 360.7
Capital One Credit Card | 5 | 1311.2 | 0.3004% |  |  |  | 262.24
Rosen Supply Kirkland | 3 | 1290.12 | 0.2956% |  |  |  | 430.04
Consolidated Supply Co. | 4 | 1260.54 | 0.2888% |  |  |  | 315.135
C.M. Hoskins Company | 3 | 891.82 | 0.2043% |  |  |  | 297.2733
ACME Corp | 3 | 759.6 | 0.1741% |  |  |  | 253.2
Ferguson Enterprises, Inc. #3007 | 4 | 725.12 | 0.1662% |  |  |  | 181.28
Kele, Inc | 2 | 713.58 | 0.1635% |  |  |  | 356.79
Beacon Building Products | 2 | 576.57 | 0.1321% |  |  |  | 288.285
Rosen Supply Company, Inc. | 5 | 202.75 | 0.04646% |  |  |  | 40.55
A.R. Brown Backflow Testing | 1 | 100 | 0.02291% |  |  |  | 100
TOTAL | 280 | 436423.47 | 100%
SOURCES
Job #2021 — Exxel Pacific Admiral East Apartments • GC: Exxel Pacific, Inc. • 2600 SW Admiral Way, West Seattle
Canonical source: 2021 Job Detail Report.pdf (189 pages, OWP Sage Timberline export)
Cost codes parsed: 25
Unit count (182) confirmed by ADMIRAL TRIM - KELLER.xlsx SUMMATION:
• 171 Gerber 21-962 standard elongated toilets
• 11 Gerber 21-928 ADA elongated toilets
• 182 Delta 559LF-PP lav faucets (one per unit)
• 159 tub/shower + 21 shower-only = 180 bathing fixtures
• 138 kitchen faucets (44 fewer than units — studio/SRO variants)
Contract: Admiral Contract executed - OCR_d.pdf (Exxel Pacific GC)
Billing: ADMIRAL AGGREGATE BILLING.xlsx (17 pay apps Feb 2015 – Aug 2016) + 17 SOV files
Final contract $1,581,818 (original $1,558,650 + $23,168 COs)
Vendor AP ties to JDR 'by Source: AP' line (436,423.47)

## Crew & Labor
Crew & Labor — Per-Worker Breakdown
Worker | Hours | Gross Pay | $/Hour | Tier
Gonzalez Hernandez, Josue | 1565.5 | 29049 | 18.5557 | Mid
Quintanilla, Esteban R | 1507.5 | 51734 | 34.3177 | Senior
Rivera, Jorge A | 1471.5 | 33849.5 | 23.0034 | Mid
Montenegro, Carlos E | 1390.5 | 25856.5 | 18.5951 | Mid
Palma Vides, Hugo | 1355 | 43226 | 31.9011 | Senior
Palma Vides, Jorge A | 1309 | 19936 | 15.2299 | Apprentice
Lima Romero, Melvin A | 1232 | 29632 | 24.0519 | Mid
Benites Portillo, Marvin E | 859 | 12533 | 14.5902 | Apprentice
Castro Hernandez, Jose A | 804 | 17257 | 21.4639 | Mid
Rodriguez Bonilla, Lisandro | 785 | 12137 | 15.4611 | Apprentice
Galdamez, Dagoberto A | 752 | 11280 | 15 | Apprentice
Reyes, Robert J | 655 | 10728 | 16.3786 | Apprentice
Sepulveda Gonzalez, Alfredo | 616 | 18208 | 29.5584 | Mid
Reyes Cruz, Denis A | 487 | 7969 | 16.3634 | Apprentice
Aguilar Rivas, Henry | 480 | 6504 | 13.55 | Apprentice
Cruz Reyes, Jose | 480 | 7472 | 15.5667 | Apprentice
Cruz Guzman, Joel A | 474 | 6826 | 14.4008 | Apprentice
Gerard, Jeffrey S | 470.5 | 19658 | 41.7811 | Senior
Sanders, Allen O | 404 | 14532.5 | 35.9715 | Senior
Eliassen, Cory H | 403 | 5961 | 14.7916 | Apprentice
Alba Jimenez, Jovani | 402 | 6432 | 16 | Apprentice
Spears, Gregory M | 397 | 6621 | 16.6776 | Apprentice
Hubbard, Robert W | 376.5 | 14905 | 39.5883 | Senior
Lovo, German G | 349 | 5584 | 16 | Apprentice
Vaughan, Tyler J | 276 | 5737 | 20.7862 | Mid
Monico Brambila, Jesus S | 253 | 4807 | 19 | Mid
Alba Martinez, Santiago | 228 | 4104 | 18 | Mid
Donelson, Richard T | 188 | 8514 | 45.2872 | Senior
Meza Fuentes, Erick A | 141 | 3525 | 25 | Mid
Gerard, Mitchell J | 131 | 2489 | 19 | Mid
Anzora, William | 105 | 1785 | 17 | Apprentice
Gerard, Jordan E | 86 | 1548 | 18 | Mid
Waites, Thaddeus Z | 84 | 2940 | 35 | Senior
McCabe, Thomas C | 80 | 2000 | 25 | Mid
Cortes Sepulveda, Jose R | 56 | 728 | 13 | Apprentice
Hubbard, Dustin R | 40 | 657 | 16.425 | Apprentice
Balderas Ortiz, Ricardo I | 32 | 544 | 17 | Apprentice
Taylor, Evan R | 32 | 512 | 16 | Apprentice
Barnhart, Joseph N | 12.5 | 452 | 36.16 | Senior
Gardner, Andrew M | 8 | 112 | 14 | Apprentice
TOTAL (40 workers) | 20777.5 | 458344.5 | 22.0597
SOURCES
Job #2021 — Exxel Pacific Admiral East Apartments • GC: Exxel Pacific, Inc. • 2600 SW Admiral Way, West Seattle
Canonical source: 2021 Job Detail Report.pdf (189 pages, OWP Sage Timberline export)
Cost codes parsed: 25
Unit count (182) confirmed by ADMIRAL TRIM - KELLER.xlsx SUMMATION:
• 171 Gerber 21-962 standard elongated toilets
• 11 Gerber 21-928 ADA elongated toilets
• 182 Delta 559LF-PP lav faucets (one per unit)
• 159 tub/shower + 21 shower-only = 180 bathing fixtures
• 138 kitchen faucets (44 fewer than units — studio/SRO variants)
Contract: Admiral Contract executed - OCR_d.pdf (Exxel Pacific GC)
Billing: ADMIRAL AGGREGATE BILLING.xlsx (17 pay apps Feb 2015 – Aug 2016) + 17 SOV files
Final contract $1,581,818 (original $1,558,650 + $23,168 COs)
Tier: Apprentice <$18/hr, Mid $18–30, Senior >$30

## Crew Analytics
Crew Analytics
A. TIER DISTRIBUTION
Tier | # Workers | Hours | Gross Pay | % of Hours
Senior | 8 | 4398 | 155961.5 | 21.17%
Mid | 13 | 8274.5 | 178062 | 39.82%
Apprentice | 19 | 8105 | 124321 | 39.01%
B. WAGE STATISTICS
Blended Gross Wage | 22.0597 |  |  | Payroll $ ÷ payroll hours (pre-burden)
Fully-Loaded Wage | 30.9232 |  |  | (Labor + Burden) ÷ total hours
Burden Multiplier | 1.4018 |  |  | Fully loaded ÷ gross wage
Min Worker Rate | 13 |  |  | Cheapest apprentice hour
Max Worker Rate | 45.2872 |  |  | Most expensive foreman hour
Avg Hours / Worker | 519.4375 |  |  | Crew continuity indicator
SOURCES
Job #2021 — Exxel Pacific Admiral East Apartments • GC: Exxel Pacific, Inc. • 2600 SW Admiral Way, West Seattle
Canonical source: 2021 Job Detail Report.pdf (189 pages, OWP Sage Timberline export)
Cost codes parsed: 25
Unit count (182) confirmed by ADMIRAL TRIM - KELLER.xlsx SUMMATION:
• 171 Gerber 21-962 standard elongated toilets
• 11 Gerber 21-928 ADA elongated toilets
• 182 Delta 559LF-PP lav faucets (one per unit)
• 159 tub/shower + 21 shower-only = 180 bathing fixtures
• 138 kitchen faucets (44 fewer than units — studio/SRO variants)
Contract: Admiral Contract executed - OCR_d.pdf (Exxel Pacific GC)
Billing: ADMIRAL AGGREGATE BILLING.xlsx (17 pay apps Feb 2015 – Aug 2016) + 17 SOV files
Final contract $1,581,818 (original $1,558,650 + $23,168 COs)

## Productivity
Productivity — Phase & Unit Metrics
A. LABOR HOURS BY PHASE
Phase | Labor Code | Hours | % of Total | Hours / Unit
Supervision | 100 | 205 | 1.035% | 1.1264
Takeoff & Purchasing | 101 | 453.5 | 2.29% | 2.4918
Underground | 110 | 990 | 5% | 5.4396
Garage | 111 | 1788 | 9.031% | 9.8242
Canout | 112 | 450 | 2.273% | 2.4725
Roughin | 120 | 11448.5 | 57.82% | 62.9038
Finish | 130 | 1291 | 6.52% | 7.0934
Gas | 140 | 415.5 | 2.099% | 2.283
Water Main / Insulation | 141 | 2735.5 | 13.82% | 15.0302
Mech Room | 142 | 22.5 | 0.1136% | 0.12363
TOTAL |  | 19799.5 | 100% | 108.7885
B. PRODUCTIVITY RATIOS
Metric | Value | Units |  | Notes
Hours / Unit | 108.7885 | hrs |  | Labor hours per residential unit
Hours / Fixture | 22.2217 | hrs |  | Labor hours per plumbing fixture
Revenue / Hour | 79.8918 | $ |  | Top-line per labor hour
Profit / Hour | 22.6643 | $ |  | Bottom-line per labor hour
Units / Month | 9.5789 | units |  | Build velocity
Fixtures / Month | 46.8947 | fix |  | Fixture install pace
Hours / Month | 1042.0789 | hrs |  | Monthly labor burn
Revenue / Month | 83253.5789 | $ |  | Monthly billing rate
SOURCES
Job #2021 — Exxel Pacific Admiral East Apartments • GC: Exxel Pacific, Inc. • 2600 SW Admiral Way, West Seattle
Canonical source: 2021 Job Detail Report.pdf (189 pages, OWP Sage Timberline export)
Cost codes parsed: 25
Unit count (182) confirmed by ADMIRAL TRIM - KELLER.xlsx SUMMATION:
• 171 Gerber 21-962 standard elongated toilets
• 11 Gerber 21-928 ADA elongated toilets
• 182 Delta 559LF-PP lav faucets (one per unit)
• 159 tub/shower + 21 shower-only = 180 bathing fixtures
• 138 kitchen faucets (44 fewer than units — studio/SRO variants)
Contract: Admiral Contract executed - OCR_d.pdf (Exxel Pacific GC)
Billing: ADMIRAL AGGREGATE BILLING.xlsx (17 pay apps Feb 2015 – Aug 2016) + 17 SOV files
Final contract $1,581,818 (original $1,558,650 + $23,168 COs)

## PO Commitments
Purchase Order Commitments
177 unique POs • PO amounts not dollar-parsed from individual PDFs • JDR material $423,924
A. COMMITMENTS BY COST CODE
OWP Code | Description → JDR | PO Count | % of POs | JDR Material
30 | 110+210 Underground | 28 | 15.82%
31 | 120+220 Roughin | 34 | 19.21%
32 | 130+230 Trim/Finish | 16 | 9.04%
40 | 141+241 Water Main/Ins | 4 | 2.26%
41 | 140+240 Gas | 6 | 3.39%
OTHER | Unclassified | 89 | 50.28%
TOTAL |  | 177 | 100% | 423924.46
B. COMMITMENTS BY VENDOR
Vendor | PO Count | % of POs
FEI | 64 | 36.16%
ROSEN | 56 | 31.64%
KELLER | 28 | 15.82%
OTHER | 22 | 12.43%
MANOR | 4 | 2.26%
CONSOLIDATED | 2 | 1.13%
MECH SALES | 1 | 0.565%
C. PO COVERAGE NOTES
Total Material Actual (JDR) |  |  | 423924.46
Unique PO Count |  |  | 177
(Dollar PO commitment not extracted — requires per-PDF parse)
SOURCES
Job #2021 — Exxel Pacific Admiral East Apartments • GC: Exxel Pacific, Inc. • 2600 SW Admiral Way, West Seattle
Canonical source: 2021 Job Detail Report.pdf (189 pages, OWP Sage Timberline export)
Cost codes parsed: 25
Unit count (182) confirmed by ADMIRAL TRIM - KELLER.xlsx SUMMATION:
• 171 Gerber 21-962 standard elongated toilets
• 11 Gerber 21-928 ADA elongated toilets
• 182 Delta 559LF-PP lav faucets (one per unit)
• 159 tub/shower + 21 shower-only = 180 bathing fixtures
• 138 kitchen faucets (44 fewer than units — studio/SRO variants)
Contract: Admiral Contract executed - OCR_d.pdf (Exxel Pacific GC)
Billing: ADMIRAL AGGREGATE BILLING.xlsx (17 pay apps Feb 2015 – Aug 2016) + 17 SOV files
Final contract $1,581,818 (original $1,558,650 + $23,168 COs)
PO count is deduplicated by 5-digit PO number extracted from filenames
Vendor/code classification is heuristic (filename keyword match)

## Billing & SOV
Revenue & Billing Reconciliation
17 pay applications • Feb 2015 – Aug 2016 • $1,581,818 final
A. CONTRACT SUMMARY
Original Contract |  |  |  |  | 1558650
Change Orders (net) |  |  |  |  | 23168
Final Contract Value |  |  |  |  | 1581818
Retainage (5%) |  |  |  |  | 79091
Net Paid to OWP |  |  |  |  | 1502727
B. PAY APPLICATION TIMELINE
App# | Date | Period Billing | Retention | Net This Period | Aggregate | % Complete
1 | 2015-02-19 | 48000 | 2400 | 45600 | 45600 | 2.883%
2 | 2015-04-20 | 20000 | 1000 | 19000 | 64600 | 4.084%
3 | 2015-05-19 | 10000 | 500 | 9500 | 74100 | 4.684%
4 | 2015-06-18 | 36075 | 1803.75 | 34271.25 | 108371.25 | 6.851%
5 | 2015-07-20 | 33220 | 1661 | 31559 | 139930.25 | 8.846%
6 | 2015-08-20 | 58580 | 2929 | 55651 | 195581.25 | 12.36%
7 | 2015-09-18 | 117505 | 5875.25 | 111629.75 | 307211 | 19.42%
8 | 2015-10-20 | 268030 | 13401.5 | 254628.5 | 561839.5 | 35.52%
9 | 2015-11-16 | 288168 | 14408.4 | 273759.6 | 835599.1 | 52.83%
10 | 2015-12-16 | 139762 | 6988.1 | 132773.9 | 968373 | 61.22%
11 | 2016-01-20 | 223492 | 11174.6 | 212317.4 | 1180690.4 | 74.64%
12 | 2016-02-19 | 184576 | 9228.8 | 175347.2 | 1356037.6 | 85.73%
13 | 2016-03-18 | 59875 | 2993.75 | 56881.25 | 1412918.85 | 89.32%
14 | 2016-04-20 | 65863 | 3293.15 | 62569.85 | 1475488.7 | 93.28%
15 | 2016-05-20 | 24778 | 1238.9 | 23539.1 | 1499027.8 | 94.77%
16 | 2016-06-20 | 3409 | 170.45 | 3238.55 | 1502266.35 | 94.97%
17 | 2016-08-19 | 485 | 24.25 | 460.75 | 1502727.1 | 95%
C. BILLING ↔ JDR TIE-OUT
Metric | SOV | JDR | Δ | Status
Final Contract Value | 1581818 | 1581818 | 0 | TIES
Retainage | 79091 | 79091 | 0 | TIES
Direct Cost | 1133076.79 | 1133076.79 | 0 | TIES
SOURCES
Job #2021 — Exxel Pacific Admiral East Apartments • GC: Exxel Pacific, Inc. • 2600 SW Admiral Way, West Seattle
Canonical source: 2021 Job Detail Report.pdf (189 pages, OWP Sage Timberline export)
Cost codes parsed: 25
Unit count (182) confirmed by ADMIRAL TRIM - KELLER.xlsx SUMMATION:
• 171 Gerber 21-962 standard elongated toilets
• 11 Gerber 21-928 ADA elongated toilets
• 182 Delta 559LF-PP lav faucets (one per unit)
• 159 tub/shower + 21 shower-only = 180 bathing fixtures
• 138 kitchen faucets (44 fewer than units — studio/SRO variants)
Contract: Admiral Contract executed - OCR_d.pdf (Exxel Pacific GC)
Billing: ADMIRAL AGGREGATE BILLING.xlsx (17 pay apps Feb 2015 – Aug 2016) + 17 SOV files
Final contract $1,581,818 (original $1,558,650 + $23,168 COs)

## Insights
Key Insights — Job #2021 Exxel Pacific Admiral East Apartments
Narrative observations distilled from the full JDR analysis
MARGIN PROFILE | Net profit of $448,741 on $1,581,818 revenue = 28.4% gross margin. Direct cost $1,133,077 absorbs 71.6% of revenue.
VENDOR CONCENTRATION | Ferguson Enterprises, Inc. alone = $121,504 (28% of all AP) across 82 invoices. Total 21 AP vendors, $436,423 total AP spend.
CREW PROFILE | 40 workers for 19,800 hours = 495 avg hrs/worker. Top 3 workers logged 4,544 hrs combined (23% of all labor).
ROUGHIN DOMINANCE | Code 120 Roughin Labor = 11,448 hrs (58% of all labor) and $232,286 actual. Code 230 Finish Material = $202,740 — 18% of total direct cost.
BUDGET DELIVERY | Revised budget was $1,145,297; actual direct cost $1,133,077 → $12,221 variance (1.1% under revised budget).
CONTRACT GROWTH | Contract grew from $1,558,650 to $1,581,818 — net +$23,168 (1.5%). Retainage of $79,091 (5%) withheld until closeout.
BURDEN RATIO | Burden codes 995 + 998 = $213,083 on $429,423 labor base = 49.6%. In line with OWP's typical 48–50% labor burden.
PROJECT SCALE | 182 units · 891 fixtures · 19 months. Revenue/unit $8,691, hours/unit 108.8, profit/unit $2,466.
PRODUCTIVITY | Blended labor rate $21.69/hr. Revenue/hour $80. Profit/hour $23. 1,042 hrs/month burn rate.
FIXTURE DENSITY | 891 fixtures ÷ 182 units = 4.90 fixtures/unit. Material/fixture $476, labor/fixture $482.
BIGGEST QUESTION
How does this job's 28.4% margin compare across similar projects in the OWP portfolio, and what operational levers drove the result — estimating accuracy, vendor pricing, or labor productivity?
SOURCES
Job #2021 — Exxel Pacific Admiral East Apartments • GC: Exxel Pacific, Inc. • 2600 SW Admiral Way, West Seattle
Canonical source: 2021 Job Detail Report.pdf (189 pages, OWP Sage Timberline export)
Cost codes parsed: 25
Unit count (182) confirmed by ADMIRAL TRIM - KELLER.xlsx SUMMATION:
• 171 Gerber 21-962 standard elongated toilets
• 11 Gerber 21-928 ADA elongated toilets
• 182 Delta 559LF-PP lav faucets (one per unit)
• 159 tub/shower + 21 shower-only = 180 bathing fixtures
• 138 kitchen faucets (44 fewer than units — studio/SRO variants)
Contract: Admiral Contract executed - OCR_d.pdf (Exxel Pacific GC)
Billing: ADMIRAL AGGREGATE BILLING.xlsx (17 pay apps Feb 2015 – Aug 2016) + 17 SOV files
Final contract $1,581,818 (original $1,558,650 + $23,168 COs)

## Benchmark KPIs
Benchmark KPIs
Normalized metrics designed for apples-to-apples comparison across all OWP projects
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2021 | Profile | OWP job ID | Verified | Benchmark KPIs / Metric Registry — see source tabs
Job Name | job_name | Exxel Pacific Admiral East Apartments | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
General Contractor | general_contractor | Exxel Pacific, Inc. | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Location | location | Seattle, WA (2600 SW Admiral Way, West Seattle) | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Project Type | project_type | 5-story 182-unit multifamily apartments + retail/garage | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Duration (months) | duration_months | 19 | Profile | Feb 2015 – Aug 2016 (~19 months) | Verified | Benchmark KPIs / Metric Registry — see source tabs
Unit Count | unit_count | 182 | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total Fixtures | total_fixtures | 891 | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Fixtures per Unit | fixtures_per_unit | 4.8956 | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Contract Value (Orig) | contract_original | 1558650 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Contract Value (Final) | contract_final | 1581818 | Financial | After change orders | Verified | Benchmark KPIs / Metric Registry — see source tabs
Change Orders ($) | change_orders | 23168 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue | revenue | 1581818 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Net Profit | net_profit | 448741.21 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Gross Margin | gross_margin | 0.28369 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Direct Cost | direct_cost | 1133076.79 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Labor Cost | labor_cost | 429422.78 | Labor | Sum of 10 labor codes | Verified | Benchmark KPIs / Metric Registry — see source tabs
Material Cost | material_cost | 423924.46 | Material | Sum of 9 material codes | Verified | Benchmark KPIs / Metric Registry — see source tabs
Overhead Cost | overhead_cost | 66646.5 | Financial | Sub+Eng+Permits | Verified | Benchmark KPIs / Metric Registry — see source tabs
Burden Cost | burden_cost | 213083.05 | Financial | Codes 995+998 | Verified | Benchmark KPIs / Metric Registry — see source tabs
Retainage | retainage | 79091 | Financial | 5% withheld | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Unit | revenue_per_unit | 8691.3077 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Profit per Unit | profit_per_unit | 2465.611 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Direct Cost per Unit | cost_per_unit | 6225.6966 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Labor Cost per Unit | labor_per_unit | 2359.4658 | Labor |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Material Cost per Unit | material_per_unit | 2329.2553 | Material |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Fixture | revenue_per_fixture | 1775.3288 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Profit per Fixture | profit_per_fixture | 503.6377 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Cost per Fixture | cost_per_fixture | 1271.6911 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Labor per Fixture | labor_per_fixture | 481.956 | Labor |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Material per Fixture | material_per_fixture | 475.785 | Material |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total Labor Hours | total_hours | 19799.5 | Labor | Sum of JDR cost code hours | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total Workers | total_workers | 40 | Labor | Unique payroll IDs | Verified | Benchmark KPIs / Metric Registry — see source tabs
Blended Gross Wage | blended_gross_wage | 2315% | Labor | Pre-burden | Verified | Benchmark KPIs / Metric Registry — see source tabs
Fully-Loaded Wage | fully_loaded_wage | 3245% | Labor | Post-burden | Verified | Benchmark KPIs / Metric Registry — see source tabs
Burden Multiplier | burden_multiplier | 1.4018 | Labor |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Hours per Unit | hours_per_unit | 108.7885 | Labor | Key benchmark | Verified | Benchmark KPIs / Metric Registry — see source tabs
Hours per Fixture | hours_per_fixture | 2222% | Labor | Key benchmark | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Hour | revenue_per_hour | 7989% | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Profit per Hour | profit_per_hour | 2266% | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Labor % of Revenue | labor_pct_revenue | 0.27147 | Cost Mix |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Material % of Revenue | material_pct_revenue | 0.268 | Cost Mix |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Month | revenue_per_month | 83253.5789 | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Hours per Month | hours_per_month | 1042.0789 | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Units per Month | units_per_month | 9.5789 | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total Vendors | total_vendors | 21 | Material | Unique AP vendors | Verified | Benchmark KPIs / Metric Registry — see source tabs
Top Vendor Spend | top_vendor_spend | 121504.28 | Material | Ferguson Enterprises, Inc. | Verified | Benchmark KPIs / Metric Registry — see source tabs
Top Vendor Concentration | top_vendor_pct | 0.27841 | Material |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total POs | total_pos | 177 | Material | Unique POs by filename | Verified | Benchmark KPIs / Metric Registry — see source tabs
Change Order % | co_pct | 0.014864 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Labor Hour | rev_per_labor_hr | 7989% | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
SOURCES
Job #2021 — Exxel Pacific Admiral East Apartments • GC: Exxel Pacific, Inc. • 2600 SW Admiral Way, West Seattle
Canonical source: 2021 Job Detail Report.pdf (189 pages, OWP Sage Timberline export)
Cost codes parsed: 25
Unit count (182) confirmed by ADMIRAL TRIM - KELLER.xlsx SUMMATION:
• 171 Gerber 21-962 standard elongated toilets
• 11 Gerber 21-928 ADA elongated toilets
• 182 Delta 559LF-PP lav faucets (one per unit)
• 159 tub/shower + 21 shower-only = 180 bathing fixtures
• 138 kitchen faucets (44 fewer than units — studio/SRO variants)
Contract: Admiral Contract executed - OCR_d.pdf (Exxel Pacific GC)
Billing: ADMIRAL AGGREGATE BILLING.xlsx (17 pay apps Feb 2015 – Aug 2016) + 17 SOV files
Final contract $1,581,818 (original $1,558,650 + $23,168 COs)
51 KPIs with snake_case data_name identifiers for database ingestion

## Change Log
Change Log — Master Register
Unified change-event ledger: RFIs, ASIs, COPs, COs, Backcharges, T&M (18 events)
Event ID | Type | Date | Subject | Originator | Linked Event(s) | Cost Impact ($) | Schedule (days) | Status | Source Document
COR-001 | COR | 2015-05-15 | 100% CD Set drawings coordination | Sub (OWP) |  | 56300 | 0 | Approved | 2021-Exxel, Admiral/Change Orders/COR_s/COR #01 100% CD Drawings.pdf
COR-002 | COR | 2015-07-17 | ASI-009 gas line to retail area | Sub (OWP) | ASI-009 | 7637 | 0 | Approved | 2021-Exxel, Admiral/Change Orders/COR_s/COR #02 ASI-009 Gas Line.pdf
CO-003 | CO | 2015-08-18 | Fiberfab shower unit substitution (21 units) per RFI-035 | GC (Exxel) | RFI-035 | 7118 | 0 | Signed | 2021-Exxel, Admiral/Change Orders/CO_s/Admiral CO #03 Fiberfab showers.pdf
COR-004 | COR | 2015-08-20 | Fiberfab shower units — pricing (21 units) | Sub (OWP) | RFI-035;CO-003 | 7118 | 0 | Approved | 2021-Exxel, Admiral/Change Orders/COR_s/COR #04 Fiberfab Showers.pdf
COR-005 | COR | 2015-09-10 | ASI-021 Fire bowl gas line | Sub (OWP) | ASI-021 | 1495 | 0 | Approved | 2021-Exxel, Admiral/Change Orders/COR_s/COR #05 ASI-021 Fire Bowl.pdf
CO-006 | CO | 2015-10-05 | Plumbing acoustics per RFI-036 (SSA Acoustic recommendations) | GC (Exxel) | RFI-036 | 3751 | 0 | Signed | 2021-Exxel, Admiral/Change Orders/CO_s/Admiral CO #06 Acoustics.pdf
CO-005 | CO | 2015-09-25 | Fixture revisions (RFI-051, 078, 098 — kitchen dimensions, fixture revisions) | GC (Exxel) | RFI-051;RFI-078;RFI-098 | 3200 | 0 | Signed | 2021-Exxel, Admiral/Change Orders/CO_s/Admiral CO #05 Fixture Revisions.pdf
COR-009 | COR | 2016-02-10 | Roof drain at Building C per RFI-122 | Sub (OWP) | RFI-122 | 2234 | 0 | Approved | 2021-Exxel, Admiral/Change Orders/COR_s/COR #09 RFI-122 Roof Drain.pdf
COR-011 | COR | 2016-05-15 | Roof drain change at Unit C512 per RFI-162 | Sub (OWP) | RFI-162 | 0 | 0 | Approved | 2021-Exxel, Admiral/Change Orders/COR_s/COR #11 RFI-162 C512 Roof Drain.pdf
TM-SEWER-BACKUP | T&M | 2016-09-07 | Sewer backup field incident — T&M response (1-day schedule impact) | Field (OWP) |  | 1971 | 1 | Invoiced | 2021-Exxel, Admiral/Invoices/ (sewer backup invoice Sept 2016)
RFI-004 | RFI | 2015 | Structural — beam holes | Sub |  | 0 | 0 | Closed | 2021-Exxel, Admiral/ASI-RFI/RFI-004
RFI-035 | RFI | 2015 | Fiberfab shower substitution (21 units) | Sub | CO-003 | 0 | 0 | Closed | 2021-Exxel, Admiral/ASI-RFI/RFI-035
RFI-036 | RFI | 2015 | SSA Acoustic recommendations | Sub | CO-006 | 0 | 0 | Closed | 2021-Exxel, Admiral/ASI-RFI/RFI-036
RFI-054 | RFI | 2015 | Domestic water routing conflict | Sub |  | 0 | 0 | Closed | 2021-Exxel, Admiral/ASI-RFI/RFI-054
RFI-122 | RFI | 2016 | Roof drain at Building C | Sub | COR-009 | 0 | 0 | Closed | 2021-Exxel, Admiral/ASI-RFI/RFI-122
RFI-162 | RFI | 2016 | Roof drain change Unit C512 | Sub | COR-011 | 0 | 0 | Closed | 2021-Exxel, Admiral/ASI-RFI/RFI-162
ADMIRAL-NORTH | Memo | 2015-2016 | Admiral North (Admiral 2) sister contract — 3 COs + 3 CORs totaling ~$13,157; partial docs only; RFI/ASI folder empty. | OWP |  | 13157 | 0 | Informational | 2021-Exxel, Admiral 2/Change Orders/
DOC-GAP-CO-DETAIL | Memo | 2016 | GAP: CO #7-#11 lack detailed cost/schedule extraction; budget transfer docs only partially reviewed; AEA-RFI series (32+ items) not fully indexed. | OWP |  | 0 | 0 | Open | 2021-Exxel, Admiral/Change Orders/
TOTAL | [5 empty] | 103981 | 1

## Root Cause Analysis
Root Cause Analysis — Change Driver Taxonomy
Categorized change events with responsible-party attribution — feeds bid-risk intelligence
CATEGORY ROLLUP
Root Cause Category | # Events | Net Cost Impact ($) | % of Events | Predominant Responsibility | Notes
Design substitution | 3 | 14236 | 16.67% | Designer | Fiberfab shower unit substitution (21 units) per RFI-035
Design clarification | 7 | 9185 | 38.89% | Designer | Plumbing acoustics per RFI-036 (SSA Acoustic recommendations
Owner directive | 2 | 9132 | 11.11% | Owner/GC | ASI-009 gas line to retail area
Coordination conflict | 2 | 0 | 11.11% | Mixed | Structural — beam holes
Scope gap | 1 | 56300 | 5.556% | Designer | 100% CD Set drawings coordination
Combined/multi-cause | 2 | 13157 | 11.11% | Mixed | Admiral North (Admiral 2) sister contract — 3 COs + 3 CORs t
TOTAL | 17 | 102010
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Events | Net $ Impact | Bid-Risk Signal
Designer | 11 | 79721 | POSITIVE — recoverable
Mixed | 5 | 15128 | POSITIVE — recoverable
Owner/GC | 2 | 9132 | POSITIVE — recoverable

## Predictive Signals
Predictive Signals — Leading Indicators
Forward-looking metrics that predict CO waves, schedule slips, and margin erosion
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Predictive Meaning
RFI Total (closed) | 32 | <50 for mid-size | INFO | Volume proxy for design doc quality
RFI Velocity (per month, derived) | See KPIs D50 | <3.0/wk | INFO | >3/wk = CO wave in 4-8 wks
RFI Avg Cycle Time (days) | Unknown | <14 | N/A | >30 avg signals schedule slip
ASI / OCD Count | 0 | <5 | HEALTHY | High ASI = owner scope churn
Backcharge Count | 0 | <3 | HEALTHY | BC clusters = coordination weakness
Change Order Count | 9 | <3 | ELEVATED | CO count signals scope definition
T&M Event Count | 1 | <2 | HEALTHY | T&M = directed work pipeline
Submittal resubmission count | 6 | <10 | HEALTHY | Repeats = coord issues incubating
Net $ Impact (all events) | 103981 | Near $0 | POSITIVE | Net recoverable vs absorbed
FORECAST MODELS (closed-project — actuals)
Forecast | Current Estimate | Confidence | Driver | Model Note
Projected final CO % of contract | 0.014864 | Actual | Closed project | CO$ / orig contract
Projected EAC (direct cost) | 1133076.79 | Actual | Closed project | Sum of L+M+OH+Burden
Projected final margin | 0.28369 | Actual | Closed project | (Rev - DC) / Rev
Composite risk score (0-100) | 20 | Medium | 0 BCs + 0 ASI/OCDs | Custom Cortex scoring

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence_level, and source_document — the machine-readable JCR index
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s) | Formula / Derivation
1 | job_number | Job Number | 2021 | id | Benchmark KPIs | Verified | JDR header | See Benchmark KPIs tab
2 | job_name | Job Name | Exxel Pacific Admiral East Apartments | text | Benchmark KPIs | Verified | Contract folder | See Benchmark KPIs tab
3 | general_contractor | General Contractor | Exxel Pacific, Inc. | text | Benchmark KPIs | Verified | Contract folder | See Benchmark KPIs tab
4 | location | Location | Seattle, WA (2600 SW Admiral Way, West Seattle) | text | Benchmark KPIs | Verified | Permit/Plans | See Benchmark KPIs tab
5 | project_type | Project Type | 5-story 182-unit multifamily apartments + retail/garage | text | Benchmark KPIs | Verified | Plans | See Benchmark KPIs tab
6 | duration_months | Duration (months) | 19 | months | Benchmark KPIs | Verified | First-to-last invoice | See Benchmark KPIs tab
7 | unit_count | Unit Count | 182 | units | Benchmark KPIs | Verified | Plumbing permit + P-tag list | See Benchmark KPIs tab
8 | total_fixtures | Total Fixtures | 891 | count | Benchmark KPIs | Verified | Permit detail | See Benchmark KPIs tab
9 | contract_original | Contract Original | 1558650 | USD | Benchmark KPIs | Verified | Contract SOV | See Benchmark KPIs tab
10 | contract_final | Contract Final | 1581818 | USD | Benchmark KPIs | Verified | Final billing SOV | See Benchmark KPIs tab
11 | change_orders | Change Orders ($) | 23168 | USD | Benchmark KPIs | Verified | JDR revised - original | See Benchmark KPIs tab
12 | revenue | Revenue | 1581818 | USD | Benchmark KPIs | Verified | Aggregate billing | See Benchmark KPIs tab
13 | net_profit | Net Profit | 448741.21 | USD | Benchmark KPIs | Verified | Revenue - Direct Cost | See Benchmark KPIs tab
14 | gross_margin | Gross Margin % | 0.28369 | % | Benchmark KPIs | Verified | Derived | See Benchmark KPIs tab
15 | direct_cost | Direct Cost | 1133076.79 | USD | Benchmark KPIs | Verified | JDR cost codes | See Benchmark KPIs tab
16 | labor_cost | Labor Cost | 429422.78 | USD | Benchmark KPIs | Verified | JDR labor codes | See Benchmark KPIs tab
17 | material_cost | Material Cost | 423924.46 | USD | Benchmark KPIs | Verified | JDR material codes | See Benchmark KPIs tab
18 | overhead_cost | Overhead Cost | 66646.5 | USD | Benchmark KPIs | Verified | JDR overhead codes | See Benchmark KPIs tab
19 | burden_cost | Burden Cost | 213083.05 | USD | Benchmark KPIs | Verified | JDR burden codes | See Benchmark KPIs tab
20 | retainage | Retainage | 79091 | USD | Benchmark KPIs | Verified | Aggregate billing row | See Benchmark KPIs tab
21 | total_hours | Total Labor Hours | 19799.5 | hours | Benchmark KPIs | Verified | JDR payroll | See Benchmark KPIs tab
22 | total_workers | Total Workers | 40 | count | Benchmark KPIs | Verified | JDR unique workers | See Benchmark KPIs tab
23 | blended_gross_wage | Blended Gross Wage | 2315% | USD/hr | Benchmark KPIs | Verified | Labor $ / Hours | See Benchmark KPIs tab
24 | total_vendors | Total Vendors | 21 | count | Benchmark KPIs | Verified | JDR AP unique | See Benchmark KPIs tab
25 | total_pos | Total POs | 177 | count | Benchmark KPIs | Verified | PO folder count | See Benchmark KPIs tab
26 | co_pct | CO % of Original | 0.014864 | % | Benchmark KPIs | Verified | Derived | See Benchmark KPIs tab
27 | rfi_total_count | RFIs Total | 32 | count | Predictive Signals | Verified | ASI-RFI folder count | See Predictive Signals tab
28 | asi_ocd_count | ASI + OCD Count | 0 | count | Change Log | Verified | ASI-RFI folder + Change Orders | See Change Log tab
29 | co_count_total | Change Order Count | 9 | count | Change Log | Verified | Change Orders folder | See Change Log tab
30 | backcharge_count | Backcharge Count | 0 | count | Change Log | Verified | Invoices/Backcharges | See Change Log tab
31 | tm_event_count | T&M Event Count | 1 | count | Change Log | Verified | Change Orders / JDR 038 | See Change Log tab
32 | submittal_resub_count | Submittal Resubmissions | 6 | count | Predictive Signals | Verified | Submittals folder | See Predictive Signals tab
33 | change_event_total | Total Tracked Events | 18 | count | Change Log | Verified | Change Log tab | See Change Log tab
34 | change_net_impact | Change Net $ Impact | 103981 | USD | Change Log | Verified | SUM H col | See Change Log tab

## Reconciliation
Reconciliation — Tie-out Proofs
Live cross-sheet formulas verify data consistency across all 17 tabs
Check | Computed | Expected | Δ | Status
A. JDR COST CODE ROLLUP
Labor subtotal (10 codes) | 429422.78 | 429422.78 | 0 | TIES
Material subtotal (9 codes) | 423924.46 | 423924.46 | 0 | TIES
Overhead subtotal (3 codes) | 66646.5 | 66646.5 | 0 | TIES
Burden subtotal (2 codes) | 213083.05 | 213083.05 | 0 | TIES
Direct Cost (all categories) | 1133076.79 | 1133076.79 | 0 | TIES
Revenue (code 999) | 1581818 | 1581818 | 0 | TIES
Net Profit (Revenue - Expenses) | 448741.21 | 448741.21 | 0 | TIES
B. LABOR HOURS ROLLUP
JDR Cost Code hours (Payroll Hours lines) | 19799.5 | 19799.5 | 0 | TIES
Per-worker hours (sum of PR Regular) | 20777.5 | 19799.5 | 978 | WITHIN
C. BILLING (SOV) ↔ JDR
Final Contract Value | 1581818 | 1581818 | 0 | TIES
Retainage | 79091 | 79091 | 0 | TIES
Direct Cost | 1133076.79 | 1133076.79 | 0 | TIES
D. VENDOR AP ↔ JDR
Vendor AP total (sum of invoices) | 436423.47 | 436423 | 0.47 | TIES
SOURCES
Job #2021 — Exxel Pacific Admiral East Apartments • GC: Exxel Pacific, Inc. • 2600 SW Admiral Way, West Seattle
Canonical source: 2021 Job Detail Report.pdf (189 pages, OWP Sage Timberline export)
Cost codes parsed: 25
Unit count (182) confirmed by ADMIRAL TRIM - KELLER.xlsx SUMMATION:
• 171 Gerber 21-962 standard elongated toilets
• 11 Gerber 21-928 ADA elongated toilets
• 182 Delta 559LF-PP lav faucets (one per unit)
• 159 tub/shower + 21 shower-only = 180 bathing fixtures
• 138 kitchen faucets (44 fewer than units — studio/SRO variants)
Contract: Admiral Contract executed - OCR_d.pdf (Exxel Pacific GC)
Billing: ADMIRAL AGGREGATE BILLING.xlsx (17 pay apps Feb 2015 – Aug 2016) + 17 SOV files
Final contract $1,581,818 (original $1,558,650 + $23,168 COs)
TIES = within $1 or 5 hrs • WITHIN = within 5% • OFF = investigate
K. CHANGE LOG ↔ ROOT CAUSE ANALYSIS
Total Event Count | 18 | 17 | 1 | TIES | 13↔14
Net $ Impact (all events) | 103981 | 102010 | 1971 | WITHIN | 13↔14
L. PREDICTIVE SIGNALS ↔ CHANGE LOG
Backcharge Count signal | 0 | 0 | 0 | TIES | 15↔13
M. METRIC REGISTRY ↔ BENCHMARK KPIs
revenue (row 17) | 1581818 | 1581818 | 0 | TIES | 16↔11
unit_count (row 12) | 182 | 182 | 0 | TIES | 16↔11
total_fixtures (row 13) | 891 | 891 | 0 | TIES | 16↔11
direct_cost (row 19) | 0.28369 | 1133076.79 | -1133076.5063 | OFF | 16↔11
total_pos (row 30) | 177 | 177 | 0 | TIES | 16↔11
N. CHANGE LOG ↔ METRIC REGISTRY (event counts)
change_event_total | 1 | 18 | -17 | OFF | 16↔13
SOURCES
Job #2021 — Cortex v2 17-tab layout
12 analytical tabs + Change Log + Root Cause Analysis + Predictive Signals + Metric Registry + Reconciliation
Canonical source: 2021 Job Detail Report.pdf (Sage Timberline export)
Change artifacts: folders scanned — ASI-RFI, Change Orders, Submittals, Invoices (Backcharges), JDR cost codes
Every Change Log row cites its source document path
TIES = within $1/5hrs/exact count • WITHIN = within 5% • OFF = investigate
Cross-sheet formulas (='Tab'!Cell) update automatically when source tabs change
Tabs: 1-12 analytical • 13=ChangeLog • 14=RootCause • 15=PredictiveSignals • 16=MetricRegistry • 17=Reconciliation

## Vendors
Vendor Detail — Job #2021
Vendors | 21 |  | Top vendor | Ferguson Enterprises, Inc.
Invoices | 280 |  | Top 3 share | 67.92%
Total AP | 436423.47 |  | Source | 2021 Job Detail Report.pdf (Sage Timberline AP export)
Avg Inv | 1558.6553
Rank | Vendor | Vendor Code | Invoices | Total Spend | % of AP | Avg / Invoice
1 | Ferguson Enterprises, Inc. |  | 82 | 121504.28 | 27.84% | 1481.7595
2 | Rosen Supply Company |  | 77 | 98623.69 | 22.6% | 1280.8271
3 | Keller Supply Company |  | 52 | 76284.33 | 17.48% | 1467.0063
4 | Franklin Engineering |  | 8 | 53259.5 | 12.2% | 6657.4375
5 | Mechanical Sales, Inc. |  | 3 | 34858.54 | 7.987% | 11619.5133
6 | Specification Sales, Inc. |  | 2 | 21294 | 4.879% | 10647
7 | Bank of America CC |  | 5 | 8886 | 2.036% | 1777.2
8 | Core & Main LP |  | 6 | 4652.03 | 1.066% | 775.3383
9 | Scan2Core, Inc. |  | 5 | 4401 | 1.008% | 880.2
10 | Quality Concrete Products, Inc. |  | 4 | 3386 | 0.7759% | 846.5
11 | Manor Hardware & Construction Supply |  | 4 | 1442.8 | 0.3306% | 360.7
12 | Capital One Credit Card |  | 5 | 1311.2 | 0.3004% | 262.24
13 | Rosen Supply Kirkland |  | 3 | 1290.12 | 0.2956% | 430.04
14 | Consolidated Supply Co. |  | 4 | 1260.54 | 0.2888% | 315.135
15 | C.M. Hoskins Company |  | 3 | 891.82 | 0.2043% | 297.2733
16 | ACME Corp |  | 3 | 759.6 | 0.1741% | 253.2
17 | Ferguson Enterprises, Inc. #3007 |  | 4 | 725.12 | 0.1662% | 181.28
18 | Kele, Inc |  | 2 | 713.58 | 0.1635% | 356.79
19 | Beacon Building Products |  | 2 | 576.57 | 0.1321% | 288.285
20 | Rosen Supply Company, Inc. |  | 5 | 202.75 | 0.04646% | 40.55
21 | A.R. Brown Backflow Testing |  | 1 | 100 | 0.02291% | 100
| TOTAL |  | 280 | 436423.47 | 100% | 1558.6553