## Overview
[CORTEX_V2.1] Job #2001 — · Overview
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| OVERVIEW |  | SOURCE
IDENTITY
| Project Job Number | 2001
| Project Name: | SRM 230 Broadway Apartments
CONTRACT & PARTIES
| General Contractor | SRM Development
JOB SITE
| Jobsite Location | 230 Broadway, Seattle, WA 98102
| Residential Units | 282 | Lavatories
SCHEDULE
| Work Period | 18 mo
| Project Duration | Apr 2011 – Sep 2012 (~18 months)
SCOPE & DESIGN
| Total Fixtures | 1315 | Floors
| Kitchen Sinks | 234 | Tubs/Showers
| Shower Stalls | 12 | Roof Drains
| CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
| $1,850,270 |  | $843,657 |  | $1,278,216 |  | 44,632
| Original $1,850,270 |  | 39.8% margin |  | 60.2% of revenue |  | 38 workers
COST BREAKDOWN
| Category | Budget | Actual | Variance | % Budget | % of Cost
| Labor | 396328 | 425500.68 | -29172.68 | 107.4% | 33.29%
| Material | 682792 | 627306.08 | 55485.92 | 91.87% | 49.08%
| Overhead | 11000 | 7343.82 | 3656.18 | 66.76% | 0.5745%
| Burden | 201813.34 | 218065.83 | -16252.49 | 108.1% | 17.06%
| TOTAL | 1291933.34 | 1278216.41 | 13716.93 | 98.94% | 100%
PROJECT PROFILE
| Plumbing Units | 282 |  | Total Fixtures | 1315 |  | Fixtures / Unit | 4.66
| Kitchen Sinks | 234 |  | Duration | 18 mo

## Budget vs Actual
[CORTEX_V2.1] Job #2001 — · Budget vs Actual
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| cost_code | description | original_budget | revised_budget | actual | variance | pct_used | hours | source
LABOR
| 011 | DS & RD Labor | 33300 | 33300 | 21823.68 | 11476.32 | 65.54%
| 100 | Supervision | 11000 | 11000 | 4198.3 | 6801.7 | 38.17%
| 101 | Takeoff & Purchase Labor | 11000 | 11000 | 1227.8 | 9772.2 | 11.16%
| 110 | Underground Labor | 6500 | 6500 | 5128.27 | 1371.73 | 78.9%
| 111 | Garage Labor | 37860 | 37860 | 51832.47 | -13972.47 | 1.369%
| 112 | Canout Labor | 12751 | 12751 | 9995.05 | 2755.95 | 78.39%
| 113 | Foundation Drain Labor | 9000 | 9000 | 3190.16 | 5809.84 | 35.45%
| 120 | Roughin Labor | 185705 | 185705 | 218574.15 | -32869.15 | 1.177%
| 130 | Finish Labor | 37212 | 37212 | 46024.72 | -8812.72 | 1.237%
| 140 | Gas Labor | 9450 | 9450 | 14211.67 | -4761.67 | 1.504%
| 141 | Water Main/Insulation Lab | 36300 | 36300 | 36651.38 | -351.38 | 1.01%
| 142 | Mech Room Labor | 6250 | 6250 | 12626.53 | -6376.53 | 2.02%
| 145 | Tub/Shower Labor | 0 | 0 | 16.5 | -16.5 | 0%
MATERIAL
| 039 | DS & RD Material | 34350 | 34350 | 10684.8 | 23665.2 | 31.11%
| 210 | Underground Material | 5400 | 5400 | 6150.1 | -750.1 | 1.139%
| 211 | Garage Material | 35055 | 35055 | 36037.82 | -982.82 | 1.028%
| 212 | Canout Material | 19308 | 19308 | 16844.65 | 2463.35 | 87.24%
| 213 | Foundation Material | 10000 | 10000 | 3564.14 | 6435.86 | 35.64%
| 220 | Roughin Material | 197530 | 197530 | 148282.22 | 49247.78 | 75.07%
| 230 | Finish Material | 372749 | 372749 | 327741.23 | 45007.77 | 87.93%
| 240 | Gas Material | 7500 | 7500 | 10163.67 | -2663.67 | 1.355%
| 241 | Water Main/Insulation Mat | 30250 | 30250 | 75553.36 | -45303.36 | 2.498%
| 242 | Mech Room Material | 5000 | 5000 | 2968.89 | 2031.11 | 59.38%
OVERHEAD
| 600 | Subcontractor | 5500 | 5500 | 5407 | 93 | 98.31%
| 601 | Engineering/Plans | 5500 | 5500 | 1835.26 | 3664.74 | 33.37%
| 603 | Permits & Licenses | 0 | 0 | 101.56 | -101.56 | 0%
BURDEN
| 995 | Payroll Burden | 170039.6 | 170039.6 | 183056.2 | -13016.6 | 1.077%
| 998 | Payroll Taxes | 31773.74 | 31773.74 | 35009.63 | -3235.89 | 1.102%
SOURCES
Job #2001 — SRM 230 Broadway Apartments • GC: SRM Development • 230 Broadway, Seattle
Canonical source: 2001 Job Detail Report.pdf (180 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count (282) from plumbing bid sheet: 270 standard units + 12 ADA units
Fixture count (1315) from material takeoff: 285 WC + 285 lav + 234 kitchen sink + 234 DW + 265 tub + 12 shower + additional drains
Contract: One Way Plumbing contract executed (SRM Development GC) with OWP markup
Billing: 230 BROADWAY AGGREGATE BILLING.xls (18 pay apps Apr 2011 – Sep 2012) + 17 SOV files
Final contract $2,121,874 (original $1,850,270 + $0 COs)
| TOTAL |  | 1326283.34 | 1326283.34 | 1288901.21 | 37382.13 |  | 0

## Cost Breakdown
[CORTEX_V2.1] Job #2001 — · Cost Breakdown
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| category | cost_codes | actual | pct_of_direct_cost | pct_of_revenue | per_unit | source
| Labor | 13 | 396328 | 1.074% |  | 1508.8677
| Material | 10 | 717142 | 88.96% |  | 2262.379
| Overhead | 3 | 11000 | 66.76% |  | 26.0419
| Burden | 2 | 201813.34 | 1.081% |  | 773.2831
B. LARGEST OVERRUNS (Actual > Revised Budget)
| Code | Description
| 241 | Water Main/Insulation Mat | 30250 | 1.498%
| 120 | Roughin Labor | 185705 | 17.7%
| 111 | Garage Labor | 37860 | 36.91%
| 995 | Payroll Burden | 170039.6 | 7.655%
| 130 | Finish Labor | 37212 | 23.68%
| 142 | Mech Room Labor | 6250 | 1.02%
| 140 | Gas Labor | 9450 | 50.39%
| 998 | Payroll Taxes | 31773.74 | 10.18%
| 240 | Gas Material | 7500 | 35.52%
| 211 | Garage Material | 35055 | 2.804%
C. LARGEST SAVINGS (Actual < Revised Budget)
| Code | Description
| 220 | Roughin Material | 197530 | 24.93%
| 230 | Finish Material | 372749 | 12.07%
| 039 | DS & RD Material | 34350 | 68.89%
| 011 | DS & RD Labor | 33300 | 34.46%
| 101 | Takeoff & Purchase Labor | 11000 | 88.84%
| 100 | Supervision | 11000 | 61.83%
| 213 | Foundation Material | 10000 | 64.36%
| 113 | Foundation Drain Labor | 9000 | 64.55%
| 601 | Engineering/Plans | 5500 | 66.63%
| 112 | Canout Labor | 12751 | 21.61%
SOURCES
Job #2001 — SRM 230 Broadway Apartments • GC: SRM Development • 230 Broadway, Seattle
Canonical source: 2001 Job Detail Report.pdf (180 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count (282) from plumbing bid sheet: 270 standard units + 12 ADA units
Fixture count (1315) from material takeoff: 285 WC + 285 lav + 234 kitchen sink + 234 DW + 265 tub + 12 shower + additional drains
Contract: One Way Plumbing contract executed (SRM Development GC) with OWP markup
Billing: 230 BROADWAY AGGREGATE BILLING.xls (18 pay apps Apr 2011 – Sep 2012) + 17 SOV files
Final contract $2,121,874 (original $1,850,270 + $0 COs)
| TOTAL |  | 2574558.68 |  |  | 4570.5717

## Material
[CORTEX_V2.1] Job #2001 — · Material
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| vendor_id | vendor_name | total_spend | transactions | category | source
| 039 | DS & RD Material | 34350 |  | 0.016748
| 210 | Underground Material | 5400 |  | 0.0096398
| 211 | Garage Material | 35055 |  | 0.056486
| 212 | Canout Material | 19308 |  | 0.026403
| 213 | Foundation Material | 10000 |  | 0.0055865
| 220 | Roughin Material | 197530 |  | 0.23242
| 230 | Finish Material | 372749 |  | 0.51371
| 240 | Gas Material | 7500 |  | 0.015931
| 241 | Water Main/Insulation Mat | 30250 |  | 0.11842
| 242 | Mech Room Material | 5000 |  | 0.0046535
B. VENDORS BY SPEND (AP)
| Vendor | # Invoices
| Ferguson Enterprises, Inc. | 210 | 343362.11
| Keller Supply Company | 161 | 261501.21
| Mechanical Sales, Inc. | 7 | 72801.65
| Franklin Engineering | 5 | 21978.91
| Bank of America CC | 5 | 15099.99
| Quality Concrete Products, Inc. | 2 | 7788
| Evergreen Concrete Cutting, Inc. | 7 | 4140
| Ferguson Enterprises, Inc. #3007 | 7 | 4097.84
| MP Industrial | 3 | 2339.19
| C.M. Hoskins Company | 8 | 2018.25
| Herc Rentals, Inc. | 6 | 1835.26
| MAD Concrete Cutting & Coring, Inc. | 3 | 1040
| Fastenal Company | 3 | 520.48
| DRSi | 4 | 468.55
| R.A. Brown Backflow Testing | 1 | 227
| Airgas USA, LLC | 1 | 90.46
SOURCES
Job #2001 — SRM 230 Broadway Apartments • GC: SRM Development • 230 Broadway, Seattle
Canonical source: 2001 Job Detail Report.pdf (180 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count (282) from plumbing bid sheet: 270 standard units + 12 ADA units
Fixture count (1315) from material takeoff: 285 WC + 285 lav + 234 kitchen sink + 234 DW + 265 tub + 12 shower + additional drains
Contract: One Way Plumbing contract executed (SRM Development GC) with OWP markup
Billing: 230 BROADWAY AGGREGATE BILLING.xls (18 pay apps Apr 2011 – Sep 2012) + 17 SOV files
Final contract $2,121,874 (original $1,850,270 + $0 COs)
Vendor AP ties to JDR 'by Source: AP' line (739,308.90)

## Crew & Labor
[CORTEX_V2.1] Job #2001 — · Crew & Labor
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| worker_id | worker_name | total_hours | gross_pay | blended_wage_per_hr | tier | work_days | source
| Hubbard, Robert W |  | 2221 | 69758.1 | 31.4084 | Senior
| McCabe, Thomas C |  | 1824.5 | 23718.5 | 13 | Apprentice
| Sepulveda Gonzalez, Alfredo |  | 1720.5 | 37851 | 22 | Mid
| Barnhart, Joseph N |  | 1558 | 38797.2 | 24.9019 | Mid
| Ross, Kelli M |  | 1451 | 38117.77 | 26.27 | Mid
| Hubbard, Dustin R |  | 1338.5 | 13479.5 | 10.0706 | Apprentice
| Palma Vides, Hugo |  | 1338 | 33450 | 25 | Mid
| Reed, Reuben H |  | 1302 | 32550 | 25 | Mid
| Quintanilla, Esteban R |  | 1231.5 | 35713.5 | 29 | Mid
| Sanders, Allen O |  | 1170.5 | 28092 | 24 | Mid
| Castro Hernandez, Carlos E |  | 1157.5 | 24926 | 21.5343 | Mid
| Mazil, Antonio |  | 884.75 | 10617 | 12 | Apprentice
| Cortes Mendiola, Victor H |  | 778.5 | 14791.5 | 19 | Mid
| Gerard, Jeffrey S |  | 733 | 23119.4 | 31.5408 | Senior
| Soto Cruz, Jovani |  | 629 | 6290 | 10 | Apprentice
| Meza Fuentes, Erick A |  | 619.5 | 7763.75 | 12.5323 | Apprentice
| Veley, Nathaniel S |  | 486 | 9112.75 | 18.7505 | Mid
| Slaton, Justin T |  | 411 | 4110 | 10 | Apprentice
| Bravo, Manuel D |  | 288 | 2880 | 10 | Apprentice
| Paco Leyva, Orlando |  | 262 | 2621.5 | 10.0057 | Apprentice
| Arreola, Israel A |  | 248 | 2480 | 10 | Apprentice
| Gerard, Jordan E |  | 220.25 | 2202.5 | 10 | Apprentice
| Waites, Thaddeus Z |  | 182 | 4368 | 24 | Mid
| Michelman, Joshua M |  | 172.5 | 1725 | 10 | Apprentice
| Morelos, Silverio |  | 53 | 1510.02 | 28.4909 | Mid
| Outson, Tyler C |  | 27.5 | 275 | 10 | Apprentice
| Rivera Romera, Arturo |  | 8 | 96 | 12 | Apprentice
| TOTAL (27 workers) |  | 22316 | 470415.99 | 21.0798
SOURCES
Job #2001 — SRM 230 Broadway Apartments • GC: SRM Development • 230 Broadway, Seattle
Canonical source: 2001 Job Detail Report.pdf (180 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count (282) from plumbing bid sheet: 270 standard units + 12 ADA units
Fixture count (1315) from material takeoff: 285 WC + 285 lav + 234 kitchen sink + 234 DW + 265 tub + 12 shower + additional drains
Contract: One Way Plumbing contract executed (SRM Development GC) with OWP markup
Billing: 230 BROADWAY AGGREGATE BILLING.xls (18 pay apps Apr 2011 – Sep 2012) + 17 SOV files
Final contract $2,121,874 (original $1,850,270 + $0 COs)
Tier: Apprentice <$18/hr, Mid $18–30, Senior >$30

## Crew Analytics
[CORTEX_V2.1] Job #2001 — · Crew Analytics
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| tier | worker_count | hours | gross_pay | pct_of_hours | blended_wage
| Senior | 2 | 2954 | 92877.5 | 13.24%
| Mid | 12 | 12428.5 | 299279.74 | 55.69%
| Apprentice | 13 | 6933.5 | 78258.75 | 31.07%
B. WAGE STATISTICS
| Blended Gross Wage | 21.0798
| Fully-Loaded Wage | 28.8388
| Burden Multiplier | 1.3681
| Min Worker Rate | 10
| Max Worker Rate | 31.5408
| Avg Hours / Worker | 826.5185
SOURCES
Job #2001 — SRM 230 Broadway Apartments • GC: SRM Development • 230 Broadway, Seattle
Canonical source: 2001 Job Detail Report.pdf (180 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count (282) from plumbing bid sheet: 270 standard units + 12 ADA units
Fixture count (1315) from material takeoff: 285 WC + 285 lav + 234 kitchen sink + 234 DW + 265 tub + 12 shower + additional drains
Contract: One Way Plumbing contract executed (SRM Development GC) with OWP markup
Billing: 230 BROADWAY AGGREGATE BILLING.xls (18 pay apps Apr 2011 – Sep 2012) + 17 SOV files
Final contract $2,121,874 (original $1,850,270 + $0 COs)

## Productivity
[CORTEX_V2.1] Job #2001 — · Productivity
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| phase | labor_code | hours | pct_of_total | hours_per_unit
| DS & RD | 011 | 928 | 4.576% | 3.2908
| Supervision | 100 | 130.5 | 0.6435% | 0.46277
| Takeoff & Purchasing | 101 | 39 | 0.1923% | 0.1383
| Underground | 110 | 203 | 1.001% | 0.71986
| Garage | 111 | 2258 | 11.13% | 8.0071
| Canout | 112 | 404 | 1.992% | 1.4326
| Foundation Drain | 113 | 130.5 | 0.6435% | 0.46277
| Roughin | 120 | 10499.75 | 51.78% | 37.2332
| Finish | 130 | 2361.25 | 11.64% | 8.3732
| Gas | 140 | 650 | 3.205% | 2.305
| Water Main / Insulation | 141 | 1968.5 | 9.707% | 6.9805
| Mech Room | 142 | 705.5 | 3.479% | 2.5018
| Tub / Shower | 145 | 1.5 | 0.007397% | 0.0053191
B. PRODUCTIVITY RATIOS
| Metric | Value
| Hours / Unit | 71.9131
| Hours / Fixture | 15.4217
| Revenue / Hour | 104.6315
| Profit / Hour | 41.0746
| Units / Month | 15.6667
| Fixtures / Month | 73.0556
| Hours / Month | 1126.6389
| Revenue / Month | 117881.8611
SOURCES
Job #2001 — SRM 230 Broadway Apartments • GC: SRM Development • 230 Broadway, Seattle
Canonical source: 2001 Job Detail Report.pdf (180 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count (282) from plumbing bid sheet: 270 standard units + 12 ADA units
Fixture count (1315) from material takeoff: 285 WC + 285 lav + 234 kitchen sink + 234 DW + 265 tub + 12 shower + additional drains
Contract: One Way Plumbing contract executed (SRM Development GC) with OWP markup
Billing: 230 BROADWAY AGGREGATE BILLING.xls (18 pay apps Apr 2011 – Sep 2012) + 17 SOV files
Final contract $2,121,874 (original $1,850,270 + $0 COs)

## PO Commitments
[CORTEX_V2.1] Job #2001 — · PO Commitments
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| po_number | date | issuer | type | status | description | amount | source
B. COMMITMENTS BY VENDOR
| Vendor |  |  |  |  | PO Count
C. PO COVERAGE NOTES
Total Material Actual (JDR)
Unique PO Count
(Dollar PO commitment not extracted — requires per-PDF parse)
SOURCES
Job #2001 — SRM 230 Broadway Apartments • GC: SRM Development • 230 Broadway, Seattle
Canonical source: 2001 Job Detail Report.pdf (180 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count (282) from plumbing bid sheet: 270 standard units + 12 ADA units
Fixture count (1315) from material takeoff: 285 WC + 285 lav + 234 kitchen sink + 234 DW + 265 tub + 12 shower + additional drains
Contract: One Way Plumbing contract executed (SRM Development GC) with OWP markup
Billing: 230 BROADWAY AGGREGATE BILLING.xls (18 pay apps Apr 2011 – Sep 2012) + 17 SOV files
Final contract $2,121,874 (original $1,850,270 + $0 COs)
PO count is deduplicated by 5-digit PO number extracted from filenames
Vendor/code classification is heuristic (filename keyword match)

## Billing & SOV
[CORTEX_V2.1] Job #2001 — · Billing & SOV
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| pay_app_number | date | contract_total | this_period | retainage | stored_materials | cumulative | pct_complete | source

## Insights
[CORTEX_V2.1] Job #2001 — · Insights
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| insight_id | title | finding | verified | source
| 1 | Labor overran budget by 7.4% | Total labor actual $425,501 vs budget $396,328 — $29,173 unfavorable variance. Review crew mix and productivity. | Derived | budget_vs_actual
| 2 | Largest variance — cost code 220 (Roughin Material) under by $49,248 | Budget $197,530, actual $148,282 (-24.9%). Flag for bid calibration. | Derived | budget_vs_actual

## Benchmark KPIs
[CORTEX_V2.1] Job #2001 — · Benchmark KPIs
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
CROSS-PROJECT BENCHMARK SCORECARD
Normalized metrics designed for apples-to-apples comparison across all OWP projects.
| KPI | DATA NAME | VALUE | CATEGORY | NOTES / BENCHMARK CONTEXT
| Job Number | job_number | 2,001 | Profile | OWP Sage job ID
| General Contractor | general_contractor | SRM Development | Profile | Customer of record
| location | location | 230 Broadway, Seattle, WA 98102 | Profile | Project address
| Project Type | project_type | Apartment building | Profile | Building category for benchmarking
| Duration Months | duration_months | 18.0% | Profile | Calendar months from start to close
| Plumbing Units | plumbing_units | 282 | Profile | Residential units delivered
| Total Fixtures | total_fixtures | 1,315 | Profile | Plumbing fixture count
| Fixtures Per Unit | fixtures_per_unit | $4.66 | Profile | ≈6 fixtures/unit typical for multifamily
| Contract Original | contract_original | $1,850,270 | Financial | Original contract value
| Contract Final | contract_final | $1,850,270 | Financial | Revised contract value (post-COs)
| Change Orders Net | change_orders_net | 0 | Financial | Net dollar change from COs
| revenue | revenue | $2,121,874 | Financial | Net billed (AR net of reversals)
| Net Profit | net_profit | $843,657 | Financial | Revenue − direct cost
| Gross Margin Pct | gross_margin_pct | 39.8% | Financial | Net profit / revenue
| Direct Cost | direct_cost | $1,278,216 | Financial | Σ labor + material + OH + burden + tax
| Overhead Cost | overhead_cost | $7,344 | Financial | Codes 600, 601, 603, 607
| Burden Cost | burden_cost | $183,056 | Financial | Code 995 payroll burden
| Retainage Outstanding | retainage_outstanding | $0.00 | Financial | Held by GC until closeout
| Revenue Per Unit | revenue_per_unit | $7,524 | Financial | Top-line per unit
| Profit Per Unit | profit_per_unit | $2,992 | Financial | Net profit normalized per residential unit
| Cost Per Unit | cost_per_unit | $4,533 | Financial | Total direct cost per unit
| Revenue Per Fixture | revenue_per_fixture | $1,614 | Financial | Top-line per fixture
| Profit Per Fixture | profit_per_fixture | $642 | Financial | Net profit per fixture installed
| Cost Per Fixture | cost_per_fixture | $972 | Financial | Total direct cost per fixture
| Labor Cost | labor_cost | $425,501 | Labor | Codes 100–150
| Total Hours | total_hours | 44,632 | Labor | All payroll hours on the job
| Total Workers | total_workers | 38 | Crew | Unique payroll IDs across job
| Blended Wage | blended_wage | $21.08 | Labor | Pre-burden average
| Fully Loaded Wage | fully_loaded_wage | $14.42 | Labor | Post-burden true cost
| Burden Multiplier | burden_multiplier | 0.68 | Labor | Loaded / gross
| Hours Per Unit | hours_per_unit | $0.00 | Labor | Key plumbing benchmark
| Hours Per Fixture | hours_per_fixture | $0.00 | Labor | Industry std for plumbing subs
| Labor Per Unit | labor_per_unit | $1,509 | Labor | Payroll only, not material
| Labor Per Fixture | labor_per_fixture | $324 | Labor | Payroll only, not material
| Labor Pct Revenue | labor_pct_revenue | 0.20 | Cost Mix | Payroll exposure
| Material Cost | material_cost | $627,306 | Material | Codes 210–244
| Material Per Unit | material_per_unit | $2,224 | Material | Cross-project benchmark
| Material Per Fixture | material_per_fixture | $477 | Material | Cross-project benchmark
| Material Pct Revenue | material_pct_revenue | 0.30 | Cost Mix | Material/sub exposure
| Total Vendors | total_vendors | 17 | Material | Distinct AP vendors invoiced on the job
| Top Vendor Spend | top_vendor_spend | $0.00 | Material | Largest single supplier
| Top Vendor Pct | top_vendor_pct | 0.0% | Material | Top vendor concentration
| Revenue Per Month | revenue_per_month | $117,882 | Throughput | Billing velocity
| Hours Per Month | hours_per_month | $0.00 | Throughput | Avg monthly labor burn
| Units Per Month | units_per_month | $15.67 | Throughput | Build pace
| Fixtures Per Month | fixtures_per_month | $73.06 | Throughput | Fixture install velocity
SOURCES
Canonical: /sessions/keen-determined-mccarthy/mnt/cortex-mockup/owp/cortex v2 files/OWP_2001_JCR_Cortex_v2.xlsx
revenue: AR net-of-reversals (validator)
labor_cost: Codes 100–150
material_cost: Codes 210–244
total_workers: count(distinct worker_id)

## Change Log
[CORTEX_V2.1] Job #2001 — · Change Log
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| event_id | type | date | subject | originator | linked_events | cost_impact | schedule_days | status | source_document
| ASI-023 | ASI | 2012-01-26 | Fireplace ventilation — intake/exhaust vent locations + steel fireplace surround (L1/P1 lobbies) | Runberg Architecture (Frances Nelson) | AS-68A, B | 0 | 0 | No-cost directive | 2001-SRM-230 BROADWAY/2001 230Broadway/ASI _23 - fireplace ventilation B230.pdf
| ASI-024 | ASI | 2012-01-31 | Deck partitions + column removal at L3 & L4 | Runberg Architecture (Frances Nelson) | AS-72A-E | 0 | 0 | No-cost directive | 2001-SRM-230 BROADWAY/2001 230Broadway/ASI _24 - L3&L4deck partitions B230.pdf
| ASI-027 | ASI | 2012-02-02 | Roof deck redesign — framing coordination + gas fixture layout (Owner-requested) | Runberg Architecture (Michele Wang) | AS-74; ASI-029, 030, 033 | 0 | 0 | No-cost directive | 2001-SRM-230 BROADWAY/2001 230Broadway/ASI _27 - Roof Deck Redesign - framing info onlyB230.pdf
| ASI-029 | ASI | 2012-02-15 | Dog run details on roof deck — fencing, drainage, irrigation, waterproofing | Runberg Architecture (Michele Wang) | AS-77a-d, WPS-03 | 0 | 0 | No-cost directive | 2001-SRM-230 BROADWAY/2001 230Broadway/ASI _29 - Dog run details.pdf
| ASI-030 | ASI | 2012-02-13 | Paver layout changes for VE options on roof deck | Runberg Architecture (Michele Wang) | L1.0, L1.01 | 0 | 0 | No-cost / VE | 2001-SRM-230 BROADWAY/2001 230Broadway/ASI _30 - Pavers VE.pdf
| ASI-031 | ASI | 2012-02-20 | West trash room coiling door width increase to 15 ft (P165) | Runberg Architecture (Michele Wang) | AS-78 | 0 | 0 | No-cost directive | 2001-SRM-230 BROADWAY/2001 230Broadway/ASI _31 - enlarge west trash room door.pdf
| ASI-033 | ASI | 2012-02-20 | Roof deck planting layout changes (Owner) | Runberg Architecture (Michele Wang) | L2.1; ASI-027, 029 | 0 | 0 | No-cost directive | 2001-SRM-230 BROADWAY/2001 230Broadway/ASI _33 - Roof Deck PLANTING.pdf
| CO-004 | CO | 2012-01-25 | CO #4 referenced in Pay App #10 (cost embedded in binary .xls) | SRM |  | 0 | 0 | Billed | 2001-SRM-230 BROADWAY/SRM-230 BROADWAY/230 B Billing/230 Broadway OWP #10 1-25-12 co4.xls
| CO-007 | CO | 2012-07-25 | CO #7 referenced in Pay App #16 (cost embedded in binary .xls) | SRM |  | 0 | 0 | Billed | 2001-SRM-230 BROADWAY/SRM-230 BROADWAY/230 B Billing/230 Broadway OWP #16 7-25-12 co7.xls
| CO-008 | CO | 2012-08-25 | CO #8 referenced in Pay App #17 (cost embedded in binary .xls) | SRM |  | 0 | 0 | Billed | 2001-SRM-230 BROADWAY/SRM-230 BROADWAY/230 B Billing/230 Broadway OWP #17 8-25-12 co8.xls
| DOC-GAP-CO-LOG | Memo |  | GAP: No master CO register with detailed cost/schedule impact. CO4/7/8 only referenced in pay-app filenames; amounts embedded in legacy .xls files. | OWP |  | 0 | 0 | Open | 2001-SRM-230 BROADWAY/SRM-230 BROADWAY/230 B Billing/
| DOC-GAP-RFI | Memo |  | GAP: No standalone RFI log or submittal register found in directory; cycle metrics not computable. | OWP |  | 0 | 0 | Open | 2001-SRM-230 BROADWAY/ (no RFI folder)
| DOC-GAP-CONTRACT | Memo |  | GAP: Original vs final contract values embedded only in binary Excel files (SRM 230 contract price summary.xls, AGGREGATE_BILLING.xls); not in discoverable log. | OWP |  | 0 | 0 | Open | 2001-SRM-230 BROADWAY/SRM-230 BROADWAY/230 B Billing/230 BROADWAY AGGREGATE BILLING.xls

## Root Cause Analysis
[CORTEX_V2.1] Job #2001 — · Root Cause Analysis
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| rca_id | observation | root_cause | responsibility | cost_impact | mitigation | source

## Predictive Signals
[CORTEX_V2.1] Job #2001 — · Predictive Signals
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| signal_id | signal_name | direction | metric | threshold | historical_outcome | source
| WAREHOUSE | Predictive signals computed at warehouse layer | Neutral | cross-project benchmark | n/a | See benchmark_envelopes view; not stored per-project. | warehouse view (predictive_signals_v)

## Metric Registry
[CORTEX_V2.1] Job #2001 — · Metric Registry
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| metric_key | metric_label | value | data_label | tab_home | verification | source
2001
SRM 230 Broadway Apartments
SRM Development
230 Broadway, Seattle, WA 98102
282-unit 7-story multifamily apartments with retail and amenity spaces
18
282
1315
1850270
2121873.5
271603.5
2121873.5
832972.29
0.39256
1288901.21
425500.68
637990.88
7343.82
218065.83
96889.2
20279.5
27
23.1966
16
0
0.14679
0
7
3
0
0
0
13
0

## Reconciliation
[CORTEX_V2.1] Job #2001 — · Reconciliation
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| check_number | check_description | value_a | value_b | difference | status | tabs
A. JDR COST CODE ROLLUP
|  | Labor subtotal (13 codes) | 425500.68 |  |  | TIES
|  | Material subtotal (10 codes) | 637990.88 |  |  | TIES
|  | Overhead subtotal (3 codes) | 7343.82 |  |  | TIES
|  | Burden subtotal (2 codes) | 218065.83 |  |  | TIES
|  | Direct Cost (all categories) | 1288901.21 |  |  | TIES
|  | Revenue (code 999) | 2121873.5 |  |  | OFF
|  | Net Profit (Revenue - Expenses) | 832972.29 |  |  | OFF
B. LABOR HOURS ROLLUP
|  | JDR Cost Code hours (Payroll Hours lines) | 20279.5 |  |  | TIES
|  | Per-worker hours (sum of PR Regular) | 20279.5 |  |  | OFF
C. BILLING (SOV) ↔ JDR
|  | Final Contract Value | 2121874 |  |  | TIES
|  | Retainage | 96889 |  |  | TIES
|  | Direct Cost | 1288901 |  |  | TIES
D. VENDOR AP ↔ JDR
|  | Vendor AP total (sum of invoices) | 739309 |  |  | TIES
SOURCES
Job #2001 — SRM 230 Broadway Apartments • GC: SRM Development • 230 Broadway, Seattle
Canonical source: 2001 Job Detail Report.pdf (180 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count (282) from plumbing bid sheet: 270 standard units + 12 ADA units
Fixture count (1315) from material takeoff: 285 WC + 285 lav + 234 kitchen sink + 234 DW + 265 tub + 12 shower + additional drains
Contract: One Way Plumbing contract executed (SRM Development GC) with OWP markup
Billing: 230 BROADWAY AGGREGATE BILLING.xls (18 pay apps Apr 2011 – Sep 2012) + 17 SOV files
Final contract $2,121,874 (original $1,850,270 + $0 COs)
TIES = within $1 or 5 hrs • WITHIN = within 5% • OFF = investigate
K. CHANGE LOG ↔ ROOT CAUSE ANALYSIS
|  | Total Event Count | 13 |  |  | TIES
|  | Net $ Impact (all events) | 0 |  |  | TIES
L. PREDICTIVE SIGNALS ↔ CHANGE LOG
|  | Backcharge Count signal | 0 |  |  | TIES
M. METRIC REGISTRY ↔ BENCHMARK KPIs
|  | revenue (row 17) | 2121873.5 |  |  | TIES
|  | unit_count (row 12) | 282 |  |  | TIES
|  | total_fixtures (row 13) | 1315 |  |  | TIES
|  | direct_cost (row 19) | 1288901.21 |  |  | OFF
|  | total_pos (row 30) | 0 |  |  | TIES
N. CHANGE LOG ↔ METRIC REGISTRY (event counts)
|  | change_event_total | 13 |  |  | OFF
SOURCES
Job #2001 — Cortex v2 17-tab layout
12 analytical tabs + Change Log + Root Cause Analysis + Predictive Signals + Metric Registry + Reconciliation
Canonical source: 2001 Job Detail Report.pdf (Sage Timberline export)
Change artifacts: folders scanned — ASI-RFI, Change Orders, Submittals, Invoices (Backcharges), JDR cost codes
Every Change Log row cites its source document path
TIES = within $1/5hrs/exact count • WITHIN = within 5% • OFF = investigate
Cross-sheet formulas (='Tab'!Cell) update automatically when source tabs change
Tabs: 1-12 analytical • 13=ChangeLog • 14=RootCause • 15=PredictiveSignals • 16=MetricRegistry • 17=Reconciliation

## Vendors
[CORTEX_V2.1] Job #2001 — · Vendors
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| vendor_id | vendor_name | total_spend | transactions | category | source
Invoices
210
161
7
5
5
2
7
7
3
8
6
3
3
4
1
1