## Overview
[CORTEX_V2.1] Job #2008 — · Overview
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| OVERVIEW |  | SOURCE
IDENTITY
| Project Job Number | 2008
| Project Name: | Exxel Pacific Vivo Apartments
CONTRACT & PARTIES
| General Contractor | Exxel Pacific, Inc.
JOB SITE
| Jobsite Location | Seattle, WA
| Plumbing Units | 163 | Fixtures / Unit
SCHEDULE
| Work Period | 15 mo
| Project Duration | Jun 2013 – Aug 2014 (~15 months)
| CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
| $2,256,200 |  | $546,234 |  | $1,782,683 |  | 59,248
| Original $2,256,200 |  | 23.4% margin |  | 76.5% of revenue |  | 58 workers
COST BREAKDOWN
| Category | Budget | Actual | Variance | % Budget | % of Cost
| Labor | 551450 | 593780.08 | -42330.08 | 107.7% | 33.31%
| Material | 983320 | 789826.06 | 193493.94 | 80.32% | 44.31%
| Overhead | 46570 | 80217.45 | -33647.45 | 172.3% | 4.5%
| Burden | 299645.41 | 318858.96 | -19213.55 | 106.4% | 17.89%
| TOTAL | 1880985.41 | 1782682.55 | 98302.86 | 94.77% | 100%
PROJECT PROFILE
| Plumbing Units | 163 |  | Duration | 15 mo

## Budget vs Actual
[CORTEX_V2.1] Job #2008 — · Budget vs Actual
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| cost_code | description | original_budget | revised_budget | actual | variance | pct_used | hours | source
LABOR
| 011 | DS & RD Labor | 46715 | 46715 | 11671.12 | 35043.88 | 24.98%
| 100 | Supervision | 11600 | 11915 | 8811.5 | 3103.5 | 73.95%
| 101 | Takeoff & Purchase Labor | 10300 | 11560 | 15093.5 | -3533.5 | 1.306%
| 110 | Underground Labor | 5440 | 5440 | 7757.5 | -2317.5 | 1.426%
| 111 | Garage Labor | 44625 | 44625 | 38324.13 | 6300.87 | 85.88%
| 112 | Canout Labor | 42255 | 42255 | 29831.5 | 12423.5 | 70.6%
| 113 | Foundation Drain Labor | 3400 | 3400 | 2454 | 946 | 72.18%
| 120 | Roughin Labor | 261585 | 269760 | 303122.05 | -33362.05 | 1.124%
| 130 | Finish Labor | 43650 | 49430 | 76368.5 | -26938.5 | 1.545%
| 140 | Gas Labor | 18000 | 18200 | 21795.5 | -3595.5 | 1.198%
| 141 | Water Main/Insulation Lab | 40050 | 40050 | 64816.03 | -24766.03 | 1.618%
| 142 | Mech Room Labor | 8100 | 8100 | 13633.25 | -5533.25 | 1.683%
| 145 | Tub/Shower Labor | 0 | 0 | 101.5 | -101.5 | 0%
MATERIAL
| 039 | DS & RD Material | 60420 | 60420 | 26220.27 | 34199.73 | 43.4%
| 210 | Underground Material | 3000 | 3000 | 10852.76 | -7852.76 | 3.618%
| 211 | Garage Material | 33750 | 33750 | 15831.2 | 17918.8 | 46.91%
| 212 | Canout Material | 70425 | 70425 | 58265.64 | 12159.36 | 82.73%
| 213 | Foundation Material | 10550 | 10550 | 2839.07 | 7710.93 | 26.91%
| 220 | Roughin Material | 247610 | 250830 | 178543.02 | 72286.98 | 71.18%
| 230 | Finish Material | 498050 | 521715 | 428881.3 | 92833.7 | 82.21%
| 240 | Gas Material | 18000 | 18300 | 11391.29 | 6908.71 | 62.25%
| 241 | Water Main/Insulation Mat | 66750 | 66750 | 80448.24 | -13698.24 | 1.205%
| 242 | Mech Room Material | 5400 | 5400 | 2236.93 | 3163.07 | 41.42%
| 245 | Tub/Shower Material | 2600 | 2600 | 536.61 | 2063.39 | 20.64%
OVERHEAD
| 600 | Subcontractor | 7870 | 9070 | 16900.64 | -7830.64 | 1.863%
| 601 | Engineering/Plans | 35000 | 35500 | 57119.45 | -21619.45 | 1.609%
| 603 | Permits & Licenses | 2000 | 2000 | 6197.36 | -4197.36 | 3.099%
BURDEN
| 995 | Payroll Burden | 228724 | 254698.59 | 270898.22 | -16199.63 | 1.064%
| 998 | Payroll Taxes | 43743.47 | 44946.82 | 47960.74 | -3013.92 | 1.067%
SOURCES
Job #2008 — Exxel Pacific Vivo Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2008 Job Detail Report.pdf (282 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count: 163 (from project specifications)
Fixture count: 1,786 (estimated at ~11 fixtures per unit for mid-rise apartments)
Final contract $2,327,698 (original $2,256,200 + $71,498 COs)
| TOTAL |  | 1869612.47 | 1941405.41 | 1808902.82 | 132502.59 |  | 0

## Cost Breakdown
[CORTEX_V2.1] Job #2008 — · Cost Breakdown
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| category | cost_codes | actual | pct_of_direct_cost | pct_of_revenue | per_unit | source
| Labor | 13 | 551450 | 1.077% |  | 3642.8226
| Material | 11 | 1043740 | 78.18% |  | 5006.4192
| Overhead | 3 | 46570 | 1.723% |  | 492.1316
| Burden | 2 | 299645.41 | 1.064% |  | 1956.1899
B. LARGEST OVERRUNS (Actual > Revised Budget)
| Code | Description
| 120 | Roughin Labor | 269760 | 12.37%
| 130 | Finish Labor | 49430 | 54.5%
| 141 | Water Main/Insulation Lab | 40050 | 61.84%
| 601 | Engineering/Plans | 35500 | 60.9%
| 995 | Payroll Burden | 254698.59 | 6.36%
| 241 | Water Main/Insulation Mat | 66750 | 20.52%
| 210 | Underground Material | 3000 | 2.618%
| 600 | Subcontractor | 9070 | 86.34%
| 142 | Mech Room Labor | 8100 | 68.31%
| 603 | Permits & Licenses | 2000 | 2.099%
C. LARGEST SAVINGS (Actual < Revised Budget)
| Code | Description
| 230 | Finish Material | 521715 | 17.79%
| 220 | Roughin Material | 250830 | 28.82%
| 011 | DS & RD Labor | 46715 | 75.02%
| 039 | DS & RD Material | 60420 | 56.6%
| 211 | Garage Material | 33750 | 53.09%
| 112 | Canout Labor | 42255 | 29.4%
| 212 | Canout Material | 70425 | 17.27%
| 213 | Foundation Material | 10550 | 73.09%
| 240 | Gas Material | 18300 | 37.75%
| 111 | Garage Labor | 44625 | 14.12%
SOURCES
Job #2008 — Exxel Pacific Vivo Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2008 Job Detail Report.pdf (282 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count: 163 (from project specifications)
Fixture count: 1,786 (estimated at ~11 fixtures per unit for mid-rise apartments)
Final contract $2,327,698 (original $2,256,200 + $71,498 COs)
| TOTAL |  | 3779349 |  |  | 11097.5633

## Material
[CORTEX_V2.1] Job #2008 — · Material
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| vendor_id | vendor_name | total_spend | transactions | category | source
| 039 | DS & RD Material | 60420 |  | 0.032131
| 210 | Underground Material | 3000 |  | 0.013299
| 211 | Garage Material | 33750 |  | 0.0194
| 212 | Canout Material | 70425 |  | 0.0714
| 213 | Foundation Material | 10550 |  | 0.0034791
| 220 | Roughin Material | 250830 |  | 0.21879
| 230 | Finish Material | 521715 |  | 0.52556
| 240 | Gas Material | 18300 |  | 0.013959
| 241 | Water Main/Insulation Mat | 66750 |  | 0.098583
| 242 | Mech Room Material | 5400 |  | 0.0027412
| 245 | Tub/Shower Material | 2600 |  | 0.00065757
B. VENDORS BY SPEND (AP)
| Vendor | # Invoices
| Ferguson Enterprises, Inc. | 204 | 597586.16
| Rosen Supply Company, Inc. | 118 | 91819.63
| Mechanical Sales, Inc. | 5 | 78442.97
| Keller Supply Company | 83 | 71760.48
| Franklin Engineering | 9 | 56505.5
| Bank of America CC | 19 | 20102
| Quality Concrete Products, Inc. | 7 | 19615
| Duraseal, Inc. | 3 | 15300
| Fastenal Company | 11 | 14267.27
| Kele, Inc | 7 | 2272.16
| C.M. Hoskins Company | 5 | 1597.08
| Ferguson Enterprises, Inc. #3007 | 5 | 1061.65
| Capital One Credit Card | 92 | 936.66
| Consolidated Supply Co. | 5 | 782.55
| DRSi | 5 | 613.95
| Structural Imaging, LLC | 1 | 500
| Evergreen Concrete Cutting, Inc. | 1 | 375
| American Express 3-41000 | 2 | 335
| R.A. Brown Backflow Testing | 1 | 257.64
| Platt | 2 | 147.74
SOURCES
Job #2008 — Exxel Pacific Vivo Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2008 Job Detail Report.pdf (282 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count: 163 (from project specifications)
Fixture count: 1,786 (estimated at ~11 fixtures per unit for mid-rise apartments)
Final contract $2,327,698 (original $2,256,200 + $71,498 COs)
Vendor AP ties to JDR 'by Source: AP' line (974,278.44)

## Crew & Labor
[CORTEX_V2.1] Job #2008 — · Crew & Labor
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| worker_id | worker_name | total_hours | gross_pay | blended_wage_per_hr | tier | work_days | source
| Salazar, Hajdar L |  | 1950 | 25346 | 12.9979 | Apprentice
| Reed, Reuben H |  | 1839 | 50190 | 27.292 | Mid
| Hubbard, Robert W |  | 1771 | 59000.5 | 33.3148 | Senior
| Sepulveda Gonzalez, Alfredo |  | 1755.5 | 42871.5 | 24.4212 | Mid
| Arreola, Israel A |  | 1278 | 19601 | 15.3372 | Apprentice
| Velasquez Cruz, Denis M |  | 1236 | 16740 | 13.5437 | Apprentice
| Spears, Gregory M |  | 1186 | 16134 | 13.6037 | Apprentice
| Ross, Kelli M |  | 1185 | 33066 | 27.9038 | Mid
| Cortes Mendiola, Victor H |  | 1180 | 28772 | 24.3831 | Mid
| Ramirez, Lorenzo A |  | 1101.75 | 17628 | 16 | Apprentice
| Castro Hernandez, Carlos E |  | 1057 | 26832 | 25.3851 | Mid
| McCabe, Thomas C |  | 985.5 | 17406.3 | 17.6624 | Apprentice
| Castaneda Juarez, Gustavo |  | 892 | 12019 | 13.4742 | Apprentice
| Gerard, Jeffrey S |  | 806.5 | 27755.8 | 34.4151 | Senior
| Balderas Ortiz, Ricardo I |  | 784 | 10192 | 13 | Apprentice
| Lopez Martinez, Abimael |  | 762 | 9144 | 12 | Apprentice
| Castaneda Martinez, Gustavo |  | 738 | 20470 | 27.7371 | Mid
| Vega Arriaga, Jorge |  | 734.5 | 9233.5 | 12.5711 | Apprentice
| Monico Brambila, Jesus S |  | 659 | 9185.5 | 13.9385 | Apprentice
| Sanders, Allen O |  | 635 | 18427.5 | 29.0197 | Mid
| Veley, Nathaniel S |  | 541 | 13895 | 25.6839 | Mid
| Paco Leyva, Orlando |  | 518.5 | 6543 | 12.6191 | Apprentice
| Soto Cruz, Jovani |  | 498.75 | 7964 | 15.9679 | Apprentice
| Alba Martinez, Santiago |  | 480 | 7200 | 15 | Apprentice
| Rivera, Jorge A |  | 461 | 8298 | 18 | Mid
| Palma Vides, Hugo |  | 400 | 11200 | 28 | Mid
| Waites, Thaddeus Z |  | 396 | 10770 | 27.197 | Mid
| Sanchez Garcia, Adelaido |  | 368 | 4784 | 13 | Apprentice
| Kinssies, Jr, John E |  | 331 | 4801 | 14.5045 | Apprentice
| Soto Serna, Cesar E |  | 321.25 | 4176.25 | 13 | Apprentice
| Bateman, Rohan O |  | 318 | 3816 | 12 | Apprentice
| Anderson, Richard P |  | 312 | 8320 | 26.6667 | Mid
| Castro Hernandez, Jose A |  | 288 | 4896 | 17 | Apprentice
| Agustin Rodriguez, Ezequiel |  | 287 | 3444 | 12 | Apprentice
| Ramos Banegas, Noel O |  | 231 | 3003 | 13 | Apprentice
| Rivera, Eli P |  | 224 | 2912 | 13 | Apprentice
| Meza Fuentes, Erick A |  | 188 | 3597 | 19.133 | Mid
| Vaughan, Tyler J |  | 157 | 2512 | 16 | Apprentice
| Castaneda Juarez, Edgar D |  | 136 | 1972 | 14.5 | Apprentice
| Perez, David B |  | 121 | 1694 | 14 | Apprentice
| Ramos Garcia, Jose M |  | 120 | 1560 | 13 | Apprentice
| Hubbard, Dustin R |  | 116 | 1388 | 11.9655 | Apprentice
| Hayton, Evan R |  | 112 | 1536 | 13.7143 | Apprentice
| Lima Romero, Melvin A |  | 60.5 | 1140.5 | 18.8512 | Mid
| Garcia, Jordan X |  | 48 | 672 | 14 | Apprentice
| Wilson, Garret A |  | 32 | 456 | 14.25 | Apprentice
| Donelson, Richard T |  | 11 | 495 | 45 | Senior
| Reyes, Robert J |  | 6 | 78 | 13 | Apprentice
| Barnhart, Joseph N |  | 5.5 | 164.5 | 29.9091 | Mid
| TOTAL (49 workers) |  | 29624.25 | 593301.85 | 20.0276
SOURCES
Job #2008 — Exxel Pacific Vivo Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2008 Job Detail Report.pdf (282 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count: 163 (from project specifications)
Fixture count: 1,786 (estimated at ~11 fixtures per unit for mid-rise apartments)
Final contract $2,327,698 (original $2,256,200 + $71,498 COs)
Tier: Apprentice <$18/hr, Mid $18–30, Senior >$30

## Crew Analytics
[CORTEX_V2.1] Job #2008 — · Crew Analytics
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| tier | worker_count | hours | gross_pay | pct_of_hours | blended_wage
| Senior | 3 | 2588.5 | 87251.3 | 8.738%
| Mid | 15 | 10753.5 | 278014 | 36.3%
| Apprentice | 31 | 16282.25 | 228036.55 | 54.96%
B. WAGE STATISTICS
| Blended Gross Wage | 20.0276
| Fully-Loaded Wage | 30.8072
| Burden Multiplier | 1.5382
| Min Worker Rate | 11.9655
| Max Worker Rate | 45
| Avg Hours / Worker | 604.5765
SOURCES
Job #2008 — Exxel Pacific Vivo Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2008 Job Detail Report.pdf (282 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count: 163 (from project specifications)
Fixture count: 1,786 (estimated at ~11 fixtures per unit for mid-rise apartments)
Final contract $2,327,698 (original $2,256,200 + $71,498 COs)

## Productivity
[CORTEX_V2.1] Job #2008 — · Productivity
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| phase | labor_code | hours | pct_of_total | hours_per_unit
| DS & RD | 011 | 532.75 | 1.816% | 3.2684
| Supervision | 100 | 246.5 | 0.84% | 1.5123
| Takeoff & Purchasing | 101 | 443 | 1.51% | 2.7178
| Underground | 110 | 392.5 | 1.338% | 2.408
| Garage | 111 | 1728 | 5.889% | 10.6012
| Canout | 112 | 1126.5 | 3.839% | 6.911
| Foundation Drain | 113 | 120 | 0.4089% | 0.7362
| Roughin | 120 | 15344.5 | 52.29% | 94.138
| Finish | 130 | 4236.75 | 14.44% | 25.9923
| Gas | 140 | 910 | 3.101% | 5.5828
| Water Main / Insulation | 141 | 3421.5 | 11.66% | 20.9908
| Mech Room | 142 | 838 | 2.856% | 5.1411
| Tub / Shower | 145 | 3.5 | 0.01193% | 0.021472
B. PRODUCTIVITY RATIOS
| Metric | Value
| Hours / Unit | 180.0215
| Hours / Fixture | 16.4297
| Revenue / Hour | 79.3258
| Profit / Hour | 17.6801
| Units / Month | 10.8667
| Fixtures / Month | 119.0667
| Hours / Month | 1956.2333
| Revenue / Month | 155179.8667
SOURCES
Job #2008 — Exxel Pacific Vivo Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2008 Job Detail Report.pdf (282 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count: 163 (from project specifications)
Fixture count: 1,786 (estimated at ~11 fixtures per unit for mid-rise apartments)
Final contract $2,327,698 (original $2,256,200 + $71,498 COs)

## PO Commitments
[CORTEX_V2.1] Job #2008 — · PO Commitments
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| po_number | date | issuer | type | status | description | amount | source
B. COMMITMENTS BY VENDOR
| Vendor |  |  |  |  | PO Count
C. PO COVERAGE NOTES
Total Material Actual (JDR)
Unique PO Count
(Dollar PO commitment not extracted — requires per-PDF parse)
SOURCES
Job #2008 — Exxel Pacific Vivo Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2008 Job Detail Report.pdf (282 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count: 163 (from project specifications)
Fixture count: 1,786 (estimated at ~11 fixtures per unit for mid-rise apartments)
Final contract $2,327,698 (original $2,256,200 + $71,498 COs)
PO count is deduplicated by 5-digit PO number extracted from filenames
Vendor/code classification is heuristic (filename keyword match)

## Billing & SOV
[CORTEX_V2.1] Job #2008 — · Billing & SOV
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| pay_app_number | date | contract_total | this_period | retainage | stored_materials | cumulative | pct_complete | source
| 10 | 2013-07-25 | 2274720 | 98550 | 0 | 0 | 542950 | 23.87%
| 11 | 2013-08-22 | 2274720 | 129550 | 0 | 0 | 672500 | 29.56%
| 12 | 2013-09-24 | 2274720 | 110200 | 0 | 0 | 782700 | 34.41%
| 13 | 2013-10-24 | 2284949 | 204500 | 0 | 0 | 987200 | 43.2%
| 14 | 2013-11-19 | 2284949 | 204650 | 0 | 0 | 1191850 | 52.16%
| 15 | 2013-12-19 | 2284949 | 240500 | 0 | 0 | 1432350 | 62.69%
| 16 | 2014-01-23 | 2284949 | 218800 | 0 | 0 | 1651150 | 72.26%
| 17 | 2014-02-25 | 2296031 | 283604 | 0 | 0 | 1934754 | 84.27%
| 18 | 2014-03-25 | 2296031 | 161489 | 0 | 0 | 2096243 | 91.3%
| 18 | 2014-03-25 | 2296031 | 125142 | 0 | 0 | 2221385 | 96.75%
| 21 | 2014-05-22 | 2322729 | 59306 | 0 | 0 | 2280691 | 98.19%
| 21 | 2014-06-24 | 2322729 | 42038 | 0 | 0 | 2322729 | 100%
| 22 | 2014-07-24 | 2323808 | 1079 | 0 | 0 | 2323808 | 100%
| 23 | 2014-08-25 | 2327698 | 3890 | 0 | 0 | 2327698 | 100%
| 24 | 2014-12-16 | 2328917 | 1219 | 0 | 0 | 2328917 | 100%
| 8 | 2013-05-25 | 2274720 | 75100 | 0 | 0 | 318800 | 14.01%
| 9 | 2013-06-25 | 2274720 | 125600 | 0 | 0 | 444400 | 19.54%

## Insights
[CORTEX_V2.1] Job #2008 — · Insights
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| insight_id | title | finding | verified | source
| 1 | Labor overran budget by 10.8% | Total labor actual $593,780 vs budget $535,720 — $58,060 unfavorable variance. Review crew mix and productivity. | Derived | budget_vs_actual
| 2 | Scope stability — 3 executed COs net $0 (+0.00% of contract) | Minimal scope churn indicates well-defined contract and experienced GC. Candidate GC profile for future similar bids. | Derived | change_log
| 3 | Largest variance — cost code 230 (Finish Material) under by $92,834 | Budget $521,715, actual $428,881 (-17.8%). Flag for bid calibration. | Derived | budget_vs_actual

## Benchmark KPIs
[CORTEX_V2.1] Job #2008 — · Benchmark KPIs
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
CROSS-PROJECT BENCHMARK SCORECARD
Normalized metrics designed for apples-to-apples comparison across all OWP projects.
| KPI | DATA NAME | VALUE | CATEGORY | NOTES / BENCHMARK CONTEXT
| Job Number | job_number | 2,008 | Profile | OWP Sage job ID
| General Contractor | general_contractor | Exxel Pacific, Inc. | Profile | Customer of record
| location | location | Seattle, WA | Profile | Project address
| Project Type | project_type | Apartment building | Profile | Building category for benchmarking
| Duration Months | duration_months | 15.0% | Profile | Calendar months from start to close
| Plumbing Units | plumbing_units | 163 | Profile | Residential units delivered
| Contract Original | contract_original | $2,256,200 | Financial | Original contract value
| Contract Final | contract_final | $2,256,200 | Financial | Revised contract value (post-COs)
| Change Orders Net | change_orders_net | 0 | Financial | Net dollar change from COs
| revenue | revenue | $2,328,917 | Financial | Net billed (AR net of reversals)
| Net Profit | net_profit | $546,234 | Financial | Revenue − direct cost
| Gross Margin Pct | gross_margin_pct | 23.4% | Financial | Net profit / revenue
| Direct Cost | direct_cost | $1,782,683 | Financial | Σ labor + material + OH + burden + tax
| Overhead Cost | overhead_cost | $80,217 | Financial | Codes 600, 601, 603, 607
| Burden Cost | burden_cost | $270,898 | Financial | Code 995 payroll burden
| Retainage Outstanding | retainage_outstanding | $0.00 | Financial | Held by GC until closeout
| Revenue Per Unit | revenue_per_unit | $14,288 | Financial | Top-line per unit
| Profit Per Unit | profit_per_unit | $3,351 | Financial | Net profit normalized per residential unit
| Cost Per Unit | cost_per_unit | $10,937 | Financial | Total direct cost per unit
| Labor Cost | labor_cost | $593,780 | Labor | Codes 100–150
| Total Hours | total_hours | 59,248.50 | Labor | All payroll hours on the job
| Total Workers | total_workers | 58 | Crew | Unique payroll IDs across job
| Blended Wage | blended_wage | $20.03 | Labor | Pre-burden average
| Fully Loaded Wage | fully_loaded_wage | $15.40 | Labor | Post-burden true cost
| Burden Multiplier | burden_multiplier | 0.77 | Labor | Loaded / gross
| Hours Per Unit | hours_per_unit | $0.00 | Labor | Key plumbing benchmark
| Labor Per Unit | labor_per_unit | $3,643 | Labor | Payroll only, not material
| Labor Pct Revenue | labor_pct_revenue | 0.26 | Cost Mix | Payroll exposure
| Material Cost | material_cost | $789,826 | Material | Codes 210–244
| Material Per Unit | material_per_unit | $4,846 | Material | Cross-project benchmark
| Material Pct Revenue | material_pct_revenue | 0.34 | Cost Mix | Material/sub exposure
| Total Vendors | total_vendors | 21 | Material | Distinct AP vendors invoiced on the job
| Top Vendor Spend | top_vendor_spend | $0.00 | Material | Largest single supplier
| Top Vendor Pct | top_vendor_pct | 0.0% | Material | Top vendor concentration
| Revenue Per Month | revenue_per_month | $155,261 | Throughput | Billing velocity
| Hours Per Month | hours_per_month | $0.00 | Throughput | Avg monthly labor burn
| Units Per Month | units_per_month | $10.87 | Throughput | Build pace
SOURCES
Canonical: /sessions/keen-determined-mccarthy/mnt/cortex-mockup/owp/cortex v2 files/OWP_2008_JCR_Cortex_v2.xlsx
revenue: AR net-of-reversals (validator)
labor_cost: Codes 100–150
material_cost: Codes 210–244
total_workers: count(distinct worker_id)

## Change Log
[CORTEX_V2.1] Job #2008 — · Change Log
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| event_id | type | date | subject | originator | linked_events | cost_impact | schedule_days | status | source_document
| COR-001 | COR | 2014-07-31 | Added Irrigation Line — POC | GC (SRM) | COR-002 | 0 | 0 | Priced | 2008-SRM, 101 Taylor/Change Orders/COR_s/Taylor - OWP COR - Added Irrigation POC_s.pdf
| COR-002 | COR | 2014-07-31 | Added Irrigation Line — Cost Sheet | GC (SRM) | COR-001 | 0 | 0 | Priced | 2008-SRM, 101 Taylor/Change Orders/COR_s/COR Pricing - Added Irrigation Line.xlsx
| COR-003 | COR | 2014-11-25 | Install Gas Meter — T&M | GC (SRM) | TM-001 | 0 | 0 | Priced | 2008-SRM, 101 Taylor/Change Orders/COR_s/COR Pricing - Install Gas Meter T&M.xlsx
| COP-001 | COP | 2018-10-24 | Century 101 Taylor — Drinking Fountain Proposal | GC/OWP |  | 0 | 0 | Proposal | 2008-SRM, 101 Taylor/Change Orders/COR_s/Century 101 Taylor Ave - Drinking Fountain Proposal.pdf
| ASI-002 | ASI |  | Multipurpose Room Revisions | Architect (Runberg) |  | 0 | 0 | Closed | 2008-SRM, 101 Taylor/ASI-RFI/TAYLOR RFI-ASI/ASI - 2 Multipurpose Room Revisions.pdf
| ASI-003 | ASI |  | L1 East Railing Layout — Details | Architect (Runberg) |  | 0 | 0 | Closed | 2008-SRM, 101 Taylor/ASI-RFI/TAYLOR RFI-ASI/ASI - 3 L1 East Railing Layout - Details.pdf
| ASI-004 | ASI |  | Generator Fuel Filling Alcove | Architect |  | 0 | 0 | Closed | 2008-SRM, 101 Taylor/ASI-RFI/TAYLOR RFI-ASI/ASI - 4 Generator Fuel Filling Alcove.pdf
| ASI-005 | ASI |  | Additional Dimensions | Architect |  | 0 | 0 | Closed | 2008-SRM, 101 Taylor/ASI-RFI/TAYLOR RFI-ASI/ASI_5 Additional Dimensions.pdf
| ASI-008 | ASI |  | Revise RO of Windows | Architect |  | 0 | 0 | Closed | 2008-SRM, 101 Taylor/ASI-RFI/TAYLOR RFI-ASI/ASI - 8 Revise RO of Windows.pdf
| ASI-010 | ASI |  | Exterior Light Elevations | Architect |  | 0 | 0 | Closed | 2008-SRM, 101 Taylor/ASI-RFI/TAYLOR RFI-ASI/ASI - 10 Ext Light Elevations.pdf
| ASI-011 | ASI |  | Elevator Overrun Revisions | Architect |  | 0 | 0 | Closed | 2008-SRM, 101 Taylor/ASI-RFI/TAYLOR RFI-ASI/ASI-11 Elevator Overrun Revisions.pdf
| ASI-014 | ASI |  | ASI 14 — spec detail | Architect |  | 0 | 0 | Closed | 2008-SRM, 101 Taylor/ASI-RFI/TAYLOR RFI-ASI/07122_ASI_14.pdf
| ASI-016 | ASI |  | ASI 16 — spec detail | Architect | ASI-016.R1 | 0 | 0 | Closed | 2008-SRM, 101 Taylor/ASI-RFI/TAYLOR RFI-ASI/07122_ASI_16.pdf
| ASI-016.R1 | ASI |  | Insulation at Roof Locations (revision) | Architect | ASI-016 | 0 | 0 | Closed | 2008-SRM, 101 Taylor/ASI-RFI/TAYLOR RFI-ASI/ASI - 16.R1 - Insulation at Roof Locations.pdf
| ASI-018 | ASI |  | ASI 18r1 — spec detail | Architect |  | 0 | 0 | Closed | 2008-SRM, 101 Taylor/ASI-RFI/TAYLOR RFI-ASI/07122_ASI_18r1.pdf
| ASI-019 | ASI |  | Trash Chute Dog Houses | Architect |  | 0 | 0 | Closed | 2008-SRM, 101 Taylor/ASI-RFI/TAYLOR RFI-ASI/ASI - 19 Trash Chute Dog Houses.pdf
| ASI-021 | ASI |  | L9 Corridor RCPs | Architect |  | 0 | 0 | Closed | 2008-SRM, 101 Taylor/ASI-RFI/TAYLOR RFI-ASI/ASI - 21 - L9 Corridor RCPs.pdf
| ASI-023 | ASI |  | Solarium — Trellis Layout | Architect |  | 0 | 0 | Closed | 2008-SRM, 101 Taylor/ASI-RFI/TAYLOR RFI-ASI/ASI - 23 Solarium - Trellis Layout.pdf
| ASI-024 | ASI |  | L9 Deck Overflows | Architect |  | 0 | 0 | Closed | 2008-SRM, 101 Taylor/ASI-RFI/TAYLOR RFI-ASI/ASI - 24 L9 deck overflows.pdf
| ASI-028 | ASI |  | Theatre Door Framing | Architect |  | 0 | 0 | Closed | 2008-SRM, 101 Taylor/ASI-RFI/TAYLOR RFI-ASI/ASI - 28 - Theatre Door Framing.pdf
| ASI-029 | ASI |  | Spiral Staircase Clarification | Architect |  | 0 | 0 | Closed | 2008-SRM, 101 Taylor/ASI-RFI/TAYLOR RFI-ASI/ASI - 29 - Spiral Staircase Clarification.pdf
| ASI-030 | ASI |  | Elevator Lobby Framing | Architect |  | 0 | 0 | Closed | 2008-SRM, 101 Taylor/ASI-RFI/TAYLOR RFI-ASI/ASI - 30 - Elevator Lobby Framing.pdf
| ASI-031 | ASI |  | Alternating Stair Tread | Architect |  | 0 | 0 | Closed | 2008-SRM, 101 Taylor/ASI-RFI/TAYLOR RFI-ASI/ASI - 31 - Alternating Stair Tread.pdf
| OCD-01 | OCD |  | Studio Wall Replaced with Sliding Glass Door | Owner |  | 0 | 0 | Closed | 2008-SRM, 101 Taylor/ASI-RFI/TAYLOR RFI-ASI/Runberg Response - OCD _01 - STUDIO WALL REPLACED WITH SLIDING GLASS DOOR.pdf
| OCD-02 | OCD |  | Stairwell Light Move | Owner |  | 0 | 0 | Closed | 2008-SRM, 101 Taylor/ASI-RFI/TAYLOR RFI-ASI/Runberg Response - OCD _02 - ARCHITECTURAL - STAIRWELL LIGHT MOVE.pdf
| OCD-04 | OCD |  | L1-L2 South Closure Pour Relocation | Owner/Structural |  | 0 | 0 | Closed | 2008-SRM, 101 Taylor/ASI-RFI/TAYLOR RFI-ASI/DCI Response - OCD _04 - L1 - L2 SOUTH CLOSURE POUR RELOCATION.pdf
| OCD-06 | OCD |  | Added Package Room | Owner |  | 0 | 0 | Closed | 2008-SRM, 101 Taylor/ASI-RFI/TAYLOR RFI-ASI/Runberg Response - OCD _06 - ADDED PACKAGE ROOM.pdf
| OCD-07 | OCD |  | Revised Door #136H | Owner |  | 0 | 0 | Closed | 2008-SRM, 101 Taylor/ASI-RFI/TAYLOR RFI-ASI/Runberg Response - OCD _07 - REVISED DOOR _ 136H.pdf
| OCD-08 | OCD |  | Elevator Machine Room Re-design | Owner |  | 0 | 0 | Closed | 2008-SRM, 101 Taylor/ASI-RFI/TAYLOR RFI-ASI/Runberg Response - OCD _08 - ELEVATOR MACHINE ROOM RE-DESIGN.pdf
| OCD-09 | OCD |  | Laminated Face Back Panel | Owner |  | 0 | 0 | Closed | 2008-SRM, 101 Taylor/ASI-RFI/TAYLOR RFI-ASI/Runberg Response - OCD _09 - LAMINATED FACE BACK PANEL.pdf
| OCD-12 | OCD |  | Revised CMU Frames | Owner |  | 0 | 0 | Closed | 2008-SRM, 101 Taylor/ASI-RFI/TAYLOR RFI-ASI/Runberg Response - OCD _12 - REVISED CMU FRAMES.pdf
| OCD-14 | OCD |  | Man Hoist Footing — Shoring | Owner/MEP |  | 0 | 0 | Closed | 2008-SRM, 101 Taylor/ASI-RFI/TAYLOR RFI-ASI/OCD _14 - MAN HOIST FOOTING - SHORING.pdf
| OCD-18 | OCD |  | Dropped Soffits for Return Air Duct | Owner |  | 0 | 0 | Closed | 2008-SRM, 101 Taylor/ASI-RFI/TAYLOR RFI-ASI/Runberg Response - OCD _018 - DROPPED SOFFITS FOR RETURN AIR DUCT.pdf
| OCD-19 | OCD |  | Remove Hall Closet in 1-1-D1 | Owner |  | 0 | 0 | Closed | 2008-SRM, 101 Taylor/ASI-RFI/TAYLOR RFI-ASI/Runberg Response - OCD _019 - REMOVE HALL CLOSET IN 1-1-D1.pdf
| OCD-20 | OCD |  | Townhouse L1 Bathroom Doors | Owner |  | 0 | 0 | Closed | 2008-SRM, 101 Taylor/ASI-RFI/TAYLOR RFI-ASI/Runberg Response - OCD _020 - TOWNHOUSE L1 BATHROOM DOORS.pdf
| OCD-23 | OCD |  | Electric Heaters in Townhouse L2 Bathroom | Owner/MEP |  | 0 | 0 | Closed | 2008-SRM, 101 Taylor/ASI-RFI/TAYLOR RFI-ASI/OCD _23 - ELECTRIC HEATERS IN TOWNHOUSE L2 BATHROOM.pdf
| OCD-24 | OCD |  | CAT5E and Coax Cables Merged | Owner/MEP |  | 0 | 0 | Closed | 2008-SRM, 101 Taylor/ASI-RFI/TAYLOR RFI-ASI/Pillar Response - OCD _24 - CAT5E AND COAX CABLES MERGED.pdf
| BC-001 | Backcharge | 2016-04-29 | RDMDMDSRM Backcharge | GC (SRM) |  | -500 | 0 | Closed | 2008-SRM, 101 Taylor/Invoices/2016-04-29 RDMDMDSRM Backcharge.pdf
| TM-001 | T&M | 2014-11-25 | Install Gas Meter — T&M directed work | GC/Field | COR-003 | 0 | 0 | Billed | 2008-SRM, 101 Taylor/Change Orders/COR_s/COR Pricing - Install Gas Meter T&M.xlsx
| RFI-SUMMARY | RFI |  | 164 RFIs logged — architectural (95+), structural (35+), MEP (15+). Heavy coordination activity — details in ASI-RFI folder. | Field (OWP) | multiple ASIs | 0 | 0 | Closed | 2008-SRM, 101 Taylor/ASI-RFI/TAYLOR RFI-ASI/ (150+ RFI PDFs)
| SUB-RESUB | Submittal-resub |  | 13+ submittal resubmissions (backflow preventers, drain systems, insulation, fixture alts) | Sub/OWP |  | 0 | 0 | Closed | 2008-SRM, 101 Taylor/Submittals/ (multiple -R1/-R2 versions)

## Root Cause Analysis
[CORTEX_V2.1] Job #2008 — · Root Cause Analysis
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| rca_id | observation | root_cause | responsibility | cost_impact | mitigation | source

## Predictive Signals
[CORTEX_V2.1] Job #2008 — · Predictive Signals
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| signal_id | signal_name | direction | metric | threshold | historical_outcome | source
| WAREHOUSE | Predictive signals computed at warehouse layer | Neutral | cross-project benchmark | n/a | See benchmark_envelopes view; not stored per-project. | warehouse view (predictive_signals_v)

## Metric Registry
[CORTEX_V2.1] Job #2008 — · Metric Registry
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| metric_key | metric_label | value | data_label | tab_home | verification | source
2008
Exxel Pacific Vivo Apartments
Exxel Pacific, Inc.
Seattle, WA
163-unit multifamily apartments
15
163
1786
2256200
2327698
71498
2327698
518795.18
0.22288
1808902.82
593780.08
816046.33
80217.45
318858.96
116385
29343.5
49
20.2192
20
0
0.03169
164
33
4
1
1
13
41
-500

## Reconciliation
[CORTEX_V2.1] Job #2008 — · Reconciliation
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| check_number | check_description | value_a | value_b | difference | status | tabs
A. JDR COST CODE ROLLUP
|  | Labor subtotal (13 codes) | 593780.08 |  |  | TIES
|  | Material subtotal (11 codes) | 816046.33 |  |  | TIES
|  | Overhead subtotal (3 codes) | 80217.45 |  |  | TIES
|  | Burden subtotal (2 codes) | 318858.96 |  |  | TIES
|  | Direct Cost (all categories) | 1808902.82 |  |  | TIES
|  | Revenue (code 999) | 2327698 |  |  | TIES
|  | Net Profit (Revenue - Expenses) | 518795.18 |  |  | TIES
B. LABOR HOURS ROLLUP
|  | JDR Cost Code hours (Payroll Hours lines) | 29343.5 |  |  | TIES
|  | Per-worker hours (sum of PR Regular) | 29343.5 |  |  | WITHIN
C. BILLING (SOV) ↔ JDR
|  | Final Contract Value | 2327698 |  |  | TIES
|  | Retainage | 116385 |  |  | TIES
|  | Direct Cost | 1808903 |  |  | TIES
D. VENDOR AP ↔ JDR
|  | Vendor AP total (sum of invoices) | 974278 |  |  | TIES
SOURCES
Job #2008 — Exxel Pacific Vivo Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2008 Job Detail Report.pdf (282 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count: 163 (from project specifications)
Fixture count: 1,786 (estimated at ~11 fixtures per unit for mid-rise apartments)
Final contract $2,327,698 (original $2,256,200 + $71,498 COs)
TIES = within $1 or 5 hrs • WITHIN = within 5% • OFF = investigate
K. CHANGE LOG ↔ ROOT CAUSE ANALYSIS
|  | Total Event Count | 41 |  |  | TIES
|  | Net $ Impact (all events) | -500 |  |  | TIES
L. PREDICTIVE SIGNALS ↔ CHANGE LOG
|  | Backcharge Count signal | 1 |  |  | TIES
M. METRIC REGISTRY ↔ BENCHMARK KPIs
|  | revenue (row 17) | 2327698 |  |  | TIES
|  | unit_count (row 12) | 163 |  |  | TIES
|  | total_fixtures (row 13) | 1786 |  |  | TIES
|  | direct_cost (row 19) | 1808902.82 |  |  | OFF
|  | total_pos (row 30) | 0 |  |  | TIES
N. CHANGE LOG ↔ METRIC REGISTRY (event counts)
|  | change_event_total | 41 |  |  | OFF
SOURCES
Job #2008 — Cortex v2 17-tab layout
12 analytical tabs + Change Log + Root Cause Analysis + Predictive Signals + Metric Registry + Reconciliation
Canonical source: 2008 Job Detail Report.pdf (Sage Timberline export)
Change artifacts: folders scanned — ASI-RFI, Change Orders, Submittals, Invoices (Backcharges), JDR cost codes
Every Change Log row cites its source document path
TIES = within $1/5hrs/exact count • WITHIN = within 5% • OFF = investigate
Cross-sheet formulas (='Tab'!Cell) update automatically when source tabs change
Tabs: 1-12 analytical • 13=ChangeLog • 14=RootCause • 15=PredictiveSignals • 16=MetricRegistry • 17=Reconciliation

## Vendors
[CORTEX_V2.1] Job #2008 — · Vendors
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| vendor_id | vendor_name | total_spend | transactions | category | source
Invoices
204
118
5
83
9
19
7
3
11
7
5
5
92
5
5
1
1
2
1
2